CENTRAL FUND FOR INFLUENZA ACTION

PROGRAMME QUARTERLY PROGRESS UPDATE Q2

as of July 8 2008

| Participating UN or Non-UN Organization: | UNDP | UNCAPAHI Objective(s): | Objective 4 |
| --- | --- | --- | --- |
| Implementing Partner(s): | UN Resident Coordinator’s Offices supported by UNDP Country Offices |
| Programme Number: | CFIA-A3 |
| Programme Title: | Support to Coordination of Avian and Human Influenza Activities |
| Total Approved Programme Budget: | US$400,000 |
| Location: | Selected countries on the African and Asian continents, with a special focus on Burkina Faso, Egypt, Niger and Indonesia |
| MC Approval Date: | 18 July 2007 |
| Programme Duration: | 24 months | Starting Date: | 18 July 2007 | Completion Date: | 17 July 2009 |
| Funds Committed: |  | Percentage of Approved: |  |
| Funds Disbursed: |  | Percentage of Approved: |  |
| Expected Programme Duration: | 24 months | Forecast Final Date: | 17 July 2009 | Delay (Months): |  |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| AHI Coordination Egypt | AHI specialist recruited for the RC office Inter-ministerial conference supported for Q3 2008 | 30% |
| AHI Coordination Indonesia | AHI specialist recruited for the RC office | 40% |
| AHI Coordination Nigeria | Study on the socio economic impact of HPAI on the poultry industry Strengthen the UN coordination mechanism; Community capacity for managing the epidemic (cross border collaboration with Benin); Capacity for livestock surveillance at the local government level | 10% |
| Qualitative achievements against outcomes and results: |
| It has taken time to recruit specialist expertise in the RC offices in Egypt and Indonesia but the support in now in place and funded for 12 months. Support for the Nigeria RC office has just been allocated and implementation is starting |