# United Nations Development Group Iraq Trust Fund

# Project #:A5-21

# Date and Quarter Updated: December 2011 (1st Quarter)

| Participating UN Organisation: UNESCO | Sector: AFSSOT |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Agriculture and Water Resources |

| Title | Rehabilitation and conservation of Kahrez systems in the Northern Governorates |
| --- | --- |
| Geographic Location | Northern governorates (Erbil, Dohuk, Sulaymaniyah) |
| Project Cost | US $ 1,600,628 |
| Duration | 15 months (extended 32 months) |
| Approval Date (SC) | 10.04.2007 | Starting Date | 10.04.2007 | Completion Date | 10.07.2008 extended up to 31 Mar 2011 |
| Project Description | The project is aimed at increasing the water supply in rural areas through the rehabilitation and conservation of the traditional Kahrez water management system. |

Development Goal and Immediate Objectives

The overall goal is to improve supply of water for drinking and for irrigation in rural areas of the Northern Governorates through rehabilitation and conservation of the traditional Kahrez water management system. The immediate objectives are (1) to rehabilitate and conserve Kahrez water systems; (2) to build technical capacity in the long-term rehabilitation and maintenance of traditional Kahrez systems; and (3) networking with concerned institutions in the region to share the information and experience in the traditional water systems.

| Outputs, Key activities and Procurement |
| --- |
| Outputs | Selected karez systems rehabilitated Rehabilitation and conservation plan developed for further rehabilitation and long-term conservation Short-term employment created 2.1. Selected community members trained to operate and maintain the system 2.2. Awareness raised on the proper use of the system 2.3. Technical capacity of experts, technicians, enhanced 2.4. Operating policies and procedures for managing the rehabilitated sections put in place 3.1. A network with regional and international experts established in order to ensure continuous exchange of information and expertise on Kahrez systems for the long term conservation |
| Activities | 1.1.1 Excavate and renovate up to ten kahrez systems in the Northern governorates 1.1.2 Procure water surveying equipment necessary 1.1.3 Undertake an impact assessment to determine the impact of the renovation on the lives of beneficiaries, including pre- and post-renovation water surveys 1.2.1 Reviewing the existing regulations and customs of management of the karez systems to develop better conservation scheme 1.2.2 Conducting a scientific survey of existing karez systems to develop further rehabilitation and protection plan 1.3.1 Employing unskilled workers from the community for the short-term rehabilitation work and setting up the general regulation of local employment 2.1.1 Train local beneficiaries of the renovated Kahrez on the use and maintenance 2.2.1 Train MoAWR to transfer the state-of-art expertise and information to conserve the traditional water systems 2.3.1 Organize training workshops for MoAWR staff on theoretical and practical techniques for Kahrez renovation and conservation 2.3.2 Train MoAWR on the use of surveying equipment 2.4.1. Developing standard operation procedures and disseminating them to stakeholders 3.1.1 Participation in the international conferences and study visits on the traditional water systems to obtain the new information and expertise, to present the situation and to call attentions and supports from the international communities |
| Procurement | Water sampling and surveying equipments for the field survey IT equipments for the development of the inventory of kahrez |

| Funds Committed | US$ 1,583,200 | % of approved | 98.95% |
| --- | --- | --- | --- |
| Funds Disbursed | US$ 1,326,400 | % of approved | 82.90% |
| Forecast final date | 31 Mar 2011 | Delay (months) | 32 months |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men | 500 unskilled labour 15 skilled labour | 100% 100% |
| Women | N/A |  |
| Children | N/A |  |
| IDPs | IOM is monitoring |  |
| Others | 900-1000 farms 300,000 rural population | 100% 100% |
| Indirect beneficiaries | 1,000,000 | 100% |
| Employment generation (men/women) | 50/10 | 100% |

| Quantitative achievements against objectives and results | % of planned |
| --- | --- |
| (1) to rehabilitate and conserve Kahrez water systems | 20 karez completed 12 Water User’s Committee (WUC) were created in 10 villages. | 100 |
| (2) to build technical capacity in the long-term rehabilitation and maintenance of traditional Kahrez systems | All 12 WUCs received a basic training on Reporting, Accounting and Procurement. Representatives of 5 communities were trained on Karez restoration techniques on May26, 2010 Manual for Sustainable Karez Restoration in Iraq finalized and designed Project liaised with NGO (Voice of Older People) to teach hygiene and safe water use in Garazel village. Filters were also distributed. | 100 |
| (3) networking with concerned institutions in the region to share the information and experience in the traditional water systems. | Iraqi MoAWR joined the membership of ICQHS for further cooperation along with Iran, Oman, Afghanistan and China. Survey and project steering committee for Phase 2 project (2010-2012) enabled exchange of international expertise | 100 |

Qualitative achievements against objectives and results

All 20 karez targeted by the project have been restored. IOM’s final report of the 15 restored karez was delivered in March 2011 with the following key messages: Average cost of a karez: 13,167 USD (293 USD per meter). Increased access to water for irrigation, livestock and/or drinking water for 286 households (approx. 1500 person, average of 6 person per household) 100 households for drinking water 239 households for irrigation and livestock Note: some households have received water for drinking as well as irrigation. 326 ha of land can be irrigated by the karezes restored. If the water discharge of all the karezes is added up, the total water discharge of the karezes has been double. It increased from 286,848 liters per day to 469,728 liters per day.

Main implementation constraints & challenges (2-3 sentences)

The ongoing severe drought of 2010/2011 is drastically reducing groundwater levels in the communities with karez. All restored karez have experienced increased discharge, but the full potential of the karez will not be felt until the groundwater tables begin to replenish.