CENTRAL FUND FOR INFLUENZA ACTION

PROGRAMME QUARTERLY PROGRESS UPDATE

as of 30 June  2008

| Participating UN or Non-UN Organization: | World Food Programme | UNCAPAHI Objective(s) covered: | Objective: Humanitarian Common Services Support |
| --- | --- | --- | --- |
| Implementing Partner(s): | NA |
| Programme Number: | CFIA-A1 |
| Programme Title: | Development of a Logistics Concept of Operations for Humanitarian Activities in a Pandemic Environment |
| Total Approved Programme Budget: | US$ 400,000 |
| Location: | Africa: Kenya & Mombassa Corridor, Southern Africa Corridor Asia: Pakistan and Afghanistan Indonesia and South East Asia Cluster |
| MC Approval Date: | 12 July 2008 |
| Programme Duration: | Initial 12 Months | Starting Date: | 14 July 2007 | Completion Date: | 26 July 2008 |
| Funds Committed: | US$ 219,566 | Percentage of Approved: | 54% |
| Funds Disbursed: | US$ 219,566 | Percentage of Approved: | 54% |
| Expected Programme Duration: | 18 Months | Forecast Final Date: | 31 December 2008 | Delay (Months): | 6 months |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| Continuity under Pandemic Conditions Ensuring the community of essential social, Economic and governance services, and effective implementation of humanitarian relief under pandemic conditions. | Contingency plans developed for the main humanitarian supply corridors in Eastern and Southern Africa. Assessment methodology refined. Lessons learnt and best practices from first segment of activities drafted for consideration throughout the remaining assessments. | 48% |
| Support provided to the preparation of a response plan in Southern Africa and South East Asia | Governments, UN partners, NGOs and private partners made aware of the importance of pandemic preparedness for the transport sector in Eastern and Southern Africa. Preparatory work to undertake the assessments relevant to the response plans in other regions as outlined in the proposal has been undertaken. | 45% |
| Qualitative achievements against outcomes and results: |
| The analysis of the potential impact of a pandemic on the supply chain of humanitarian goods along the East and South African Logistics corridor is complete. A review of the process and methodology of the analysis has produced a set of lessons learnt and best practices. These will be taken into consideration throughout the remaining phase of the project’s implementation. Building on an existing network of stakeholders, the project engaged UN agencies, NGOs, IFRC, both the national and local authorities, together with critical partners from the commercial sector. This is illustrated by the various requests from national government and commercial entities for expertise and advice on pandemic preparedness. |