# United Nations Development Group Iraq Trust Fund

# Project #:D2-26 Atlas # 00074326

# Date and Quarter Updated:  12 April 2011 Quarter 1: January - March 2011

| Participating UN Organisation: WHO | Sector: Health and Nutrition |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Health |

| Title | HIV/ AIDS Policy support and capacity building |
| --- | --- |
| Geo. Location | Nationwide |
| Project Cost | $1,000,000 |
| Duration | 22 months |
| Approval Date | 23.02. 2010 | Starting Date | 02.03.2010 | Completion Date | 02.03.2011 extended to 31.12.2011 |
| Project Description | The project is structured around three Key Services Delivery Areas (SDAs): Support to Policy Development and Planning Generation of Strategic Information Capacity Development and Training |

Development Goal and Immediate Objectives

The main goal of the project is to enhance the national HIV/AIDS response through proper policy development, information generation and capacity building. The interventions in this project demonstrate a growing UN and Government of Iraq commitment to achieve the MDGs and universal access to health and social services as envisioned in the Constitution, NDS (2007-2010) and the ICI. The immediate objectives of the project are (a) development of the National AIDS Strategic Plan (b) development of M&E framework, M&E plan including surveillance plan, (c) establish surveillance system addressing most at risk and vulnerable populations and (d) capacity building of national program officers and NGO partners.

| Outputs, Key activities and Procurement |
| --- |
| Outputs | Output 1.1 – Capacity of GOI and partners enhanced to develop HIV/AIDS related policies, plans and strategies in a participatory manner Enhanced capacity of the National HIV/AIDS committee and line ministries to develop a Health Sector Response Strategy on HIV/AIDS Enhanced capacity of National HIV/AIDS committee and line ministries to develop a national Multi-sectoral Strategic Plan on AIDS Enhanced institutional capacity of key ministries (Interior , Education , Displacement and migration , Women Affairs and Youth and Sports) to respond to HIV/AIDS) Output 1.2 – HIV/AIDS information generation system in place 1.2.1 Enhanced capacity of the national AIDS committee and focal points at key ministries to develop an M& E plan and Second Generation Surveillance for the National Response on HIV/AIDS 1.2.2 Support provided GOI to undertake studies and surveys on the HIV/AIDS among prisoners and IDUs 1.2.3 Support provided GOI to undertake Qualitative and Formative Research on HIV/AIDS and Sex Work Output 1.3 – Enhanced capacity of the National AIDS Programme, NGO’s and Higher Committee on AIDS for better HIV/AIDS programming. 1.3.1 Enhanced capacity of NAP officers and youth organizations on HIV/AIDS Youth Programming 1.3.2 Enhanced capacity of women organizations to integrate gender and HIV/AIDS in development programming 1.3.3 Enhanced capacity of MOH to integrate HIV/AIDS in MCH Programs 1.3.4 Enhanced capacity of GOI, NGOs, UNCT and Higher Committee to better respond to the issue of HIV/AIDS in Iraq 1.3.5 Capacity of humanitarian NGOs enhanced to integrate HIV/AIDS within their humanitarian Programs |
| Activities | Develop the NSP and conduct consensus and validation workshop for NSP development Support resources mobilization through GF application by CCM Conduct HIV/AIDS situation, response analysis and priority setting as part of NSP development process Dialogue and advocacy meetings with the Ministries of Education, Women Affairs, Youth & Sports, Displacement & Migration and Interior on establishment of HIV/AIDS Units/focal points Develop M&E framework, M&E plan with reporting tools Develop protocol and implementation plan for second generation HIV surveillance activities National training of surveillance officers on surveillance and M&E Develop study protocols and implement assessment of HIV among prisoners and IDUs Develop study protocol and implement assessment of HIV among FSWs National training of NGOs and NAP officers on out of school youth programming National training of NGOs and NAP officers on out in school youth programming National training of women organizations on HIV and Gender National training for MOH staff and NGOs on HIV integration in MCH program Study tour for officers from the NAP, NGOs and Higher Committee to a country in the with good HIV program National training of local NGOs in HIV/AIDS integration in humanitarian programs |
| Procurement | No major procurements were conducted. |

# Financial report

| Budget (USD) | Committed funds (USD) | Committed funds (%) | Disbursed funds (USD) | Disbursed funds (%) |
| --- | --- | --- | --- | --- |
| 1,000,000 | 603,869 | 60% | 577,731 | 58% |

# Agency share of budget

| Agency | USD |
| --- | --- |
| WHO | 614,359 |
| UNDP | 104,954 |
| UNFPA | 170,646 |
| UNESCO | 60,302 |
| WFP | 49,739 |
| TOTAL | 1,000,000 |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men |  | 0 |
| Women |  | 0 |
| Children |  | 0 |
| IDPs |  | 0 |
| Others | The main beneficiary of the project will be the MOH, as it is the key duty bearer for formulation, implementation and monitoring of the HIV Control Program. Participants in the various trainings will also be direct beneficiaries. | 0 |
| Indirect beneficiaries | People living with HIV/AIDS, most at risk population, young people and institutions that would benefit from the policy and capacity building programs | 0 |
| Employment generation (men/women) | This project doesn’t directly generate local employment. However, it offers opportunities for national officers and consultants to build their skills and utilize the skills gained for individual and social development. | 0 |

| Quantitative achievements against objectives and results | % |
| --- | --- |
| UNESCO and WFP implemented 100% of planned activities. Around 40% of activities assigned to WHO including responsibilities transferred from UNODC are implemented. UNDP’s activities are linked to NSP development and will be completed with completion of NSP development process by September 2011. UNFPA has initiated development of TORs for initiation of assessment of HIV among FSWs. | Overall 50% |

Qualitative achievements against objectives and results

WHO Desk review of HIV surveillance system in Iraq conducted and workshop on assessment of HIV surveillance in Iraq conducted in Istanbul on February 17-18, 2011 with 20 participants. Draft HIV surveillance plan has been developed and being circulated for comments. Next steps include refining the surveillance plan by conducting site visits in Iraq and training of health workers on HIV surveillance and M&E. Desk review on HIV situation and response analysis conducted as part of data collection for evidence-based strategic planning; and findings of the review were discussed in a workshop conducted in Istanbul on February 19, 2011. The workshop also developed work plan for NSP development. Next steps include conducting in-depth interviews of key informants in Baghdad and Erbil to enrich the situation and response analysis. A national workshop is planned on June 12-16 in Beirut to discuss the findings of the situation and response analysis and develop priority strategic interventions for NSP. Agreement has been signed with WHO Collaborating Center for HIV surveillance in Zagreb, Croatia to conduct HIV assessment in prisoners and injecting drug users. This activity was initially assigned to UNODC and later transferred to WHO in March. Next steps include conducting planning workshop on May 12-19, 2011 and initiation of the assessment in Iraq. Budget revision request to extend the project end date from 28 February 2011 to 31 December 2011 and to transfer activities of UNODC to WHO has been approved by UNDG in March 2011. Joint UN Team on HIV/AIDS and the National AIDS Program (GoI) are fully informed and involved in the activities being implemented. UNESCO A study tour to learn from the experience of Jordan in youth HIV programming in education and training on youth HIV programming for MoE NAP program managers, senior MoE officials and staff working with non-formal education in Iraq was successfully conducted on 13-17 February 2011 in Amman. WFP All activities for the capacity building of local NGOs and Civil Society Organisations in integration of HIV in humanitarian response have been completed. In total 192 participants from 7 NGOs/CSOs were trained and a toolkit for integration of HIV/AIDS in humanitarian response was created for Iraq and disseminated. UNDP A program manager has been recruited who will manage the HIV project in addition to the Global Fund TB program. Joint planning meeting was conducted between WHO and UNDP in January and March 2011 to coordinate NSP development activities. UNFPA UNFPA is currently developing terms of reference for consultants who will provide technical assistance in conducting assessment of HIV among female sex workers.

Main implémentation contraints & challenges (2-3 sentences)

Coordination between WHO and Ministry of Health has improved with regular e-mail and telephone communications. Coordination among UN participating agencies has also improved but there is still room for improvement especially in timely reporting of implementation progress and joint planning.