CENTRAL FUND FOR INFLUENZA ACTION

PROGRAMME QUARTERLY PROGRESS UPDATE

June 30, 2008

| Participating UN or Non-UN Organization: | UNWTO | UNCAPAHI Objective(s) covered: | 5. Public Information and communication to support behaviour change 6. Continuity under pandemic conditions |
| --- | --- | --- | --- |
| Implementing Partner(s): | WHO, UNICEF, FAO, OIE, OCHA |
| Programme Number: | CFIA-A4 |
| Programme Title: | Targeted Communications for travellers, the travel industry, and tourist destinations |
| Total Approved Programme Budget: | US$ 400,000 |
| Location: | Madrid, Spain |
| MC Approval Date: | 12 July 2007 |
| Programme Duration: | 12 months | Starting Date: | 17 July 2007 | Completion Date: | 16 January 2009 |
| Funds Committed: | US$ 130,928.62 | Percentage of Approved: | 32.7% |
| Funds Disbursed: | US$ 45,745.50 | Percentage of Approved: | 11.4% |
| Expected Programme Duration: | 18 months | Forecast Final Date: | January 2009 | Delay (Months): | 6 months |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| Organizational set-up | Recruitment of staff completed and operational by Feb 2008 | 100% |
| Defining partner links | Campaign inception report developed March 2008, Strategic/tactical plan finalized June 2008; Some plan refinement may take place in execution phase | 80% |
| Developing and setting up a campaign framework | Campaign inception report developed March 2008; Strategic/tactical plan finalized June 2008; Some plan refinement may take place in execution phase | 75% |
| Defining local and national media contacts | Communication staff joined UNWTO Feb 2008; Evaluation of media database complete; expect to contract database in July 2008 | 75% |
| Multiplying outreach through pro-bono work with PR companies | More suitable partners identified in order to ensure that the objectives are achieved, pursuing relationships. This area continues to be slightly delayed | 20% |
| Multiplying partner links and external network contacts | Campaign inception report developed March 2008, Strategic/tactical plan finalized June 2008; Select network-building efforts currently active, others to be implemented later in the year | 50% |
| Deploy instruments | Microsoft engaged in SOS.travel phase II project at strategic and implementation level, full architecture design has been undertaken, site build phase on schedule for first delivery in October 2008. Other instruments to be deployed according to plan. | 45% |
| Qualitative achievements against outcomes and results: |
| During this reporting period, the strategic and tactical elements of the project have been largely finalized, including the delivery of the campaign inception report developed March 2008, and the approval of the strategic/tactical plan finalized in June 2008. This plan covers, among other aspects, identification of partnerships and networks, the approach to the media, and development of communication materials. Most executional aspects are planned for later in the year, during which some plan refinement may take place. UNWTO has been providing regular targeted communication with core tourism and travel associations and its Tourism Emergency Response Network (TERN) related to the current situation of Avian and Human Influenza, guidelines and best practices. On the media side, the evaluation of the media database has been completed and we expect to contract with the database partner in July 2008. Additionally select network-building efforts are currently active, including a regular project update sent via email to key project stakeholders. On the technical deployment side, UNWTO’s Microsoft partners have been engaged in the project at a strategic and implementation level. The project vision has been deemed viable and a high-level architecture design was undertaken in June. The site-build is on schedule for first phase delivery in October 2008. Other instruments will be deployed according to plan. |

# Footnotes

The term “programme” is used for projects, programmes and joint programmes.