# Human Rights Annual Work Plan 2011: Papua New Guinea

UNCP Outcome(s):	Enhanced governance and crisis management

Expected Intermediate Outcome(s):	Government is aware of, respects, and provides for people’s human rights while it empowers citizens to demand the protection of those rights from Government.

Expected Output(s):  	1.National Human Rights Commission, faith-based organizations, CBOs and human rights NGOs have the capacity to promote and protect human rights.

2. Key Government departments have the capacity to protect and promote human rights, ratify core human rights treaties, implement and report on treaty obligations, effectively implement treaty body recommendations and engage with UN special procedures and the Universal Periodic Review.

Implementing partner:	Department of Justice and Attorney General

Responsible Parties and other Partners:	Department for Community Development, RPNGC, CIS, Ombudsman Commission, Public Solicitor, CLRC, civil society.

ExCom Agency	UNDP

Participating Agencies	OHCHR, UNHCR, UNICEF, IOM, UNIFEM, WHO, UNESCO

Agreed by (Implementing Partner): _________________________________ Date: __________

Dr. Kalinoe, Secretary

Department of Justice and Attorney General

Agreed by (ExCom Agency):	__________________________________ Date: __________

David McLachlan-Karr, Resident Representative

UNDP

|  | Expected output | Indicators |  |  |  |  |  |  | Baseline | Annual Target |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Output code 4.1 |  |  |  |  |
|  | National Human Rights Commission (NHRC), faith-based organizations, CBOs and human rights NGOs have the capacity to promote and protect human rights. | Enabling legislation and constitutional amendments in relation to NHRC passed by parliament | No | Yes |  |
|  |  | NHRC functioning as a Paris Principles compliant institution | No | Yes |  |
|  |  | Regional urban centres with an operational NHRC office | 0 | 10 |  |
|  |  | Number of human rights defenders working to promote and protect human rights | 0 | 75 |  |
|  | Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
|  | 1.1 Government, parliament, civil society and general public informed about human rights and the importance of establishment of a NHRC | Technical Working Committee on NHRC/DJAG | OHCHR/UNDP |  |
|  | Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
|  | Public awareness campaign on human rights an d NHRC (with OHCHR TA) | x | x | x | x | OHCHR | Media costs, printing | 0 | 10,000 |  |
|  | 1.1.2 Advocacy on role of parliamentarians in the protection and promotion of human rights and NHRC (OHCHR TA) | x | x | x | x | OHCHR | Meeting costs | 0 | 5,000 |  |
|  | 1.1.3 Human Rights Task Team Project support | x | x | x | x | Core-UNDP | Staff costs | 10,000 | 10,000 |  |
|  | Subtotal |  |  |  |  |  |  | 10,000 | 25,000 |  |

|  | Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1.2 Increase in measures taken to prevent violence and improve access to justice and basic services for victims of human rights violations | Civil society | OHCHR/UNDP |  |
|  | Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
|  | 1.2.1 Financial and technical support to lawyers providing legal aid on human rights cases |  | x |  |  | OHCHR | Grant | 2,000 | 20,000 |  |
|  | 1.2.2 Capacity building of residents of settlements and other marginalized groups to advocate for justice and basic services |  | x |  |  | OHCHR | TA, travel | 5,000 | 15,000 |  |
|  | 1.2.3 Establishment of network of lawyers who either undertake pro bono work or undertake interventions against lump sum arrangements | x | x | x | x | UNHCR | Costs lawyers, court fees |  | 5,000 |  |
|  | Subtotal |  |  |  |  |  |  | 7,000 | 40,000 |  |
|  | Annual Deliverable |  |  |  | Resp. Party | UN Agency |  |
|  | 1.3 Increased number of local human rights defenders reporting on the human rights situation in PNG | Civil society | OHCHR (in cooperation with UNHCR and UNIFEM) |  |
|  | Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
|  | 1.3.1 Training on monitoring, documenting and reporting on human rights violations | x |  | x |  | OHCHR | Travel, meeting costs, printing | 11,000 | 0 |  |
|  | 1.3.3 Provide small grants for HRDs to document cases and report on thematic and regional human rights concerns | x | x | x | x | OHCHR | Grants for HRD’s | 2,000 | 5,000 |  |
|  |  | x | x | x | x | Core-UNDP | Grants for HRD’s | 0 | 12,000 |  |
|  | 1.3.4 Training for Women Human Rights Defenders to address issues relating to VAW |  |  |  |  | Core-UNIFEM | TA, travel, meeting costs | 10,000 | 20,000 |  |
|  | 1.3.5 Documentation of cases to analyze and develop recommendations for better protection of and support systems for WHRDs. |  |  |  |  | Core-UNIFEM | TA, travel, meeting costs | 10,000 | 10,000 |  |
|  | Subtotal |  |  |  |  |  |  | 33,000 | 47,000 |  |

|  | Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1.4 Media and public awareness campaign developed | DfE, DfCD, Media Council | OHCHR (in cooperation with UNHCR, UNDP) |  |
|  | Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
|  | 1.4.1 Develop and implement a media and public awareness campaign on human rights (including during the 20 days of human rights activism (20 Nov-10 Dec)) as well as refugees (WRD, 60 yrs 1951 Convention) | x | x | x | x | OHCHR | Artwork, printing, media, publicity costs | 2,000 | 62,000 |  |
|  |  |  | x |  | x | UNHCR | Services artists printing, media | 0 | 15,000 |  |
|  |  | x | x | x | x | UNDP | Staff costs | 0 | 20,000 |  |
|  | 1.4.2 Support human rights/refugee rights education in schools (with OHCHR/UNESCO TA) |  |  |  |  |  |  |  |  |  |
|  |  |  | x | x |  | UNHCR | Printing | 0 | 2000 |  |
|  | 1.4.3 Design and disseminate human rights kits and materials to different target groups (public) (with OHCHR TA) |  |  | x | x | OHCHR | Printing | 0 | 20,000 |  |
|  |  |  |  | x |  | UNHCR | Printing | 0 | 2,0000 |  |
|  | 1.4.4 Support establishment of “human rights corners” in public libraries and Universities- provision of materials/reports (including on specific groups such as refugees). | x |  | x |  | OHCHR | Printing, transportation | 0 | 0 |  |
|  |  | x |  | x |  | UNHCR | Printing, transportation | 0 | 2,000 |  |
|  | Subtotal |  |  |  |  |  |  | 2,000 | 123,000 |  |

|  | Expected output | Indicators |  |  |  |  |  |  | Baseline | Annual Target |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Output code 4.2 |  |  |  |  |
|  | Key Government departments have the capacity to protect and promote human rights, ratify core human rights treaties, implement and report on treaty obligations, effectively implement treaty body recommendations and engage with UN special procedures and the Universal Periodic Review. | # core human rights treaties and optional protocol’s ratified and reservations removed | 5 | 7 |  |
|  |  | # initial and periodic reports submitted to Treaty bodies and UPR | 1 | 2 |  |
|  |  | # invitations extended to UN Special Procedures and replies sent under communications procedure | 1 | 2 |  |
|  |  | #concluding observations of treaty bodies, special procedure and UPR recommendations disseminated and effectively implemented -reforms in law/policy/practice according to international standards | 1 | 3 |  |
|  | Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
|  | 2.1 Ratification of international human rights treaties and removal of reservations | DfFAT, DJAG, DfCD, PM & NEC | OHCHR (in cooperation with UNHCR, UNDP and UNICEF) |  |
|  | Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
|  | 2.1.1 Advocacy on the ratification of core human rights treaties (CAT, OP ICCPR, OP ICESCR, OP CEDAW, OP CRC, CPWD) and statelessness conventions, as well as removal of reservations (1951 Convention) (in cooperation with OHCHR, UNHCR,UNICEF (TA)) |  | x |  | x | UNHCR | Meeting costs/printing | 0 | 3,000 |  |
|  |  |  | x |  | x | OHCHR | Meeting costs | 0 | 3,000 |  |
|  | Subtotal |  |  |  |  |  |  | 0 | 6,000 |  |

|  | Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2.2 Domestication of ratified international treaties and harmonization of national legal and policy framework | DfFAT, DJAG, DfCD, CLRC, DP, | OHCHR (in coordination with UNDP, UNHCR,UNICEF) |  |
|  | Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
|  | 2.2.1 Workshop on ICCPR and ICESCR, HRBA and development of implementation plan with special focus on right to education(with OHCHR TA) |  |  | x |  | Core-UNDP | Meeting costs, travel | 0 | 10,000 |  |
|  | 2.2.2 Baseline study on implementation of international human rights obligations, focus on right to education |  |  | X |  | OHCHR | Staff costs | 0 | 20,000 |  |
|  | 2.2.3 Legal gap analysis on right to adequate housing |  |  | X |  | OHCHR | Staff costs | 0 | 5,000 |  |
|  | 2.2.4 Support for the drafting of Refugee Policy and action plan (including a broadened Limited Integration Policy and revision of fee for grant of PNG citizenship for refugees) | x | x | x | x | UNHCR | TA, meeting costs, studies | 0 | 10,000 |  |
|  | 2.2.5 Support for the revision of Migration Act and setting up Refugee Status Determination Procedures/RSD Toolkit (with IOM TA re Revision of Migration Act) |  | x | x | x | UNHCR | TA, meeting costs | 0 | 20,000 |  |
|  | 2.2.6 Training on refugee protection for Government officials (Dep Defence, border authorities) |  | x | x |  | UNHCR | Meeting costs, travel | 0 | 10,000 |  |
|  | 2.2.8 Translation and dissemination of international human rights instruments into local languages | x | x | x | x | OHCHR | Translation, printing | 0 | 5,000 |  |
|  | 2.2.10 Assessment of the health situation in prisons of the country, including among prisoners and the overall policy framework and inter-ministry collaboration |  | x | x |  | WHO | TA, travel | 0 | 15, 000 |  |
|  | 2.2.11 Identification of case studies and best practices from disease control programmes on which broader prison health activities can be built |  | x | x |  | WHO | TA | 0 | 5,000 |  |
|  | 2.2.12 Meeting with stakeholders to review issues and challenges, and make recommendations aimed at improving health services in prisons |  |  | x | X | WHO | Meeting costs | 0 |  |  |
|  | 2.2.13 Conduct a comprehensive legal mapping on domestic law and domestic practice in selected provinces re. domestic violence | x | X |  |  | Core-UNIFEM | TA, travel | 30,000 | 30,000 |  |
|  | 2.2.14 Support to CLRC to undertake consultations and awareness on sorcery related torture and killings, collection of sex disaggregated data and research to propose legislative change to address safety and protection of women and other targeted groups. |  |  | x | X | Core-UNIFEM | TA, travel | 0 | 50,000 |  |
|  | 2.2.15 Support to CLRC and Ministry of Justice and A-G on review of laws on sex work and MSM and Special Supreme Court Reference on the practice of polygamy. | x | x | x | x | Core-UNIFEM | TA travel | 20,000 | 50,000 |  |
|  | Subtotal |  |  |  |  |  |  | 50,000 | 100,000 |  |
|  | Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
|  | 2.3 System in place for reporting to UPR, treaty bodies and responding to communications and requests for visits from Special Procedures | DfFAT, DJAG, DfCD | OHCHR/UNDP |  |
|  | Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
|  | 2.3.1 Support for MFA-led mechanism to respond to human rights mechanisms, including monitoring of human rights situation (e.g. database, statistics) | x | x | x | x | UNDP | Staff costs | 0 | 20,000 |  |
|  | 2.3.2 Support for the UPR review (mock session) and follow up | x |  | x |  | OHCHR | Travel, meeting costs | 0 | 5,000 |  |
|  | 2.3.4 Advocacy on cooperation with Special Procedures and implementation of SP and treaty body recommendations (TA no funding required) | x | x | x | x | OHCHR | Meeting costs | 0 | 5,000 |  |
|  | Subtotal |  |  |  |  |  |  | 0 | 30,000 |  |
|  | Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
|  | 2.4 Mechanisms established within the criminal justice system to investigate, prosecute and provide remedy for human rights violations | DJAG, OC, RPNGC, CIS, Magisterial Services | OHCHR (in coordination with UNDP, UNHCR, UNICEF and UNIFEM) |  |
|  | Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
|  | 2.4.1 Human Rights capacity building and training; strengthening curriculum for RPNGC (with OHCHR TA) (in cooperation with UNHCR) | x | x | x | x | Core-UNDP | TA, travel, meeting costs | 17,000 | 63,000 |  |
|  | 2.4.2 Human Rights capacity building / training for Correctional Services |  | x |  |  | OHCHR | TA, Travel, meeting costs | 0 | 10,000 |  |
|  |  |  | x |  |  | Core-UNDP | TA, Travel, meeting costs | 0 | 10,000 |  |
|  | 2.4.3 Documentation of human rights cases reported in the media 2009-2011 and establishment of database for follow up | x | x | x | x | OHCHR | Staff costs | 0 | 20,000 |  |
|  | 2.4.4 Support RPNGC and CS on delivering information to the public on rights and avenues for redress in case of violations (use of media, posters, leaflets, etc.) | x | x | x | x | OHCHR | Publications, printing | 0 | 0 |  |
|  | 2.4.5 Judicial colloquium on combating impunity for torture and ill-treatment by police/correctional services (with OHCHR TA) against whole population including refugees |  | x |  |  | Core-UNDP | Travel, meeting costs | 0 | 10,000 |  |
|  |  |  | x |  |  | UNHCR | Meeting costs | 0 | 2,000 |  |
|  | 2.4.7 Grants to lawyers to take test cases for accountability/justice for human rights violations, in particular criminal prosecution of torture | x | x | x | x | OHCHR | TA, meeting costs | 3,000 | 12,000 |  |
|  | 2.4.9 Establish peer- learning mechanism for actors of the formal and informal justice system | x |  | x |  | Core-UNIFEM | TA | 10,000 | 30,000 |  |
|  | Subtotal |  |  |  |  |  |  | 30,000 | 157,000 |  |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
| 2.5 Action Plan on Human Trafficking and Smuggling developed and implemented | DJAG (before CLRC) | IOM (in cooperation with UNHCR, UNIFEM, UNICEF, OHCHR) |  |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
| 2.5.1 Provide Secretariat work for the existing Committee on Human Trafficking and Smuggling, including the development of a Prevention and Response to Human Trafficking and Smuggling Strategy / Action Plan (with UNIFEM, UNHCR, UNICEF, OHCHR TA) | x | x | x | x | Core funds-IOM | TA | 30,000 | 0 |  |
| 2.5.2 Enhance criminalization and prosecution by supporting law enforcement and judiciary structures to more effectively detect and act against crimes of human trafficking |  |  | x | x | Non core funds-IOM | TA | 60,000 | 0 |  |
| 2.5.3 Improve legislation by providing support to legislators to draft and/or enact effective legislation that enables PNG to comply with the international law standards on trafficking | x | x | x | x | Core funds-IOM | TA | 20,000 | 0 |  |
| 2.5.4 Data collection through research to establish baseline data and evaluation to assess the impact of the counter-trafficking activities |  |  |  | x | Non core funds-IOM | TA | 20,000 | 0 |  |
| 2.5.5 Prevention through targeted public awareness campaign and field workshops |  |  |  | x | Non core funds-IOM | TA | 60,000 | 0 |  |
| 2.5.6 Provide protection through development of SOPs for victims of referral system and training to NGOs on direct assistance to victism |  | x | x | x | Non core funds IOM | TA | 60,000 | 0 |  |
| 2.5.7 Support to CLRC to conduct workshop on human trafficking and smuggling |  |  |  |  | Core-UNIFEM |  | 40,000 | 0 |  |
| Subtotal |  |  |  |  |  |  | 290,000 | 0 |  |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
| 2.6 Tools and mechanisms provided to government and private sector/companies’ on Business and Human Rights | DfFAT, DJAG, DfCD, DNPM, Dep. of Environment, Forestry, Mining | OHCHR/UNDP |  |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
| 2.7.1 Consultations on business and human rights to operationalize SRSG’s framework / Global Compact (OHCHR in cooperation with UNHCR, UNDP, IOM, UNICEF (TA)) |  |  | x |  | OHCHR | meeting costs | 0 | 5,000 |  |
| Subtotal |  |  |  |  |  |  | 0 | 5,000 |  |

* Funding request has already been submitted – but no positive response yet.

# Footnotes

Slight rephrase in order to adequately reflect the broader engagement of the increased HR TT; subject to approval of the Programme Steering Committee.

New indicator - subject to Programme Steering Committee approval.

In collaboration with JUNTA

# Endnotes

Annual target will not be met as behind in establishment of the NHRC, efforts will be made to advance in 2011.

# Text boxes

Programme Period:		2011

Programme Component:		Governance

Intervention Title:		Human Rights

Budget Code:			______________

Duration:			2008-2012

Total Estimated annualized budget:	   1,013,000

- Unfunded budget:	     392,000

- Funded budget:	   	     533,000

Allocated resources

- Government                  	    ___________

- Regular 	                                 ___________

Other:

- Donor

Narrative

The UN will work with the main counterparts, chief among them being DJAG, DCD, OC, PubSol, law enforcement, justice system and civil society towards strengthening the human rights discourse in PNG , as well as strengthening the capacity both of duty bearers to fulfill their responsibilities and that of rights holders to bring forward their grievances free of fear. The UN will continue to work with government counterparts such as DJAG on issues linked to reporting on human rights instruments already ratified or acceded to by PNG. The UN will work with the Government to establish a reporting regime to treaty bodies and encourage ratification of the outstanding human rights treaties. On the rights holder side, it is noteworthy that there is not yet a Human Rights Commission in PNG. The UN will work with the Technical Working Committee to assist the process of establishing this important institution which would facilitate the access of rights holders to a dedicated Government institution with the mandate to oversee the human rights situation in PNG. An important part of this work will be to facilitate the establishment of district level consultation mechanisms, both to provide access to the NHRC, and also to strengthen human rights awareness more generally among the public.