The Government of Papua New Guinea and the United Nations in PNG

2011 Annual Work Plan for

Education

# Country: Papua New Guinea

UNCP Outcome(s):	Foundation for Human Development (Health, Education and Child Protection) - By 2012, children, youth, women and men benefit from basic quality health, education and protection.

Expected Intermediate Outcome(s):	By 2012, DOE have established mechanisms and strategies in place to achieve Universal Basic Education (UBE) and Gender equality in elementary and primary education at the national, provincial and school levels, in partnership with other Government institutions, provinces, churches, and development partners

Expected Output(s):

- National Department of Education (NDOE) have strengthened its capacity to develop and implement strategic plans to achieve Universal Basic Education

- NDOE, Provincial education offices, and Department for Community Development have strengthened their capacity to implement policies on literacy, gender equity in education, and Early Childhood Care and Development

- NDOE and Provincial education offices have enhanced institutional commitment and capacity to promote child friendly school at the national, provincial, district and school levels

- NDOE have strengthened capacity to promote population education in primary and secondary school

Implementing partner: Department of Education

Responsible Parties and other Partners: Department for Community Development | Eastern Highlands Provincial Administration | Western Highlands Provincial Administration | Simbu Provincial Administration | East Sepik Provincial Administration | Autonomous Region of Bougainville

ExCom Agency:	UNICEF

Participating Ag):	UNESCO

Narrative The United Nations (UN) is committed to working with the GoPNG in realizing its developmental objectives in education sector, and affirms its support to doing so within a process led and owned by the government. The UN Country Programme (UNCP) 2008-2012. The UNCP has five outcomes, namely: (1) Governance and Crisis Management; (2) Foundation for Human Development (Health, Education and Child Protection); (3) Sustainable livelihoods and Population; (4) Gender; and (5) HIV and AIDS. UNICEF supports the Department of Education (DOE) to improve the education sector with a focus on Education for All (EFA) and the related two Millennium Development Goals (i.e. Universal Primary Education and Gender equality). The Government of Papua New Guinea (GoPNG) through the DOE has clearly articulated these objectives in the National Education Plan (NEP) 2005-2014 and the Medium Term Development Strategy (MTDS) 2005-2010. The major pillar of the current work plan directly addresses and responds to the priorities identified by the DOE in the UBE and incorporated in the Annual Operational and Financial Plans (AOFP) and in the Medium Term Expenditure Framework (MTEF). These are spread across three main outputs: capacity building in support of UBE, interventions to address the equity pillar, child friendly schools, non formal education and education in emergencies. A major component of this work plan, early childhood care and development, will be implemented in collaboration with the Department for Community Development (DfCD). The same has been reflected in DfCD’s priorities for 2011.

| Programme Period: 2008 - 2012 Programme Component: Education Intervention Title: Education Budget Code: 0470 E602 Duration: 2010 | Total Estimated annualized budget: 4,234,166 Unfunded budget: 966,291 Funded budget: 3,267,875 Allocated resources Government In kind Regular 184,000 Other: Donor UNDP BCPR Donor UNDP Trac Donor 3,083,875 |
| --- | --- |

Agreed by the Secretary for Education:

______________________________________

Dr. Joseph Pagelio

Agreed by the Representative of UNICEF PNG:

_______________________________________

Dr. Bertrand Desmoulins

| Expected output | Indicators | Baseline | Annual Target |
| --- | --- | --- | --- |
| Output code 8.1 | # of training workshops mounted on UBE components | 0 | 2 |
| NDOE have strengthened its capacity to develop and implement strategic plans to achieve Universal Basic Education | # of materials developed based on the UBE communications strategy | 0 | 2 |
|  | # of new research studies done on various aspects of UBE | 0 | 2 |
|  | # of awareness workshops for BOMs | 0 | 10 |
|  | # of education in emergency policy produced | 0 | 1 |
| Annual Deliverable | Resp. Party | UN Agency |
| 8.1.1 Strategies for continuous capacity support to NDOE for the successful implementation of UBE in place | DOE | UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| In-country strategic planning /options for secondary education course by WBI for DOE's PPR mounted | x | x |  |  | UNICEF | CAG | 40,000 | 0 |
| Follow on in-house workshop on study tours by participants |  | x |  |  | UNICEF | CAG | 2,000 | 0 |
| At least six DOE Officers sponsored for online education planning and policy analysis courses | x | x | x | x | UNICEF | CAG | 15,000 | 0 |
| UBE awareness workshops with BOMs, head teachers and district planning officers | x | x | x | x | UNICEF | CAG | 30,000 | 0 |
| Support the implementation of the UBE Communication Strategy | x | x | x | x | UNICEF | CAG | 85,000 | 0 |
| Sensitization of school, district and provincial staff on need for school census as a source of education data | x | x | x | x | UNICEF | CAG | 15,000 | 0 |
| Technical Assistance to UBE Secretariat / PE for 2 UBE EOs | x | x | x | x | UNICEF | CAG | 20,000 | 0 |
| Printing of district and provincial education plans | x | x | x | x | UNICEF | CAG | 135,000 | 0 |
| Assistance to the Capacity Development TWG | x | x | x | x | UNICEF | TA | 35,000 | 0 |
| Implement two studies on transition and multigrade teaching in support of UBE |  | x |  |  | UNICEF | CAG, TA | 36,000 | 0 |
| Follow up training on EFA Info by DevIno Group |  |  | x |  | UNICEF | CAG, TA | 28000 | 7,000 |
| Subtotal Deliverable 8.1.1 | 441,000 | 7,000 |
| Annual Deliverable | Resp. Party | UN Agency |
| 8.1.2 Education in Emergencies (EiE) cluster team established and members trained | DOE | UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Roll out of Provincial level / cluster EiE TOTs | x | x | x | x | UNICEF | CAG, TA | 135,000 | 0 |
| Review of provincial EiE Plans and drawing up plans for other provinces | x | x |  |  | UNICEF | CAG, TA | 37,000 | 0 |
| National EiE Policy finalized | x | x |  |  | UNICEF | CAG | 500 | 0 |
| Subtotal Deliverable 8.1.2 | 172,500 | 0 |
| Monitoring and Evaluation (review and planning meetings, monitoring visits, official trips and travel) | x | x | x | x | UNICEF | TA, CAG | 25,000 | 0 |
| Output 8.1 Total Budget | 638,500 | 7,000 |
| Expected output | Indicators | Baseline | Annual Target |
| Output code 8.2 | # of National Literacy & Awareness Task Force Working Committees established | 0 | 1 |
| NDOE, provincial education offices, and DCD have improved capacities to implement and monitor policies on literacy, gender equity in education, non-formal education (NFE) and Early Childhood Care and Development (ECCD) | # of literacy environment and assessment surveys conducted | 0 | 1 |
|  | # of NFE Management Information System workshop conducted | 0 | 1 |
|  | # of ECCD EiE pilot program on ECCD in emergencies implemented | 0 | 1 |
|  | # of comprehensive ECCD curriculum created | 0 | 1 |
|  | # of strategic plans for NFE and literacy in place | 0 | 1 |
|  | # of literacy survey and language mapping done | 0 | 1 |
|  | # of literacy portals established | 0 | 1 |
| Annual Deliverable | Resp. Party | UN Agency |
| 8.2.1 DOE implements specific inclusive education measures that address the equity pillar of UBE | DOE | UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Hold meetings and workshops for the AGE National Steering Committee | x | x | x | x | UNICEF | CAG | 7,500 | 0 |
| Documentation of the CGEAs program in the highland provinces done | x | x | x | x | UNICEF | CAG | 25,000 | 0 |
| Implement gender audit of education sector in PNG in collaboration with other partners |  |  | x | x | UNICEF | CAG | 38,000 | 16,000 |
| Workshop on evidence based gender mainstreaming held |  | x |  |  | UNICEF | CAG | 35,000 | 0 |
| Establish a national gender resource centre at the DOE and other centres in the provinces |  |  | x | x | UNICEF | CAG | 30,000 | 65,000 |
| Support the 'Bamboo Bank' for Girls Education' in Simbu in partnership with the Catholic Church | x | x | x | x | UNICEF | CAG | 125,000 | 30,000 |
| Internal study tour to the provinces to learn on the implementation of AGE and the activities of the CGEA |  | x |  |  | UNICEF | CAG | 15,000 | 0 |
| Support National Girls Guides Association of PNG to expand the CGEA program to the rest of PNG | x | x | x | x | UNICEF | CAG | 135,000 | 55,000 |
| Implement the National Gender Policy and Action Plan | x | x | x | x | UNICEF | CAG | 55,000 | 35,000 |
| Carry out media awareness on gender equity and national gender policy | x | x | x | x | UNICEF | CAG | 15,000 | 23,000 |
| Support CLCs in selected provinces as a complementary pathway UBE in partnership with stakeholders | x | x | x | x | UNICEF | CAG | 135,000 | 175,000 |
| Sensitization workshops on the National Special Education Policy, national and provinces | x | x | x | x | UNICEF | CAG | 0 | 40,000 |
| Establish special education resource centres in nine provinces |  |  | x | x | UNICEF | CAG | 0 | 45,000 |
| Hold a national conference on special education |  |  | x |  | UNICEF | CAG | 0 | 35,000 |
| Organize early intervention training workshops for SERC teachers and elementary trainers |  |  | x | x | UNICEF | CAG | 0 | 30,000 |
| Conduct a curriculum development workshop for SE practitioners and teachers |  |  | x | x | UNICEF | CAG | 0 | 15,000 |
| Subtotal Deliverable 8.2.1 | 615,500 | 564,000 |
| Annual Deliverable |
| 8.2.2 NDOE and DfCD have improved capacities to effectively manage literacy and non-formal education programs | DOE | UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Inter-departmental coordination and multi-sectoral partnership mechanism in place. National Literacy and Awareness Task Force with 5 Working Committees established. | x | x |  |  | UNESCO | UIL | 25,000 | 0 |
| Consultative meetings to scope project with all stakeholders to ensure partner/donor harmonization and alignment on literacy non-formal education activities |  | x | x |  | UNESCO | UIL | 10,000 | 0 |
| Consultative meeting on legislative policy review |  |  |  | x | UNESCO | FO | 5,000 | 0 |
| Consultative meetings on development of NFE-MIS and strategic planning |  |  |  | x | UNESCO | FO | 10,000 | 0 |
| Sub-contract for the development of legislation and policy review |  |  |  | x | UNESCO | FO | 10,000 | 0 |
| Sub-contract for the development of NFE-EMIS |  |  |  | x | UNESCO | FO | 20,000 | 0 |
| Sub-contract for IT component of training on NFE-MIS |  |  |  | x | UNESCO | FO | 8,000 | 0 |
| Sub-contract for development of training materials |  |  |  | x | UNESCO | FO | 2,500 | 0 |
| Sub-contract to support training needs analysis |  |  |  | x | UNESCO | UIL | 10,000 | 0 |
| Sub-contract for the development of training programme and delivery |  |  |  | x | UNESCO | UIL | 15,000 | 0 |
| Sub-contract for production of training materials, stationary and printing |  |  |  | x | UNESCO | UIL | 2,500 | 0 |
| Subtotal Deliverable 8.2.2 | 118,000 | 0 |
| Annual Deliverable |
| 8.2.3 NDOE and DfCD have baseline data to guide the process of improving literacy and NFE programs | DOE | UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Technical training in undertaking the diagnostic study, indicator development, adapting the data collection tools, data entry, data analysis and report writing |  |  | x | x | UNESCO | FO | 30,000 | 0 |
| Sub-contract to conduct literacy assessment |  |  | x | x | UNESCO | FO | 170,000 | 0 |
| Sub-contract data collection, data entry, data analysis and production of NFE-MIS report |  |  | x | x | UNESCO | FO | 20,000 | 0 |
| Subtotal Deliverable 8.2.3 | 220,000 | 0 |
| Annual Deliverable |
| 8.2.4 DoE has improved human resource capacity to manage the literacy and NFE information | DOE | UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Consultative meetings on literacy assessment |  | x | x |  | UNESCO | FO | 20,000 | 0 |
| Consultative meetings for training needs analysis |  | x | x |  | UNESCO | RB | 20,000 | 0 |
| Consultative meetings on development of training need programme |  |  |  | x | UNESCO | RB | 5,000 | 0 |
| Implementation of training workshops |  |  |  | x | UNESCO | FO | 81,500 | 0 |
| Capacity building workshop for the establishment of a NFE-MIS |  | x |  |  | UNESCO | FO | 20,000 | 0 |
| Consultative meetings to conduct mapping and analysis of NFE |  |  | x | x | UNESCO | UIL | 10,000 | 0 |
| Training workshop on archiving and website use with NLAS |  |  |  | x | UNESCO | FO | 5,000 | 0 |
| Training workshop on the use and maintenance of portal |  |  |  | x | UNESCO | FO | 10,000 | 0 |
| Sub-contract for development of external website and installation |  |  |  | x | UNESCO | FO | 15,500 | 0 |
| Sub-contract for bi-lingual portal, including training materials |  |  |  | x | UNESCO | FO | 10,000 | 0 |
| Sub-contract for distribution and publishing |  |  |  | x | UNESCO | FO | 15,000 | 0 |
| Subtotal Deliverable 8.2.4 | 212,000 | 0 |
| Annual Deliverable | Resp. Party | UN Agency |
| 8.2.6 NDCD supported to implement Early Childhood Care and Development (ECCD) programs | DfCD | UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Support the implementation of a pilot program on ECCD in emergencies in East Sepik province | x |  |  |  | UNICEF | CAG, TA | 35,000 | 7,000 |
| DCD makes a study tour to Asia / Indonesia |  | x |  |  | UNICEF | CAG | 35,000 | 0 |
| Grants to select community driven ECCD centres | x | x | x | x | UNICEF | CAG, TA | 50,000 | 18,000 |
| Support to CBOs/FBOs led ECCD teacher training programs | x | x | x | x | UNICEF | CAG, TA | 50,000 | 35,000 |
| Support officers at DCD to attend relevant international and regional training workshops on ECCD |  | x | x |  | UNICEF | CAG | 35,000 | 0 |
| Development of a comprehensive ECCD curriculum by DCD, in partnership with DOE |  | x | x | x | UNICEF | CAG, TA | 45,000 | 25,000 |
| Printing of ECCD Forum Report and IEC materials | x |  | x |  | UNICEF | CAG, TA | 35,000 |  |
| ECCD Policy Review |  |  | x |  | UNICEF | CAG, TA | 50,000 | 27,000 |
| Support provided to the Association for Early Childhood and Family Services (AEFCS) for advocacy on ECCD | x | x | x | x | UNICEF | CAG, TA | 50,000 | 0 |
| Creation of basic quality and minimum standards (norms) for ECCD programs and institutions |  | x | x | x | UNICEF | CAG | 25,000 | 10,000 |
| Subtotal Deliverable 8.2.6 | 410,000 | 122,000 |
| Monitoring and Evaluation (review and planning meetings, monitoring visits, official trips and travel) | x | x | x | x | UNICEF | TA, CAG | 25,000 | 0 |
| Output 8.2 Total Budget | 1,600,500 | 686,085 |
| Expected output | Indicators | Baseline | Annual Target |
| Output code 8.3 | % of provinces and districts with education plans with CFS as a strategy for UBE and girls' education | 0 | 2 |
| NDOE and Provincial education offices in WHP, EHP, Simbu, East Sepik, and Bougainville have enhanced institutional capacity to promote Child Friendly Schools at the national, provincial, district and school levels | # of minimum standards on quality school developed based on CFS, SLIP and other initiatives | 0 | 1 |
|  | # of strategy to scale up CFS | 0 | 1 |
|  | % of Standards and Guidance Officers trained on CFS concepts | 0 | 40 |
|  | # of child rights and school quality sensitization workshops held | 0 | 5 |
|  | # of schools debates and essay competitions conducted | 0 | 15 |
|  | # of strategies on CFS in elementary education in place | 0 | 1 |
|  | # of in-service CFS course designed | 0 | 1 |
|  | Dissemination workshop on WASH in schools done | N/A | Yes |
|  | # of in-service CFS modules created | 0 | 1 |
| Annual Deliverable | Resp. Party | UN Agency |
| 8.3.1 Package of interventions to mainstream CFS in education system in place | DOE | UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Conduct CFS curriculum review workshop for teacher colleges and other stakeholders | x |  |  |  | UNICEF | CAG | 30,000 | 0 |
| Revised version of CFS Resource Handbooks for students and teachers printed. | x | x |  |  | UNICEF | CAG | 15,000 | 0 |
| Conduct CFS sensitization training workshop for Community Development Strand | x |  |  |  | UNICEF | CAG | 25,000 | 0 |
| Support college based in-service /curriculum review workshops (CFS assessment, projects, course evaluation) |  | x | x |  | UNICEF | CAG | 20,000 | 0 |
| Conduct assessment/evaluation of CFS (college based) |  |  | x |  | UNICEF | CAG | 75,000 | 0 |
| Conduct sensitization on child rights and quality school at quarterly regional consultations | x | x | x | x | UNICEF | CAG | 100,000 | 0 |
| Support to schools' essay and debate competitions |  | x | x |  | UNICEF | CAG | 55,000 | 0 |
| Support the implementation of the Behaviour Management Policy | x | x | x | x | UNICEF | CAG | 55,000 | 0 |
| Train standards and guidance officers to effectively monitor child rights, protection and quality schools |  | x | x |  | UNICEF | CAG | 35,000 | 0 |
| Support debate broadcast in collaboration with NBC and communications unit | x | x | x | x | UNICEF | CAG | 15,000 | 70,000 |
| Reprint student curriculum support materials on school clubs for 10,000 schools | x | x |  |  | UNICEF | CAG | 40,000 | 0 |
| Design a strategy for CFS in elementary education in PNG |  | x | x |  | UNICEF | CAG | 5,000 | 0 |
| Design an in-service CFS TOT course to be implemented at all colleges | x | x |  |  | UNICEF | CAG | 45,000 | 0 |
| Curriculum sensitization for education officers on Elementary CFS INSET Course | x |  |  |  | UNICEF | CAG | 25,000 | 0 |
| Printing of CFS in-service booklets |  | x |  |  | UNICEF | CAG | 15,000 | 0 |
| Creation and distribution of Head Teacher and BOM Handbook | x | x |  |  | UNICEF | CAG | 30,000 | 0 |
| Creation and distribution of poster and checklist for a quality schools | x | x |  |  | UNICEF | CAG | 20,000 | 0 |
| Dissemination workshops on WASH in schools survey in POM and in the provinces |  |  | x |  | UNICEF | CAG, TA | 15000 | 0 |
| Printing of Final Report of WASH in schools survey |  |  | x |  | UNICEF | CAG, TA | 35000 | 0 |
| Conduct an M&E study on the impact of school based counselors |  |  | x |  | UNICEF | CAG, TA | 30,000 | 0 |
| Subtotal Deliverable 8.3.1 | 685,000 | 70,000 |
| Monitoring & Evaluation (review and planning meetings, monitoring visits, official trips and travel) | x | x | x | x | UNICEF | TA, CAG | 40,000 | 0 |
| Output 8.3 Total Budget | 725,000 | 70,000 |
| Total Program Implementation | 2,964,000 | 763,085 |
| Program Support |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Support Staff: Chief of Section, 2 NOBS | x | x | x | x | UNICEF | TA | 293,000 | 25,500 |
| NOC, NOB | x | x | x | x | UNICEF | TA |  | 157,000 |
| Finance Assistant | x | x | x | x | UNICEF | TA |  | 20,706 |
| Program Assistant | x | x | x | x | UNICEF | TA | 10,875 |  |
| Total Program Support | 303,875 | 203,206 |
| Total Programme Implementation and Program Support | 3,267,875 | 966,291 |
| Grand Total Education 2011 Work Plan (Funded and Unfunded) | 4,234,166 |
| Summary Work Plan Funding |
| Output | Funded | Unfunded | Total |  |  |  |  |
| 8.1 | 638,500 | 7,000 | 645,500 |  |  |  |  |
| 8.2 | 1,600,500 | 686,085 | 2,286,585 |  |  |  |  |
| 8.3 | 725,000 | 70,000 | 795,000 |  |  |  |  |
| Program Support | 303,875 | 203,206 | 507,081 |  |  |  |  |
| Total Work Plan | 3,267,875 | 966,291 | 4,234,166 |  |  |  |  |
| Distribution by Agency: UNESCO | 469,618 | 0 |  |  |  |  |  |
| UNICEF | 2,045,967 | 966,291 |  |  |  |  |  |
| Total | 2,515,585 | 966,291 | 4,234,166 |  |  |  |  |
| Acronym Glossary |
| AOFP -Annual Operational and Financial Plan | MTEF - Medium Term Expenditure Framework |
| BOM - Board of Management | NLAS - National Literacy and Awareness Secretariat |
| CAG - Cash Assistance to Government | RB - Regional Bureau |
| CFS - Child Friendly School | SERC - Special Education Resource Centre |
| CGEA - Community Girls' Education Advocate | TA - Technical Assistance |
| CLDC - Community Learning Dev Centre | TOT - Training of Trainers |
| DCD - Dept for Community Development | UBE - Universal Basic Education |
| EFA - Education for All | UIL - UNESCO Institute for Lifelong Learning |
| EiE - Education in Emergency | WBI - World Bank Institute |
| INSET - In-Service Teacher Education |  |