The Government of Papua New Guinea and the United Nations in PNG 2011 Annual Work Plan for

Child Protection

Country: Papua New Guinea

Main implementing partner: Department for Community Development

Responsible Parties and other Partners: Department for Justice and Attorney General, Royal Papua New Guinea Constabulary, Magisterial Services, Correctional Institutions Services, Department of National Planning and Monitoring, Institute of National Affairs, Family and Sexual Violence Action Committee, Provincial Administrations of Eastern Highlands, Simbu, Western Highlands, East Sepik and Milne Bay, the Autonomous Region of Bougainville, Milne Bay Counselling Service, Eastern Highlands Family Voice, Western Highlands Children’s Voice, National and Provincial Juvenile Justice Working Groups, National Department of Health, National Research Institute, the National Department of Education, Young Women’s Christian Association, and the Catholic Diocese of Kundiawa.

UN ExCom Agency: UNICEF Participating Agencies: UNIFEM, UNDP, UNHCR, UNOHCHR

Narrative

The Foundation for Human Development pillar of the United Nations Country Program 2008 - 2012 aims to support children, youth, women and men benefit from basic, quality health, education and child protection. The Government has developed an extensive reform agenda to ensure improved protection of children from violence, abuse and exploitation. During the previous Country Program (2003 – 2007), significant advances were made in the development of legislation, policy and the introduction of child protection programs by a range of key Government agencies. This program now focuses on ensuring that these frameworks and programs are enforced, and made accessible to vulnerable children, through rapid and effective implementation of the Lukautim Pikinini Act, Juvenile Justice Act and the implementation of the National Juvenile Justice Policy and the child protection components of the Department for Community Development Corporate Plan and Community Development Policy. Additionally, the program will support the Government to focus on, and respond to the growing number of orphans and other children vulnerable to violence, abuse and exploitation though strengthening policy and legislative frameworks and enabling evidenced based decision making through collecting analysing and disseminating data and existing best practice models. A new area of programming is societal behaviour change. The purpose of the campaign is to enable children to identify their protection rights and to equip families and communities with the skills and knowledge to strengthen community based child protection practices. The child protection program will continue to promote a human rights-based approach and use the Protective Environment for Children Framework as a key programming tool.

| Programme Period: 2008 - 2012 Programme Component: Child Protection Budget Code: 0470 YS605-02 Duration: 2011 | Estimated annualized budget: $3,164,000 Allocated resources: Regular: 220,000 Other: 944,000 Unfunded: 2,110,000 Total: 3,164,000 |
| --- | --- |

| Joseph Klapat Secretary, Department for Community Development Signature: ________________________ Date: ________________________ | Bertrand Desmoulins UNICEF Representative Signature: ________________________ Date: ________________________ |
| --- | --- |

UNCP Outcome(s): By 2012, children, youth, women and men access basic and quality health, education and protection services, especially in disadvantaged areas.

Expected Intermediate Outcome(s): Children and young people access rights-based national, sub national and community level child protection mechanisms and services and are supported by welfare, justice and social protection legislation and policy frameworks that protect them from violence, abuse and exploitation.

Sub Programs and Expected Output(s):

Sub Program One: Social Protection and Violence Prevention

Output 1: The welfare sector has the capacity to manage and improve national and community child protection systems through the allocation of human and financial resources from the National and sub national governments.

Output 2: Civil society organisations, the Family Support Centre Programme and Psychosocial Support Networks have the capacity to provide preventative and tertiary protection services to children and women vulnerable to violence, abuse and exploitation.

Output 3: Contributors to the development of the Long Term Development Strategy (The Departments for National Planning and Monitoring, Community Development, and Treasury and Finance) have increased knowledge of social and cash transfers and child-inclusive transformative social protection.

Sub Program Two: Legal Protection and Justice for Children

Output 4: The national and provincial juvenile justice working groups has the capacity to manage and improve the juvenile justice system through the allocation of human and financial resources from National and sub national governments.

Output 5: National, provincial, district and local level governments have the capacity including human and financial resources, to enable the full implementation of existing legislation to protect the rights of child witnesses and survivors.

Sub Program Three: Cultural Practices and Behaviour Change

Output 6: The Village Courts Secretariat has the capacity to incorporate child protection rights into the Village Courts Act and supports provincial, district and local level governments to implement the amendments and to develop strategies to equip village courts with the knowledge and skills to strengthen community child protection practices.

Output 7: The PNG Child Welfare Council and the Family And Sexual Violence Action Committee (FSVAC) and their partners have the capacity to design and implement a national societal behaviour change campaign to enable children to identify their protection rights and to equip families and communities with the skills and knowledge to strengthen community based child protection practices.

| Expected output | Indicators |  |  |  |  |  |  | Baseline | Annual Target |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Output 9.1 | # provinces with the technical capacity to implement the LPA | 0 | 22 |  |
| The welfare sector has the capacity to manage and improve national and community child protection systems through the allocation of human and financial resources from the national and sub national governments | # key child protection policy and planning initiatives submitted for endorsement to relevant agencies | 0 | 2 |  |
|  | # key child protection studies completed | 0 | 2 |  |
|  | # children aged 0-5 in focal districts, including health districts who have their births registered | <10% | 60% |  |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
| The Office of the Director of Child Welfare and 21 provincial offices of the Division of Community Development have the capacity to implement the Lukautim Pikinini Act and to utilise standardised templates to prepare an annual reports on progress | DfCD | UNICEF |  |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
| On shore and off shore mentoring local technical assistance provided to the National Department and 21 Divisions of Community Development to implement the Lukautim Pikinini Act | x | x | x | x | UNICEF | Int TA x 1/ Nat TA x 2/ DCT | 70,000 |  |  |
| Conduct a review to identify recommendations to guide the introduction of child-friendly provisions for children and mothers in Corrective Institutions |  | x |  |  | UNICEF | TA/ DCT | 5,000 |  |  |
| Provide support to establish a national child protection communication systems to facilitate professional supervision, transfer of reports and interagency collaboration | x | x |  |  | UNICEF | TA | 1,000 |  |  |
| Capacity development opportunities for national and sub-national welfare sector actors identified to strengthen knowledge of and implement good practices in child protection, including Child Protection in Emergencies (CPiE), in line with the Lukautim Pikinini Act | x | x | x | x | UNICEF | TA/DCT | 20,000 | 100,000 |  |
| Develop and endorse standards for out-of-home care services in line with the Lukautim Pikinini Act and the Most Vulnerable Children Strategy |  | x |  |  | UNICEF | TA/DCT | 5,000 | 50,000 |  |
| Review and reprint IEC materials to raise the visibility of the Lukautim Pikinini Act |  | x | x |  | UNICEF | Supplies | 15,000 | 105,000 |  |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
| Lukautim Pikinini Councils are established and have the knowledge management capacity to influence the development of an evidence based child protection system at the national and sub-national levels | DfCD | UNICEF |  |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
| Establish provincial Lukautim Pikinini Councils in 11 provinces | x | x | x |  | UNICEF | TA |  | 50,000 |  |
| Convene a high-profile forum of the National Lukautim Pikinini Council and representatives from all Provincial Lukautim Pikinini Councils to promote vertical and horizontal sharing of knowledge and lessons learned in child protection and the implementation of the Lukautim Pikinini Act |  |  |  | x | UNICEF | TA |  | 80,000 |  |
| Provide technical leadership and resources to enable a baseline study to be conducted on violence against children | x | x | x |  | UNICEF | TA | 80,000 | 420,000 |  |
| Identify and support opportunities to strengthen the child protection research base and resource mobilisation capacity of partners | x | x | x | x | UNICEF | TA |  | 50,000 |  |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
| 40 per cent of planned 2011 activities in the National Most Vulnerable Children Strategy are implemented under the guidance of the National MVC Coordination Committee and the Principles Advisory Committee | DfCD | UNICEF |  |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
| Support the establishment of the MVC Strategy coordination mechanisms, including child representatives | x |  |  |  | UNICEF | TA | 5,000 | 10,000 |  |
| Provide technical inputs into the development of the Operational Plan for MVC Strategy coordination mechanism | x | x |  |  | UNICEF | TA | 5,000 | 5,000 |  |
| Provide technical leadership to the NDoE to enable it to meet its obligations for the MVC Strategy resourcing and implementation | x | x | x |  | UNICEF | DCT/TA |  | 50,000 |  |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
| Office of Civil Registry and sub-national birth registration points have the capacity to implement a bottom up registration strategy for all children | DfCD | UNICEF |  |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
| Birth registration strategy 2011 - 2013 finalised and submitted to DfCD TMT for endorsement | x |  |  |  | UNICEF | TA | 10,000 |  |  |
| Resource mobilisation strategy for birth registration finalised and implemented | x |  |  |  | UNICEF | TA | 5,000 |  |  |
| Birth registration Operational Plan 2011 - 2013 finalised and implemented |  | x | x | x | UNICEF | TA/DCT/Supplies | 10,000 | 100,000 |  |
| Technical support provided to write new legislation on birth registration |  | x | x |  | UNICEF | Int TA | 20,000 | 25,000 |  |
| Expected output | Indicators |  |  |  |  |  |  | Baseline | Annual Target |  |
| Output 9. 2 | # women and children accessing family support centres | 1500 | 8000 |  |
| Civil society organisations, the Family Support Centre Programme and Psychosocial Support Networks have the capacity to provide the preventative and tertiary protection service prevention services to children and women vulnerable to violence, abuse and exploitation. | # districts with 10 trained counsellors | 0 | 34 |  |
|  | # districts with at least one trained FBO that identifies and monitors vulnerable children | 0 | 20 |  |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
| 11 Family Support Centres launched and all Centres strengthened through staff capacity building and findings of evaluation | FSVAC | UNICEF |  |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
| Train new Family Support Centre staff and promote opportunities for professional attachments to further increase staff capacity to operate the centre in line with national and international standards of best practice | x | x | x | x | UNICEF | Int TA/Supplies | 20,000 |  |  |
| Provide financial and technical support to complete construction of 11 new Family Support Centres | x | x | x | x | UNICEF | TA/Supplies | 160,000 | 100,000 |  |
| Conduct an evaluation of the Family Support Centre Programme |  | x | x |  | UNICEF | TA | 30,000 |  |  |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
| A network of 500 new community child protection advocates have increased capacity to deliver and report on counselling for vulnerable children and to respond to child protection in Emergencies (CPiE) | FSVAC | UNICEF |  |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
| Provide technical assistance to the Family and Sexual Violence Action Committee to coordinate the roll-out of the community child protection programme to train 500 new advocates through a functional advocate’s network | x | x | x | x | UNICEF | TA | 10,000 | 50,000 |  |
| Develop and distribute a Community Advocates Guidelines reflecting the minimum standards for community advocates |  | x | x |  | UNICEF | TA/Supplies | 5,000 | 15,000 |  |
| Provide technical support to the Family and Sexual Violence Action Committee to advocate for the introduction of Ethical Reporting Guidelines for the Media when reporting on gender-based violence and child protection issues. |  |  | x | x | UNICEF | TA | 5,000 |  |  |
| Conduct an impact assessment of the community advocates programme |  | x |  |  | UNICEF | Int TA |  | 40,000 |  |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
| 300 faith-based leaders have the capacity to identify and support the most vulnerable children through implementation of developed community child protection action plans | DfCD | UNICEF |  |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
| Support Catholic Diocese of Kundiawa to continue to expand its Centre of Excellence for the Most Vulnerable Children and to review programme impact since 2009 | x | x | x | x | UNICEF | DCT/TA |  | 20,000 |  |
| Roll out the FBO training for the Protection, Care and Support of the Most Vulnerable Children to 15 new districts. | x | x | x | x | UNICEF | DCT | 0 | 50,000 |  |
| Conduct a progress review of the FBO training for the Protection, Care and Support of the Most Vulnerable Children | x | x | x | x | UNICEF | TA | 5,000 | 20,000 |  |
| Expected output | Indicators |  |  |  |  |  |  | Baseline | Annual Target |  |
| Output 9.3 | The Government’s National Social Protection Policy incorporates child inclusive social protection |  | Yes |  |
| Contributors to the Long Term Development Strategy (the Departments of Planning and Monitoring, Community Development, Treasury and Finance) have increased knowledge of social and cash transfers and child-inclusive transformative social protection |  |  |  |  |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
| The National Task Team on Social Protection integrate child-sensitive social protection principles into the development of the National Social Protection Policy | NTTSP | UNICEF |  |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
| Provide technical support to the National Task Team on Social Protection | x | x | x | x | UNICEF | TA | 0 | 50,000 |  |
| Identify and support opportunities to build the capacity of contributors and other partners in social protection in child-sensitive approaches | x | x | x | x | UNICEF | TA/Travel/Supplies | 10,000 | 20,000 |  |
| Expected output | Indicators |  |  |  |  |  |  | Baseline | Annual Target |  |
| Output 9.4 | % children diverted by police in NCD and Lae | 15 | 65 |  |
| The national and provincial juvenile justice working groups have the capacity to manage and improve the juvenile justice system through the allocation of human and financial resources from the national and sub national governments | % children diverted by the Court in all juvenile courts | 0 | 65 |  |
|  | # children per 100,000 children's population held in CIS on remand | 13 | 5 |  |
|  | # children per 100,000 children's population held in CIS on custodial sentence | 8 | 2 |  |
|  | Degree to which specialised juvenile justice system exists | Level 2 | Level 3 |  |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
| The National Juvenile Justice Committee has increased capacity to coordinate, monitor and report on progress of juvenile justice reforms nation-wide | DJAG | UNICEF |  |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
| Provide specialised technical support and resources to the National Juvenile Justice Working Committee to implement the Juvenile Justice Policy Operational Plan | x | x | x | x | UNICEF | TA/DCT | 10,000 | 50,000 |  |
| Convene regional forums for Juvenile Justice Working Group representatives to consolidate the role of working groups in the reform process and to enhance the monitoring and evaluation framework for juvenile justice through data collection capacity building | x | x | x | x | UNICEF | TA/DCT/Supplies | 40,000 |  |  |
| Implement a training plan to build the capacity of key justice agencies represented on the National Juvenile Justice Committee and the provincial Juvenile Justice working groups | x | x | x | x | UNICEF | TA/DCT | 10,000 | 40,000 |  |
| Finalise and distribute updated juvenile justice IEC materials for children, justice actors and communities | x | x | x | x | UNICEF | DCT/Supplies | 10,000 | 40,000 |  |
| Under the coordination of the National Juvenile Justice Committee, design and undertake research into the situation of girls who come into conflict with the law |  |  | x |  | UNICEF | TA/DCT |  | 15,000 |  |
| Expected output | Indicators |  |  |  |  |  |  | Baseline | Annual Target |  |
| Output 9.5 | Degree to which child witnesses and victims have their rights protected by the Law and Justice Sector | Level 2 | Level 3 |  |
| National, provincial, district and local level governments have the capacity, including human and financial resources, to enable the full implementation of existing legislation to protect the rights of child witnesses and survivors | % children, as per eligibility criteria, accessing special measures orders in POM and Lae | 0 | 75 |  |
|  | % children, as per eligibility criteria, accessing special measures orders nationally (excl. POM and Lae) | 0 | 50 |  |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
| The justice sector has increased capacity to implement recommendations of the situation analysis of child survivors and witnesses | DJAG | UNICEF |  |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
| Provide specialist technical support to implement key recommendations of the situation analysis on survivors and witnesses | x | x |  |  | UNICEF | TA /DCT | 10,000 | 30,000 |  |
| Strengthen the capacity of the Young Women's Christian Association and other NGOs to promote child participation in justice programming | x | x | x |  | UNICEF | TA/DCT | 5,000 | 5,000 |  |
| Provide specialised technical support to the Law and Justice Sector Programme to implement Community Crime Surveys that include child-sensitive questions and are analysed to extract data on children in contact with the law | x | x |  |  | UNICEF | TA/Supplies/DCT |  | 35,000 |  |
| Expected output | Indicators |  |  |  |  |  |  | Baseline | Annual Target |  |
| Output 9.6 | Extent to which Village Courts Act incorporates child protection rights standards | Level 1 | Level 4 |  |
| The Village Courts and Land Mediation Secretariat have the capacity to incorporate child protection rights into the Village Courts Act and supports provincial, district and local level governments to implement the amendments and to develop strategies to equip village courts with the knowledge and skills to strengthen community child protection practices | % provincial governments with a provincial Village Courts Act implementation strategy and work plan | 0 | 15 |  |
|  | % of children in focal districts living in communities covered by the village courts child protection programme (extended programme) | 0 | 50 |  |
|  | % of children in focal provinces living in communities covered by the village court’s child protection program (existing program) | 25 | 100 |  |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
| The revised Village Courts Women and Children’s Access to Justice (Child Protection) Programme is implemented in 8 districts | DfCD | UNICEF |  |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
| Technical support to revise the Village Courts Programme in line with evaluation findings and secure budgetary support for roll-out of the programme | x | x |  |  | UNICEF | TA | 10,000 |  |  |
| Support pilot implementation of the revised child protection programme in 8 districts (four new districts and refresher training for four previously trained districts) | x | x | x | x | UNICEF | TA | 20,000 | 80,000 |  |
| Expected output | Indicators |  |  |  |  |  |  | Baseline | Annual Target |  |
| Output 9.7 | % of school aged children (5-18 yrs) reached by television and radio spots on protection rights | 0 | 50 |  |
| The PNG Child Welfare Council and the Family and Sexual Violence Action Committee and their partners have the capacity to design and implement a national societal behaviour change campaign to enable children to identify their protection rights and to equip families and communities with the skills and knowledge to strengthen community based child protection practices | % of school aged children in focal provinces provided with written material on protection rights | 0 | 30 |  |
|  | % of communities in focal provinces provided with information on child protection practices | 0 | 30 |  |
|  | Societal behavioural change campaign meets agreed standards in quality, effectiveness, efficiency and efficacy | 0 | Yes |  |
| Annual Deliverable: |  |  |  |  |  |  | Resp. Party | UN Agency |  |
| Child protection communication campaign developed and launched | DFCD (Lukautim Pikinini Council) | UNICEF |  |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
| Design communications strategy for a long-term behaviour change campaign | x | x |  |  | UNICEF | IntTA | 30,000 |  |  |
| Produce and distribute first phase campaign materials |  | x | x |  | UNICEF | TA |  | 120,000 |  |
| Design and produce a child protection media campaign targeting foreign workers and investors to advocate for increased corporate responsibility for child protection including corporate sponsorship of the Lukautim Pikinini Care Fund and safeguards to limit child sexual abuse and exploitation |  | x | x |  | UNICEF | TA |  | 100,000 |  |
| Programme Support |  |  |  |  |  |  |  |  |  |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
| 1x Chief, Child Protection (L4) All outputs supported | x | x | x | x | UNICEF | TA | 180,000 |  |  |
| 1x Justice for Children Specialist (L3) Outputs 4, 5 and 6 supported | x | x | x | x | UNICEF | TA | 180,000 |  |  |
| 1x Child Protection Officer (NOB) All outputs supported | x | x | x | x | UNICEF | TA | 50,000 |  |  |
| .5 x Programme Assistant (xxx) All outputs supported | x | x | x | x | UNICEF | TA | 8,000 |  |  |
| 1x Most Vulnerable Children and Social Protection Advisor (TA – L3) Outputs 1,2, 3 and 7 supported | x | x | x | x | UNICEF | TA |  | 180,000 |  |
| HACT quality assurance - monitoring | x | x | x | x | UNICEF | TA/Travel/Supplies | 5,000 | 5,000 |  |

|  | Funded | Unfunded |
| --- | --- | --- |
| Output 1 | 251,000 | 1,045,000 |  |
| Output 2 | 235,000 | 295,000 |  |
| Output 3 | 10,000 | 70,000 |  |
| Output 4 | 70,000 | 145,000 |  |
| Output 5 | 15,000 | 70,000 |  |
| Output 6 | 30,000 | 80,000 |  |
| Output 7 | 30,000 | 220,000 |  |
| Programme Support | 423,000 | 185,000 |  |
| Total | 1,064,000 | 2,110,000 | 3,164,000 |