CENTRAL FUND FOR INFLUENZA ACTION

PROGRAMME QUARTERLY PROGRESS UPDATE

(for posting on the CFIA website)

31 March 2012

| Participating UN or Non-UN Organization: | International Civil Aviation Organization (ICAO) | UNCAPAHI Objective(s) covered: | Contingency planning for operational continuity during a pandemic |
| --- | --- | --- | --- |
| Implementing Partner(s): | World Health Organization (WHO)/Pan American Health Organization (PAHO), Office for the Coordination of Humanitarian Affairs (OCHA), United Nations World Tourism Organisation (UNWTO), World Food Programme (WFP), International Organization for Migration (IOM), International Air Transport Association (IATA), Airports Council International (ACI), International Federation of Air Line Pilots’ Associations (IFALPA), Latin American and Caribbean Air Transport Association (ALTA), Centers for Disease Control and Prevention (CDC), Iberoamerican Aerospace Medicine Association (IAMA) |
| Programme Number: | CFIA-A14 (RLA 08/901 ICAO numbering) |
| Programme Title: | Cooperative Arrangement for the Prevention of Spread of Communicable Disease by Air Transport (CAPSCA) |
| Total Approved Programme Budget: | US$400,186.00 |
| Location: | Americas Region |
| MC Approval Date: | December 2008 |
| Programme Duration: | 24 months | Starting Date: | December 2008 | Completion Date: | December 2010 |
| Funds Committed: | $0 | Percentage of Approved: |  |
| Funds Disbursed: | $327,439.00 | Percentage of Approved: | 81% |
| Expected Programme Duration: | 48 months | Forecast Final Date: | December 2012 | Delay (Months): | 24 months |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| State participation Organised and attended Meetings CAPSCA Guidelines CAPSCA web site www.capsca.org | Ecuador and Paraguay joined CAPSCA Americas Presented CAPSCA at the ICAO/LACAC Regional Facilitation Seminar, Santiago, Chile, 20 – 22 March 2012. CAPSCA State and Airport Assistance Visit guidelines, questionnaire and report template revised and translated into Spanish. CAPSCA Middle East section created. | 81% |

Qualitative achievements against outcomes and results:

Continued to foster collaboration between civil aviation and health sectors – WHO/ICAO, PHA/CAA, Government authorities/industry service providers. Increased State membership to 85% of States in the region Progressed the CAPSCA Americas work programme. improved the assistance visit process by revising the guidelines and tools Promoted CAPSCA through the seminar and expanded web site.

# Footnotes

The term “programme” is used for projects, programmes and joint programmes.