South Sudan 2012 CHF Standard Allocation Project Proposal Proposal for CHF funding against Consolidated Appeal For further CHF information please visit http://unocha.org/south-sudan/financing/common-humanitarian-fund or contact the CHF Technical Secretariat chfsouthsudan@un.org

This proposal shall be submitted by cluster partners in two stages to the Cluster Coordinators and Co-coordinators for each project against which CHF funds are sought. In the first stage, before cluster defenses, applying partners fill sections I and II. The proposal should explain and justify the activities for which CHF funding is requested and it is intended to supplement information already available in the CAP Project Sheets. The proposals will be used by the cluster Peer Review Team in prioritizing and selecting projects for CHF funding during CHF Standard Allocation round. Partners should also fill and submit to cluster coordinator/ co-coordinator the CHF Project Summary (Annex 1). In the second stage projects recommended for funding by the CHF Advisory Board must complete Section III of this application and revised/update sections I and II if needed.

SECTION I:

| CAP Cluster | NUTRITION |
| --- | --- |

| CHF Cluster Priorities for 2012 Second Round Standard Allocation This section should be filled by the cluster Coordinators/Co-coordinators before sending to cluster partners. Provide a brief articulation of Cluster priority activities and geographic priorities that the cluster will recommend for funding from the CHF. |
| --- |
| Cluster Priority Activities |  | Cluster Geographic Priorities |
| Cluster objectives and activities as outlined in CAP Treatment services for Severe Acute Malnutrition and Moderate Acute Malnutrition in children under 5 years, P&LW and other vulnerable groups, through SCs, OTPs and TSFPs - including training of staff Prevention services for children under 5 years and P&LW through - micronutrient supplementation U5 & P&LW, community screening (MUAC) and referral of U5, blanket supplementary feeding in hunger gap and in acute emergency 3-36mths, promotion and support of IYCF; includes training health workers, MSGs and CBOs Strengthen Nutrition emergency preparedness and response capacity - Cluster coordination, Management and analysis of nutrition information, Rapid assessments and SMART surveys in line with cluster standards, Capacity building of CBOs, MSGs, NNGOs and CHD & SMOH on emergency preparedness and response. |  | Hot spot areas in high priority states will be prioritized. |

| Requesting Organization | Project Location(s) (list State, County and if possible Payam where CHF activities will be implemented. If the project is covering more than one State please indicate percentage per state) |
| --- | --- |
| Malaria Consortium | Northern Bahr el Ghazal State (Aweil Centre and West counties) Host community: Aweil West County- Achana, Ayat Centre, Ayat East, Ayat West, Gomjuer Centre, Gomjuer East and Gomjuer West, Mariem East, Mariem West payams Aweil Centre County- Aroyo, Awoda, Awulic, Bar Mayan, Chel South, Nyalath, Umora (Achana) payams Returnee community : Apada Camp : Apada Centre, Bilfam, Kush, Kokek, New Side |
| Project CAP Code |  |
| SSD-12/H/15700/7607 |  |
| CAP Project Title (please write exact name as in the CAP) |  |
| Addressing emergency nutrition needs of vulnerable groups through community based structures |  |
| Total Project Budget in South Sudan CAP | Amount Requested from CHF | Other Secured Funding |
| US$1,058,705 | US$250,000 | DfID128,788USD UNICEF 200 094 USD |
| Direct Beneficiaries (scaled appropriately to CHF request ) | Indirect Beneficiaries (scaled appropriately to the CHF) |
| Women: | 1839,749 |  |
| Men: | 956 |  |
| Girls: | 157 | Catchment Population (if applicable) |
| Boys: | 157 | Total population of Aweil West and Aweil Centre is estimated at 373,152 (calculated from Malaria Consortium’s population figures from the state wide 2009 mass net distribution. Assumes population growth at a rate of 2.85% and takes into account 28,800 returnees). |
| Total: | 41,315 |  |
| Beneficiary breakdown indicate where applicable Women P&LW MAM 0 P&LW Micronutriment-supplementation & deworming 0 Trainees h/workers, community volunteers, etc 18176 Beneficiaries of IYCF promotion 39,574 Other - vulnerable 0 Men Trainees h/workers and community volunteers etc 65 Beneficiaries of IYCF promotion 891 Other - vulnerable 0 Children U5 Yrs SAM 314 MAM 297 BSFP 0 Micronutrient supplementation 0 Deworming 0 |
| Implementing Partner/s (Indicate partner/s who will be sub-contracted if applicable and corresponding sub-grant amounts) | CHF Project Duration (max. of 12 months, starting date will be Allocation approval date) |
| N/A | 3 Months Start Date (mm/dd/yy): 01/01/13 End Date (mm/dd/yy): 31/03/13 |
| Address of Country Office | Address of HQ |
| MALARIA CONSORTIUM: Plot 367, Block 3-K South, First Class Residential District, Tong Ping, Juba, Republic of South Sudan Project Focal Person: Ruth Allan – Country Director Mobile MTN: +211 (0)922 400 572 Mobile GemTel: +211 (0)977 536 872 Juba office: +211 (0)922 400 574 Country Director: r.allan@malariaconsortium.org Country Finance Manager: cfm.juba@malariaconsortium.org | MALARIA CONSORTIUM Development House, 56-64 Leonard Street, London EC2A 4LT Tel: +44 (0)20 7549 0210 Jocelyn Boughton – Chief Finance Officer: J.Boughton@malariaconsortium.org MALARIA CONSORTIUM Plot 25, Upper Naguru East Road, Naguru PO Box 8045, Kampala, Uganda Cristine Betters - Africa Programme Director: c.betters@malariaconsortium.org |

SECTION II

A. Humanitarian Context Analysis Briefly describe (in no more than 500 words) the current humanitarian situation in the specific locations where CHF supported activities will be implemented. Provide evidence of needs by referencing assessments and key data, including the number and type of the affected population

OCHA identified NBeG as a ‘hot spot’ adversely affected by combination of shocks resulting in multiple deteriorating humanitarian indicators. Malaria Consortium (MC) is the main provider of t nutrition services in Aweil Centre which includes the site of Apada, a large returnee camp. MC is already implementing Integrated Community Case Management (ICCM) of malaria, diarrhea and pneumonia aligned to Outpatient Therapeutic Programme (OTP) sites in Aweil West and Aweil Centre. Nutrition Emergency The GAM rate in both Aweil Centre and West continues to be above WHO emergency threshold of 15%. The need for continued essential nutrition interventions which addresses the impacts on morbidity and mortality in children under five cannot be over emphasized. MC’s 2012 pre harvest SMART survey in Aweil Centre showed SAM prevalence of 5.0% (5.3% SAM post-harvest) and GAM of 21.6%, an increase from 17% for post-harvest. Concern Worldwide 2011 pre harvest survey in Aweil West showed SAM rate of 3.8% and GAM of 24.6%.. Food Insecurity NBeG’s food security status remains at a ‘crisis’ level. Following Independence, NBeG has experienced extremely disrupted market supply of essential commodities following the closure of the northern border causing escalation in food prices. Population access to the limited supplies has been adversely affected by austerity. Flooding from early heavy rains is expected to destroy crops creating poor yields from traditional first harvest. Returns NBeG has the highest number of spontaneous returns of any state over the last year. The impact of 72,768 returnees has had a huge impact also on host populations in terms of shelter, sanitation facilities, food and provision of basic health services. The Nutrition SMART survey funded by CHF 2011 showed GAM rate of 27.4 % and 9.3 % SAM compared to the 2011 proxy of SAM (8.3%) and GAM (23.2%) for Apada. As a response to the needs of returnees in Apada, mass nutrition screening using MUAC and immunization for children under 1 year, vitamin A supplementation and deworming was conducted (July 2012) with SMoH. A total of 2,158 children were screened for malnutrition between 18-28 July using CHF 2012 Round 1 and provided soap for hand washing; 1,965 children 12-59 months were dewormed and 1,831 children 6-59 months given Vitamin A. Childhood Illness Data indicates that malaria, diarrhea, and pneumonia are the three most common communicable diseases contributing to morbidity and mortality in South Sudan and have key associations with malnutrition. MC’s 2012 SMART survey in Aweil Centre/Apada showed fever as the most reported illness in children under 5 years two weeks preceding the survey; 32.6% and 35.8% respectively. An interagency WASH assessment completed in the Apada camp identified an extreme lack of clean water points and sanitary facilities, plus risk of flooding during the rainy season increasing the risk of diarrhea and malaria contributing further to the of high rates of malnutrition. From Jan- June 2012, MC has treated 77,648 cases of fever (suspected malaria) in the community in children under five across Aweil Centre/West.

B. Grant Request Justification Briefly describe (in no more than 500 words) how proposed activities support the agreed cluster priorities and the value added by your organization

Supporting Nutrition Cluster Priorities: Contribute to cluster objectives 1, 2 &3: Treatment: 45 community based OTP sites will be strengthened to treat under fives for SAM, continuing services established with 2010, 2011, 2012 CHF grants. MC’s extensive network of 1,700 Community Drug Distributors (CDDs) will treat children with malaria, pneumonia and diarrhea following set protocols; routinely screen and refer children under five for malnutrition (using MUAC and oedema). This method of Community Case Management ensures common childhood diseases and malnutrition can be treated through community structures, catching diseases before they become severe. Complicated cases of SAM are referred to inpatient facilities where feasible; (MSF iTFC-Aweil Civil Hospital (Aweil Centre) or Concern SC Marial Bai PHCC (Aweil West). Children referred by Community Drug Distributor (CDDs) and Community Nutrition Workers (CNWs) to Outpatient Therapeutic feeding Programme (OTPs) and Targeted Supplementary Feeding Programme (TSFP) and onward to health facilities will be followed up to assess their access to care and the progress of recovery . Home visits will be conducted by CNWs to follow-up children admitted in the OTP and TSFP. There are major gaps in TSFP service coverage in NBeG. As such, MC is proposing to establish 2 TSFP Centres (at Aroyo PHCC in Aweil Centre and Apada returnee camp) pending an agreement with WFP. These sites will act as a pilot with the intention of expansion of services, based on the successful outcome of the new services. The TSFP component will complement current OTP services with the aim of ensuring that children with Moderate Acute Malnutrition (MAM) will receive timely care before the condition deteriorates in to SAM. Scarcity of services and lack of access to functional health facilities increases the value of community based treatment structures supporting early treatment. Prevention: Nutrition education/BCC elements will be implemented to promote good practices in Infant and Young Child Feeding (IYCF) through positive deviance/role models in communities. Community dialogues will be held to investigate community practices influencing IYCF with the aim of addressing and improving IYCF practices. Outreach and active screening will promote the early detection of SAM/MAM cases. Referral and monitoring of these cases will reduce risks of serious complications developing as a result of malnutrition. Strengthen Nutrition Emergency Preparedness/Response Capacity - Emergency Assessment: through a combination of regular nutrition programme surveillance (both routine data and pre and post harvest SMART surveys in Aweil Centre & Apada returnee camp) and can will conduct rapid assessments in response to a changing humanitarian situation. In addition nutrition surveillance Malaria Consortium will also monitor treatment data from the ICCM programme ensuring that trends are captured, addressed and regularly shared with SMoH, CHDs and partners enabling rapid response to identified hot spots or rapid increases in returnee populations. Note on vulnerable groups: Trained CNWs and CDDs screen/identify/treat cases of SAM/MAM in host/returnees communities of Aweil West/Centre. P&LW will be targeted for health and nutrition messages. Note on Malaria Consortium’s added value: Ongoing programming, value for money: builds on MC’s wider ICCM programme allowing savings in overheads. Extensive networks of trained/supervised CDDs provide ongoing detection/referral mechanisms, much wider than could be reached by CNWs. Referring and treatment of cases of SAM/MAM at early stages prevents deterioration in to complicated SAM cases requiring inpatient care, providing considerable savings to the cost of treatment. Organizational expertise: MC has technical expertise at all programme levels of implementing nutrition programmes in country

d

| C. Project Description (For CHF Component only) |
| --- |
| i) Purpose of the grant Briefly describe how CHF funding will be used to support core cluster priorities |
| The purpose of the grant is to address emergency nutrition needs of vulnerable groups through community based structures and health facilities in two highly affected counties. The focus is on providing continued OTP and TSFP services to both host and returnees communities. Responding to emergencies Malaria Consortium is an active member of the Nutrition Cluster and will be involved in conducting rapid needs assessment along with other partners and the Ministry of Health when the need arises especially in the areas where there are a high number of returnees and refugees. Maintaining front-line services In Aweil Centre and Aweil West where many populations (host and returnees) have difficulty in accessing health facilities, Malaria Consortium is providing county wide prevention and treatment interventions for SAM and for malaria, pneumonia and diarrhoea, the 3 leading causes of morbidity and mortality in children under five in remote communities and high returnees, not reached by other service providers. Using CHF funding, Malaria Consortium plans to establish 2 TSFP sites as a pilot in addition to the 12 OTP sites established under CHF 2012 round one and the existing 33 OTPs established under CHF 2011. Ramping up support for returnees Malaria Consortium will continue to provide screening, prevention, treatment and follow up services for acutely malnourished children in returnee communities and will coordinate with other actors (health, WASH, Food Security and Education) on cross sectoral responses. Malaria Consortium plans to support in conducting nutritional assessment and response as and when more returnees arrive to NBeG. |
| ii) Objective State the objective/s of the project. Objective/s should be specific, measurable, achievable, relevant and time-bound (SMART) |
| To contribute to improved nutritional status of children under 5 through increasing access to community-based therapeutic, supplementary and preventative nutritional programmes and enhancing capacity building for service provision in Aweil Centre & West, Northern Bahr el Ghazal State. |
| iii) Proposed Activities List the main activities to be implemented with CHF funding. As much as possible link activities to the exact location of the operation and the corresponding number of direct beneficiaries. |
| Assessments Rapid MUAC screening assessment of children (6-59 months) to determine areas of high need where necessary. Continued membership of the statewide emergency nutrition assessment team. Particularly carrying out rapid assessments in response to population movements, including returnees. Please note: SMART survey conducted by MC in May 2012 was funded by CHF 2011 (on NCE). Nutrition survey (post harvest) planned for October 2012 is funded by CHF 2012 Round 1. Special attention will be paid to the returnees during these surveys with separate assessments for this group Treatment Support to 45 existing OTP sites and establishment of 2 TSFP sites (66% of all treatment sites); 1 facility based at Aroyo PHCC in Aweil Centre and 1 community based at Apada returnee camp; responding to the nutritional emergency in the returnee population and remote underserved areas in Aweil Centre and Aweil West Treatment of 314 boys and girls 6-59 months with Severe Acute Malnutrition through 45 OTPs and 297 boys and girls with MAM at 2 TSFPs in Aweil West and Aweil Centre, not served by other nutrition partners. Across Aweil West and Centre, 22 of 45 of MC’s OTPs are run from health facilities, with the rest operated from decentralized community based treatment sites. Both locations are strategic and offer advantages; with OTPs at health facilities strengthening the link and integration of our nutrition programme with the formal MoH system whilst the community based OTPs bring life saving nutrition interventions to populations with limited access to health facilities. Type of sites/Location Aweil Centre Aweil West Health facility based Community Treatment site Health facility based Community Treatment Site Out-Patient Therapeutic Programme(OTP) 14 6 8 17 Therapeutic Supplementary Feeding Programme(TSFP) 1 1 0 0 Total 15 7 8 17 Prevention, Referral and Behavior Change Communication (BCC) Training of 178 (66% of 270) community volunteers to conduct Nutrition screening (using MUAC and checking for oedema and referrals for treatment of SAM in Aweil West and Aweil Centre. Treat underlying causes of malnutrition in children under five (both boys and girls) – for malaria, diarrhoea, pneumonia, through a network of 1,700 community volunteers covering throughout the county in Aweil West and Aweil Centre. BCC campaign including 59 (66% of 90) community meetings (conducted by each CNWs once every 2 months) with a focus on mothers’ groups with an aim of promoting: optimal IYCF practices, nutrition education for children and pregnant and lactating women; hygiene (including hand washing) in Aweil West and Aweil Centre: (1,485female participants and 891male participants) 39,574 caregivers receiving health education and IYCF messaging through the network of 1,700 CDD volunteers which will be assess through focused group discussions and the nutrition survey. Capacity development Training and refresher training on management of outpatient SAM, MAM and IYCF for Community Nutrition Workers (CNW),OTP /TSFP supervisors in Aweil West and Aweil Centre. Formation of an emergency response team to conduct rapid nutrition assessment (dependent on location and MC security guidelines) in collaboration with other partners and SMoH in line with the Nutrition cluster guidelines. Training and sensitization meetings with SMoH in NBeG, CHDs in Aweil West and Aweil Centre on Malaria Consortium’s nutrition programme and links with other health services in the community. MC will provide technical support where necessary to National NGOs providing OTP and / or TSFP services in Aweil South, as MC acknowledge Aweil South to have significant needs with little partner support. However MC currently does not have the operational capacity to scale up to fully cover Aweil South directly Coordination Participation and support to the cluster system at the state and national level (including participation in 2 Technical Working Groups and chairing state level health and nutrition cluster meetings). In areas where other nutrition actors are working (Concern Worldwide in Aweil West) MC will closely coordinate to ensure that services are complementary and not duplicating (e.g. SMART surveys, location of treatment sites etc.) and to ensure better outcome for referrals and to coordinate treatment of patient discharged from inpatient facilities to enable continued treatment closer to their homes. MC will link closely with other nutrition actors that are providing additional services in NBeG; referral of complicated SAM cases (MSF F and Concern Worldwide both have iTFC/SC in Aweil town and Aweil West respectively) and MAM cases to supplementary services where they exist Malaria Consortium will document lessons learnt and share experience from implementation both national and internationally. Supervision, Monitoring and Evaluation Regular data collection and analysis to feed back to CNWs during supervisory visits (2 weekly support supervision visits a month to all CNWs through OTP Supervisors). Completion of nutrition cluster and MoH monthly reporting format with ongoing analysis of nutritional trends. |
| iv). Cross Cutting Issues Briefly describe how cross-cutting issues are taken into consideration (i.e. gender, environment, HIV/AIDS) |
| Gender: Pregnant and lactating women will be targeted for education messages on nutrition during pregnancy, breastfeeding, how to prepare nutritious weaning foods from locally available food sources, the gradual introduction of complementary foods to infants, infant and child feeding. If feeding practices are identified as being gender-imbalanced, tailor-made behavior change communications messages will address this. Focus will also be given to messages on water sanitation and hygiene linking to childhood diseases. The majority of CDDs who will refer SAM cases to the OTPs are women and are increasingly recognized as an integral part of the success of the wider programme by the local leaders and the county health departments. Considerations will also be given to some of the socio-cultural practices through community conversations related to feeding and care practices that affects the nutritional status of both boys and girls, pregnant and lactating women. In the analysis of SMART surveys results and programme treatment records, the gender dimensions will be consider to identify specific vulnerabilities between boys and girls with reference to nutritional status. Through follow-up visits of children admitted to the nutrition programme, the power relations and other factors at the household level which could hinder mothers’ attendance to the OTP/TSFP with her child with will be explored and strategies developed to prevent high defaulter rates. Co-infections with attention to HIV /AIDS The programme will consider the presence of other co- infections related to malnutrition such as TB and HIV focusing on the timing for admission in the OTPs and response to treatment. If children have remained in the treatment programme for more than the required duration of treatment without improvement, recognition and referral for other co-infections maybe necessary. These skills will be included in trainings for CNWs. Environment: The environmental conditions within the project lifespan will be taken into consideration especially in terms of access to services during the rainy season and period of insecurity. By combining supervision visits to the OTP sites with those of other elements of the wider integrated community case management programme, the vehicle usage will be markedly reduced, presenting a financial as well as environmental saving. The programme is otherwise environmentally neutral with the programme field teams in place, reducing the number of national or international flights required to implement the project. Behaviour change communication will include messages on water and sanitation, and messages aim to have improving impact on nutrition status. |
| v) Expected Result/s Briefly describe (in no more than 300 words) the results you expect to have at the end of the CHF grant period. |
| The overall expected result of this project is to contribute to the reduction in child morbidity and mortality through early identification and treatment of SAM and its underlying diseases. Strengthened nutrition services in health facilities and community sites with improved access to nutrition treatment for SAM in Aweil Centre and Aweil West with referral for complicated cases to SCs Establishment of 2 TSFP sites as a pilot for the provision of treatment of MAM Treatment for malaria, diarrhoea and pneumonia at community level in remote locations Improved nutrition surveillance in NBeG: by early detection of malnutrition in the community through community mobilisation and mass screening campaigns, completing pre and post SMART surveys in Aweil Centre and conducting rapid assessments with Malaria Consortium and other partners make appropriate responses to the need and emergencies Improved delivery of quality OTP and TSFP services by the training and supervision of Health and Community Nutrition volunteers Enhance community awareness on improved nutrition practices through promotion of messages on Infant and Young Child Feeding (IYCF), nutrition in pregnancy and during lactation Improved coordination and support to the national and state Nutrition Cluster to be able to identify gaps and advocacy on the necessary services for host and returnees communities. |
| List below no more than five indicators you will use to measure the extent to which those results will have been achieved. At least three of the indicators should be out of the cluster defined Standard Output Indicators (annexed). |
|  | Indicator | Target (indicate numbers or percentages) |
| 1 | No. of MAM Centres /TSFP | 2 TSFP sites |
| 2 | Quality of SAM treatment | Overall cure rate >75%, defaulter rate <15%, death rate <10% |
| 3 | Number of SAM cases treated | 314 boys and girls < 5 years |
| 4 | Number of health and nutrition workers trained (includes facility and community level health workers) | Training on out-patient management for SAM and MAM for the following staffs: TSFP: 7 TSFP volunteers, 1 CHD/SMOH, 2 Health facility staff OTP: 3 Supervisors, 30 CNWs ,1 CHD and 16 Health facility staffs |
| 5 | Number of cluster coordination meetings attended in a quarter | 3 meetings attended per quarter (state and national level) |
| vi) Implementation Mechanism Describe planned mechanisms for implementation of the project. Explain if it is implemented through implementing partners such as NGOs, government actors, or other outside contractors. |
| Given the remote location of the beneficiary communities in NBeG, their low access to lifesaving curative services and urgent need for nutritional care, the aim of this project is to continue to implement a highly decentralised model of outpatient therapeutic programmes (OTP and TSFP) for eligible children 6-59 months with Severe and Moderate Acute Malnutrition (SAM & MAM) within the community. The project is working through Malaria Consortium’s established network of CDDs and their supervisors. CDDs are volunteer community members trained to provide basic health education messages to communities as well as home-based treatment of common infectious diseases. Each CDD is responsible for 40 households. Supervisors have more public health/clinical experience and are responsible for overseeing the work of 15 CDDs each. In the scope of this project, CDDs play a role in community mobilization and creating demand for the curative services provided by the project as well as case identification, health education and follow-up of defaulters. Each CDD is supervised by a supervisor who is literate and capable of data collection and on the job training. Additional volunteers have been selected to serve as Community Nutrition Workers (CNWs), operating OTPs within the community, mostly out of their homes with some based in health facilities. CDDs are to identify cases of SAM and refer them to CNWs. At the OTP sites, CNWs carry out clinical management of the identified cases according to the modified OTP treatment guidelines (based on the South Sudan Integrated Management of Severe Acute Malnutrition (IM-SAM)) and in TSFP sites (using the South Sudan MAM ready packs) and coordinate follow-up of the cases enrolled in the nutrition programme. Prevention activities (deworming and Vitamin A supplementation) will be further linked to the MoH Immunizations campaigns as a supportive mechanism patients who need referral will be sent to suitable SCs or to existing functional PHCC/PHCUs. Community structures will be engaged at every level of implementation of the project especially women’s groups to promote the health and well-being of boys and girls under five and PLWs. Collaboration and coordination will be maintained with partners and the MoH within the project area. Where the need exists in Aweil South, Malaria Consortium will provided technical support (training and capacity building) to local NGOs implementing OTP programmes. |
| vii) Monitoring Plan Describe how you will monitor progress and achievements of the project. |
| Malaria Consortium will continue to provide programmatic and financial updates to CHF (UNDP) as per reporting requirements. In addition technical and operational updates will be shared with the Cluster on a regular basis through the cluster coordination network at the state and central levels. The project will involve the Malaria Consortium team working closely with the local County Health Departments who will also receive ongoing reports of progress. There will be two key M&E elements for this project; Discrete activities e.g. trainings or SMART surveys, will be recorded and assessed as they take place, with lessons learned feeding back from the field teams to the wider programme and cluster teams as appropriate. This feedback loop will ensure that the programme has the flexibility to evolve on a micro-operational front to ensure the most effective implementation. Treatment numbers and outcomes both for SAM and MAM cases and the underlying diseases. This information will be examined during routine supervision visits by Malaria Consortium and will be analyzed both for data quality and impact, in terms of impact the Sphere indicators on OTP and TSFP outcomes should provide a minimum guide. The data from each OTP and TSFP site and the supervisory visits will be an opportunity to reinforce the formal training programme, provide immediate correction of any deficiencies and ensure quality of service provision. Through our experience, such supportive supervision has been shown to improve the retention and motivation of community based workers. Similar information on the treatment of malaria, pneumonia & diarrhoea will also be collected at a community level, collated on a regular basis, feed back to providers and used both to inform operational decisions and to evaluate the technical impact of the project. |

| E. Committed funding Please add details of committed funds for the project from other sources including in-kind supports in monetary terms. |
| --- |
| Source/donor and date (month, year) | Amount (USD) |
| UNICEF (PCA February 2012 – January 2013) DfID (1st January 2012 – 31st March 2013) | 200,094.97 USD 128,788 USD |

SECTION III:

| LOGFRAME |  |  |
| --- | --- | --- |
| CHF ref./CAP Code: SSD-12/H/15700/7607 | Project title: Addressing emergency nutrition needs of vulnerable groups through community based structures | Organisation: Malaria Consortium |

| Overall Objective: What is the overall broader objective, to which the project will contribute? Describe the expected long-term change. To contribute to improved nutritional status of children under 5 through increasing access to community-based therapeutic, supplementary and preventative nutritional programmes and enhancing capacity building for service provision in Aweil Centre & West, Northern Bahr el Ghazal State. | Indicators of progress: What are the key indicators related to the overall objective? Number of OTP sites established and maintained (45) Number of TSFP sites established and maintained (2) Number of children treated and screened for SAM (314 children treated, 39,574 children screened) | How indicators will be measured: What are the sources of information on these indicators? Monthly nutrition reports |  |
| --- | --- | --- | --- |
| Specific Project Objective/s: What are the specific objectives, which the project shall achieve? These relate to the immediate effect of the intervention measured at the end of the project. To improve access to quality treatment of SAM for children under 5 at the community level To improve access to quality treatment of MAM for children under 5 at the community level To contribute to the prevention of malnutrition through IYCF promotion To strengthen the capacity of community volunteers and health staff for the provision of curative and preventative services To support the nutrition cluster coordination mechanism at state and national level To maintain programme supervision, monitoring and evaluation | Indicators of progress: What are the quantitative and qualitative indicators showing whether and to what extent the project’s specific objectives are achieved? Number of Outpatient Therapeutic Programme (OTP) sites for the treatment of Severely Acutely Malnourished (SAM) children (45 sites) Number of children treated for 314 Cure rate >75% Defaulter rate <15% Death rate <10% GoW <60 days LoS >4g/kg/day Number of Targeted Supplementary Feeding Programme (TSFP) sites for the treatment of Moderately Acutely Malnourished (MAM) children (2 sites) Number of children treated for 314 Cure rate >75% Defaulter rate <15% Death rate <3% GoW <60 days LoS >4g/kg/day Numbers of community meetings conducted to promote IYCF promotion / nutrition education for children and pregnant and lactating women & hygiene promotion (59 meetings) 1,485female participants and 891male participants Number of caregivers receiving health education and IYCF messaging through the network of 1,700 CDD volunteers (39,574 caregivers) Number of health and nutrition workers trained (includes facility and community level health workers) 354 (178 Community Volunteers trained in screening and referral & IYCF, 45 CNWs OTP, 6 CNW TSFP trained and 27 Health Facility Staff, and 6 CHD and SMoH trained in outpatient management of SAM & MAM) Number of cluster coordination meetings attended in a quarter (4 per quarter state and national level) Number of Technical Working Groups (TWG) attended (2 TWG) Number of CNW supervisory visits conducted per month by OTP supervisors (2 per month per CNW) Number of complete and timely reports submitted monthly (2 per month) | How indicators will be measured: What are the sources of information that exist and can be collected? What are the methods required to get this information? Monthly nutrition reports, OTP treatment registers Monthly nutrition reports, OTP treatment registers Monthly nutrition report Monthly nutrition report + training report and registers Meeting minutes M&E reports Monthly nutrition report | Assumptions & risks: What are the factors and conditions not under the direct control of the project, which are necessary to achieve these objectives? What risks have to be considered? Access is not hindered to treatment sites by insecurity or seasonal flooding No stock outs of plumpynut or other supplies provided in kind by UNICEF Large population movement does not overwhelm existing infrastructure It will be possible to recruit and retain sufficiently qualified and experienced staff for programme implementation |
| Results - Outputs (tangible) and Outcomes (intangible): Please provide the list of concrete DELIVERABLES - outputs/outcomes, leading to the specific objective/s: Improved access to nutrition treatment in Aweil Centre and Aweil West through the continuation of services at 45 OTP sites for the provision of nutrition services and treatment for malaria, diarrhoea and pneumonia in the community level in remote locations with referral for complicated cases to SC, PHCU/Cs. Improved access to nutrition treatment in Aweil Centre through the establishment of 2 TSFP sites in a health facility and community based site Improved nutrition surveillance in NBeG: by early detection of malnutrition in the community through community mobilisation and mass screening campaigns, rapid assessments with Malaria Consortium and other partners make appropriate responses to the need and emergencies Improved delivery of quality OTP services by the training and supervison of Health and Community Nutrition volunteers Enhance community awareness on improved nutrition practices through promotion of messages on Infant and Young Child Feeding (IYCF), nutrition in pregnancy and during illness Improved coordination and support to the national and state Nutrition Cluster. | Indicators of progress: What are the indicators to measure whether and to what extent the project achieves the envisaged results and effects? Nutrition Programme Officer, OTP Supervisors and additional CNWs Refresher training materials for CNWs Supplies for OTP sites Nutrition Programme Officer, TSFP Supervisors and additional CNWs Training materials for CNWs Supplies for TSFP sites and start up equipment ICCM Nutrition Programme Coordinator, Programme Officer, OTP Supervisor time Temporary staff to conduct assessments and campaigns Training manual Staff to deliver the training Training materials Staff time | How indicators will be measured: What are the sources of information on these indicators? | Assumptions & risks: What external factors and conditions must be realized to obtain the expected outcomes and results on schedule? It will be possible to access the field locations – the security situation will allow this and areas will not be cut off Supplies will be available from UNICEF for treatment Supplies will be available from WFP for treatment HF staff are available to attend the training OTP supervisors are able to access the OTP sites for supervision visits |
| Activities: What are the key activities to be carried out and in what sequence in order to produce the expected results? Continuation of treatment of 314 boys and girls with SAM Screening and referral of SAM cases from the ICCM programme to OTP sites Active screening sessions in the community for referral of SAM & MAM cases Establish 2 TSFP sites Begin treatment of 297 boys and girls with MAM Carry out rapid assessments in response to nutritional emergencies Ongoing treatment data collection and analysis of nutritional trends Training 178 community volunteers on to conduct Nutrition screening (using MUAC and checking for oedema and referrals for treatment of SAM in Aweil West and Aweil Centre Training and refresher training on management of outpatient SAM and IYCF for Community Nutrition Workers (CNW) in Aweil West and Aweil Centre Training to 18 health facility staff on outpatient SAM treatment and links to referral to health services in Aweil West and Aweil Centre Training and sensitisation meetings with SMoH in NBeG, CHDs in Aweil West and Aweil Centre on Malaria Consortium’s nutrition programme and links with other health services in the community 2 weekly support supervision visits to CNWs by OTP Supervisors Conduct community meetings on IYCF 39,574 caregivers receiving health education and IYCF messaging through the network of 1,700 CDD volunteers Participation in national level cluster meetings) Chairing state level health and nutrition cluster Participation in Nutrition cluster Technical Working Groups Documenting lessons learnt and share experience from implementation with cluster and partners | Inputs: What inputs are required to implement these activities, e.g. staff time, equipment, mobilities, publications etc.? Nutrition Programme Officer, OTP Supervisors and additional CNWs Training materials for newly recruited CNWs Equipment for OTP sites Supplies for OTP sites FLA with WFP Training materials for newly recruited CNWs Equipment for OTP sites Supplies for OTP sites ICCM Nutrition Programme Coordinator, Programme Officer, OTP Supervisor time Temporary staff to conduct the survey Hire vehicles Training manual Staff to deliver the training Training materials Staff time |  | Assumptions, risks and pre-conditions: What pre-conditions are required before the project starts? What conditions outside the project’s direct control have to be present for the implementation of the planned activities? It will be possible to access the field locations – the security situation will allow this and areas will not be cut off Supplies will be available from UNICEF for treatment HF staff are available to attend the training OTP supervisors are able to access the OTP sites for supervision visits Communities will be willing to spend time on the distribution |

| PROJECT WORK PLAN This section must include a workplan with clear indication of the specific timeline for each main activity and sub-activity (if applicable). The workplan must be outlined with reference to the quarters of the calendar year. |
| --- |
| Activity | Q3/2012 | Q4/2012 | Q1/2013 | Q2/2013 | Q3/2013 |
|  |  |  | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep |
| Result 1: Improved access to nutrition treatment in Aweil Centre and Aweil West through the continuation of services at 45 OTP sites for the provision of nutrition services and treatment for malaria, diarrhoea and pneumonia in the community level in remote locations with referral for complicated cases to SC, PHCU/Cs |
| Activity (1.1) Continuation of treatment of 314 boys and girls with SAM |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |
| Activity (1.2) Screening and referral of SAM cases from the ICCM programme to OTP sites |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |
| Activity (1.3) Active screening sessions in the community for referral of SAM & MAM cases |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |
| Result 2: Improved access to nutrition treatment in Aweil Centre through the establishment of 2 TSFP sites in a health facility and community based site |
| Activity (2.1)Establish 2 TSFP sites |  |  |  |  |  | X | X |  |  |  |  |  |  |  |  |
| Activity (2.2) Begin treatment of 297 boys and girls with MAM |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |
| Result 3: Improved nutrition surveillance in NBeG: by early detection of malnutrition in the community through community mobilisation and mass screening campaigns, rapid assessments with Malaria Consortium and other partners make appropriate responses to the need and emergencies |
| Activity (3.1) Carry out rapid assessments in response to nutritional emergencies |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |
| Activity (3.2) Ongoing treatment data collection and analysis of nutritional trends |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |
| Result 4: Improved delivery of quality OTP services by training and supervision of Health and Community Nutrition volunteers |
| Activity (3.1) Training 178 community volunteers on to conduct Nutrition screening (using MUAC and checking for oedema and referrals for treatment of SAM in Aweil West and Aweil Centre |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |
| Activity (3.2) Training and refresher training on management of outpatient SAM and IYCF for Community Nutrition Workers (CNW) in Aweil West and Aweil Centre |  |  |  |  |  |  | X |  | X |  |  |  |  |  |  |
| Activity (3.3) Training to 18 health facility staff on outpatient SAM treatment and links to referral to health services in Aweil West and Aweil Centre |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |
| Activity (3.4) Training and sensitisation meetings with SMoH in NBeG, CHDs in Aweil West and Aweil Centre on Malaria Consortium’s nutrition programme and links with other health services in the community |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |
| Activity (3.5) 2 weekly support supervision visits to CNWs by OTP Supervisors |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |
| Activity (4.4) Report writing and data collection of the campaign |  |
| Result 5: Enhance community awareness on improved nutrition practices through promotion of messages on Infant and Young Child Feeding (IYCF), nutrition in pregnancy and during illness. |
| Activity (5.1) Conduct community meetings on IYCF |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |
| Activity (5.2) 39,574 caregivers receiving health education and IYCF messaging through the network of 1,700 CDD volunteers |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |
| Result 6: Improved coordination and support to the national and state Nutrition Cluster |
| Activity (6.1) Participation in national level cluster meetings) |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |
| (Activity 6.2) Chairing state level health and nutrition cluster |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |
| Activity (6.3) Participation in Nutrition cluster Technical Working Groups |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |
| Activity (6.3) Documenting lessons learnt and share experience from implementation with cluster and partners |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |

*: TIMELINE FOR EACH SPECIFIC ACTIVITY MUST BE MARKED WITH AN X AND SHADED GREY 15%

# Footnotes

OTPs do not cover the entire payam, MC is operating within specific Bomas and villages but does not cover entire payam.

UNICEF PCA for supplies

Figure gained from SSRRC in Aweil October 2011 and UNHCR and assuming a 20% increase

66% of 250 female CDDs trained on screening, referral and IYCF messages (most CDDs will be trained outside of this period), 5 female TSFP workers, 10 female HF staff, 1 female Nutrition Programme Officer

All caregivers who access treatment from the CDD network receive IYCF and health messaging through the BCC campaign – 66% of all consultations

66% of 20 male CDDs trained on screening, referral and IYCF messages (most CDDs will be trained outside of this period), 45 CNWs OTP, 5 CNW TSFP, 17 Health Facility Staff and 6 CHD / SMoH, OTP Supervisors and 1 TSFP Supervisor

Numbers of males targeted through community mobilization meetings – this will include IYCF messaging as men are key decision makers relating to feeding practices

Calculated based on projected increase in population, returnees and 2012 admission and taking into account Concern/MC surveys conducted in 2011-2012

Estimated beneficiaries using pre-harvest survey results for 2012 Apada and Aweil Centre and consider % increase in population for host and returnees. This will be achieve from 2 pilot  TSFP sites in Aweil Centre county (one Health facility based –host and one community based-returnees)

Malaria Consortium proposes to begin implementation of the CHF 2012 Round 2 grant to commence immediately following the CHF 2012 Round 1 funding. This will assure sustained programming and avoid overlap of activities in the first two quarters of 2012

To the extent possible reference needs assessment findings and include key data such as mortality and morbidity rates and nutritional status, and how the data differs among specific groups and/or geographic regions. Refer situation/data/indicators to national and/or global standards.

Results still awaiting validation from the South Sudan nutrition cluster

2011 Crop and Food Security Mission report

OCHA, Map: ‘Cumulative No. of returnees, by type, arriving at final destination 30 Oct. 2010 - 10 Jul. 2012’

Sudan Household Health Survey, Star base Dataset 2010

South Sudan ANLA 2011

Presumptive treatment on the basis of the presentation of fever. RDTs are not currently being used for community treatments in South Sudan

This programme implementation strategy has shown high quality indicators to date. In NBeG the average cure rate was 93.1%, 2.0% defaulter rate and 1.2% death rate ; all well within the SPHERE Standards

MC exploring field  level agreements(FLA)  with WFP for support for TSFP

SMART Survey post harvest will be conducted under round 1 funding in Aweil Centre.

Number of Outpatient Therapeutic Programme (OTP) sites for the treatment of Severely Acutely Malnourished (SAM) children already functional are 45 .

Currently under amendment,  submission with UNICEF – indications are good that this will be approved

# Text boxes

Document: SS CHF.SA.01