Costa Rica

| Programme Title: | Networks for coexistence, communities without fear |
| --- | --- |
| Programme number & MPTF ref: | MDGF-1961-F-CRI (67225) |
| Window: | Conflict Prevention & Peacebuilding |
| Approved Budget by NSC (US$): | 3 million |
| Participating Organizations: | UNDP, UNESCO, UNHABITAT, UNICEF |
| Dates of First /Second /Third installments: | 28-May-2009 / 23-Nov-2011 / 11-Nov-2011 |

ACTIVITIES Reported:

Main Substantive Activities:

The JP exceeded the targeted beneficiaries by 459% (85,201 vs. 18,542). 9 regional networks to promote peaceful social relations created. Agenda for the promotion of conflict prevention targeted to youth and children promoted in 9 regions. Conflict prevention plans implemented in 3 regions. National conflict prevention plan under review. School re-insertion plan designed. "Justice support houses" operational in 6 regions. National mapping of potential conflict areas completed. National Cohabitation Program and Strategy developed. National security policy drafted and under implementation. Agenda against VAW promoted in 7 cantons. National school re-insertion strategy under implementation. Promotional material for all 9 cantons completed/distributed.

Problems and lessons learned:

UN agency coordination. Joint programme design. Coordination within Government. Managerial.

The programme has communications strategy in place: Yes

CHARTS & FIGURES

As of 31 December 2011