### PROGRESS REPORT

| Reporting UN Organization | : | United Nations Development Programme (UNDP) |
| --- | --- | --- |
| Country | : | Lebanon |
| Award ID | : | 00047251 |
| Award Title | : | CEDRO II & III – “Country energy efficiency and renewable energy demonstration project for the recovery of Lebanon” |
| Award Timeframe | : | Oct 2009 – Oct 2013 |
| Award Components | : | CEDRO 2 – 00060150 CEDRO 3 – 00071261 |
| Reporting Period | : | 01 July 2012 – 30th Sep 2012 |

### List of Acronyms

BDL		Bank du Liban

CDR		Council for Development and Reconstruction

CO		Country Office

GDP		Gross Domestic Product

EDL		Electricty of Lebanon

EE		Energy Efficiency

EIA		Environmental Impact Assessment

GSHP		Ground Source Heat Pump

ITB		Invitation to Bid

LCEC		Lebanese Centre for Energy Conservation

LED		Light Emitting Diodes

LRF		Lebanon Recovery Fund

MoET		Ministry of Economy and Trade

MoEW		Ministry of Energy and Water

MoF		Ministry of Finance

MoU		Memorandum of Understanding

PV		Photovoltaic

RE		Renewable energy

SHW		Solar hot water

UNDP		United Nations Development Program

WWTP	Waste Water Treatment Plants

I. PURPOSE

Project Summary:

The aim of the CEDRO project is to support Lebanon’s recovery, reconstruction and reform activities and to complement the national power sector reform strategy through the implementation of end-use energy efficiency and renewable energy projects and through the removal of barriers for the promotion of sustainable energy applications in Lebanon. To achieve this, the project will work on three levels: the first involves the establishment of a demonstrative model addressing public sector building and facilities, the second involves the activation of the replication process, and the third involves the triggering of a national sustainable energy strategy and action plan. The CEDRO project is financed through the Lebanon Recovery Fund, and is in-line with Lebanon’s ongoing efforts to improve national patterns of energy consumption and cost.

Project Phases and Outputs:

| CEDRO 2 3.50 million USD | Implementation of end-use energy efficiency and renewable energy applications for public sector buildings and facilities (app. 60 sites across Lebanon) Technology transfer to enable the conversion of other public sector buildings and facilities into energy efficient modalities |
| --- | --- |
| CEDRO 3 3.50 million USD | Implementation of end-use energy efficiency and renewable energy applications for public sector buildings and facilities (app. 60 sites across Lebanon) Technology transfer to enable the conversion of other public sector buildings and facilities into energy efficient modalities Research and development to enable the formulation of a national sustainable energy strategy and action plan |

Project Linkages to National Priorities and Reconstruction Goals:

Lebanon imports around 97% of its energy needs in the form of fossil fuel. In 2004, the national energy bill amounted to around 1.6 billion USD (around 20% of the annual public expenditure and around 7.8% of the national GDP), and in 2005 it reached 2.1 billion USD (around 26% of the annual public expenditure and around 10% of the national GDP).

The government of Lebanon has placed the reform of the power sector among its highest national priorities, as outlined in the recovery, reconstruction and reform paper submitted to the Paris 3 conference after the 2006 conflict. However, given the enormity of the challenges faced by the power sector, the power sector reform strategy has concentrated on addressing the energy supply side, without extending the scope to the demand side of energy management.

Knowing that reform on the supply side needs to be accompanied by reform on the demand side, the proposed CEDRO program has sought to complement the national power sector reform strategy by targeting end-use energy conservation and renewable energy demonstrations which will assist in the above categories of demand-supply imbalance, security of supply, diversification of energy sources, economic cost and the environment.

Moreover, the current Lebanese government has set itself a goal of achieving 12% of its total energy needs from renewable energy sources. CEDRO is seeking to assist in achieving this goal through its demonstration projects of various zero carbon to low carbon technologies and its analysis of renewable energy resources.

This project is an initiative by the Government of Spain to assist the Government of Lebanon in its recovery and reconstruction efforts with a clear focus on promoting sustainable energy services and concentrating on public sector buildings and facilities.

This project is in inline with Lebanon’s recovery, reconstruction and reform objectives, and falls within the Ministry of Energy and Water’s main priority to meet national demand for electricity.

Project Implementation Partners:

The CEDRO partners and their respective roles are indicated to in the Table below;

| Institution | Role |
| --- | --- |
| Spanish Agency for International Cooperation | Funded the CEDRO project through the LRF. The agency simply observes the work of the CEDRO project and sends representations to any event or occasion that CEDRO launches. |
| Ministry of Energy and Water (MoEW) and Lebanese Center for Energy Conservation Project (LCEC) | CEDRO’s works closely with the Ministry and the LCEC as they are the main players in the energy sector. CEDRO’s work augments that of the Ministry and the LCEC, particularly in terms of knowledge-sharing through research activities for the energy sector. |
| Ministry of Finance | Part of the established Steering Committee for CEDRO. |
| Ministry of Economy and Trade | Part of the established Steering Committee for CEDRO. |
| Council for Development and Reconstruction | Part of the established Steering Committee for CEDRO, and monitors the works and finances of CEDRO. |

International Partners: 	-     Spanish Agency for International Cooperation

National Partners: 	-     Ministry of Energy and Water (MoEW)

and Lebanese Center for Energy Conservation Project (LCEC)

- Ministry of Finance

- Ministry of Economy and Trade

- Council for Development and Reconstruction

- Project Management

- Coordination and follow-up on a regular basis with the Technical Backstopping Agency, TTA, on all technical assessments for the selection of new sites, installation designs, supervision and monitoring of works;

- Preparation of regular progress reports and financial management of expenditures;

- Organization of stakeholder meetings (regular meetings with the Ministry of Energy and Water (MoEW) and with EDL) – leading to and following up on several projects to be implemented on hydropower assessment, bioenergy from wastewater treatment plants, and geothermal assessment, among others.

- Daily follow-up with site engineers and project staff;

- Providing technical and policy advice to decision-makers (MoEW) and UNDP CO on renewable energy issues.

- Assess future requirements for renewable market enhancement in Lebanon

- Implementation of end-use energy efficiency and renewable energy demonstration projects for public sector buildings and facilities

In the third quarter of 2012, the focus has been mostly on launching the project that have had their technical specifications done, and effort also was put on preparing TORs for several new projects. Following on Q2 2012 report, please note;

- 3 microwind sites listed below are well underway;

El Mkayteaa Intermediate Public school

Karha Public School

Ras Baalback Community Center

- Military Academy School, Fayadieh (Beirut); a 14,000 liter SHW system, works are well underway

- Larger PV sites; works are well underway

Several projects are in the evaluation phases, i.e., the winning bids are being identified;

- The Batroun Port Renewable Energy Street Lighting bid is being evaluated and winner is expected to sign a contract in Q4 of 2012.

- Green Roof at the Central Bank; evaluation has been completed and winner selected, contract will be signed in Q4 of 2012.

- Hybrid PV-microwind bid has been launched and bids evaluated. Contractor is expected to sign in Q4 of 2012.

- Pico-Hydro power; a pico-hydro power system is being investigated by CEDRO. The site, in the south, where the system will be installed, has been identified. A Surveyor completed and technical/civil works assessment and an environmental study has been implemented to ensure that this system will not, in any way, have negative impacts on the environment. The expert that will write the civil, electric and mechanical TORs has been hired as well and has begun this work.

- As indicated in the last Quarterly report (Q4 of 2011), 3 winners of the Madinati khadraa Competition’ were announced;

  - A solar street lighting and energy efficiency application (energy saving light-bulbs to be distributed) project will be implemented in Qobeiyeet (North Lebanon)

  - A hybrid PV (for electricity) and SHW (for hot water) system will be installed in Aley Prison where both of these (electricity and hot water) are hard to come by.

These two project above have been granted the go-ahead and have begun their work.

  - Roumin pico-hydro; this project is the first of its kind, where a water network pipe will be used to turn a small turbine to light both the municipality of Roumin, and a public street. This will not affect the delivery of water.  Given the complexity and novelty of this type of project in Lebanon, CEDRO has recruited international experts to identify the system specifications, build the capacity of the CEDRO engineers in this field and assist in the procurement of the pico-hydro equipment.

The final project mentioned in Q2 of 2012 was the volleyball court thin-film project. This project has been put on hold for the time being because the public sports court of Batroun itself has failed to secure the funds required to build the roof. This project will be cancelled if this roof is not completed by February of 2013 and will be replaced by another PV project in the same region.

The expected timeframes of the above project is shown in the Table below;

| ID. | Type | ITB/RFQ delivered to bidders | Project commences | Project completion |
| --- | --- | --- | --- | --- |
| 1 | Fayadiyi SHW | Done | June 2012 | Nov 2012 |
| 2 | Large PV sites | Done | July 2012 | Dec 2012 |
| 3 | Microwind | Done | June 2012 | Nov 2012 |
| 4 | Hybrid PV/U-wind | July 2012 | Aug 2012 | Feb 2013 |
| 5 | Green Roof App. | July 2012 | Sept 2012 | April 2013 |
| 6 | Volleyball Court | Put on hold | - | - |
| 8 | Batroun Port | July 2012 | Oct 2012 | April 2013 |
| 9 | Pico Hydro | July 2012 | Nov 2012 | June 2012 |

- Setting an enabling environment for the conversion of public sector buildings and facilities into energy efficient modalities

- The CEDRO website (www.cedro-undp.org) has been completely restructured in Q3 of 2012 and will be online in early Q4 of 2012. A notification to this end will be delivered as soon as the new website is online.

- Newsletter 7 of CEDRO is being prepared and will be completed in Q4 of 2012.

CEDRO was also going to officially open the 28,000 liter SHW project in Baalbeck with the Ministry of Defence, the Lebanese Army, and the Ministry of Energy (and other partners). This event was, unfortunately, called off at the last moment due to the political situation at that time. A new event will be rescheduled once Fayadieh SHW system will be completed.

- Assisting the establishment of a sustainable Energy Strategy for Lebanon

- Geowatt, the consultants for the geothermal assessment, are well underway with their work and are getting full support for data from the Ministry of Energy and Water and their geological data center.

- A study for energy from sewage sludge from wastewater treatment plants (WWTP) has been completed. The findings will be published in Q4 of 2012 and will be given out to various stakeholders after a new section will be added concerning the costs of shifting to these systems.

- Entec, the consultancy that is undertaking the study to identify the non-river hydropower sources have delivered a preliminary first draft of what has been found so far. The findings are very encouraging and particularly focused on the main power plants on the shore line of Lebanon, where the cooling system that takes water from the sea and dumps it back, can be used to generate power in the return process. The final draft is due in Q4 of 2012.

All in all, CEDRO aims to assist the government in Lebanon in deciding which energy source to utilize to reach its objective of 12% of its energy mix to come from renewable energy sources by 2020 – an objective approved by the Council of Ministers and asserted in the Copenhagen Summit.

II. RESOURCES

|  |  | CEDRO 2 | CEDRO 3 |
| --- | --- | --- | --- |
| Total budget approved | : | USD 3,500,000 | USD 3,500,000 |
| Total disbursements as for 30 Sep 2012 | : | USD 3,353,550 | USD 1,204,803 |
| Available Balance | : | USD 146,050 | USD 2,295,197 |
| Commitments for next quarter | : | USD 146,050 | USD 400,000 |

Budget and Expenditure Breakdown per LRF Category:

|  | CEDRO2 | CEDRO3 |
| --- | --- | --- |
| CATEGORY | Total Budget (USD) | Total Exp. to date (USD) | Total Budget (USD) | Total Exp. to date (USD) |
| 1. Personnel (Incl. staff and consultants) | 220,000 | 553,541 | 170,000 | 90,831 |
| 2. Contracts (Incl. companies, professional services) | 440,000 | 415500 | 440,000 | 367,128 |
| 3. Training (incl. AV printing / production) | 40,000 | 0 | 40,000 | 0 |
| 4. Transport (local) | 10,000 | 14,570 | 10,000 | 5053 |
| 5. Supplies and commodities (Incl. IT equip and rental & maintenance) | 50,000 | 828,671 | 50,000 | 40214.6 |
| 6. Equipment (including installation) | 2,450,000 | 1,207283 | 2,500,000 | 517125 |
| 7. Travel | 15,000 | 33,658 | 15,000 | 24694 |
| 8. Miscellaneous | 46,000 | 81,097 | 30,000 | 80,938 |
| 9. Agency Management Support (7%) | 186,048 | 219402 | 245,000 | 78,818 |
| TOTAL | 3,500,000 | 3,353,722 | 3,500,000 | 1,204,803 |

* total expenditure for staff and consultants exceeds the total allocated budget because most of the technical design and supervision of works is being implemented by project personnel and not sub-contracted to third-party companies as originally planned.  A budget revision is therefore being requested should this be necessary.

** The expenditures being reported under this budget account not is only related to the “supplies and commodities” for project running costs but mostly for the installation of equipment; i.e. implementation activities. However, given the difference in budget line description between UNDP and the LRF accounts, the expenditure appears in this budget line

| CEDRO Project | CEDRO 2 3.50 million USD | CEDRO 3 3.50 million USD |
| --- | --- | --- |
| Activity Results | Indicators |  |
| 1 - Implementation of end-use energy efficiency and renewable energy demonstration projects for public sector buildings and facilities | Identification and Implementation of 60-80 EE/RE demonstration projects the remaining regions of Lebanon | Identification and Implementation of 60-80 EE/RE demonstration projects across Lebanon |
| 2 – Outreach and technology transfer to enable the conversion of other public sector buildings and facilities into energy efficient modalities | Development and implementation of technical workshops and awareness tools Development of GIS energy data base and EE/RE procurement specs | Development and implementation of technical workshops and awareness tools Development of GIS energy data base and EE/RE procurement specs Validation of project results and development of replication schemes |
| 3 – Research and development to enable the formulation of a national sustainable energy strategy and action plan | - | Assessment of national renewable energy resources Assessment of national energy efficiency potential Development of national EE/RE strategy & action plan |

Progress in Project Implementation:

| Activity Results | Activity Actions | Targets for 2012 | Status for 2012 |
| --- | --- | --- | --- |
| 1 – Project Management | Technical Management Financial Management Operational Management | Organization of 3 conferences and/or events and end of year project board meeting Opening of Baalbeck Army SHW sites | 2 conferences (have already occurred; Bioenergy dissemination event and Madinati Khadra event) 1 opening event of 3 PV sites in the South has been implemented Preparation of launching of Baalbeck SWH unit has been cancelled due to security situation. The event will be repeated next year in Fayadieh SHW system |
|  |  | Organization of 2 international backstopping missions; | 1 backstopping mission has been completed. |
|  |  | Apply the issues raised in the report on the status and results of the CEDRO I pilot projects published in Q4 of 2012 | Recommendations of CEDRO 1 Evaluation Report have been completed |
|  |  | Provide advisory support services on EE/RE policies and legislations | Advisory services for MoEW and EDL on net metering has led to a successful outcome. EDL has now adopted new metering and this was announced in January 2012. |
|  |  | Attendance of capacity building workshops for CEDRO team | CEDRO Project Manager attended The Qatar Alternative Energy Summit in Doha, the European Biomass Conference and Exhibition 2 CEDRO engineers have attended 2 PV conference respectively |
|  |  | Preparation of regular progress reports | Q1,Q2 progress report prepared |
| Activity Results | Activity Actions | Targets for 2012 | Status for 2012 |
| 2 - Implementation of end-use energy efficiency and renewable energy demonstration projects for public sector buildings and facilities | 2.1 Undertake targeted assessment and identification of project beneficiary sites; 2.2 Develop tender documents and undertake bidding & procurement of goods/services; 2.3 Undertake commissioning of works and supervision and monitoring of sites; 2.4 Undertake testing of performance & data collection; | Implementation of 30 demonstration projects; Launch 3 sites for micro-wind Launch Army Fayadieh Military school (SHW) Launch Batroun Port Launch Batroun Volleyball court thin-film PV Launch three sites of Madinati Khadra competition Launch pico-hydro Launch larger PV sites Launch hybrid PV/microwind sites Launch Green Roof initiative at the Central Bank Complete work on Bejji Municipality (GSHP) Complete work on Roumieh Prison Complete work on 4 SHW projects (final review) Complete work on 36 PV sites (controllers and commissioning) Continuous cooperation between CEDRO, the MoEW and the LCEC for on-going projects | Works on 36 PV sites completed Works on 4 public hospitals done GSHP project is completed, awaiting building completion and inhabiting. Works on Roumieh has Jacketing of system only remaining. This was hoped to be done in Q1 of 2012 yet has been pushed to Q2 of 2012 due to security issues. Works are still ongoing Launch of microwind works underway Launch of Army SHW works underway Evaluation of Batroun Port is bids underway - Batroun Volleyball Court put on hold (see above) - Pico-hydro terms of reference being drafted - hybrid PV/microwind evaluation of bids underway - Larger PV sites works underway - Green roof at BDL evaluation of bids has been completed |
| Activity Results | Activity Actions | Targets for 2012 | Status for 2012 |
| 3 – Outreach and technology transfer to enable the conversion of other public sector buildings and facilities into energy efficient modalities | Develop and implement technical workshops and awareness activities; Develop GIS energy data base and EE/RE procurement specs; Validate project results and enable replication schemes; | Development and implementation of 2 technical workshops | Microwind and Ground source heat pump technical workshops are being prepared by CEDRO |
|  |  | Continuation and expansion of CEDRO outreach and visibility; 2 newsletters to be produced in 2012 Complete revamping of CEDRO website to be implemented Environment play to complete its tour across all public and private schools of Lebanon. | Updating project website: www.cedro-undp.org (En/Ar); Articles on CEDRO in (1) Beyond magazine. (2) Environment and Development magazine, … (3) Executive magazine Full press coverage for the Bioenergy Event Full press coverage on the PV opening events (in the South) Documentary has been prepared for CEDRO. 1st newsletter of 2012 is out, 2nd newsletter will be distributed in Q4 of 2012. Theatre (environment play) has toured Lebanon and completed all tasks |
|  |  | Set-up of GIS database for 200 public sector sites; Interactive Map for CEDRO sites to be installed on new webstie | Set-up of GIS database for 109 public sector sites completed Interactive Map being set up |
| 4 – Research and development to enable the formulation of a national sustainable energy strategy and action plan | Asses national renewable energy resources; Assess national energy efficiency potential; Develop national EE/RE strategy & action plan; | Publish Bioenergy Report for Lebanon and disseminate results Continue with energy from waste water treatment plants study, and finalize results by Q2 of 2012 Continue with study on hydropower resources from non-river sources. Continue with international consultant on the plant rehabilitation in Lebanon and the writing of specificaiton documents specification documents Launch and implement the national geothermal power assessment for the country. | Bioenergy report completed and disseminated in a conference in March 2012 WWTP study is nearly completed and will be published in Q4 of 2012 Small to micro-hydro has been awarded and work is under way and should be completed by Q4 of 2012 Iinternational hydro-power consultant has been hired and assessment of rehabilitating old hydropower plants is underway and is almost complete Geothermal assessment study has been awarded and has launched in Q2 of 2012. |

* EE/RE = Energy Efficiency and Renewable Energy

Implementation Constraints and Lessons Learned during this quarter:

In this third quarter of 2012 (i.e., Q2), CEDRO has experienced the following; CEDRO has realised that many of the pre-planned projects have been delayed due to several issues such as (1) delay in drafting/agreeing the terms of reference, and (2) delay in evaluation of projects (especially new projects like the Green Roof application). This is understandable given that this year is focusing on new project like the Green Roof, Pico Hydro, Batroun Port., and hybrid microwind and PV. The evaluation was also done by external parties and respective/concerned public official (e.g. Ministry of Energy and Bank of Lebanon (BDL)) which took much time.

IV. FUTURE WORK PLAN

|  | 2012 |
| --- | --- |
| Outputs and Activities | Q1 | Q2 | Q3 | Q4 |
| 1. Implementation of end-use EE/RE demonstration projects Identification of beneficiary sites Development of tender documents Procurement of goods / services Site Supervision and hand-over Monitoring of system performance | Launch microwind ITB Launch new PV project (larger sites) ITB Launch SHW ITB for army Prepare Pico hydro sites Monitor performance of earlier projects and collect data | Monitor implementation of microwind project Monitor implementation of larger PV sites Monitor implementation of SHW sites Launch pico hydro-sites Monitor performance of earlier projects and collect data | Monitor implementation of current works Monitor performance of earlier projects and collect data | Monitor implementation of works (commission sites of 2012) Record all data collected from sites Monitor all installations Launch of Green Roof with BDL Launch of Pico Hydro Launch hybrid ITB |
| 2. Outreach and Technology transfer for the activation of EE/RE applications Establishment of energy saving data base for public sector facilities Development & Implementation of capacity building & awareness programs Development of relevant EE/RE policies and procedures Validation of project results | Launch Army SHW event Launch technical workshop on microwind and GSHP Award Madinati Khadra competition Launch bioenergy assessment event Launch theater event | Awareness activity to be determined Continue theater event | Technical workshop - to be deteremined Launch Energy manual for hospitals Continue theater event | Technical workshop - to be deteremined Launch Energy manual for banking sector with green roof application |
| 3. Research and development for the formulation of a national EE/RE strategy and action plan Assessment of national RE potential Assessment of national EE potential Identification of viable EE/RE actions Identification of Implementation tools and funding mechanisms | Launch Geothermal assessment Launch Central Bank green roof study Launch Energy Manual | Monitor studies progress | Monitor studies progress |  |

|  | 2013 |
| --- | --- |
| Outputs and Activities | Q1 | Q2 | Q3 | Q4 |
| 1. Implementation of end-use EE/RE demonstration projects Identification of beneficiary sites Development of tender documents Procurement of goods / services Site Supervision and hand-over Monitoring of system performance | Monitor implementation of works Record all data collected from sites Monitor all installations Prepare Operation and maintenance plan post-CEDRO | Monitor implementation of works Record all data collected from sites Monitor all installations Prepare Operation and maintenance plan post-CEDRO | Terminate project Prepare Operation and maintenance plan post-CEDRO Prepare Operation and maintenance plan post-CEDRO |  |
| 2. Outreach and Technology transfer for the activation of EE/RE applications Establishment of energy saving data base for public sector facilities Development & Implementation of capacity building & awareness programs Development of relevant EE/RE policies and procedures Validation of project results | Awareness activity to be determined | Awareness activity to be determined | Closing event for CEDRO project |  |
| 3. Research and development for the formulation of a national EE/RE strategy and action plan Assessment of national RE potential Assessment of national EE potential Identification of viable EE/RE actions Identification of Implementation tools and funding mechanisms | No new studies possible Put together all CEDRO’s work on RE and EE in one document; a national document for RE and EE | Put together all CEDRO’s work on RE and EE in one document; a national document for RE and EE | Put together all CEDRO’s work on RE and EE in one document; a national document for RE and EE |  |

| CEDRO |
| --- |
| CEDRO 2 Implementation of end-use energy efficiency and renewable energy applications for public sector buildings and facilities (60sites across Lebanon) Technology transfer to enable the conversion of other public sector buildings and facilities into energy efficient modalities | CEDRO 3 Implementation of end-use energy efficiency and renewable energy applications for public sector buildings and facilities (60-80 sites across Lebanon) Technology transfer to enable the conversion of other public sector buildings and facilities into energy efficient modalities Research and development to enable the formulation of a national sustainable energy strategy and action plan |