### LRF PROGRESS REPORT

| Reporting UN Organization | : | United Nations Development Programme |
| --- | --- | --- |
| Country | : | Lebanon |
| Project No. | : | 00073450 |
| Project Title | : | Monitoring & Evaluation Team for the LRF |
| LRF Signature date | : | December 15, 2009 |
| Project Start date | : | December 15, 2009 |
| Reporting Period | : | 2013 – Q2: April - June 2013 |

Contents

I. PURPOSE	1

II. RESOURCES	2

III. RESULTS	3

IV. IMPLEMENTATION CONSTRAINTS AND LESSONS LEARNED	8

V. FUTURE WORK PLAN	8

### List of acronyms

M&E: Monitoring and Evaluation

LRF: Lebanon Recovery Fund

UNRCO: United Nations Resident Coordinator’s Office

FAO: Food and Agriculture Organization

UNIDO: United Nations Industrial Development Organization

UNDP: United Nations Development Programme

UNFPA: United Nations Population Fund

ILO: International Labour Organization

UNESCO: United Nations Educational, Scientific and Cultural Organization

MPTF: Multi-Donor Trust Fund

PAG: Project Approval Group

SC: Steering Committee

HQ: Head Quarters

Q: Quarter

MoM: Minutes of Meeting

I. PURPOSE

Project Summary:

The M&E unit was designed to enhance the LRF monitoring mechanism by incorporating the below activities into a more coherent and efficient framework and by expanding overall oversight management. The M&E unit aims at enhancing the efficiency, preventing unnecessary expenditures and avoiding project delays. This framework will consist of:

- An increased frequency of field trips and monitoring meetings;

- Closer and more technical follow ups on project implementation and financial activities;

- A continuous evaluation and objective re-assessment of project achievements against pre-set targets;

- A support system to meet timely completion with the objective of raising the effectiveness of projects and ensure cost-efficiency in their implementation, and

- A support system to examine the final evaluation of the projects implemented under the LRF.

Effective oversight management of the LRF projects is time-enhancing and cost-efficient to both donors and beneficiaries. And since the M&E team will oversee all aspects of the project activities, Project Managers are supported in achieving their pre-set deadlines in a timely manner. This will be advantageous to the benefactors since it will prevent the postponement of the project’s activities.

Furthermore, any revisions made in the outstanding projects-such as a no cost time extension, a budget reevaluation or change in scope is effectively assessed and evaluated by the M&E team and hence, improving the cost-efficiency and decision making outcomes of those projects by the PAG team and LRF Steering Committee.

Project Objectives:

The development goal of the M&E Team is to generate a framework whereby the operation and delivery of current and prospective projects approved under the LRF are able to improve efficiency, recognize and prevent unnecessary expenditures and project delays that may arise over the present time frame of each individual project.

The immediate objective of establishing an M&E Team is to strengthen the existing LRF monitoring mechanism by improving the timeliness, cost efficiency and reliability of the current LRF project activities.

Project Outputs:

Main outputs include:

- Support Project Managers in achieving their pre-set deadlines in a timely manner, thus working in favor of the beneficiaries of each project, and

- Revisions made in the outstanding projects - such as a no cost time extension, a budget re-evaluation or change in scope - will be effectively assessed and evaluated by the M&E team. This will improve all decision making outcomes and will ensure compliance with the above revisions.

Project Implementation Partners and roles:

- Ministry of Economy and Trade: Chair of the LRF Steering Committee

- Ministry of Finance: Member of the LRF Steering Committee

- Prime Minister’s Office: Member of the LRF Steering Committee

- UNRCO: <ember of the LRF Steering Committee

- UN Implementing Agencies (UNIDO, UNDP, FAO, UNFPA, ILO, UNESCO)

II. RESOURCES

| Total budget approved | USD $218,657.49 |
| --- | --- |
| Total disbursements as of 30 June 2013 | USD $162,635.74 |
| Commitments for next quarter | USD 10,000.00 |
| Available Balance | USD $56,021.75 |

| CATEGORY | TOTAL BUDGET (USD) | TOTAL EXP (USD) to Date |
| --- | --- | --- |
| 1. Personnel (Incl. staff and consultants) | 157,694.44 | 134,534.84 |
| 2. Contracts (Incl. companies, professional services) | 4,544.35 |  |
| 3. Training |  | 400.00 |
| 4. Transport |  |  |
| 5. Supplies and commodities | 5,010 | 2,213.80 |
| 6. Equipment | 9,515 | 19,686.92 |
| 7. Travel |  | 58.00 |
| 8. Miscellaneous | 27,289.00 | 5,800.18 |
| 9. Agency Management Support | 14,284.65 |  |
| TOTAL | 218,337.44 | 162,635.74 |

III. RESULTS

Progress in Project Implementation:

Reporting

The M&E unit completed the review of the 2012 annual reports and the 2013 1st quarterly reports of the following LRF projects:

- LRF-23	UNDP	Hydro Agricultural Development for Marjeyoun Area

- LRF-17	UNDP	Flood Risks Prevention and Management in Baalbeck - Hermel (PHASE II)

- LRF-10	UNDP	Country Energy Efficiency and Renewable Energy Demonstration Project for the Development of Lebanon (CEDRO II)

- LRF-16	UNDP	Country Energy Efficiency and Renewable Energy Demonstration Project for the Development of Lebanon (CEDRO III)

- LRF 24 UNDP Early recovery of Nahr el Bared surrounding Lebanese communities affected by 2006 and 2007 conflicts

- LRF-26 FAO Recovery and Rehabilitation of Dairy Sector in Bekaa Valley and Hermel-Akkar Uplands (PHASE II)

In collaboration with the concerned UN agencies, the reports were amended in order to highlight on the results and the impact of the LRF initiatives. The final versions of the reports have been uploaded on the MPTF gateway.

The LRF-10 UNDP Country Energy Efficiency and Renewable Energy Demonstration Project for the Development of Lebanon (CEDRO II) was successfully completed in December 2012. The M&E unit supported the operational closure of the project and the final narrative report is uploaded on the MPTF gateway.

In addition, the LRF 23, Hydro Agriculture Development Project for Marjeyoun area, and the LRF 17, Flood Risk Prevention and Management in Baalbeck Phase II project, that were granted 18 months time extension were successfully completed in February 2013. Consequently, the M&E unit is working closely with the project teams to finalize the operational closure of both projects.

Extended Projects

The LRF M&E Unit was following up closely with the extended projects on the progress achieved on monthly basis and through filed visits to the targeted areas. Challenges were reported to the LRF PAG and SC for decision.

The LRF 24, “Early recovery for Nahr El Bared Surrounding Lebanese Communities Affected by 2006 and 2007 Conflicts”, has been granted a time extension of 12 months to complete the pending activities related to the provision of new models of green houses to the farmers in Akkar area, the establishment of an olive solid waste facility in Bkarzala and the installation of new sewage channels as well as upgrading a mini-football field in Bkarzala.

The M&E Unit is closely following up with the project on the progress achieved, with regard to listed components, in addition to meeting with the project staff to clarify critical issues pertaining to the implementation of the project’s activities.

LRF visibility

The M&E unit is working, in cooperation with the Information Unit at the RCO and the IT unit at the Ministry of Economy and Trade, to share updates on the LRF webpage on the Lebanon UN website and on the MOET website. Updated information includes statistical data, financial figures, and publications which are available for the public.

The M&E unit is also working on the design of a new issue of the LRF newsletter that shares the success stories and positive outcomes of the LRF projects. This newsletter issue will be distributed to the Heads of the UN agencies in Lebanon, counterparts Ministries and other stakeholders including embassies and consulates during the 3rd quarter of 2013.

Coordination

During the reporting period, the M&E unit provided technical support and advice to the LRF steering committee and project approval group on issues related to the ongoing projects and submitted extension or transfer requests during the 2013 Q2.

Moreover, the M&E unit facilitated and supported the review process of a new LRF project proposal that was approved and funded with a total of 700,000 USD for a period of 18 months. This new project “LRF-28 Reviving farmers' livelihoods in South Lebanon” aims to improve farmers' livelihoods in South Lebanon through assisting small farmers in overcoming post-production constraints.

| Project Outputs | Activities | Indicators |
| --- | --- | --- |
| Support Project Managers in achieving their pre-set deadlines in a timely manner, thus working in favor of the beneficiaries of each project | Quarterly review of the progress reports submitted by the projects; inquiries, comments and suggestions are shared with the program managers with regard to the obstacles faced and the alternative measures to be adopted to overcome the constraints. Monthly review of the progress reports submitted by the extended projects Coordination meetings with the projects’ teams to assess the progress made and the obstacles facing the implementation. | Activities completed as per the projects’ set up work plans; Obstacles assessed and alternative measures suggested to the LRF PAG and SC; Meetings with the projects’ teams and updating the work plans |
| Revisions made in the outstanding projects - such as a no cost time extension, a budget re-evaluation or change in scope - will be effectively assessed and evaluated by the M&E team. This will improve all decision making outcomes and will ensure compliance with the above revisions. | Periodic updates to the LRF PAG and SC on the progress achieved and the obstacles faced. Ensuring visibility of the LRF to publicize the achievements of the projects Attendance of the LRF projects’ events to promote the LRF visibility as funding party. | PAG and SC minutes of meeting Website updated Events debriefing reports, minutes and press releases |

IV. Implementation Constraints and Lessons Learned:

Constraints: The bureaucratic challenges of the caretaker government The developing security situation in Lebanon that has resulted in limiting the access of the M&E unit to certain sites. Lessons Learned: To improve the coordination mechanism of the LRF, the M&E Unit is conducting individual meetings with the project/program managers to clarify the required info to be included in the progress reports, in addition to the focus on the collaboration between the implementing UN Agencies and the M&E Unit vis-à-vis the visibility of the LRF and the MPTF requirements. To request monthly reports from the implementing UN Agencies to assess the progress made vis-à-vis the set work plans for projects with high risks and challenges. To participate in the LRF projects’ major events.

| V. FUTURE WORK PLAN |
| --- |
| KEY MILESTONES | July-13 | August-13 | September-13 |
|  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 |
| Coordinate with Project/program managers |  |  |  |  |  |  |  |  |  |  |  |  |
| Manage projects progress reports |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct field visits to assess project progress |  |  |  |  |  |  |  |  |  |  |  |  |
| Coordinate with RCO |  |  |  |  |  |  |  |  |  |  |  |  |
| Coordinate with MoET |  |  |  |  |  |  |  |  |  |  |  |  |
| Provide technical support to the SC |  |  |  |  |  |  |  |  |  |  |  |  |
| Provide technical support to the PAG |  |  |  |  |  |  |  |  |  |  |  |  |
| Manage and support the management of LRF visibility (LRF video, website, newsletter…) |  |  |  |  |  |  |  |  |  |  |  |  |
| Support resource mobilization for new LRF phases |  |  |  |  |  |  |  |  |  |  |  |  |
| Coordination with LRF stakeholders |  |  |  |  |  |  |  |  |  |  |  |  |
| Maintain library of key assessments, evaluations, lessons learned and surveys |  |  |  |  |  |  |  |  |  |  |  |  |