CENTRAL FUND FOR INFLUENZA ACTION

PROGRAMME QUARTERLY PROGRESS UPDATE

(for posting on the CFIA website)

31 March 2012

| Participating UN or Non-UN Organization: | International Civil Aviation Organization (ICAO) | UNCAPAHI Objective(s) covered: | Contingency planning for operational continuity during a pandemic |
| --- | --- | --- | --- |
| Implementing Partner(s): | World Health Organization (WHO), Office for the Coordination of Humanitarian Affairs (OCHA), International Air Transport Association (IATA), Airports Council International (ACI) |
| Programme Number: | CFIA-A17 (RAB 09/801 ICAO numbering) |
| Programme Title: | Cooperative Arrangement for the Prevention of Spread of Communicable Disease by Air Transport (CAPSCA) |
| Total Approved Programme Budget: | US$112,724 |
| Location: | Middle East |
| MC Approval Date: | 17 May 2010 |
| Programme Duration: | 24 months (probable extension) | Starting Date: | May 2010 | Completion Date: | May 2012 |
| Funds Committed: | $0 | Percentage of Approved: |  |
| Funds Disbursed: | $36,025.00 | Percentage of Approved: | 32% |
| Expected Programme Duration: | 31 months | Forecast Final Date: | December 2012 | Delay (Months): | 7 months |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| Organised Meetings State participation Assistance Visits to International airports | The next CAPSCA-MID/2 meeting re-scheduled to 3-5 December 2012. Four states joined CAPSCA-MID project (Egypt, Jordan, Saudi Arabia, and Sudan) Progressed the CAPSCA-MID project. Two assistance visits planned during June 2012 to Jordan and Saudi Arabia. One State (Sudan ) requested an assistance visit to assess the contingency preparations at Khartoum airport.(visit planned in September 2012) Promoted CAPSCA at MIDANPIRG meeting 22-26 April. . | 32% |

Qualitative achievements against outcomes and results:

Created awareness of CAPSCA Project during MIDANPIRG/13 meeting 22-26 April 2012.. Continued efforts to promote participation of the States of the Middle East in CAPSCA-MID project.(Increased State membership to 26% of States in the region)

# Footnotes

The term “programme” is used for projects, programmes and joint programmes.