PEACE BUILDING FUND (PBF)

ANNUAL programme NARRATIVE progress report

REPORTING PERIOD: 1 january – 31 December 2011

| Programme Title & Project Number |  | Country, Locality(s), Thematic/Priority Area(s) |
| --- | --- | --- |
| Programme Title: Solid Waste Management Programme Number (if applicable) …………………. MPTF Office Project Reference Number: PBF/IRF-34 (ID00078254) |  | (if applicable) Country/Region: Puntland State, Somalia |
|  |  | Thematic/Priority: Solid Waste Management |

| Participating Organization(s) |  | Implementing Partners |
| --- | --- | --- |
| Organizations that have received direct funding from the MPTF Office under this programme: UNHCR |  | National counterparts (government, private, NGOs & others) and other International Organizations - Municipal authorities of Galkayo north and south - COOPI |

| Programme/Project Cost (US$) |  | Programme Duration |
| --- | --- | --- |
| MPTF/JP Contribution: by Agency (if applicable) | $470,959 |  | Overall Duration (months) | 18 Months |
| Agency Contribution by Agency (if applicable) | Relevant staffing |  | Start Date (dd.mm.yyyy) | 01 January 2011 |
| Government Contribution (if applicable) | 00.00 |  | End Date (or Revised End Date) | 30 June 2012 |
| Other Contributions (donors) (if applicable) | 00.00 |  | Operational Closure Date | 31 July 2012 |
| TOTAL: | $470,959 |  | Expected Financial Closure Date | 31 July 2012 |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Assessment/Review - if applicable please attach Yes No Date: dd.mm.yyyy Mid-Term Evaluation Report – if applicable please attach Yes No Date: dd.mm.yyyy |  | Name: Bruno Geddo Title: Representative Participating Organization (Lead): UNHCR Representation in Somalia Email address: geddo@unhcr.org |

List of acronyms

| UNCT | United Nations Country Team |
| --- | --- |
| PBF | Peace Building Fund |
| COOPI | Cooperazione Internazionale |
| CBOs | Community Based Organizations |
| IDP | Internally Displaced People |
| INGO | International Non-governmental Organisation |
| MoI | Ministry of Interior |
| MoS | Ministry of Security |
| NRC | Norwegian Refugee Council |
| PAR | Participatory Action Research |
| UNHCR | United Nations High Commissioner for Refugees |
| IPFMR | Implementing Partner Financial Monitoring Report |

NARRATIVE REPORT FORMAT

# Purpose

The large scale-influx of Internally Displaced Persons (IDPs) into Puntland as a result of protracted conflict, human rights violations and natural disaster in Somalia, coupled with the presence of asylum-seekers and refugees from neighboring Ethiopia, has been contributing to rising tensions between the local and displaced population in Puntland. These tensions, exacerbated by the growing clan conflicts, threaten fragile stability in Puntland and risk the situation slipping back to an open conflict.

Against this background, UNHCR proposed to reduce the tensions between the two communities through four sets of projects: (1) peaceful coexistence and conflict resolution, (2) capacity-building of the police and judiciary in the areas of IDP concentration, (3) solid waste management in Galkacyo and (4) construction of permanent shelter and basic services for IDPs and local population in Galkacyo. All the four pillars aim to bring the local and displaced communities together towards the overall goal of the reduction of tensions between the two.

Within this context, this project is designed to bring the local and displaced communities together through waste management efforts. A large number of IDP women rely on door-to-door garbage collection as their main livelihood activity. Since they are also required to pay fee to dispose collected garbage in privately run dumping grounds, they tend to keep it next to their residence for some days in order to minimize the payment of the fee. The local population residing in the proximity of IDP settlements often complains about the unhygienic state of affairs, contributing to the tension between the communities. The project tries to address the issue through better management of solid waste while also contributing to safe livelihood of IDP women. The project is also designed to bring the divided city of Galkacyo together – Darod dominated north and Hawiye dominated south – around solid waste management.

# Resources

This project is funded by MPTF/JP to the tune of $470,959. There has been no budget revision undertaken through out project implementation

The good practices adopted by UNHCR in financial management of the project include the following;

- Routine monitoring of the project activities by UNHCR field office in Galkayo. This ensures that all agreed activities were implemented according to the agreed work plan

- Regular activity planning meetings between UNHCR and the implementing partner engaged to carry out the different activities. This ensures a smooth and consistent follow up of agreed specific activities

- Verification of implementing partner financial monitoring reports (IPFMRs) prior to disbursement of any subsequent installments. This ensures safety of project resources and value for money for any particular procurement or service.

- UNHCR direct implementation for some activities in which the implementing partner had no comparative advantage, and also for particularly large procurements including procuring of solid waste trucks. This practice was not only cost saving but also ensures safety of operational funds

- Full consultation with and engagement of the municipal authorities throughout the process to instill the sense of ownership and ensure sustainability

Challenges faced:

- The level of tension between north and south Galkacyo has risen to an unexpected level during the implementation period. As a result, instead of promoting a coordinated, collaborative waste management system between the two parts of Galkacyo, it was decided to implement the same activities separately in the two locations.

- The municipality in Galkayo North failed to identify land for the construction of a landfill. The piece of land which had initially been identified became disputed as someone emerged to claim its ownership. This compelled the halting of this specific activity to allow the matter to be resolved by the authorities there. Discussions are going on to resolve this impasse

Human Resources:

International Staff

|  | Title | Type | Number | Location |
| --- | --- | --- | --- | --- |
| 1 | Representative | Programme | 1 | Nairobi |
| 2 | Deputy Representative | Programme | 1 | Nairobi |
| 3 | Snr. Protection Officer | Operation | 1 | Nairobi |
| 4 | Head of Field Office Galkayo | Operation | 1 | Galkayo |
| 5 | Associate Programme Officer | Operation | 1 | Galkayo |
|  | Total |  | 05 |  |

National Staff

|  | Title | Type | Number | Location |
| --- | --- | --- | --- | --- |
| 1 | Assistant Programme Officer | Programme | 1 | Nairobi |
| 2 | Field Associate | Operation | 1 | Galkayo |
| 3 | Supply Associate | Operation | 1 | Galkayo |
|  | Total |  | 03 |  |

# Implementation and Monitoring Arrangements

UNHCR entered into an implementation agreement with COOPI, an Italian NGO with solid waste management experience in Somalia. The project has been implemented and monitored in accordance with UNHCR’s standard rules and regulations governing project implementation. The project involved conducting awareness campaigns and the creation of IDP women Community Based Organizations (CBOs), which have been supported to register with Galkayo municipalities. These CBOs are to make payments of nominal monthly fees, constituting a modest revenue stream for the running and maintenance the solid waste management system.  The CBOs have been trained in financial management, and equipped with donkey carts, protective clothes, wheelbarrows, etc. to facilitate door-to-door collection of garbage.

Construction/rehabilitation of public collection points have been undertaken through cash for work, accompanied with a cleaning campaign to remove existing garbage.  This created a positive, initial “quick win” of the project, presenting visible and tangible impact on both displaced and local communities. In the second phase, a workshop for the municipality and principal stakeholders was conducted alongside awareness campaigns.  A Solid Waste Management Unit created within the municipality is designed to supervise the entire garbage collection process and benefit from training on technical and management skills with byelaws to support this system.  The final phase involves the construction/rehabilitation of public landfill site and provision of equipment (truck, tools, protective clothes, etc.) to the municipality. This series of interventions is designed to benefit the whole of municipality and its residents, contributing to the spirit of coexistence through the project. In North Galkayo, this has not taken place as the land identified by the municipality authorities was later claimed by an individual. Discussions to resolve the matter are under way.

In terms of monitoring and coordination, UNHCR field office in Galkayo has been fully engaged in overseeing the project.  COOPI is present in Galkayo throughout the project implementation cycle.  The local municipal authorities were also fully involved in all aspects of the project.

Urban IDP women currently engaged in ad hoc garbage collection will form an integral part of the project and will benefit from technical coordination, increased economic empowerment and overall increased level of sanitation.  This should lead to the reduction in social tensions.  The IDP women were consulted through participatory assessments and were profiled.

The host community has benefited from an increased level of sanitation, thereby reducing social tensions with urban IDPs who were sometimes forced to bring garbage home due to “gatekeeper” fees charged for dumping.  The host community was consulted through participatory assessments and meetings. The municipal authorities should benefit from a viable and sustainable solid management service, leading to improved sanitation, reduction in social tension, capacity building and potential earnings

# Results

4 CBOs comprising 150 members each have been established and registered with the local municipalities (2 each in North and South Galkayo). The details of the CBOs are as follows:

Galkayo North.

CBO 1 Name: Hilaac

Women	137

Men	13

TOTAL    150

CBO 2 Name: Wadajiir

Women	138

Men	12

TOTAL    150

Galkayo South

CBO 1 Name: Hormar

Women:   128

Men:        22

TOTAL:   150

CBO 2 Name: Midnimo

Women:   138

Men:      12

TOTAL  150

80% of the CBO members are IDPs while 20 % are from the host community.

Memorundums of Understanding (MoUs) have been signed between COOPI (UNHCR’s implementing partner for this project) and the four CBOs defining the modalities of operations. The CBOs have also been facilitated to sign MoUs with the respective municipalities of Galkayo north and south. The CBO members are now engaged in waste collection in an organised manner, where they work in groups and in close collaboration with the municipalities.

Sanitation tools comprising the following have been purchased and provided to the 4 No. CBOs

| ITEM | No. |
| --- | --- |
| Wheelbarrow | 40 |
| Shovels | 100 |
| Mining Bars | 40 |
| Pick axes | 60 |
| Rakes | 100 |
| Brooms | 200 |

The CBO members are making use of the tools provided in their day-to-day activity of collecting solid waste.

541 CBO members are earning income through waste collection activities with an account opened for each CBO.

4 CBOs have been provided with safety gear kits. Each kit consists of dust coat, dust masks, leather gloves and gum boots. The items were provided follows:

| Dust coats: | 240 |
| --- | --- |
| Dust masks: | 328 |
| Leather gloves: | 328 |
| Gum boots: | 186 |

14 skips designed in a participatory approach involving COOPI, CBOs and the municipalities have been manufactured and distributed. The skips have been placed in strategic sites within the towns and Bulo Bacley & Jawanley IDP settlements to be used as waste transit points.

One garbage truck was procured and provided to Galkayo South Municipality, another is planned for Galkayo North.

Training sessions for 44 members of the CBOs and 12 members of the Galkayo North & South municipal snitation departments were conducted. Due to lack of freedom of movement between the two parts of the city, two separate sessions had to be held. The participants were trained in guiding principles and sustenance of CBOs, basic skills in management of finances/revolving credit, effective and safe garbage collection and disposal, institutionalisation of solid waste management system, preparation of plans to revamp solid waste management within the town, and in preparation of draft gender sensitive by-laws.

Sessions to review the existing solid waste plans and bylaws were also conducted. Ammendiments were made to these plans and bylaws. The session comprised of 44 members of the CBOs and 12 members of the Galkayo North & South municipal sanitation departments, who had been trained earlier.

Construction of a landfill in Galkayo South is underway, with 250 labourers engaged, earning US$5.00 per cubic meter of soil excavated and removed. In the north, the activity has been faced with challenges related to land,, but it is expected that the local authorities will resolve the issue soon and construction will be commence.

Three clean-up campaigns (each taking 3 days) were conducted to remove the accumulated waste in Bulo Bacley (Galkacyo North) and Jawanley IDP (Galkacyo South) settlements and their surroundings through cash for work approaches engaging 340 members. The clean-up campaigns were done by engaging the settlement IDP committee, CBO members and with participation of families from neighboring urban poor households. The respective local authorities took a lead role in mobilization and supervision of the activity. A total of 414 tons of garbage was removed from Bulo Bacley IDP settlement and 450 tons in Bulo Jawanley IDP settlement and the surroundings. The campaigns also served as an opportunity to raise awareness about the CBOs, and also highlight the benefits of staying in a garbage free environment.

The project has so far contributed to the reduction of tensions between IDPs and the host community, as well as strengthening the capacity of the municipalities in managing solid waste generated by its residents. IDP women have also  benefited from an improved working environment with a stable income stream.

# Future Work Plan (if applicable)

There were challenges faced in the allocation of land by the local authorities for the construction of a land fill in Galkayo north. This activity could not be implemented in 2011 to allow the local authorities to sort out ownership issues with the claimant of the identified land. Therefore construction of a land fill in Galkayo north is expected to start soon. Other 2011 activities proceeded as planned.

|  | Performance Indicators | Indicator Baselines | Planned Indicator Targets | Achieved Indicator Targets | Reasons for Variance (if any) | Source of Verification | Comments (if any) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 1: Women are empowered to overcome specific post-conflict hardship (eg economic insecurity) and to end gender-based violence and discrimination. |
| Output 1.1 Women are formed into CBOs to engage with the authorities | Indicator 1.1.1 Number of garbage collection CBOs operating | Absence of organized garbage collection organizations | 4 women garbage collection groups (CBOs) are established | 4 women garbage collection groups (CBOs) have been established | No variance, output achieved as planned | Field monitoring reports CBO Registration certificates | CBOs will need continued support in terms of capacity building |
| Outcome 2: The local community perceives the IDPs as a contributing factor, rather than a destabilizing factor or burden. |
| Output 2.1 Women are equipped with tools and protective gear and are trained in basic sanitation principles and apply them. | Indicator 2.1.1 Number of women trained in basic sanitation principles | Women were ignorant about basic sanitation principles | 541 women are trained in basic sanitation principles | 541 women were trained in basic sanitation principles | No variance, output achieved as planned | Field monitoring reports Training reports Attendance lists project progress reports and results frameworks | Nil |
|  | Indicator 2.1.2 Number of women equipped with tools and protective clothing | IDP women involved in garbage collection have no appropriate tools and protective gear | Women who are members of CBOs are provided with tools and protective gear | 541 women 100% members of CBOs were provided with appropriate tools and protective gear | No variance out put achieved as planned | Field monitoring reports Distribution lists project progress reports and results frameworks | Continued monitoring by the municipality in the use of the tools and their replacement |
| Outcome 3: Basic infrastructure and services are restored and expanded |
| Output 3.1 Existing garbage in Galkayo town is removed | Indicator 3.1.1 Within 3 months of start of project, current solid waste dumpsites are removed | Huge hips of solid waste littered allover Galkayo municipalities | 100% solid waste in dumpsites are removed from the municipalities | 100% solid waste in dumpsites measuring 864 tons was removed from the municipalities | No variance out put achieved as planned | Field monitoring reports Activity reports project progress reports and results frameworks | Nil |
| Output 3.2: Women are empowered economically to engage in income generation | Indicator 3.2.1 Number of IDP women with increased access to economic resources | IDP women lacked appropriate means of livelihoods, had no access to economic resources | Women are encouraged to become members of CBOs and to engage in commerce through their revolving fund | 80% of the women are members of CBOs are engaged in the activities of the revolving fund | No variance out put achieved as planned | Field monitoring reports Activity reports project progress reports and results frameworks | Nil |
| Output 3.3: Municipality improves solid waste management systems and increases the volume of solid waste removed | Indicator 3.3.1 Number of garbage collections per week | No systematic garbage collection system in the municipalities | Number of times of garbage collection is increased to 5 times a week | The municipalities of Galkayo have been capacitated to collect garbage 5 times a week | No variance out put achieved as planned | Field monitoring reports Activity reports project progress reports and results frameworks | Nil |
|  | Indicator 3.3.2 Number of garbage landfills constructed | No landfills or skips where garbage is first collected | 02 landfills are constructed and 12 skips are fabricated and distributed in designated areas of the municipalities | 01 landfill was constructed in south Gal kayo municipality. 12 skips were fabricated and distributed in designated areas of the municipalities | 01 landfill in north Gal kayo could not be constructed due to a dispute over land which had been identified by the municipality. | Field monitoring reports Activity reports project progress reports and results frameworks | The dispute over land is being handled by the municipality authorities, once solved the activity will be implemented |
|  | Indicator 3.3.3: Number of garbage collection trucks operational | No truck for garbage collection therefore limiting the quantity of garbage removed | 02 trucks are provided to the two municipalities, one for north, the other for south Gal kayo | 01 truck was procured and provided to south Gal kayo | 01 truck was not procured | Field monitoring reports Activity reports project progress reports and results frameworks | UNHABITAT has promised to provide a truck to north Gal kayo municipality |

# Footnotes

The term “programme” is used for programmes, joint programmes and projects.

Strategic Results, as formulated in the Performance Management Plan (PMP) for the PBF; Sector for the UNDG ITF.

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval by the relevant decision-making body/Steering Committee.

All activities for which a Participating Organization is responsible under an approved MPTF programme have been completed. Agencies to advise the MPTF Office.

# Text boxes

VI. INDICATOR BASED PERFORMANCE ASSESSMENT