## Dec 2014-Dec 2015 WP
NAME: Scaling Up Nutrition-Civil Society Alliance (SUN CSA) DEPARTMENT: Quality Assurance(QA) WORK PLAN: December 2014 to December 2015
Outcomes | Activity | Sub-Activity (ies) | TIME FRAME | [13 empty] | Completion Date | Source of Funds | Responsible Person (s) | Performance Indicator & Output | Status
|  |  | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
Outcome 1: Civil Society Alliance established to scale up nutrition in Kenya
| Finalization of CSOs mapping conducted at county level | Finalize on the CSOs mapping,Hold one national meeting with all CSA members for dissemination of the mapping report | [14 empty] | 28th February 2015 | MPTF | Grace Gitau | 47 counties mapped,1 mapping report finalized and disseminated | 28 individual mapping reports submitted
| Establish CSA governance structure (Finalize CSA ToR and ToR for the CSA EC) | Formation of TOR taskforce,Review of Draft TOR,One day workshop on TOR finalization with external Consultant based on need,EC Validation and Dissemination to CSA members | [14 empty] | 31st March 2015 | MPTF | Pius Mulonzya and Timothy Bainbridge | 1 CSA TOR finalized and disseminated | Review by EC ongoing
| Hold Monthly Executive Committee (EC) meetings to discuss and review implementation of CSA activities | Invitation of EC members to alternate face to face meetings,Minutes Taking and Timely Circulation of Minutes | [14 empty] | 31st December 2015 | MPTF | Grace Gitau and Titus Mung'ou | 12 meetings held,minutes finalized and circulated to members | All monthly meetings held
| Hold Quarterly CSA Meetings | Invitation of CSA members to quarterly meetings,Minutes Taking and Timely Circulation of Minutes | [14 empty] | 31st December 2015 | MPTF | Grace Gitau and Titus Mung'ou | 5 CSA Quarterly meetings held,minutes finalized and circulated to members,EC Members participating in CSA advocacy initiatives | 3 CSA meetings held,next CSA meeting tentative date 10th Dec 2014-Head of Nutrition invited
| Facilitate development of CSA strategic plan | Development of consultant TOR,selection of Consultant,stakeholders workshop on strategic planning,Hold Strategic Plan Validation meeting,Dissemination of CSA Strategic Plan | [14 empty] | 31st March 2015 | MPTF | Grace Gitau and Titus Mung'ou | 1 CSA Strategic Plan completed and disseminated | Draft Consultant TOR shared to EC on 30/11/14 for review
| Facilitate training of CSA members on nutrition policy influence and advocacy | Sharing of the nutrition advocacy agenda in NTF,Mobilization,identification of training facilitators,procurement of stationery,venue,recognition awards,follow up with CNC on nutrition advocacy initiatives at the county level | [14 empty] | 31st January 2015 | PRB | Grace Gitau,Manaan Mumma and Wema Adere | 1 training conducted,1CSA Chapter formed | Priority County identified,county team awaiting confirmation on implementation date
| Hold an annual learning forum for CSA members on nutrition specific and nutrition- sensitive programming | Mobilization,Hold planning meetings,procurement of stationery,media and publicity materials | [14 empty] | 28th February 2015 |  | Grace Gitau and Conference Steering Committee | 1 learning forum conducted,Sharing of best practices in nutrition advocacy done | No funding available,Donor Network conducting nutrition symposium same month
| Hold annual CSA conference on nutrition | Mobilization,Hold planning meetings,procurement of stationery,media and publicity materials | [14 empty] | 28th February 2015 |  | Grace Gitau and Conference Steering Committee | 1 training conducted,1CSA Chapter formed | No funding available,Donor Network conducting nutrition symposium same month
Outcome 2: Effective participation of the CSOs in the SUN movement
| Facilitate participation of CSA members in multi- sectoral platforms at national and county levels to champion scaling up nutrition | CSA members mobilization to participate in the Multi Stakeholder Platform and other multi-sectoral platforms at national level;mobilization of the county chapters to participate in County NTFs and multi-sectoral platforms | [14 empty] | 31st December 2015 | MPTF | Grace Gitau | CSA Members contributing to the nutrition agenda at county and national level | The national MSP will be formed early 2015; County CSA members participating in CHSFs and other relevant forums
| Facilitate annual engagement with National Assembly and the Executive to champion scaling up nutrition | Mobilize National Assembly and Executive for sensitization meetings on scaling up nutrition; conducting courtesy calls to the National Assembly and Executive on Scaling Up Nutrition; sharing peridic updates on SUN through the SUN Government Focal Point | [14 empty] | 31st March 2015 | MPTF and PRB | Grace Gitau | Review of Nutrion Action Plans and County Integrated Development Plans | Not done
| Facilitate engagement with County Executives and County Assembly | [15 empty] | 31st December 2015 | MPTF | Grace Gitau | 6 meetings with County Governments to sensitize on scaling up nutrition
| Support CSA forums and meetings in 6 Counties to generate discussions and collective action on the nutrition action plan and County Integrated Development Plans (CIDP) | Mobilize CSA Members at the county,Procurement of meeting venue,stationery and sourcing for finalized CNAPs and CIDPs for discussion at county level | [14 empty] | 31st December 2015 | MPTF and World Vision | County CSA Chapters Chairs | Increased invewstment in county nutrition budgets; Harmonized CNAPs and CIDPs | Engagement of some county executive and assemebly engaged in initial discussions during CNAT trainings
| Support annual policy meetings at county level | Support semi- annual policy meetings for CSA nodes/chapters in 6 Counties
| Advocate for formulation of policy frameworks to support implementation of NNAP and CIDP | Conduct meeting with the Parliamentary Health Committee to influence the Draft Health Policy and Draft Health Bill,Conduct post 69th United Nations General Assembly meeting on brdging knowledge gap on SDGs and adoption of the Outcome Document,follow up on Kenya's commitment to Rome Declaration on Nutrition through ICN2 Particpants CSO Forum | [14 empty] | 31st December 2015 | MPTF | County CSA Chapters Chairs | Enhanced policy environment on the review of Draft Health Policy 2014/2030, Draft Health Bill 2014, National Nutrition Action Plan,Post 2015 Development Agenda,follow up on Kenya's commitment in Rome Declaration in Nutrtion Nutrition agenda well articulated in Draft Health Policy and Draft Health Bill, workshop on bridging the SDGs knowledge gap anmong parliamentarians done and adoption of the Outcome Document | Position papers developed and submitted on Health Policy 2014/2030.Draft Health Bill 2014 and Kenyan CSOs Common Position on SDGs,participation in the development of the CSOs Vision Statement on ICN2 Rome Declaration on Nutrition and Framework for Action and positioning of nutrition in the MOH.
| Facilitate participation of CSA nodes and communities in 6 Counties budgeting processes | CSA members mobilization to participate in county budgeting processes for 2015/2016 | [14 empty] | 30th November 2015 | World Vision | County CSA Chapters Chairs | 6 counties participating actively in 2015/2016 budgeting processes and increased nutrition investment in | CSA has joined a budget review partnership
| Facilitate media training on nutrition reporting | Identification of training participants and trainers; Procurement of stationery,training venue; Conduct media training for journalists,CSO communications staff,CSA editorial committee and CHWs,report compilation and dissemination; follow up with trainees on nutrtion reporting | [14 empty] | 30th April 2015 | MPTF and PRB | Grace Gitau and Manaan Mumma | 30 Media and CSA Programme personel capacity built on nutrition reporting | Nil
| Facilitate media visits and documentation exercises to profile stories on SUN, nutrition action plan | Identification of media journalists and media stories; planning for visit logistics and mobilization for media interview participants;documentation of media stories | [14 empty] | 30th October 2015 | MPTF and PRB | Grace Gitau and Titus Mung'ou | Media stories on SUN and NNAP reported; | Nil
| Produce semi- annual SUN CSA e-bulletin and newsletter for sharing with members and stakeholders nationally, regionally and globally | Hold meetings with the CSA editorial board,selection of suppliers,designing and review of CSA bulletin,printing and distribution of bulletin | [14 empty] | 31st December 2015 | MPTF | Grace Gitau | 3 timely CSA semi-annual bulletins developed and disseminated for increased CSA visibility | Request on articles from CSA members done
| Facilitate participation of Kenya SUN CSA in national, regional and international SUN movements activities/ forums and events | Mobilize CSA members to participate in SUN movement activities through conference presentations-oral and poster,exhibitions,participation in SUN organized activities | [14 empty] | 31st December 2015 | No Cost Activity | Grace Gitau and Executive Committee | Increased SUN visibility and report on participation in these forums | CSA represented in regional and international forums
| Mobilize CSA members to actively participate in national/ nationwide campaigns during nutrition related events | Mobilize CSA members to participate in national/nationwide activities through conference presentations-oral and poster,exhibitions,participation in CSA,MOH and other partner organized activities | [14 empty] | 31st December 2015 | No Cost Activity | Grace Gitau and Executive Committee | CSA members participation in national MSP platforms, learning forum and in six CSA priority counties | Members participating in national,regional and international commemorations
Outcome 3: CSA advocates for increased commitment and accountability in scaling up nutrition
| Identify and empower nutrition champions in strategic positions of policy influence | Develop the nutrition champions selection criteria; validation of criteria by Nutrition Division;Engage the CSA in identification of nutrition champion nationally and county chapters in selection of county nutrition champions; sensitization of selected nutrition champions on SUN;engagement of nutrition champions in SUN activities | [14 empty] | 31st December 2015 | No Budget Allocation | Grace Gitau | 6 nutrition champions scaling up leading the scaling up nutrition campaign at county level for improved nutritional status. CSA represented in relevant forums and timely feedback shared | Nutrition Champions selection criteria shared with Head of Nutrition and Dietetics Unit;on county nutrtion champion identified.Need for budget allocation consideration on sensitization.
| Facilitate meeting with the Council of Governors and Parliamentary Health Committee to sensitize them on scaling up nutrition | Mobilization of the COG and PHC;conduct one breakfast sensitization meeting for the COG and PHC on scaling up nutrition and its priority for the Counties | [14 empty] | 30th October 2015 | MPTF and PRB | Grace Gitau,Titus Mung'ou and Manaan Mumma | Increased investment in nutrition across all sectors | Not done
| Produce simplified IEC materials on SUN and nutrition action plan | Hold meetings with the CSA editorial board,selection of suppliers,designing and review of IEC materials,printing and dissemination of IEC materials to CSA audiences | [14 empty] | 15th April 2015 | MPTF | Grace Gitau | CSA increased visibility; increased CSA funding | Requests done from procurement on estimated costs to guide procurement process
| Support interface meetings between 6 CSA nodes and County leadership | Conduct consultative and interface meetings with the CSA Chapters and the County Government | [14 empty] | 30th November 2015 | MPTF | County CSA Chapters Chairs | Review of the County nutrition plans for progress performance review (include narrative and Budget)
| Facilitate CSA nodes in 6 Counties to develop simple tracking tools for implementation of nutrition interventions across sectors | Conduct meeetings in 6 counties,development of CNAP tracking tool,Piloting of the tracking tool,review and dissemination of tracking tool | [14 empty] | 30th April 2015 | MPTF | County CSA Chapters Chairs | Review of the County nutrition plans for progress performance tracked (include narrative and Budget) to inform implementation and budget allocation | Discussions on CNAP overview done with selected County Government Officials in some counties during CNAT
| Facilitate 6 accountability and feedback forums on the implementation of nutrition interventions across sectors | Conduct accontability and feedback forums in partnership with BBC Media Action on NNAP implementation | [14 empty] | 30th June 2015 | MPTF | Grace Gitau and Diana Njeru | 6 counties feedback meetings held and recommendations implemented | Initial discussions done with BBC Media Action on possible collaboration and joint resource mobilization on the deliverable
| Facilitate budget review and analysis on investment in nutrition across different sectors | Development of consultant TOR,selection of Consultant,stakeholders workshop on strategic planning,Hold Strategic Plan Validation meeting,Dissemination of CSA Strategic Plan | [14 empty] | 31st May 2015 | MPTF | Grace Gitau & Timothy Bainbridge | 6 counties participating actively in 2015/2016 budgeting processes and increased nutrition investment in | Initial meeting with Institute of Economic Affairs set on 05/12/14
| Facilitate production and dissemination of policy briefs on investment in nutrition in different sectors | Hold meetings with the CSA editorial board, conduct audience segmentation; selection of suppliers,designing and review of policy briefs,printing and distribution of bulletin | [14 empty] | 31st March 2015 | World Vision | Grace Gitau | Thematic policy briefs developed and disseminated | Initial meeting with Institute of Economic Affairs set on 05/12/14
Note on N18: Grace Gitau: 2 county,1 national

## Annual Workplan (hidden)
NAME: SEXUAL REPRODUCTIVE HEALTH,EMPOWERMENT AND RIGHTS (SERHER) DEPARTMENT: PREVENTIVE AND PROMOTIVE HEALTH PERIOD: MAY 2014 TO DECEMBER 2014 (YEAR 2013-2014)
| Specific Objective (s) | Output (s)/Target | Detailed activity (ies) | TIME FRAME | [11 empty] | Budget | Responsible person (s) | Performance indicator | Status/Comments
|  |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
|  |  |  | J | F | M | A | M | J | J | A | S | O | N | D
SERHER PROJECT
Specific Objective 1 | To expand Comprehensive Sexuality Education for youth in and out of school | 7 forums held at county level(Homa Bay,Migori,Nairobi,Kajiado,Kilifi,Machakos and Samburu Countiies) | Hold Comprehensive Sexuality Education (CSE) consultations and sensitizations at county level | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 389,000/= | Program Manager
|  | 7 forums held on key populations at County Level | Hold sensitization meetings on key populations at county level | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 0 | 0 | 0 | 0 | 0 |  | Program Manager
|  | 20 TOT and 100 champions trained and certified | Conduct 5 day training of 20 National TOT in CSE | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 100,000/= | Associate Program Officer-Youth
|  |  | Conduct regional champions training in CSE and health equity | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 600,000/= | Associate Program Officer-Youth
|  | 10,000 youth in and school trained in Comprehensive Sexuality Education through cyber peer | Conduct e-training on CSE to youth in and out of school through cyber peer | 0 | 0 | 0 | 0 | 0 | 500 | 1000 | 2500 | 2500 | 2500 | 1500 |  | 500,000/= | Associate Program Officer-Youth
|  | 7 youth empowerment centres equipped with computers to deliver cyber-peer | Procure youth empowerment centres computers for delivery of cyber peer | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 350,000/= | Procurement Assistant
|  | 100 Cyber Peer Educators trained | Conduct regional training of 100 Cyber Peer Trainers for 5 days from 7 project sites(Nairobi,Kajiado,Migori,Homa Bay,Kilifi,Machakos and Samburu) | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 368,500/= | ICT Manager
|  | 7 YECs equipped with toll free phones | To install toll free phones for CSE services provision to youth and key populations | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 84,000/= | Procurement Assistant
|  | 700 Educative DVDs and other materials procured | Procure Cyber Peer DVDs and other educative materials and distribution to YECs | 0 | 0 | 0 | 0 | 0 | 200 | 500 | 0 | 0 | 0 | 0 | 0 | 105,000/= | Procurement Assistant
|  | 1000 effective referrals conducted for youth in and out of school and key populations | Facilitate inward and outward referrals for the target populations for SRH services | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 150 | 250 | 200 | 150 | 150 | 0/= | Associate Program Officer-Youth
|  |  | Develop referral tools for youth and key populations | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 150 | 250 | 200 | 150 | 150 | 2,500/= | Associate Program Officer-Youth
|  | 50 youth and 10 allies sponsored to the 6th NOPE's biennial conference | Sponsor 60 delegates to the conference on 18th to 20th June 2014 and youth day on 19th June 2014 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 1,850,000/= | Conference Coordinator
Specific ObjectIve 2 | To increase key populations participation and representation and claim space for participation and full citizenship | 7 key populations dialogue forums conducted | Conduct key dialogue forums with key populations and relevant stakeholders in the 7 targeted counties | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 3 | 100,000/= | Program Manager
|  | 10 KPs mentored on promotion of effective participation and representation at policy and decision making structures | Conduct mentorship on effective participation and representation to Key Populations at policy and decision making structures-NACC,County Governments and development agencies | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 175,000/= | Associate Program Officer-Youth
|  | 3 KP networking and expression through arts and sports events organized | Identify and mentor KPs to participate in the arts and sports events | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 100,000/= | Associate Program Officer-Youth
|  |  | Mobilize resources for the arts and sports events | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0/= | Associate Program Officer-Youth
|  |  | Organize and conduct the quarterly arts and sports events in 3 counties | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 300,000/= | Associate Program Officer-Youth
Strategic Objective 3 | To strengthen youth networking and SRH advocacy nationally to support advancement of changing perceptions around sexuality,teenage pregnancy,sexual diversity and safe abortion | Periodic arts and sports for expression contest conducted | Conduct annual art for expression contest in one of the counties | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 100,000/= | Associate Program Officer-Youth
|  |  | Conduct annual RH sports tournament targeting sexual minority,young girls and YLHIV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 150,000/= | Associate Program Officer-Youth
|  |  | Conduct quarterly county arts and cycling events in two counties(Homa Bay and Migori) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 150,000/= | Associate Program Officer-Youth
|  | 200 Champions trained nationally on promoting girls and young women sexual rights | Conduct SRH advocacy champions training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 50 | 50 | 50 | 25 | 100,000/= | Associate Program Officer-Youth
|  | 1 boy cooking contest conducted | Organize for boys cooking contest/koroga day in Samburu County | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 30,000/= | Associate Program Officer-Youth
|  | 2 Mr.Right contests conducted in two counties-Kilifi and Machakos | Organize and crown Mr.Right in SRH Advocacy in Kilifi and Machakos as amabassadors of change | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 138,000/= | Associate Program Officer-Youth
|  | National YPEER Focal Point appointed | To recruit National YPEER Peer Focal Point to coordinate YPEER interventions nationally | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30,000/= | Prgogram Manager
|  | 7 YPEER networks formed and strengthened | Conduct YPEER formation sensitization meetings in all the sele cted counties | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 100,000/= | Associate Program Officer-Youth
|  | 1 National YPEER network forum held | Conduct national YPEER forum for all counties | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 150,000/= | Associate Program Officer-Youth
|  | 7 County YPEER network forums conducted | Conduct 7 YPEER forums in the selected counties in SERHER project | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 2 | 454,000/= | Associate Program Officer-Youth
|  | 1 SERHER Project Communications Strategy and materials developed | Engage a consultant to develop the Communications Strategy and implementation plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | HIVOS to source and pay the selected consultant | Program Manager
|  |  | Conduct a 3 day message development workshop with key staff,target beneficiaries and stakeholders | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | HIVOS to cater for the related expenses | Program Manager
|  |  | Develop and distribute IEC materials | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2000 | 2000 | 2000 | 2000 | 2000 | HIVOS to cater for the related expenses | Program Manager
Note on Q7: ggitau: The budget was not sufficient thus the remainder 123,000/= from trainings will be utilized for the County Forums in the 7 counties The youth and key populations will be held concurrently to cut on cost.
Note on Q12: ggitau: The project will be implemented in couunty ICT hubs to cut on costs
Note on Q17: ggitau: This will be designed and produced internally thus only cost incurred on printing paper.