## Sheet1
PBF Assessment of project performance - calendar year 2013
Country | Project name | Project number | PRF or IRF | PBF focus area/ PMP area (e.g. 1.1, 1.2 etc) | Demonstrated catalytic effect: score 0: no effect so far; score: 1: financial leverage; score 2: unleashing peace processes; score 3: both. | Evidence of demonstrated catalytic effect (bullet points) | Risk-taking nature of project (given the existing country context): score 0: low risk; score 1: medium risk; score 2: high risk | Basis for the assessment of risk-taking nature (bullet points) | Project performance for period assessed: score 1: off-track; score 2: on-track; score 3: on-track AND demonstrating significant peace-relevant results | Evidence for performance score (bullet points with key results or issues) | Data sources for this performance assessment (list data sources used, e.g. RUNO report, field mission etc) | Any additional comments on the project
Sudan | Immediate Response for protection and peacebuilding in Southern Kordofan/ Nuba Mountain State | PBF/IRF-35 | IRF | R 2.1 | 0 |  | 2 |  | 0 |  | RUNO reports | MPTFO notes: UNHCR to make NCE request to PBSO and to move Darfur (Joyce). Status is On Going
Sudan | Empowering Women for Peace and Recovery | PBF-IRF-58 | IRF | R 2.3 | 1 | - UN Women recruited a Livelihoods Officer to support a holistic approach to women's economic empowerment and to support the implementation of this particular project. -Project went beyond giving grants and equipment to actually assess needs including capacity needs of beneficiaries (women’s organizations and micro finance institutions) and established linkages with existing government interventions such as the East Sudan Reconstruction Fund. This adds value to the existing structures for economic recovery through strengthening their capacity to deliver for women which will impact more lives than the resources available in the project. A local capacity on Women Entrepreneurship Development (WED) has been created and local female trainers are available to continue promoting WED in East Sudan | 0 | No violent conflict has been registered in the project's intervention areas since 2006. Inter tribal frictions are relatively low in numbers Political tensions are not expressed violently | 2 | Output 1.1: Livelihoods of conflict affected and vulnerable households/women stabilized through income generation and technical training: - Livelihoods and value chain assessment conducted, provided necessary information to outline a capacity building strategy in the project target areas -Strengthening of SME development mechanism within institutions in the target areas through training of 48 participants (local authorities, universities, MFIs, NGOs and community colleges), in turn these participants trained 300 women from different tribes in Kassala, New Halfa, Khshm Algirba, Gadarif, Alguraisha and Doka livelihoods. This contributed to the promotion of peace and social cohesion since preliminary consultations had revealed that the main causes of conflicts were poverty and the lack of communication between the several tribes present in the region Output 1.2 Build local training capacity to promote women in enterprise in the two targeted locations Kassala and Gadarif -Food processing training conducted in Kassala and Gadarif for a group of 47 women provided skills in food transformation, a valuable asset for income diversification Output 1.3: Women’s ability to start IGAs/micro enterprise /cooperatives /agribusinesses in the two locations is strengthened -13 groups of women received grants and complete Get Ahead and Entrepreneurship trainings in agri business. -Two women associations for IGA registered - Gadarif University contracted to conduct a baseline study on women and tribal economy and land tenure in Kassala and Gadarif State | Field missions; project reports | Some of the project's activities were delayed, UN Women requested a NCE till 31 March 2014 to complete project implementation -Limited capacity of the State Ministries of Welfare to provide leadership for women’s economic recovery -The cultural norms that limit women’s access to productive resources including land and participation in viable economic activities remain a challenge -Operational issues (logistics) during field missions, contributed to delays in project implementation [remoteness, bad quality of roads, flash floods. Limited funds in this project, an impediment to reaching a large number of women.
Sudan | Consolidating Peace through DDR in Southern Kordofan State and Khartoum State | PBF/IRF-29 | IRF | R 1.3 | 1 |  | 1 |  | 2 |  | RUNO reports