# RUNO Half Yearly Reporting 					TEMPLATE 4.3

[COUNTRY: Liberia]

PROJECT HALF YEARLY PROGRESS UPDATE

PERIOD COVERED: JANUARY – JUNE 2015

| Project No & Title: | PBF/00088059/Strengthening Local/Traditional Mechanisms for Peace |
| --- | --- |
| Recipient Organization(s): | United Nations Development Program (UNDP) |
| Implementing Partners (Government, UN agencies, NGOs etc): | Ministry of Internal Affairs, Peacebuilding Office |
| Total Approved Budget : | 1500000 |
| Preliminary data on funds committed : | 1,434,187.60 | % of funds committed / total approved budget: | 95.61% |
| Expenditure: | 306,521.99 | % of expenditure / total budget: (Delivery rate) | 23.43% |
| Project Approval Date: | 10/21/2013 | Possible delay in operational closure date (Number of months) | 8 montths up to June 30, 2016. |
| Project Start Date: | November 4, 2013 |  |  |
| Expected Operational Project Closure Date: | October 31, 2015 |  |  |
| Project Outcomes: | County Peace Committees (CPCs) and Early Warning & Early Response (EWER) mechanisms prevent and resolve local disputes in 15 counties |
| PBF Focus Area (select one of the Focus Areas listed below) | County Peace Committees (CPCs) and Early Warning & Early Response (EWER) mechanisms prevent and resolve local disputes in 15 counties |

# Qualitative assessment of progress

| For each intended outcome, provide evidence of progress during the reporting period. In addition, for each outcome include the outputs achieved. (1000 characters max per outcome.) | Outcome 1: The project built upon the gains made in year one completing planned tasks. To date, peace structures have been harmonized in 7 counties while plans have been completed for additional 4 by June ending. Those structures are already collaborating with each having convened atleast one meeting. Early Warning and Early Response Center was set up at the Gbarnga Regional Justice and Security Hub while logistical supplies were procured for the other two centers in Zwedru and Harper. Conducted Awareness building at the Gbanga hub building strategic linkage between the community based EWER system and the Justice and Security Sector; conducted training in Gbarnga, Zwedru, Fish Town and Harper for 88 Early Warning reporters (Output 2); In a competitive process, 10 small grants were awarded to CSOs to support grassroot capacity building; conducted two mini workshops and a reflection session for grantees. CSOs’ engagements at both grass root and national levels are gaining momentum. Outcome 2: Outcome 3: Outcome 4: |
| --- | --- |
| Do you see evidence that the project is having a positive impact on peacebuilding? (1000 characters max.) | The project is already making some positive impact at the community levels. Peace structures are being harmonized at the county level with the goal of ensuring greater collaboration and collective actions on issues relating to building peace, violence prevention and promoting reconciliation. County Peace committees already are taking the lead in ensuring peace. For example, when violence broke up in Lofa County recently, the county peace committee mediated during the early stages which led to the appointment by the Government of Liberia of the Head of the County Peace Committee to chair a committee to investigate the causes of the violence and to come up with recommendations to prevent a reoccurrence. In the same vein, the Margibi County Peace committee held a peace consolidation to inform the public and local government of their existence. Among others, small Grant Funds are providing skills for women, youth and community dwellers in the project counties. |
| Were there catalytic effects from the project in the period reported, including additional funding commitments or unleashing/ unblocking of any peace relevant processes? (1000 characters max.) | The project received from UNDP $25,000 which was applied to certain aspects of the budget not provided adequate funding initially. Earlier, towards the end of 2014, the PBO received on behalf of the Early Warning and Early Response Working Group (EWER WG) approximately $47,000 from Humanity United to fight violence related to the the spread of Ebola Virus. This complimented the work of this project. Also, Humanity United, a US based Foundation, through a grant to Trust Africa has committed to cover the pay of the the Project Manager for 12 months until January 2016. |
| If progress has been slow or inadequate, provide main reasons and what is being done to address them. (1000 characters max.) | At the moment, the project is progressing according to plan; though we had to move some activities forward due to delays (2.5 months) in approving of project annual work plan. Also, project vehicles were turned over towards the end of the first quarter making movements to the field very challenging until recently. The project activities were adjusted bringing activities back on track. There will still be a need for project extension because of valuable time lost in year one due to the five months delay in approving year one work plan and the outbreak of the Ebola virus which caused some activities to be postponed. |
| What are the main activities/expected results for the rest of the year? (1000 characters max.) | Complete harmonization of peace structures, reorganize dormant county peace committees; Strenghten CPC and provide them with logistics and other support as was decided through their action planning process. Gender sensitive leadership and peacebuilding training will be delivered to 400 of the targeted 900 Peace committees and similar structures. Two additional Early warning rapid response centers will be established and made functional. Atleast five additional small grants will be provided to CSOs following a transparent vetting process. This will increase the number of small grantees to about sixteen national CSOs. The project will provide capacity building and logistical support to the National Secretariat of two peace consolidation and violence prevention structures namely the National Civil Society Council and the Early Warning and Early Response Working Group. Disseminate Peace and reconciliation messages by 20 community radio stations. |
| Is there any need to adjust project strategies/ duration/budget etc.? (1000 characters max.) | There is no need to adjust project strategies rather, steps are being taken to mainstream post-ebola activities so that activities remain the same but consideration is given to the effects of the EVD attack. what is necessary to do is to adjust the duration of the project. The project commenced on a Very slow start- five months delay in approving initial work plan and then two months in approving year two work plan. Coupled with that, the Ebola virus and the delay in procuing project vehicles kept the team slow initially. We are therefore requesting 8 month no cost extension up to and including June 30, 2016. |
| What is the project budget expenditure to date (percentage of allocated project budget expensed by the date of the report) – preliminary figures only? (1000 characters max.) | To date, the project has expended approximately USD 306,521.99. This however excludes funds already committed through contract and purchase order currently awaiting payment. The total project budget is 1.5 million United States Dollars. This means we have expended approximately 23% of project funds. The project is designed in a way that most of the cost intensive deliveries to CPCs , CSOs and other community actors will happen during the next eight months which will increase the delivery rate accordingly. |
| Any other information that the project needs to convey to PBSO (and JSC) at this stage? (1500 characters max.) | The project emphasized a lot on collaboration with other PBSO funded projects. The project collaborated with the Independent National Human Rights Commission, The Ministry of Gender/UN Women Project and the Justice and Security Program; evidence of this is the inclusion of participants of these projects in the harmonized county peace structures. Income generation and skill development activities supported as part of the small grant initiative is showing positive signs at this early stage. |

INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (250 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 County Peace Committees (CPCs) and Early Warning & Early Response (EWER) mechanisms prevent and resolve local disputes in 15 counties | Indicator 1.1 Number of County Peace Committees (CPCs) preventing and resolving local conflicts (disagregated by m/f CPC members and by m/f of the person bringing the dispute) | 7 CPCs Funtional (Sept.2013) | 15 CPCs Functional (Sept. 2016) | 10 county peace committees functional | No delay | None |
|  | Indicator 1.2 Number of counties with a functional Early Warning and Early Response (EWER) Working Group (disagregated by m/f members) Indicator 1.3 Propotion of Early Warning alerts (by SMS) that result in early responses | 4 Counties with representatin of 10% female (Sept. 2013) 26% (Sept.2012) | 13 Counties with representation of atleast 40% female and 60% male (Sept. 2016) 60% by (Sept. 2016) | 5 EWER Working Group functional with representation of 20% female Data not available this period | No delay but we are requesting an adjustment in the target from 13 to 7. The EWER Working Group will now be organized in counties covered by one of the three regional hubs. This information will be gathered annually | Adjustment to 7 focus on the Regional Hubs counties |
| Output 1.1 County Peace Committees reactivated and strengthened in 15 counties | Indicator 1.1.1 # of peace structures including County Peace Committees assessed, re-activated and strengthened | 7 counties CPCs partially functional and access limited support (Sept, 2013) | 13 CPCs structures fully functional by 2016 | 14 CPC Assessed 10 functional | None. Activities on track | None |
|  | Indicator 1.1.2 # of CPCs trained in conflict mediation leadership and general peacebuilding Indicator 1.1.3 7 CPCs benefited from grants to address conflict at local level (Sept. 2013 Indicator 1.1.4 # of CPCs deployed and | 325 CPC members trained (Sept. 2013 7 CPC s benefit from grants to address local conflict O CPC anchored within county council (September 2013 | 900 CPC members trained, of which at least 30% women (December 2015) 13 CPCs access or benefit from grants to address local conflict At least 7 CPCs anchored within the County Council (CC) once the CC is fu | Training of 88 (40%) female CPC EWER Focal persons. Not available | Training this period focused on building capacity for early warning and early response. The next 3 to 6 months will see the delivery of gender sensitive leadership and peacebuilding training. None. System put in place to link PC with grantees | None |
| Output 1.2 Early Warning and Early Response centers established and functional at 3 Regional Hubs (Bong, Grand Gedeh and Maryland) | Indicator 1.2.1 Number of EWER Centres established and functional at Regional Justice & Security Hubs | 0 (Sept.2013) | Targets: (Dec 2015) 3 centers 3set up and functional | 1 center set up and functional at Gbarnga Regional Hub | No centralized location identified for regional hub 2 and 3 |  |
|  | Indicator 1.2.2 % of support to EWER center | 0 | 50% logistical support including computer, transport, communication, etc. (August 2016) 25 CBO. CSO benefit from small grant | Gbarnga EWER center currently receiving support. | On track | None |
| Output 1.3 CSOs and CBOs captivity strengthened to support CPCs to respond to emerging threats to peace at the district and communities to prevent and resolve conflict. | Indicator 1.3.1 # of mechanisms in place to access grant # of CSOs and CBOs awarded small grants # of conflicts collectively (CSOs, CBOs including CPCs) resolved, mitigated and alerts provided for timely respons | 8 CPCs/CBOs benefited PBF funds (Oct. 2013) | 25 CBO. CSO benefit from PBF funds by September, 2015 | 10 CSOs received grants to date | On track. Additional grants to be awarded during the next quarter | Adjusted to 15 due to the budget, scope and duration of most of the proposals. |
|  | Indicator 1.3.2 |  |  |  |  |  |
| Outcome 2 | Indicator 2.1 |  |  |  |  |  |
|  | Indicator 2.2 |  |  |  |  |  |
| Output 2.1 | Indicator 2.1.1 |  |  |  |  |  |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 | Indicator 2.2.1 |  |  |  |  |  |
|  | Indicator 2.2.2 |  |  |  |  |  |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

# Footnotes

Please note that where there are multiple agencies, only one consolidated project report should be submitted.

Approved budget is the amount transferred to Recipient Organisations.

# Funds committed are defined as the commitments made through legal contracts for services and works according to the financial regulations and procedures of the Recipient Organisations. Provide preliminary data only.

# 4 Actual payments (contracts, services, works) made on commitments.

5 PBF focus areas are:

PBF Focus Areas are:

1: Support the implementation of peace agreements and political dialogue (Priority Area 1):

(1.1) SSR, (1.2) RoL; (1.3) DDR; (1.4) Political Dialogue;

2: Promote coexistence and peaceful resolution of conflicts (Priority Area 2):

(2.1) National reconciliation; (2.2) Democratic Governance; (2.3) Conflict prevention/management;

3:Revitalise the economy and generate immediate peace dividends (Priority Area 3);

(3.1) Employment; (3.2) Equitable access to social services

4) (Re)-establish essential administrative services (Priority Area 4)

(4.1) Strengthening of essential national state capacity; (4.2) extension of state authority/local administration; (4.3) Governance of peacebuilding resources (including JSC/ PBF Secretariats)