RUNO ANNUAL PROJECT REPORT		TEMPLATE 4.4

PEACEBUILDING FUND (PBF)

ANNUAL PROJECT progress report

COUNTRY:   LIBERIA

REPORTING PERIOD: 1 january – 31 December

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: Enhancing Access to Security and Justice at the Decentralized Level – Gbarnga Justice and Security Regional Hub, covering Bong, Lofa and Nimba Counties. Programme Number (if applicable) PBF/LBR/B-1 MPTF Office Project Reference Number: 00076699 |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: United Nations Development Program |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: The Liberian Judiciary; Ministry of Justice and its law enforcement agencies including the Liberia national Police , Bureau of Immigration and Naturalization, Solicitor Generals Office, Bureruau of Correction and Rehabilitation, Probation Program, Juvenile Diversion Program, SGBV Crimes Unit, Independent National Commission on Human Rights. |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) 418,737.00 |  |  | Overall Duration (months) 48 Months |  |
|  |  |  | Start Date (dd.mm.yyyy) 07.02.2012 |  |
| Government Contribution (if applicable) Government of Liberia provided an amount of US$500,000 for the operatonalization of the Gbarnga Regional Hub in the FY 2015/2016 budget |  |  | Original End Date (dd.mm.yyyy) | 31.01.2015 |
| Other Contributions (donors) (if applicable) |  |  | Current End date(dd.mm.yyyy) 31.12. 2016 |  |
| TOTAL: |  |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Assessment/Review - if applicable please attach Yes No Date: Mid-Term Evaluation Report – if applicable please attach Yes No Date: |  | Name: Joyce G. Cassell Frankfort Title: Program Manager Participating Organization (Lead): Ministry of Justice; UNDP Email address: jfrankfort@gmail.com |

PART 1 – RESULTS PROGRESS

  - Assessment of the current project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project is contributing:

Priority Plan Outcome to which the project is contributing. LPP Outcome 1.1 Enhanced access to justice and community security at the reegional and county levels in preparation for UNMIL transition.

Priority Plan Outcome indicator(s) to which project is contributing. 1.1 - % of justice and security services provided by the Gbarnga Regional Hub. 1.2 - % of people who feel safe or very safe in their community (disaggregated by county in the Hub region). 1.3 - % of people who trust the court system (disaggregated by Hub region). 1.4 - % of criminal cases adjudicated per court term (CT) (disaggregated by type of case and by county). 1.5 - # of trials on SGBV cases held in the Hub regions (disaggregated by county and by court term). 1.6 - # of cases prosecuted by the SGBV CU.

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  Enhanced access to justice and community security at the

regional and county levels in preparation for UNMIL transition

Rate the current status of the outcome:

| Indicator 1: 1.1 - % of justice and security services provided by the Gbarnga Regional Hubs Indicator 2: 1.2 - % of people who feel safe or very safe in their community (disaggregated by county in the Hub region) Indicator 3: % of people who trust the court system (disaggregated by county in the Hub region) | Baseline: December 2012: 64% (10 out of 14) Target: December 2015: 100% Progress:November 2015: 100% Baseline: June 2012: 65% June 2014:80% (Nimba 85%, Bong 76%, Lofa 77%) Target: December 2014: 80%??? Progress:No survey conducted in 2015??? Baseline: Gbarnga Hub: Bong, Lofa and Nimba, June 2012: 37% June 2014: 45% (Bong 57%, Lofa 52, Nimba 32) Target: (December 2015) Increased in the percentage of people accessing the court system. Progress: Although no survey was conducted during the reporting period, the midline survey conducted by the Peacebuilding Office in June 2014 suggests an increased in the percentage of people now accessing the court system based on gradual trust as evidenced by the number of cases being prosecuted. |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

1. JSC and the JSB approved funding to complete the water system and perimeter fence;

2. Two Toyota Hilux vehicles  purchased to increase the operational response of the Liberia National Police/ Police Support Unit in the  Hub 1 region;

3. All 14 services  are  being delivered at the Gbarnga Regional Hub.

4. Public Outreach Officers in Hub 1 raised awareness in 82 communities reaching out to 5423 residents in the region.

5. Prosecution indicted 45 cases, tried 28 and won 25 of the 28 cases.

6. LNP PSU responded to 16 incidents including riots and mobs.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Criminal justice institution in Hub 1 continued during the year to make tremendous strives in achieving the program' outcome. For example, Public Outreach Officers (PSO) in Hub 1 raised awareness in 82 communities reaching out to 5,423 residents in the region of which 3554 residents reached were male and 1869 females. The  PSOs also referred 13 complaints from residents in the region who felt aggrieved by the actions of criminal justice actors  through the complaint mechanism. Prosecution indicted 45 cases, tried 28 and won 25 of the 28 cases. LNP PSU responded to 16 criminal incidents including riots and mobs which could have derailed the peace in the region. 33 trainings were provided for criminal justice actors in the region. BIN/ BPU made 26 visits reaching 205 border communities (some of the communities were revisited through this period.

SGBV Crimes Unit handled 21 rape cases in three court terms, tried 11(52%) with 8 ( 72%) convicted. The unit also received 167 cases through the hotlines and provided psycho social and medical support to 20 survivals of rape.

The Gbarnga Regional Hub  is widely used by residents of the region in response  to critical issues of justice and security which strengthens peace and security. Through these combined efforts by criminal justice actors in the region residents are sure that they can get redress or immediate response to incidents as they arise. During the recent joint monitoring visit by PBF partners in Liberia citizens responded that they now feel secure by the presence of the hub and the actors operating in the region. They lauded the immediate response of Liberia National Police including regular confidence patrols in communities which deters criminal. The immediate response to criminal incidents by the Liberia National Police was also applauded by community members.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Communcation equipment installation remains a challenge. .

Outcome Statement 2:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

.

Outcome Statement 3:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 4:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender in the reporting period

| Evidence base: What is the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | The Regional Hub Manager in Gbarnga collects monthly reports from all criminal justice actors delivering services in the region, compiles the reports and submit to the Program Management Unit, The Program Management Unit then contact the heads of all agencies either through the Sector Finance Committee meeting or directly to gather feedback on the report as a form of validation. Some reports are gathered directly from the institutions. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | Rolling out justice and security services after the crisis was critical to peace and security. However the government in the midst of limited budget with competing priorities needs external support to to boost the limited scale at which the services were provided. The external support through this program provided capacity development training, logistics, infrastructure, equipment and other support for criminal justice actors and enabled government to deploy them in time. Government the consolidated and took over the operationalization of the hub and staff salary as a means of sustainability. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | Completing the Gbarnga Regional Hub water facility and perimeter fence was delayed due to funding constraints experienced at the end of the construction of Hub 1. During the reporting period the Justice and Security Policy Board and the Joint Steering Committee jointly approved the amount of US 80,000 for the completion of the Gbarnga Regional Hub. Additionally US 600,000 was approved by the Justice and Security Board for the construction of 2 Barracks in Yekepa and Yeala with funding from SIDA. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | Providing food for 100 officers assigned at the Gbarnga Regional Hub was initially implemented by and external catering contractor. As it became extremely expensive PMU then decided to initiate self in-house catering to reduce cost. Initiating this service was a total risk as PMU did not have the expertise to implement. This turned out to be an innovation as it has proven to work effectively and reduce the costs by approximately 60% and is maintaining 100 para-military personnel who are contributing to maintaining peace in the region through responding to crime and ensuring border security. |
| Gender: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | Justice and Security institutions in Liberia have adopted mainstreaming gender in the security sector through a policy first introduced by the Liberia National Police. The Policy now adopted by other agencies, requires institutions to recruit at least 20% women in the sector to reduce the gender disparity between men and women and is proven to be effective in recent recruitments. The Construction of 2 Barracks in Yeala and Yekepa also took into consideration creating space and access to basic facilities for both men and women taking into consideration the 20% minimum ratio of women to men in the security sector. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) | Government of Liberia has been very effective in sustaining staff and operationalizing the hub. However, it has been proven that the Independent National Commission on Human Rights did not roll-out the Human Rights Offices on the GOL budget for salary. This has undermined the performance of Human Rights Monitors in the region. |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (250 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Enhanced access to justice and community security at the regional and county levels in preparation for UNMIL transition | Indicator 1.1 Indicator 1.1 - % of justice and security services provided by the regional hubs (disaggregated by Gbarnga, Harper and Zwedru Hubs) Gbarnga: 15 | Gbarnga 2011: 0% Gbarnga 2014: 100% | December 2015: 100% | Gbarnga : 100% |  |  |
|  | Indicator 1.2 % of people who feel safe in their community, disaggregated by county in the Hub region. | June 2012: 65% June 2014:80% (Nimba 85%, Bong 76%, Lofa 77%) | December 2015= 100% | Perception survey was conducted by PBO in June 2014, No new survey was conducted in 2015 |  |  |
|  | Indicator 1.3 % of people who trust the court system (disaggregated by county in the Hub region) | Gbarnga Hub: Bong, Lofa and Nimba, June 2012: 37% June 2014: 45% (Bong 57%, Lofa 52, Nimba 32) | Target (December 2015) Increased in the percentage of people accessing the court system. |  | No new perception was done during the reporting year. |  |
| Output 1.1 Infrastructure, equipment, and systems critical for command, control and operational response put in place for the Regional Hub | Indicator 1.1.1 - % of facilities completed (disaggregated by Gbarnga, Harper and Zwedru Hub) | December 2013 – 97% completed facilities. | Gbarnga Hub December 2015 – 100% | November 2015: Gbarnga 98% | Funding for the complection of the water system and perimeter fence was approved by the JSC and the JSB in October 2015. |  |
|  | Indicator 1.1.2 Indicator 1.1.2 – % of shared regional command, control and communication structures and systems of LNP, BIN and BCR functional at the Gbarnga Regional Hub, disaggregated by 5 factors: 1. infrastructure to house the LNP and BIN regional commanders a | Gbarnga Regional Hub: Dec. 2013: 75% 1.Automated Record case management is at 75%.. 2.SOP for each agency 75% 3. Communications network 61%. 21 of 34 Cellcom GSM towels | December 2015: 100% | Automated case management software completed but not rolled out. SOP for individual institution completed 100% Government of Liberia has paid Cellcom GSM the amount of US 450,000. Completion of installation is still at 61%. |  |  |
| Output 1.2 Justice and security service providers at the regional hubs level able to provide fair and accountable professional services | Indicator 1.2.1 - # of PSU officers deployed in the Hub regions (disaggregated by Hub) | Gbarnga Hub June 2014: 77 officers in the region based on a rotational or quarterly basis. Gbarnga Hub – 52 PSU officers Nimba – 10 PSU officers Lofa – 15 PSU officers Harper Hub Region: June 2014 - 0 Zwedru Hub Region: June 2014: 0 January – |  | November 2015 Gbarnga : 55 PSU Officers 45 BIN/BPU Officers |  |  |
|  | Indicator 1.2.2 # of confidence patrols undertaken by the PSU annually | December 2013: Gbarnga Hub region: 11 June 2014:13 |  | November 2014 Gbarnga Hub: 18 |  |  |
| Output 1.3 Justice and security service providers are responsive to community concerns | Indicator 1.3.1 # of people sensitized by PBF-funded community based actors about their rights and how to access the justice system (disaggregated by county) | Gbarnga Hub region: As of December 2013 – 0 Dec 2014: 15 CSOs trained and awaiting small grants to commence operations (Bong 5, Lofa 5, and Nimba 3) |  |  | No report is forthcoming for CSO in the region about the number of people sensitized. |  |
|  | Indicator 1.3.2 # of referrals by the PSO to existing CBO services (disaggregated by justice advisory, human rights monitoring, advocacy, ADR and support services and by county) | Gbarnga Regional Hub 2014: Gbarnga Regional Hub Bong : 1 JPC Nimba: 0 Lofa: 0 |  |  | PSOs in the region referred a total of 13 cases but to the heads of criminal justice instituions. No case needed the attention and intervention of of CBOs. |  |
| Outcome 2 | Indicator 2.1 |  |  |  |  |  |
|  | Indicator 2.2 |  |  |  |  |  |
| Output 2.1 | Indicator 2.1.1 |  |  |  |  |  |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 | Indicator 2.2.1 |  |  |  |  |  |
|  | Indicator 2.2.2 |  |  |  |  |  |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | The implementation of planned activity by partners institutions should be followed up constantly until they are implemented. For example, INCHR was aware that they they needed to put their Human Rights Officers on Government Salary after PBF support. With the trust that they aware of the implementation, follow-up to the end was reduced. They did not enroll the officers which has reduced the performance of the Unit. |
| --- | --- |
| Lesson 2 (1000 character limit) | The restructuring of the Justice and Security Joint Program which reduced the meeting time from monthly to quarterly has a bearing on the program implementation. Discussion and decisions about the impelentation of the program has been delayed due to the quarterly meetings schedules. |
| Lesson 3 (1000 character limit) | The removal of UNDP as fund managers from the Justice and Security Policy Management Board during the Program restructuring sets a gap in the implementation as UNDP is not aware of the implementation of key decisions in line with their operational policy. This in amny cases have delayed implementation. |
| Lesson 4 (1000 character limit) |  |
| Lesson 5 (1000 character limit) |  |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures are on track, slightly delayed, or off track:

If expenditure is delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of expensed project budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: Enhanced access to justice and community security at the regional and county levels in preparation for UNMIL transition. |
| Output 1.1 | Output 1.1 Infrastructure, equipment, and systems critical for command, control and operational response put in place for the Regional Hub | UNDP | 418,737.00 | 379,588 | the balance funding is tied to the completion of the installation of the communication towers. The delay is as a result of the stalmate between the Government and the CELLCOM |
| Output 1.2 | Justice and security service providers at the regional hubs level able to provide fair and accountable professional services |  |  |  |  |
| Output 1.3 |  |  |  |  |  |
| Outcome 2: |
| Output 2.1 |  |  |  |  |  |
| Output 2.2 |  |  |  |  |  |
| Output 2.3 |  |  |  |  |  |
| Outcome 3: |
| Output 3.1 |  |  |  |  |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total: |  |  |  |  |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when); or whether any changes are envisaged in the near future (2000 character maximum):

Management and implementation modalities of  the program is guided by the Justice and Security Policy Management Board as oversight decision makers. Impementation of the program is carried out by the Program Management Unit in consultation with the United Nations Development Program as fund managers. Partners and donors participate in the decision making of the project through the Sector Finance Committee  where partner  and donors are represented by their heads of agencies.  Decision made during these engagements are then implemented by the Program Managment Unit of the Justice and Security Joint Program. In the event were joint decision is required on program implementation, the Justice and Security Policy Management Board and the Joint Steering Committee meet to make decision.

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.