### LRF Fourth Quarterly PROGRESS REPORT2013

| Reporting UN Organization | : | FAO |
| --- | --- | --- |
| Country | : | LEBANON |
| Project No. | : | LRF-26 OSRO/LEB/201/UNJ |
| Project Title | : | Recovery and Rehabilitation of the Dairy Sector in Bekâa Valley and Hermel - Akkar Uplands |
| LRF Signature date | : | 15 May 2012 |
| Project Start date | : | 01 Sep- 2012 |
| Reporting Period | : | October−November− December 2013 |

### List of Acronyms

MOA:		Ministry of Agriculture

LRF:		Lebanon Recovery Fund

FAO:		Food and Agriculture Organization of the United Nations

VDPA’s:	Village Dairy Producers’ Association

Summary

The LRF FAO Project on “Recovery and Rehabilitation of the Dairy Sector in Bekâa Valley and Hermel - Akkar Uplands” has introduced the innovative approach of setting up 40 small milk collection centres at village levels with the formulation of 30 producers cooperatives. This strategy had been an excellent breakthrough for the milk production and processing sectors in Lebanon. The project has very pronounced impact on the livelihood of people especially small farmers and women mainly in the poorest areas of Beqaa and North Lebanon.

The support of the Project to the dairy cooperatives and village milk collection centre network is playing a key role in improving the general conditions of small farmers and increasing their income by 20% as well as improving the quality of milk as a whole. As the above mentioned FAO – LRF Dairy project is heading towards its end (31st December 2014), it is necessary that continuous monitoring and follow up be applied to ensure the continuity and sustainability of these cooperatives and milk collection centres network.

The project has organized Inaugural Ceremony on 16th November 2013 held under the patronage of the Minister of Agriculture for opening of a milk collection and cooling center and a dairy processing center in Bezzalliyeh as well as for the launching of activities of the DFID-funded project on “Emergency vaccination and targeted feeding of livestock in Syria-Lebanon border”.

The project has organised intensive courses on Artificial insemination in Zahle, Bekaa covering the Bekaa, Baalbek – Hermel with 38 trainees and another one in Batroun covering the North, Akkar, and part of Mont Lebanon with 42 trainees. Each session lasted for almost three weeks with theoretical and practical training and final examinations. The major topic was on Artificial Insemination while the minor topic was on all aspects of ruminant nutrition and animal health. All successfully completing students were provided with modern equipment for Artificial Insemination so that they can serve the farmers in their respective areas in coordination with the dairy cooperatives. Twenty-seven artificial insemination centres are now created and fully operational in project sites.

I. PURPOSE

The aim of this proposal for PHASE TWO was to build on LRF-21’s activities to reach a higher number of poor livestock farmers and improve the livelihoods of poor farmers and sustain the dairy sector in Lebanon, emphasis was made on improving the quality and hygienic standards of milk and dairy products to safeguard the Lebanese consumer and improve the milk prices. The proposed project was also aimed at introducing pilot demonstrations on intensive breeding of genetically improved or imported milking goats in dairy farms to improve income-generation of the poor farmers in rural areas living from goat rearing. The project is targeting 2000 farmers to draw direct benefits from project interventions (distribution of project inputs, livestock services & milk services) with an additional 1000 farmers who will draw indirect benefits from the project through milk collection, cooling and transport services as well as training sessions.

The major expected Outputs and Key Activities are the following:

- Strengthening village dairy producers’ associations: 10 additional Dairy Cooperatives will be created in addition to the 23 existing ones grouping 2 000 participating co-operative dairy farmers;

- Setting up a network of Primary Village Milk collection and Cooling Centers: 10 additional centres will be established in addition to 23 existing ones grouping 2000 cooperative dairy farmers;

- Empower female-headed households through the provision of mini dairies and  stainless steel milk cans: 100 additional beneficiaries in addition to 135 farmers already granted  mini-dairies and 1 000 additional beneficiaries in addition to 1 105 farmers already provided with milk cans;

- Capacity building of farmers and MOA extension service people: 3 000 beneficiaries;

- Support to artificial insemination and veterinary services: 2 000 direct beneficiaries; and

- Strengthened sustainability to facilitate livestock services inputs for 1500 co-operating smallholder dairy producers’ beneficiaries.

By the end of the project, the smallholder dairy producers and dairy communities will be in good position to improve their chances of becoming self-supporting and sustainable. Provision of extension and other support services to livestock farmers by the project, MOA, private dairies and processing/marketing firms will lay the foundation stone for sustainable dairy sub-sector.

This report is related to the main activities implemented by the project during the fourth quarter of 2013 (October-November-December 2013).

II. RESOURCES

| Total budget approved | 1,474,023 US$ |
| --- | --- |
| Total disbursements as of | 1,010,889 US$ |
| Commitments for next quarter | 463,134 US$ |
| Available Balance | 463,134 US$ |

| CATEGORY | ORIGINAL ALLOCATION (USD) | TOTAL EXP (USD) to Date |
| --- | --- | --- |
| 1. Supplies, commodities, equipment and transport | 835,000 | 556,566 |
| 2. Personnel (staff, consultants and travel) | 266,500 | 243,981 |
| 3. Training of counterparts | 210,000 | 84,482 |
| 5. Other direct costs | 64,841 | 59,727 |
| Total Programme Costs | 1,376,341 | 944,756 |
| Indirect Support Costs (7% of total programme cost) | 97,682 | 66,133 |
| TOTAL | 1,474,023 | 1, 010,889 |

III. RESULTS

1.	Controlling and monitoring the progress and activities of Dairy Producers Cooperatives and Intermediate Milk Collection and Refrigeration Centers

1.1. Background

The LRF FAO Project “Recovery and Rehabilitation of the Dairy Sector in Bekâa Valley and Hermel - Akkar Uplands” has introduced the innovative approach of setting up 40 small milk collection centres at village levels with the formulation of 30 producers’ cooperatives. This strategy had been an excellent breakthrough for the milk production and processing sectors in Lebanon. The project has very pronounced impact on the livelihood of people especially small farmers and women, mainly in the poorest areas of Beqaa and North Lebanon.

The support of the Project to the dairy cooperatives and village milk collection centre network is playing a key role in improving the general conditions of small farmers and increasing their income as well as improving the quality of milk as a whole. As the above mentioned FAO – LRF Dairy project is heading towards its end (31st December 2014), it is necessary that continuous monitoring and follow up be applied to ensure the continuity and sustainability of these cooperatives and milk collection centres network.

During its final lifetime (Year 2014) the project is focussing on monitoring and follow-up. This is very important for the sustainability of the project in order to affirm to all farmers, parties, and stakeholders that monitoring and controlling of the milk quality and hygiene is a continuous and permanent procedure. The main activities are:

- Protecting and boosting the current achievements by communication and monitoring;

- Maintaining the training programs and courses along with extension and widening the range of topics and subjects;

- Controlling and monitoring the progress and activities of the cooperatives to safeguard it from disintegration and demolishing as was the case in previous experiences;

- Supervising the running of the milk cooling and collection centers especially milk hygiene and milk testing;

- Apply this successful experience in other areas of Lebanon such as Mont Lebanon and the South, subject to the availabilty of funding.

During thr 4th quarter of year 2013, twenty five field inspection visits were conducted reaching out to the different cooperatives and centers located in the targeted areas of the project namely, Bekaa, Baalbeck-Hermel, Akkar, and North Lebanon. The objective of the field missions was to follow up with farmers and producers about the conditions of their production and milk processing and marketing, to identify new beneficiaries before granting the final approval to provide the necessary material support and giving instructions to upgrade the hygienic standards of milk and dairy products.

1.2.	Conclusions

a) The major problems faced by the cooperatives include:

- Some milk dealers and dairy processing plants are not committed to the recommended price of the MOA. In many cases the cooperatives receive a price lower by 100 L.L. or more of the assigned price. This is naturally reflected badly on the income of the farmers and the cooperative.

- Refusal of some dairy processing plants to sign contracts with the cooperatives to stabilize the milk price through a year or a season.

- The checks for milk payment are often post dated by three weeks or two months and in some cases by three months.

- Many milk traders work as middle men between the cooperatives and the dairy processing plants exploiting the need of the cooperatives for cash and dictate their prices and terms of payment.

- The vast majority of the cooperatives is administered and managed by individuals (usually the president) rather than the administrative board as a whole.

- There is complete lack of follow up from the Cooperative Department of the North to the conditions of the dairy cooperatives in Akkar.

b) Advantages and rewards:

The following are some of the advantages and rewards of the dairy cooperatives and their positive impact on the dairy sector in general and on the small farmers in particular:

- Improving the quality of milk and consequently the price and income of the farmer. The milk price has been improved by 20% with project intervention;

- Milk collection from small farmers that produce less than 50 kgs daily with better price for the farmers compared with the milk price before joining the cooperatives;

- Outreaching remote areas otherwise were almost neglected from the agricultural map of Lebanon thus improving milk production quantitatively and qualitatively;

- Substantial benefit (e.g. value added products, better health care and nutritional status of dairy animals, increased milk yield, etc) of the farmers and producers from the training sessions and workshops about all aspects of farm management and home dairy processing.

- Increased number of cows at the existing dairy farms and starting of new dairy businesses or small dairy farms. The total number of milking cows increase from 25 000 to 35 000 cows before and after the project interventions.

- Establishment of a new sense of security and tranquility among the small farmers and their families in their remote villages and districts.

c) Recommendations:

The achievements and accomplishments of FAO dairy project need to be protected and maintained with all available means and resources. The inert or stagnating cooperatives be rehabilitated and monitored closely to recover and restart properly. Well organized and successful cooperatives should be given encouragement letters, recognition certificates and direct support of the MOA to become a good example for other cooperatives.

2.	Minutes of meeting about milk sector and milk price

Place: Lebanese Ministry of Agriculture (MOA)

Date:  10 December 2013

A meeting was held at the office of H.E. Mistier of Agriculture Dr. Hussein Hajj Hassan, with Minister of Trade and Commerce Mr. Nicolas Nahhas, Minister of Industry Mr. Vreij Sabonjian), the representative of FAO in Lebanon Dr. Ali Moumen, and employees of the MOA and ministry of Trade and Commerce and ministry of industry with a group of major stakeholders in the sector of milk production such as dairy cooperative presidents milk traders, and dairy processing plants owners or managers. The objective of this meeting was to discuss issues and problems related to the sector. The big fluctuation in milk prices and the complaints received from all parties made this meeting an essential necessity to protect this important sector that subsists more than ten thousand poor families.

After elaborate discussion shared by most of the attendants that expressed freely their points of view and concerns and conveying these with the ministers it was possible to reach some significant decisions unanimously. Details of Minutes of the meeting are given in Annex 1.

3.	Mission of United Nations Office for the Coordination of Humanitarian Affairs (OCHA) Staff to LRF−FAO dairy project Sites

Date: Wednesday and Thursday 13 and 14 November 2013

In the framework of the Food and Agriculture Organization project “Recovery and Rehabilitation of Dairy Sector in Bekaa Valley and Hermel – Akkar Uplands” (FAO/LRF-26/ OSRO/LEB/901/UNJ), funded by Lebanon Recovery Fund (LRF), FAO staff and OCHA (United Nations Office for the Coordination of Humanitarian Affairs) representatives Mr. Thomas conducted several inspection field trips to different sites of the project activities. These visits covered random beneficiary sites selected in Bekaa and the North and Akkar. The objective of this visit was to monitor and touch the actual achievements in the field resulting from the project progress activities especially the impact on the life and livelihood of the small farmers for identification of project sites and beneficiaries to be filmed. A detailed report is presented in annex 2.

4. Inaugural Ceremony organised by the project on 16th November 2013

This ceremony held under the patronage of H.E. Minister Hussein Hajj Hassan and a representative of Dr. Ali Moumen FAO representative in Lebanon and distinguished persons and activists and a remarkable crowd of farmers and producers especially from the Bekaa and Baalbeck Hermel Mohafazat. Through the project "Recovery and Rehabilitation of Dairy Sector in Beqaa Valley and Hermel -Akkar Uplands" and the project "Emergency Vaccination and Targeted Feeding of Livestock Grazing in Areas along the Syria-Lebanon Border", and collaboration with the Lebanese Ministry of Agriculture, invited to the inauguration of a milk collection and cooling center and a dairy processing center in Bezzalliyeh and the launching of activities of the vaccination and feeding project. The press release produced for this occasion is indicated in annex 3.

5.	The Artificial Insemination Training Courses

During this reporting period, the project has organised Artificial insemination intensive courses in Zahle, Bekaa covering the Bekaa, Baalbek – Hermel with 38 trainees and another one in Batroun covering the North, Akkar, and part of Mont Lebanon with 42 trainees. Each session lasted for almost three weeks with theoretical and practical training and final examinations. The major topic was Artificial Insemination while the minor topic was all aspects of ruminant nutrition and animal health. The passing outstanding students were provided with full modern equipment for Artificial Insemination so they can serve the farmers in their respective areas in coordination with the dairy cooperatives. Twenty seven artificial insemination centres are now created and operating in project sites

It was necessary to support both training sessions and workshops with educational and extension material. Four thousands books and booklets were published covering all training material using very simple language and colourful attractive presentations: Good practices of processing of improved traditional dairy products and Good practices on improvement of dairy cow reproduction. Details are provided in Annexes 4A, 4B, 4C, 4D and 4E.

6.	Procurement and delivery of project inputs:

During the reporting period, the project has completed the distribution and delivery of dairy equipment procured during phase 2 to the project beneficiaries. The List of Dairy Equipment procured within LRF 26- Phase 2 distributed to Project Beneficiaries (All Quantities Procured had been Distributed) is as follows:

| Supplies | Quantities | Number of beneficiaries | Mohafazat | Percentage | Remarks |
| --- | --- | --- | --- | --- | --- |
| Milk Cans & Filter | 2000 Cans & 3000 Filters | 1500 | Bekaa: 643 Akkar: 500 North: 357 | 43 % 33% 24% |  |
| Mini Dairy Units | 65 Complete units | 65 | North: 57 Akkar: 2 Beqaa: 6 | 88% 3% 9% | 70% of beneficiaries in the North are from Caza Donnieh Minieh |
| Medium Dairy Units | 14 Units | 14 | North: 7 Akkar: 1 Beqaa: 6 | 50% 7% 43% |  |
| Milking Machines | 100 Units | 100 | North: 94 Beqaa: 06 | 94% 6% | 85% of beneficiaries in the North are from Caza Donnieh Minieh |
| Cooling Tanks | 10 Units (5 with 2000 litres capacities & 5 with 1000 litres capacities | Creation of of 4 New Milk Collection centres in Donnieh (3) and Koura (1) supporting 150 poor dairy smallholders Creation of 5 New Milk Collection centres in Akkar (3 in wadi Khaled, one in Beinou & one in Akkar El Atika) supporting 250 poor dairy smallholders Creation of 2 new milk collection centres in Beqaa (one in Taraya Shmistar & one in Bazzalia) supporting 100 poor dairy smallholders Upgrading of Five milk collection centres: Two in Akkar (Halba & Kobayat), Three in Beqaa (Hermel, Machariaa El Qaa, Baalbeck) NB: Considering the high demand for small and medium cooling tanks (550 and 1000 litres capacity) in Donnieh & Akkar because those regions are dealing with very small dairy farmers and because of the absence of electricity “Triphase”, the project management decided to replace the small & medium cooling tanks in the existing cooling centres with larges ones (2000 litres capacity) and to retake the small and medium ones to the North & Akkar. |

Details of dairy supplies with purchase order number as well as lists of beneficiaries are presented in annex 5.

Furthermore, the artificial insemination kits and supplies procured within LRF 21 (Phase 1) were distributed to inseminators and Coop’s recently on 28th December 2014. Detailed list of equipment and list of beneficiaries will be presented in the next reporting report.

In response to the intensive demands and requests by the small dairy producers and smallholder dairy farmers, particularly in the poorest areas of Akkar, the project has launched procurement of additional dairy equipment as follows:

- Four (4) milk cooling tanks of one ton capacity each

- Two (2) milk pumps

- Twenty five (25) Milking machines

- Five (5) small medium size milk batch pasteurisers (250 litters capacity)

- Five (5) working tables (Large)

- Three (3) Labneh bag hangers.

- Two (2) cheese presses.

- Fifteen (15) mini dairy processing units 60 – 70 litres (Complete)

Progress in Project Implementation:

| Project Outputs | Activities | Indicators | Reason for variance |
| --- | --- | --- | --- |
| Protecting and boosting 30 Village Dairy Producers’ Association as well as 40 Village Milk Collection centres Established by the project | Visit and monitoring the Dairy Cooperatives and Milk Collection and Refrigeration Centers and the milk transportation trucks | An individual report about each cooperative and center and truck was written and signed by the members of the inspection committee. A final cumulative report that included the findings and problems and recommended remedies was prepared. | It was expected that some cooperatives shall face internal problems and obstacles that will interfere with their activities and goals. This situation was actually perceived during the field inspection. The reason for this unfortunate foreseen variance is due to the fact that cooperative work is new to the Lebanese farmers that consider the cooperatives just as a source of individual and personal aid and support. Other political or familial factors played an important role in obstructing the development of the retarded cooperatives. |
| upgrade the hygienic standards of milk and dairy products | Escort the delivery and confirm the reception of milk jars and dairy processing units to Batroun and Bakhoon. Inspect the storage areas and the beneficiaries’ production sites before granting the final approval to provide the necessary material support. | Delivery notes were signed by the project beneficiaries. | There was a delay in this activities because of the security reasons in the North region, there was also a delay in procurement of additional dairy equipment (requested in october 2014 and delivered in January 2014) because of FAO bureacratic procedures. |
| Improved management of milk collection centres and selection of project beneficiaries | undertaken a field visit to Baalbeck and North areas to evaluate the need to UPGRADE the Milk Collection and Dairy Processing Centers and identify the items they require and that can be provided by the project to project beneficiaries | A detailed report on field visit and milk collection centre was produced. It was pointed out that the physical utilization of resources on field level has been so remarkable that there is an urgent need to UPGRADE milk production and processing facilities to increase the dairy sector output and processing facilities to increase the dairy sector output, especially to cope with Syrian crisis | Lack of enough funding is a major problem in satisfying the essential needs of many milk collection centers. More funding needed: FAO has been working in Bekaa, Akkar and North Lebanon and the dairy program has to become a national program for whole of Lebanon under the MoA (with FAO support) to pull donors funding. Simultaneous, work independently to raise more FAO funding to continue dairy program activities. |
| Upgrading Dairy Sector | Meeting grouping three Ministers (Agriculture, Economy & Industry), FAO & major stakeholders in the sector of milk production | Production of a detailed minutes of meeting with major recommendations and decisions: Request potential donors for funding national dairy project, Establishement of a National Council of Milk to look over all the issues related to the sector, Creating of a general union for all the milk producers' cooperatives on the national scale, Reinforcement and apply laws and regulations to protect dairy sector and local production. | No Variance |
| Increased capacity of milk collection and processing in North Baalbeck | inauguration of a milk collection and coolimg cemter and a dairy processing center in Bezzalliyeh | Press release produced on Inaugural Ceremony in Bazzalia Delivery note to project beneficiaries | No Variance |
| Capacity building of skilled artificial inseminator for improvement of dairy cattle fertility | Conducting two training sessions of 3 weeks each in Beqaa (38 persons) and Akkar & North (42 persons) for young enthusiastic and energetic farmers from dairy coop’s and from MOA extension service Equipment of successful trainees with AI supplies (establishment of 27 AI centres) | Lists of attendance with signature of participants and detailed report produced on organization of training courses Delivery notes of AI Kits to successful trainees Distribution of semen doses to trained inseminators | There was a delay in this activities because of the security reasons in the region |

Implementation Constraints and Lessons Learned during this quarter

During this reporting period, the project faced constrains which were forecasted while others were not. To overcome these barriers we sought solutions or have made modifications. Few cases were not curable as the decisions were not within our scope. The variety of stakeholders involved in the project elected coordinator among all the parties, especially conflicting benefits: dairy farmers, milk dealers, dairy processing plant, milk smugglers, and last but not the least the consumer. The vast geographical expansion in North Lebanon has forced us to squeeze the selection of direct beneficiaries very severely because of the budget restriction. Everyday we receive several calls from needy farmers that want their names to be added to the list of direct beneficiaries. The areas of North Lebanon, Akkar, Baalbeck, El Hermel are mainly characterized with extreme poverty and most of the farmers in these areas are in grief need to any basic or essential support. The limited budget has forced us to put very strict criteria for selection of direct beneficiaries among the poorest farmers. Taking into consideration the geographical area and the number of farmers involved and the volume of inputs and follow up necessary to achieve the goals of the project, we can confirm that the number of the working team is not sufficient. If we look at most if not all the achievements and accomplishments of the project especially the Farmers cooperatives and Primary milk collection and cooling centers, operation of the milk transportation trucks etc. We find that all of these require continuous follow up, control, and monitoring in order to reach a state of stability and sustainability. Also more training and milk sampling and testing are required. More time and personnel are required because the past experience has involved very hard work and lengthy working hours. Another major constraint faced by the project is the negative attitude of many farmers. Unfortunately, the Lebanese farmers have formulated a wrong idea about cooperative work over the decades. The government and the international organizations have unintentionally participated in the creation of such attitude. Usually, the agricultural development projects emphasized and were limited to the material support to the farmers. Very few projects stressed the importance of team work and self sustainability of farmers groups or cooperatives. That is why every farmer asked what you are going to give us?? Before asking what we are going to do. We are aware at this stage, and even after the formation of 28 cooperatives, that many farmers joined just for the hope to get some material individual benefit. We utilize this negative attitude to teach the farmers that they can gain much more by cooperating together on the long run. The conflict in Syria and its social and security implications has affected the mobility and implementation of the project interventions. In many cases the project team was not granted the security clearance to visit the targeted areas. Furthermore the influx of the Syrian refugees has altered the formula and multiplied the number of indirect beneficiaries in the Mohafazat as a whole. In addition to that the North is very vast geographically and requires lengthy time and sturdy efforts to be covered and surveyed. In these unfavourable conditions the project team was able to perform and accomplish major very important interventions that are listed below: Also another major constraint faced by the project is the restriction on movement due to security conditions. The current prevailing security conditions in Lebanon as mainly reflected by the situation in Syria have forced the UN security authorities to restrict our movement to the minimum. Furthermore; there are many areas that are prohibited to go under any circumstances such as Al Qaa, Masharee Al Qaa, Akkar, Wadi Khaled etc…. It is also important to mention that these unfavourable conditions have been reflected on the activities and efficiency of work of the cooperatives, milk collection centers, and farmers located in these areas. We can also confirm that these unstable conditions are affecting everything in the country starting from the head of the State to the smallest shepherd in Jroud El Hermel. We are having direct contacts with farmers in the border areas that come regularly at our office; moreover we spent nights on sites (North Lebanon) when the situation is calm working successive days. The impact of the current security situation on the LRF 26 work plan for the next reporting period will probably continue to be the same as we are not able to cover all the areas adjacent to the Lebanese ─ Syrian borders in the North and East with less follow up of Hermel, Machariaa Al Quaa and Akkar areas. We are having direct contacts with farmers in the border areas that come regularly at our office. Another constraint is the very slow budget transfer and release. Although we had many good and generous sources for financial support from the MOA and the LRF, we were not able to use these funds yet. The MOA has proposed US$ 200 000 for training contract with the FAO Project but due to FAO administrative routine it seems that the project is loosing such donation, also the project had lost a kind donation of US$ 20000 from big hearted American journalist to support one poor dairy project. Also, FAO was not able to sign an agreement with Save the Children (-UKan NGO), for a total amount of US$ 60 000 to train and supply groups of women-headed households with equipment for processing of improved traditional dairy products. The LRF Steering Committee agreed to transfer the remaining fund of US$ 88 000 that was not used during implementation of LRF 21 (Phase 1) to LRF 26 (Phase 2). Unfortunately, the LRF administration is still waiting for the final financial closure of LRF 21 which was ended since September 2012 in order to proceed to transfer of the balance. Here also at FAO HQ’s the administrative routine is a major constrain as the project is in urgent need of funding to maintain and sustain its activities while supporting more needy farmers. Another major constraint is the high influx of Syrian refugees. It is documented that there are more than a million Syrian refugees that have crossed the Syrian – Lebanese boarders during the last two years with an increasing rates in the last few months. Almost all of these are very poor, helpless, and vulnerable families composed of a high percentage of children and babies. The areas that are most populated with these poor refugees are concentrated in the border villages of Akkar, Baalbeck - hermel, and Minniyeh - Donniyyeh areas. Most of these areas are covered by the project interventions. The presence of such large numbers of refugees had interfered with the activities of the project. In most cases we have to take into consideration the increased population (more than 25% in some villages) and the magnified demand on food supplies and dairy products. Some of the refugees have brought with them some of their livestock that they were able to save. It was also necessary to attend to the needs of these herds such as feeds, vaccination, and milk collection and marketing etc... Major Lessons Learnt Lesson № 1: Plan beforehand and predict what to expect before doing any move. The situation in Lebanon as is affected by several surrounding and internal military and security instabilities require special alerting and vigilant vision and planning. These facts necessitate the continuous coordination with the SIOC Lebanon before planning any movements. In areas where the security clearance is not granted at all we contact the pertinent persons and ask them to come to our office in Zahle in order to follow up with them and listen to their problems and complaints. In all cases substitute plan should be available in case something unexpected occurs (which is quite possible). Under these circumstances it is advisable that foreign delegates or visitors restrict their movements in the project sites. Lesson № 2: Supporting the farmers to improve their potential in order to get a better value for their milk. The main objective of our project is to improve the life standard of small dairy farmers and producers through increasing their income. Anything which leads to this objective is considered a positive step towards our goals. This is what we should be actually doing to help the dairy farmers to improve their potential in order to get a better value for their milk. This can be done through improving the quality of the milk produced at the farm level and maintaining its quality through the proper cooling and use of hygienic utensils and facilities for transportation. Imposing better prices on the dairy processing plants without improving the quality of milk will never bestow the desired effect on the long term. A win win agreement must be reached in order to maintain sustainability. Lesson № 3: taking into account the Syrian refugees in project interventions. As it was mentioned before the Syrian refugees represented between 25 and 35 % of the population of some villages in Lebanon. They became an integral component of the social framework of these villages, and any intervention should take them into consideration. The increased population in these originally poor and unprivileged communities requires additional inputs of food and water and all other essential aspects for living. We were obliged as a project to take into account these refugees as targeted beneficiaries as dairy producers and consumers of more dairy products. Many of these refugees were originally dairy farmers that have rescued some of their livestock with them and need emergency support like their Lebanese counterparts. The demand on dairy products has increased and it has to be met mainly through local production. Lesson № 4: Increase training sessions and workshops especially in new targeted areas. As a feedback from the all training sessions conducted by the project, there is a great demand for more such sessions and workshops. The same subjects have to be repeated in other areas and new topics such as nutrition and reproduction be introduced. The under skilled farmers and producers suffer a lot just due to bad management and lack of knowledge. Furthermore more dairy equipments are necessary to cope with the additional volume of producers and farmers such as small dairy processing equipment, milking machines, cooling tanks etc. Lesson № 5: Be friendly but strict with the farmers. Most of the farmers and stakeholders appreciate and value good relations with the project team and administration. This is usually was reflected as better chances for better implementation of the project interventions. Some farmers or stake holders abuse these relations and wanted to benefit from them unlawfully. They do not meet deadlines or abide by directions and instructions thinking that being in good terms with the FAO team gives them this privilege. In the case of such farmers that misunderstand kindness and good relations, severe reactions and strict measures should be taken in order to correct their attitude towards the project. Lesson № 6: Follow up on dairy cooperatives as they are routes for our interventions and connection with the farmers. Cooperatives are simply business companies that are established for the sake of profit. Every member of this cooperative is a partner in the company that has rights and entails duties. Involvement and participation of each member are very essential for continuity and sustainability of these cooperatives. Transparent accounts and financial records should be available and updated daily. Any member should have the right to look over and see what is going on in the company that he owns a share in it. Extensive efforts should be exerted to change the individualistic mentality and convince the farmers and the members of the cooperatives of the feasibility and importance of cooperative and team work. Unfortunately training alone is not enough to create this change but an integrated sociological and psychological program must be implemented. Finally, these were some of the major constrains and lessons learnt during the last period of the project. We hope that this short presentation may add to the wellbeing and advancement of the project in the future stages.

IV. FUTURE WORK PLAN

| Outputs | Activities | 2014 |
| --- | --- | --- |
|  |  | January | February | March |
| Upgrading dairy sector through sustaining dairy Coop’s and Functioning Village Milk Collection Centres | carry out continuous monitoring and supervision of all the facilities and achievements accomplished by the project with regard to dairy coop’s and mil collection centres including insulated truck Finalise the constitution of the 10 additional dairy coop in the North (Koura, Zgharta and Minieh Donnyeh) Establish new milk collection centres and increasing the capacity when required | ========== | ========== | ========== |
| Distribution of additional dairy equipment to satisfy the needs of poor farmers in project sites. | Distribution of 4 milk refrigeration tanks, 25 milking machines, 15 small dairy processing units and 4 medium dairy processing units. | Procurement | Distribution | Training |
| Capacity building on dairy processing, milk handling, and on cow reproduction | Conduct 5 training workshops about dairy processing, milk handling for groups of women Start training sessions (20 sessions) to farmers on cow reproduction to support the artificial insemination programm |  | ========== | ========== |

| Help in supporting the Syrian refugees and their hosting community. | Contribute to the humanitarian efforts aimed at meeting the most urgent unmet basic socio-economic needs of Lebanese returnees who fled into Lebanon from Syria and their hosting communities in the North of Lebanon, and reduce the socio-economic burden of displacement on both communities, through preparation of concept notes for kind donors Increase the supply of dairy products in those areas through increasing capacity of milk collection & processing. Increasing support to DFID-funded project on emergency vaccination and targeting feeding of livestock in Lebanon | ========== | ========== | ========== |
| --- | --- | --- | --- | --- |

Annex 1

Minutes of a Meeting on Milk Sector and Milk Price

Place: Lebanese Ministry of Agriculture

Date:  10 December 2013

A meeting was held at the office of H.E. Mistier of Agriculture Dr. Hussein Hajj Hassan, with Minister of Trade and Commerce Mr. Nicolas Nahhas, Minister of Industry Mr. Vreij Sabonjian), the representative of FAO in Lebanon Dr. Ali Moumen, and employees of the MOA and ministry of Trade and Commerce and ministry of industry with a group of major stakeholders in the sector of milk production such as dairy cooperative presidents milk traders, and dairy processing plants owners or managers. The objective of this meeting was to discuss issues and problems related to the sector. The big fluctuation in milk prices and complains received from all parties made this meeting an essential necessity to protect this important sector that subsists more than ten thousand poor families.

The meeting started with a presentation made by the project manager Dr. Chedly Kayouli of LRF-21 and LRF 26 dairy project “Recovery and Rehabilitation of Dairy Sector in Bekaa Valley and Hermel – Akkar Uplands”. The title of the presentation was, "A brief summary about the problem of milk prices fluctuations and its impact on the small dairy farmers".  Part one of this presentation included a historical overview of the problem with a rational study about the cost of production of milk that confirmed that the weakest and most fragile ring in the milk chain is the small dairy farmer. Part two of the presentation covered the interventions and initiatives taken by H.E. Minister of Agriculture in coordination with LRF−FAO dairy project to contain the crisis. These steps reined milk price vicissitudes to a certain extent. Unfortunately, the lack of commitment from all parties with the price guidelines set by the Minister reduced the effectiveness of these interventions. 
Finally the Project Manager (Dr. Chedly Kayouli) explained the role of the LRF−FAO project in developing the milk production sector in quantity and quality and he gave some practical recommendations to manage the prevailing critical situation.

After elaborate discussion shared by most of the attendants that expressed freely their points of view and concerns and conveying these with the ministers it was possible to reach the following decisions unanimously:

- Their Excellency   the Ministers collectively appreciated the importance of the interventions made by the LRF−FAO dairy project “Recovery and Rehabilitation of Dairy Sector in Bekaa Valley and Hermel – Akkar Uplands” and the necessity to expand its geographical coverage to include all Lebanon. Same or similar interventions are to be made and analogous support items to be provided to the small farmers such as small dairy units, electric milking machines, milk jars etc… along with training and capacity building. H.E. Nisolas Nahhas, Minister of Economy & Trade demanded to prepare a letter in this respect to be raised to potential donors for funding and support.

- Establishment and activating of the National Council of Milk to look over all the issues related to the sector such milk pricing, complaints, transactions, etc… This Council will have representatives of: Ministry of Agriculture, Ministry of Trade and Commerce, Ministry of Industry, Department of Scientific Agricultural Research, dairy processing plants, milk producer's cooperatives, and feed manufactures and producers.

- Creating of a general union for all the milk producers' cooperatives on the national scale. A special committee shall be trusted to prepare the bylaws and the constitution of this union as soon as possible.

- Establishing a Collaborative Milk Fund joined by all the milk producers' cooperatives in Lebanon and contribute in its finance each cooperative proportional its volume of business. The objective of this fund is to protect small farmers of the sudden price fluctuation of milk or feeds or in cases of natural disasters (to be discussed in the next meeting).

- Signing of mandatory milk sales contracts between the dairy processing plants and the milk producers cooperatives specifying: the time period, the daily quantity of milk (plus or minus 15%), the price, the quality of the milk, (Special forms t be reviewed and modified).

- The MOA feed support program shall be linked with the milk producer's cooperatives in a manner that only those farmers associated with the cooperatives and deliver their milk to the milk centers operated by these cooperatives. Every farmer that fails to deliver his milk as stated above and according to the mutual agreement shall lose his right to benefit from the feed subsidy program.

- Activate and modernize the laws and regulations related to the sector by all parties and provision of the deterrent power to prevent violations in the following and related issues:

- Review the customs tariffs on the cheeses and yogurts similar to those that are produced locally and watch for smuggling of such goods and products.

- Inspection and monitoring of the health and hygiene conditions at the dairy processing plants especially the illegal ones that operate seasonally and adversely affect the reputation of the producers.

- Strictly comply with the laws for granting licenses for the import of powdered milk and trace its course to make sure that it does not end up at the dairy processing plants. It is very important in this respect to strengthen the role of the Consumer Protection Agency in fighting adulteration and fraud products.

- Prevent the sales of cheese and yogurt in bulk containers that do not have and trade mark or production address or details. Enforcing LIBNOR norms and standards for containers and labels for dairy products.

- Holding campaigns to encourage the consumption of locally produced cheese and yogurts and emphasizing the advantage of fresh milk.

The next meeting was scheduled on 15th of Jan. 2014 at 1:30pm.

Annex 2

Mission of United Nations Office for the Coordination of Humanitarian Affairs (OCHA) Staff to LRF−FAO dairy project Sites

a. Introduction

In the framework of the Food and Agriculture Organization project “Recovery and Rehabilitation of Dairy Sector in Bekaa Valley and Hermel – Akkar Uplands” (FAO/LRF-26/ OSRO/LEB/901/UNJ), funded by Lebanon Recovery Fund (LRF), FAO staff and OCHA (United Nations Office for the Coordination of Humanitarian Affairs) representatives Mr. Thomas conducted several inspection field trips to different sites of the project activities. These visits covered random beneficiary sites selected in Bekaa and the North and Akkar. The objective of this visit was to monitor and touch the actual achievements in the field resulting from the project progress activities especially the impact on the life and livelihood of the small farmers for identification of project sites and beneficiaries to be filmed.

b. Attendees:

- Dr. Chedly Kayouli, FAO project manager.

- Mr. Thomas, OCHA

- Ms. Rawad, OCHA

- FAO Project staff

c. Areas Visited

Kafar Meshki Cooperative (Rola El Farkh):

The first visit was to Kafar Mishki of Western Bekaa to the Dairy Producers Cooperative of Kafar Mishki and the surrounding villages. The president of this cooperative is an active woman name Rola El Farkh. She owns and manages the place where the milk collection center is located. Adjacent to the milk collection center she runs a medium size dairy processing facility which is used to transform part of the milk produced by the farmers into demanded local varieties of yoghurt, cheese, and other dairy products. The remaining milk is delivered to milk transportation truck that this cooperative shares with another cooperative (Kherbet Rouha). The final destination of this tested and refrigerated milk is the dairy processing plants in the Bekaa. It is good to mention that all the equipments present at the milk collection center including the milk cooling tanks, laboratory, electric generator, and other accessories along with the dairy processing facility and the milk transportation truck are all provided by the LRF−FAO recovery and rehabilitation project. The number of farmers that benefit from the services ranges between 45 and 50 depending on the season.

After that Mrs. Rola took the group to visit few small dairy farmers in adjacent villages. These farmers benefited from the project interventions as milking machines, milk jars, disinfectants, and training. Mrs. Rola and the farmers emphasized the importance and the pronounced impact of the interventions and activities conducted by the LRF−FAO project funded by LRF, and she explained how it helped her in improving the milk production by quality and quantity hence the income of herself and other farmers in the area.

El Rafid Dairy processing center:

This collective dairy processing center managed by a woman name Sawsan Faraj was previously located in a very small place equipped with primitive equipments. This center is affiliated with Kherbet Rouha dairy cooperative. The LRF−FAO project understood that this center is serving more than 25 small farmers by giving them added value to the milk they produce. The material interventions and the training offered have increased the number of farmers into about 50 and improved the hygienic and quality standards of milk and dairy products by many folds. They rented a new spacious place located on the main road instead the small isolated one. Their volume of production increased more than 100% and they are sending products to Beirut. The success fast development of this business encouraged other workers in the sector to indulge in some kind of dairy processing and marketing of cheese and yoghurt in order to gain more income for the milk they produce.

Ghazza Dairy Cooperative:

The Ghazza Cooperative is considered one of the biggest in the area. The LRF−FAO dairy project has supplied this cooperative with a complete milk collection and refrigeration centre, a milk transportation truck, and a dairy processing centre. The cooperative serves more than 60 small dairy farmers either by collecting and cooling their milk then selling it at reasonable prices or transforming part of the milk into dairy products such as Labneh, Yogurt, and cheeses. These facilities provided the cooperative with a better stand when negotiating with the dairy producing plants owners. They get good price for their refrigerated, tested, and hygienically transported milk. A workshop about dairy processing was conducted at the dairy processing centre attended by more than 40 women. The Gazza center is a pioneer in the production of Mozzarella cheese a variety that the project dairy technologist introduced to the area.

Halba Cooperative (North):

The milk collection and processing center of this cooperative was established with the support of USAID and when we first visited it in our primary survey we found that it lacks many essential elements to make it strong and sustainable. The cooling capacity was insufficient so the FAO project more than doubled this capacity because the milk of many farmers was refused to the lack of space. The centre did not have a milk analysis facility so the project provided an automatic milk analyzing machine with several other small kits for fast testing of milk before being added to the rest. There are also two small collection and cooling centers located in villages relatively far away from the original one. This cooperative serves between 50 and 60 farmers but after the influx of the Syrian refugees with some of their livestock the number increased by 25%. Many traders purchase dairy products from the center and sell it to Syrian refugees at their camps or residence sites. The demand on dairy products has increased and the capacity of the collection and cooling and processing facilities ought to be expanded.

Ilat (Akkar):

This small milk collection and cooling center belongs to El Joumeh cooperative. This village is far from other centers so it was necessary to establish one small facility to serve the poor farmers that live in this village. Some of these farmers bring the milk on donkey's backs, and some use their hands to hold the milk buckets walking their way to the centre. The milk truck passes once a day at the morning to collect the refrigerated milk.

Joumeh Cooperative (North):

Joumeh cooperative is one of the most active and successful cooperatives in the Akkar. It includes a milk collection centre and a dairy processing facility. It serves a large number of farmers more than 40 most of them are small producers 25 to 60 kg of milk daily. The quantity of milk collected daily is around 2.5 tons and the cooling capacity is only 2 tons so the remaining milk is transformed into dairy products. The distinguished quality of these products has increased the demand to a great extent. Furthermore; and as result of the increased number of the Syrian refugees in the town of Beino the demand has further increased. They are obliged to employ women mostly Syrian to help in working two shifts in order to satisfy the growing demand. The citizens of Beino are trying their best to help the Syrian refugees although their resources are very limited. The center requires urgent need for another batch pasteurizer of 250 kg of milk.

In the same village two small dairy farmers were visited to have an idea about the problems and suffering they are facing.

Annex 3

Inaugural Ceremony organised by the project on 16th November 2013

This ceremony held under the patronage of H.E. Minister Hussein Hajj Hassan and a representative of Dr. Ali Moumen FAO representative in Lebanon and distinguished persons and activists and a remarkable crowd of farmers and producers especially from the Bekaa and Baalbeck Hermel Mohafazat. Through the project "Recovery and Rehabilitation of Dairy Sector in Beqaa Valley and Hermel -Akkar Uplands" and the project "Emergency Vaccination and Targeted Feeding of Livestock Grazing in Areas along the Syria-Lebanon Border", and collaboration with the Lebanese Ministry of Agriculture, invited to the inauguration of a milk collection and coolimg center and a dairy processing center in Bezzalliyeh and the launching of activities of the vaccination and feeding project.

The "Recovery and Rehabilitation of Dairy Sector in Beqaa Valley and Hermel-Akkar Uplands" is a development project sponsored by the Lebanese Relief Fund (LRF) and supported by the Lebanese Ministry of Agriculture (MOA). The Vaccination and Feeding project is an emergency project financed by generous donation from the British Government (1 Million USD) and it is also implemented by the MOA and the FAO.

The project "Emergency Vaccination and Targeted Feeding of Livestock Grazing in Areas along the Syria-Lebanon Border" responds to urgent health and veterinary requirements of the livestock present at the Syrian – Lebanese boarders and other Lebanese territories. As a consequence of the Syrian crisis, several hundreds of sick and infected animals infiltrated to Lebanon illegally which make this project an essential necessity. This project will contribute to the protection of the livestock wealth of Lebanon and support the small livestock farmers with feeds.

The Recovery and Rehabilitation of Dairy Sector in Beqaa Valley and Hermel-Akkar Uplands have established two milk collection and cooling centres in Al Labbwah (North of Baalbek). The dairy farmers have become more convinced with the importance and the obligation of fast cooling of milk. The demand for more collection and cooling capacity has increased subsequently this new centre has been established with the coordination with the MOA. This new centre like its two other sisters belong to the dairy producers cooperative of Bezzalliyeh, Rasm El Hadath and the surrounding villages. These centres play a very important role in maintaining the quality of milk and better prices for the small farmers.

One of the major important interventions of LRF FAO dairy project is the distribution of 250 mini & medium dairy producing units all made of food grade stainless steel. The impact was very encouraging as most farmers are processing their own milk now and getting better returns for the products they sell to neighbors and relatives. These modern units that replace the old non hygienic ones have provided the farmers and the consumers with health cheese and yogurt and other dairy products. The project Milk processing gives the farmer an additional added value to his milk equivalent to 50 – 80 % of the price of fresh milk.

The direct outcomes of years of continuous cooperation and collaboration between the LRF FAO dairy project and the MOA have shown positive and substantial results at various levels. The dairy sectore in Lebanon has never gained such consideration and attention as it received during the last three years due to the LRF FAO dairy project and the unlimited efforts and support of H.E. Minister Hussein Hajj Hassan to this project.

5.1.	Introduction

The project team has lived and resided with poor farmers in their homes, their tents, and their pastures and has looked closely at their problems and sufferings. The project has been in constant contact with more than 3,000 farmers, which made the team very well and directly informed about the needs and priorities for the development of the livestock sector and milk production in Lebanon.

The project has noticed that the most important obstacle in the progress and development of dairy cattle production sector in Lebanon is the lack of adequate coverage for artificial insemination which is believed to ensure genetic upgrading, lower the cost to the farmer, and prevent disease transmission. The following observations were discovered through extended field research:

1 - The very low fertility rate in cows may be one of the most important obstacles and barriers in front of converting the business of dairy cows breeding from a losing into a lucrative and profitable one. This theory actually applies to all private farms especially the small ones.

2 - The Artificial insemination services in Lebanon are in general very weak, except for individual pursuits for some large farmers. The proportion of farmers who use artificial insemination regularly does not exceed 10% , while 30 % use both artificial insemination and the bull together, while the largest proportion of 60% of farmers rely on natural mating. Usually the farmers prefer to raise their own bulls in a farm that does not exceed 4 or 5 cows. This means that the production of one cow or more goes entirely to the feeding and raising of this bull. The low cow fertility continuously lowers the production capacity of the cow and shortens its commercial life. The natural consequence of this mischief is exhausting the budget of the poor farmer by the importation of pregnant heifers. Furthermore; the use of natural mating may harbor many risks of transmission of venereal diseases by the bull.

Therefore reproductive improvement of dairy cows are major components in the primary interventions of the LRF FAO project," Recovery and Rehabilitation of Dairy Sector in Beqaa Valley and Hermel-Akkar Uplands" (LRF-26 OSRO/LEB/201/UNJ).  This intervention was to train a group of Artificial Inseminators from different parts of the targeted areas of the project and provide them with the necessary tools and equipment to serve the farms located at their respective areas. Although this intervention was postponed due to forceful reasons, two sessions were finally executed:

- Between 15th of September to the 3ed of October 2013 in Zahle, for Bekaa and Baalbeck – Hermel Mohafazat (for 38 trainess) and

- Between 18th Of November to 4th of December 2013 in Batroun at the Marine Science Institute (MOA) for areas in North Lebanon, Akkar, and Mont Lebanon.

The aim of this particular intervention was to train a group of Artificial Inseminators from different parts of the project sites and to support them with distribution of the necessary Insemination Kits to be immediately operationally ready to start working within the Dairy Coop’s and to give services to dairy small holders.

5.2.	The Trainees

The trainees in this project were chosen with the collaboration of Dairy Producers Cooperatives and MOA in the regions included in the project, the number of the trainees was forty two (42) from Akkar, North Lebanon and Mont Lebanon and thirty eight (38) from Beqaa, Baalbeck−Hermel. They are young enthusiastic and energetic farmers or sons or daughters of farmers or from extension service (MOA) or students from Lebanese University. Most of them came daily to attend the courses and some that came from distant areas. The lists of participants are indicated in annexes 4 C & 4 ED.

5.3.	The trainers

Distinguished veterinarians were the principle trainers and instructors. Government (MOA) personnel were involved such as Dr. Obeidah Modawwar, Dr. Ali Raad, and Dr. Iqbal Ziadeh. Private highly experienced veterinarians also actively participated such as Dr. Jamal Khazaal (Liban vet) and Dr. Jirji Maasri (Maasri Holshtein), Dr. Amin OuAchem (Liban lait) and Dr. Christiane Cornu (Sersia France)

Dr. Obeidah Modawwar and Dr. Ali Raad, Private highly experienced veterinarians also actively participated such as Dr. Jamal Khazaal (Liban vet) and Dr. Jirji Maasri (Maasri Holshtein) , Dr. Amin OuAchem (Liban lait) and Dr. Christiane Cornu (Sersia France). The daily follow up of the training activities and organization was secured by a team of Dr. Issam Nahhal coordinator (National Project Consultant), Dr. Mohamad younis (MOA), Dr. Mostafa Refaai (MOA), as Assistants. Logistics and clerical services were accomplished by Engineer Miss Aline Zeidan and Mr. Anthony Gossein and Mr. Maher Fouaani. Dr. Chedly Kayouli (The FAO Project Manager) was the head officer of the course that was present on daily basis and monitored every detail and activity.

5.4.	The Training Program

The daily training schedule included a morning theoretical and audio visual presentations and lectures accompanied with discussion and question / answer sessions. The trainees were divided into four groups of about ten students each. Each group was accompanied by four trainers and one master visiting veterinarian AI expert at a general average of one trainer for every two trainees. On each afternoon two groups were admitted for the practical training at an average of 5 trainers and 5 cows per group or one trainer and a cow for every two students. An adjacent barn equipped with all necessary feeding and sleeping areas for the cows was established in Batroun while three dairy farms were selected in Zahle surroundings for practice. After the two weeks of training course and during the third week, the trainees underwent a one day review, discussion and evaluation of the course followed by two days of theoretical and practical examination. The examiners were neutral professors that have no relations or acquaintance with the trainees themselves for impartial and honest evaluation.

5.5.	The theoretical part

The lecturers and instructors emphasized on the following topics:

- An account about the history of AI and its importance and impact on the genetic improvement of dairy herds around the world.

- The anatomy and physiology of the reproductive system of the cow. Dissection autopsy was made of an actual reproductive system of a cow retrieved from the slaughter house.

- Estrus Cycle of the cow and important principles in Heat detection.

- Some diseases and irregularities that may disturb the function of the reproductive organs and the reproductive efficiency as a whole.

- Role of improved nutrition on cow fertility

- The AI technique with full details and direct demonstration on the proper ways of preparations and practicing of this technique.

5.6.	The Practical Part

As mentioned before the practical part of the course took place at a special facility equipped for this purpose. Ten cows were leased on a daily basis from farmers in the area. Each trainee had to practice on the ten different cows in order to detect the individual differences among the reproductive tracts of different cows. The practical part of the course emphasized on the following:

- Using the required gloves and lubricating jell after removing watches and rings. Cleaning the rectum out of its fecal content.

- The direct rectal palpation to locate the reproductive tract of the Cow.

- Trace the cervix and the uterus and feel the uterine horns when accessible.

- Manipulate the Cervix in order to feel the cervical rings.

- Trace the AI gun and follow it inside the vagina, cervix, and uterus when possible.

- Opening of the liquid nitrogen tank and withdrawing of a frozen semen straw and closing it as fast as possible. Identifying the sire used by reading the labels on the straw.

- Thawing the frozen seamen.

- Loading the AI gun and cutting the straw and dressing it with the disposable plastic tube.

- Each trainee had to exercise the AI operation every day for several times on different cows during the whole training course.

5.7.	Final examinations

At the end of the training course a final examination was conducted to evaluate the level of learning of each trainee. The trainees were divided into two groups and each group was given a full day of examinations. Each trainee was subjected to a theoretical and practical test. In the theoretical test each student was questioned orally and individually by six veterinarians and each examiner gave a grade to the student. The average of these six grades was recorded and considered as the result of the student’s theoretical achievement. The questions asked were related and relevant to the theoretical material that was given to the students (please refer to the section Theoretical Part).

The practical test was conducted in a similar manner where each student had to complete the whole operation of Artificial Insemination starting from preparing the cow and preparing the equipment and performing the actual insemination process. Each trainee had to do the practical test on three different cows and he was supposed to explain what he was doing to the examining committee. Each examiner gave a grade to each student where the average of the six grades represented the student’s practical achievement.

The final course grade was calculated by adding the grade of the theoretical part to the grade of the practical part multiplied by three. Giving more weight to the practical part was employed due to the importance of field practice and actual operation of Artificial Insemination. Since the original grades were over 5 the final grade was over 20. (5 + 5X3 = 20)

| Grade | Evaluation |
| --- | --- |
| 5 | Excellent |
| 4 | Good |
| 3 | Acceptable |
| 2 | Poor |
| 1 | Bad |

5.8. Artificial Insemination Course Evaluation

The trainees were very attentive and interested in the training topics where they interacted very well with the trainers. The feedback of the trainees about the training course was evaluated through preparation 15 questionnaires in simple Arabic language where most of the answers can be by giving grades of 1 to 5 where 5 is the most  and one is the least. The trainees were urged to write any comment negative or positive and to elaborate on how they think such courses may be improved in the future. They had the freedom to write their names or not. Almost all did not identify themselves which gave them more freedom to express themselves liberally.

The analysis of their answers and remarks indicated the general appreciation of the trainess to the course as a whole with average grade of 4.5 / 5 which is a good score. Their main recommendation are related to: 1) Follow up with the Inseminators in their field work, 2) Extend the training course, 3) Increase the number of cows for practical demonstration, 4) Reduce the number of participants in each session for better participation and 5) organize sessions for farmers and for technicians separately. Details of evaluation are presented in annexes A & 4 B.

5.9. Strategy for Assignment of Inseminators and Distribution Supplies

The project has applied innovative strategy to reinforce artificial insemination (A.I.) services in Lebanon based on conducting intensive training courses on Artificial Insemination to selected people especially from the farmer’s cooperatives with their supply of the necessary semen and A.I. equipment. The key strategy will be to use the VDPA’s as focal point to give AI services to smallholders through successful trained inseminators.

The highest scoring and outstanding trainees were granted AI equipments that will enable them to start practicing and serving immediately areas of the cooperatives at low charge (under the supervision of the Dairy Coop). The project has equipped 27 AI centers distributed in all project sites plus Mont Lebanon as follow:

- West Bekaa and Rashaya: 5 centers

- Central Bekaa: 3 centers

- Baalbek -Hermel: 7 centers

- Akkar and North: 10 centers.

- Mount Lebanon: 2 centers

Each centre is now equipped with complete Artificial Insemination tools and special liquid nitrogen vessels to store the frozen semen. The MOA has afforded 18 000 doses of imported frozen semen while each centre and inseminator has provided a special car for insemination in order to provide faster and better service for AI in each center.

Each inseminator will be followed up to see his or her performance and achievements. Any person that proves to be inefficient or incompetent in the field work of Artificial Insemination will be denied from the AI equipment to be offered to another successful inseminator. In the near future competent and capable Inseminators will be subjected to a practical training about using the ultra sound pregnancy detectors and may be given such a machine upon successfully completing the field training session.The details of artificial insemination centres and groups of assigned inseminators as well as the lists of AI supplies distributed are presented in annexes E & 4 F.

Annex 4 B

Course evaluation by the students AI in Zahle

15 September  to 4 October 2013

Introduction

A questionnaire in simple Arabic language was prepared to study the feedback of the students about the training course.  There were 15 questions where most of the answers can be by giving grades of 1 to 5 where 5 is the most  and one is the least. Few questions had to be answered by yes or no and all the questions are accompanied by spaces for comments and remarks. The students were urged to write any comment negative or positive and to elaborate on how they think such courses may be improved in the future. The student had the freedom to write their names or not. Almost all did not identify themselves which gave them more freedom to express themselves liberally. Twenty nine students out of 38 participated in answering these questionnaires.

Analysis

The grades given by each student for each question were tabulated on an excel sheet and the averages were calculated. The other types of answers were also recorded and analyzed. Following are the questions and average grades or answers given by the 29 students and their interpretation. When applicable a sample of the remarks and comments are included:

Question No. 1:
What is your overall evaluation of the training course ?

The average grade was 4.8 / 5 which is an excellent score. It reflects general appreciation of the students to the course as a whole.

Random remarks:

- It was excellent.

- All trainers were highly knowledgeable and professional.

- Very informative.

Question No.2:

Did the course contributed in improving your understanding of Artificial Insemination??

The average grade was 4.6 / 5 which is a very good score it indicates that a new understanding to the whole principles and practices of AI was created.

Random remarks:

- Everything was new and important.

- The combination of theoretical and practical training was very fruitful.

- Emphasis on nutrition as a very important element in reproduction was very interesting.

Question No.3:

What is your evaluation to the method of organization and running of the training course?

The average grade was 4.6 / 5 which is a very good score.

Random remarks:

- It was good.

- It was excellent but the number of cows should be increased.

- It was serious and well organized.

Question No.4:

To what extent did this course meet your expectations?

The average grade was 4.4 / 5 which is a good score actually most of the students were not sure what to expect from the course.

Random remarks:

- My attention was attracted to many new things and Ideas.

- It fulfilled my expectations for relating AI to management and nutrition.

- It was fine but I expected more practical work with much more cows.

Question 5:

Was the language used in lectures and explanation clear and implicit?

The average grade was 4.7 / 5 which a very good score that reflects easy language and smooth communication of learning.

Random remarks:

- Everything was clear and understood.

- It was easy and simple even to an ordinary farmer.

- Even when the language was English or French the translation to the everyday Arabic language was excellent.

Question No. 6:

Was the lecture hall satisfactory as the seats and display and communication?

The average grade was 4.5 / 5 which is a good score.

Random remarks:

- Everything was all right.

- Noise and chaos made by the students affected the communication.

- It was satisfactory.

Question No. 7:

Were the locations and the necessary training elements satisfactory?

The average grade was 4.4 / 5 which is a satisfactory score.

Random remarks:

- Everything was satisfactory.

- The number of cows was very little compared to the number of students.

- There was no problem in all that.

Question No. 8:

Do you consider the chances were fair and equal among the students to participate in the practical section?

The average grade was 4.25 / 5. The grades ranged between 1 and 5 and the number of virtual insemination according to the students ranged between 4 and 25. Most students indicated that they practiced a minimum of 10 operations each.

Random remarks:

- I made around 25 palpations and insemination operations during the course.

- I do not know but now I have more confidence.

- It was little and unfair more cows are required.

Question No. 9:

Was the number of trainers sufficient especially during the practical section?

The average grade was 4.7 / 5 which is very good score as usually there were a minimum of two trainers per group of 10 students.

Random remarks:

- A minimum of two trainers were with us at all times.

- Usually two veterinarians and one trainer.

- More trainers are better (three instead of two).

Question 10:

Was the duration of the course (Two weeks) satisfactory?

Seven respondents said it was short, two said it was long, and 19 said it was just right.

Random remarks:

- The training course should be extended to allow for more supervised practical training.

- It must be three weeks.

- Reduce the theoretical part about hormones and such details.

Question No. 11:

Did the training course contributed in:

- Introducing new ideas and technologies?

- Teaching new and useful practices?

- Changing some prevailing and inherited ideas about the subject?

- Improve the general understanding of veterinary health?

- Suggesting solutions for some difficult problems?

Twenty three respondents answered that all the five elements mentioned in the question were affected positively by the training course while the rest said that only four were affected with one with only 3 out of five.

Question 12:

Were the logistic services such as food and transportation satisfactory?

The average grade was 4.5 / 5 which is good. Some of the trainees have their private cars while others were taken by the project cars. The food was mainly sandwiches for practicality and time saving. Hot and cold drinks were available at all times during lectures and discussions and recesses.

Random remarks:

- Everything was excellent: delicious food, generous hospitality, and good transportation facilities. thank you.

- Transportation was not well organized more vehicles are required.

- I hated sandwiches every day.

Question 13:

How do you think we can improve such training courses in the future?

Random answers:

- Introducing new technologies such as Echo for pregnancy diagnosis.

- More explanation and demonstrations.

- Conduct such courses on regular basis to refresh the trainees.

- Introduce other topics in the training course to cover all nutrition, management, and veterinary practices.

- Increase the number of cows.

- Reduce the number of participants in each session for better control and participation.

- Maintain a relatively analogous educational standard of the trainees.

- Increase the sets of equipment and materials used for training.

Question No. 14:

Do you advise your working mates to attend such training courses?

All the answers were YES.

Question 15:

Do you have any other remarks?

Random answers:

- We thank Dr. Kayouly and the project team and the professors.

- Follow up with the Inseminators in their field work.

- Increase the number of such courses all over Lebanon.

Work more closely with the dairy farmers.

Annex 4 C

Course evaluation by the students AI In Batroun

18 November – 3 December 2013

Introduction

A questionnaire in simple Arabic language was prepared to study the feedback of the students about the training course.  There were 15 questions where most of the answers can be by giving grades of 1 to 5 where 5 is the most  and one is the least. Few questions had to be answered by yes or no and all the questions are accompanied by spaces for comments and remarks. The students were urged to write any comment negative or positive and to elaborate on how they think such courses may be improved in the future. The student had the freedom to write their names or not. Almost all did not identify themselves which gave them more freedom to express themselves liberally. Thirty five students out of 41 participated in answering these questionnaires.

Analysis:

The grades given by each student for each question were tabulated on an excel sheet and the averages were calculated. The other types of answers were also recorded and analyzed. Following are the questions and average grades or answers given by the 35 students and their interpretation. When applicable a sample of the remarks and comments are included:

Question No. 1:
What is your overall evaluation of the training course ?

The average grade was 4.4 / 5 which is a good score. It reflects general appreciation of the students to the course as a whole.

Random remarks:

- It was excellent.

- All trainers were highly knowledgeable and professional.

- Very informative.

- Mixing farmers and technicians together in the same session is not a good idea.

Question No.2:

Did the course contributed in improving your understanding of Artificial Insemination??

The average grade was 4.6 / 5 which is a very good score it indicates that a new understanding to the whole principles and practices of AI was created.

Random remarks:

- Everything was new and important.

- The combination of theoretical and practical training was very fruitful.

- More emphasis should be made on practical side.

- Emphasis on nutrition as a very important element in reproduction was very interesting.

Question No.3:

What is your evaluation to the method of organization and running of the training course?

The average grade was 4.2 / 5 which is a satisfactory score.

Random remarks:

- It was good.

- It was excellent but the number of cows should be increased.

- It was serious and well organized.

Question No.4:

To what extent did this course meet your expectations?

The average grade was 4.4 / 5 which is a good score actually most of the students were not sure what to expect from the course.

Random remarks:

- My attention was attracted to many new things and Ideas.

- It fulfilled my expectations for relating AI to management and nutrition.

- It was fine but I expected more practical work with much more cows.

Question 5:

Was the language used in lectures and explanation clear and implicit?

The average grade was 4.6 / 5 which a very good score that reflects easy language and smooth communication of learning.

Random remarks:

- Everything was clear and understood.

- It was easy and simple even to an ordinary farmer.

- Even when the language was English or French the translation to the everyday Arabic language was excellent.

- Avoid foreign languages in the future.

Question No. 6:

Was the lecture hall satisfactory as the seats and display and communication?

The average grade was 4.3 / 5 which is a satisfactory score.

Random remarks:

- Everything was all right.

- Noise and chaos made by the students affected the communication.

- It was satisfactory.

- Better sound system and visual facilities are required.

Question No. 7:

Were the locations and the necessary training elements satisfactory?

The average grade was 4.3 / 5 which is a satisfactory score.

Random remarks:

- Everything was satisfactory.

- The number of cows was very little compared to the number of students.

- There was no problem in all that.

- It was good that the lecture hall and the practical site were very close to each other.

Question No. 8:

Do you consider the chances were fair and equal among the students to participate in the practical section?

The average grade was 3.5 / 5. The grades ranged between 1 and 5 and the number of virtual insemination according to the students ranged between 3 and 16. Most students indicated that they practiced a minimum of 8 operations each.

Random remarks:

- I made around 15 palpations and insemination operations during the course.

- I do not know but now I have more confidence.

- It was unfair and some students had the chance to make more operations than others for this reason more cows are required.

- Some students have harmed and wounded the cows and these cows were not available anymore for training.

Question No. 9:

Was the number of trainers sufficient especially during the practical section?

The average grade was 4.6 / 5 which is very good score as usually there were a minimum of two trainers and one visiting veterinarian per group of 10 students.

Random remarks:

- A minimum of two trainers per group were with us at all times.

- Usually two veterinarians and two trainers.

- More trainers are better.

Question 10:

Was the duration of the course (Two weeks) satisfactory?

Two respondents said it was short, one said it was long, and 32 said it was just right.

Random remarks:

- The training course should be extended to allow for more supervised practical training.

- It must be three weeks.

- Reduce the theoretical part and increase practical training.

Question No. 11:

Did the training course contributed in:

- Introducing new ideas and technologies?

- Teaching new and useful practices?

- Changing some prevailing and inherited ideas about the subject?

- Improve the general understanding of veterinary health?

- Suggesting solutions for some difficult problems?

Seven respondents said they were affected positively by less than 4 items, while 28 answered said that all the five elements mentioned in the question were affected positively by the training course.

Question 12:

Were the logistic services such as food and transportation satisfactory?

The average grade was 4.4 / 5 which is good. Some of the trainees have their private cars while others used public transportation. The food was mainly sandwiches for practicality and time saving. Hot and cold drinks were available at all times during lectures and discussions and recesses.

Random remarks:

- Everything was excellent: delicious food, generous hospitality, and good transportation facilities. thank you.

- Transportation was not well organized students from remote areas such as Akkar and Donniyyeh have to pay lot for transportation.

- I hated sandwiches every day especially that they usually arrived cold.

Question 13:

How do you think we can improve such training courses in the future?

Random answers:

- Introducing new technologies such as Echo for pregnancy diagnosis.

- More explanation during practical demonstrations.

- Conduct such courses on regular basis to refresh the trainees in each Caza.

- Introduce other topics in the training course to cover all nutrition, management, and veterinary practices.

- Increase the number of cows.

- Reduce the number of participants in each session for better control and participation.

- Maintain a relatively analogous educational standard of the trainees. Two major categories were present the farmers and the technicians. The technicians said the farmers should not be included because their educational and scientific background is very low. The farmers said that the technicians should not be included because they made so much noise talking and discussing issues that they do not understand.

- Increase the sets of equipment and materials used for training.

Question No. 14:

Do you advise your working mates to attend such training courses?

All the answers were YES.

Question 15:

Do you have any other remarks?

Random answers:

- We thank Dr. Kayouly and the project team and the professors.

- Better sound systems are required.

- Increase practical training and reduce theoretical.

- Follow up with the Inseminators in their field work.

- Increase the number of such courses all over Lebanon.

- Work more closely with the dairy farmers.

Annex 4 C: List of Participant to Artificial Insemination (Beqaa)

| Caza | الجمعية التعاونية لإنتاج الحليب في Dairy Coop | الإسم Name | التلفون Telephone | المصدر Origin |
| --- | --- | --- | --- | --- |
| راشيا | خربة روحا وجوارها | 1 | حسين غازي بو حسين | 03- 603 347 | التعاونية (البيرة) |
|  |  | 2 | خالد محسن أبو فارس | 70- 832 994 | التعاونية (كفردينس) |
|  |  | 3 | أيمن يوسف | 03- 015 640 | التعاونية (الرفيض |
|  | كفرمشكي وجوارها | 4 | يوسف أحمد صبح | 03- 683 854 | التعاونية (سحمر) |
|  |  | 5 | سعيد عطا الله سعيد | 03- 730 511 | التعاونية (كفرمشكي) |
| البقاع الغربي | الصويري وجوارها | 6 | محمد زيتون | 03- 841 491 | وزارة الزراعة جب جنين (الصويري) |
|  | غزة وجوارها | 7 | عبدو المجذوب | 70- 449 262 | التعاونية (غزة) |
|  |  | 8 | بلال أحمد خليل | 03- 092 238 | التعاونية (غزة) |
|  |  | 9 | عبدالله علي سعيد | 70- 449 262 | التعاونية (غزة) |
|  | المرج وجوارها | 10 | كمال أبو عديلة | 71- 148 085 | وزارة الزراعة جب جنين (حوش الحريمة) |
|  |  | 11 | لؤي ابو عثمان | 03- 659 113 | التعاونية (المرج) |
|  |  | 12 | أحمد زياد شمّوري | 71- 729 658 | التعاونية (المرج) |
|  |  | 13 | شامل الجرّاح | 03- 933 550 | طالب (المرج) |
|  | الجمعية التعاونية لإنتاج الحليب في | الإسم | التلفون | التعاونية |
| البقاع الاوسط | زحلة وجوارها | 14 | طانيوس المعلوف | 70-422 472 | طالب )زحلة) |
|  |  | 15 | إلسا زعتر | 76-772 024 | طالبة (زحلة) |
|  |  | 16 | دوريس شمعون | 70-631 726 | طالبة (برج حمود) |
|  |  | 17 | علي الديراني | 03-290 585 | التعاونية (قصرنبا) |
|  |  | 18 | د. جاد سعيد معكرون | 03- 931 452 | التعاونية (رياق) |
| بعلبك |  | 19 | احمد زين الدين | 70- 941 969 | وزارة الزراعة جلالا (رياق) |
|  | الناصرية وجوارها | 20 | عباس فقيه | 71-328 619 | وزارة الزراعة جلالا (علي النهري) |
|  |  | 21 | علي ملحم الترشيشي | 76- 667 501 | التعاونية (الناصرية) |
|  |  | 22 | علي محمد الترشيشي | 76-769 897 | التعاونية (الناصرية) |
|  | حوش النبي وجوارها | 23 | د.علي النجار | 03- 690 625 | التعاونية (شمسطار) |
|  |  | 24 | حسين محمد القرصيفي | 71- 178 246 | طالب (حوش الرافقة) |
|  | طاريا وجوارها | 25 | د.محمد سعدون حمية | 03- 979 005 | التعاونية (سرعين) |
|  |  | 26 | مصطفى شهاب الدلباني | 71- 123 283 | طالب(تمنين الفوقا) |

| المنطقة | الجمعية التعاونية لإنتاج الحليب في | الإسم | التلفون | التعاونية |
| --- | --- | --- | --- | --- |
| بعلبك | شليفا وجوارها | 26 | حمودي ناصيف | 71- 468 037 | طالب (بوداي) |
|  |  | 27 | علي مصطفى الذكرى | 03- 182 807 | تعاونية (بعلبك) |
|  |  | 28 | زاهر صلح | 70-547 509 | تعاونية (بعلبك) |
|  | رسم الحدث | 29 | د. علي رستم | 76- 044 149 | تعاونية (يونين) |
|  | اللبوة- البزالية وجوارها | 30 | د.عماد صوان | 03- 562 394 | وزارة الزراعة اللبوة (يونين) |
|  |  | 31 | بلال نزهة | 70-545 055 | وزارة الزراعة اللبوة (اللبوة) |
|  |  | 32 | نواف البزال | 70-731 161 | وزارة الزراعة اللبوة (البزالية) |
| الهرمل | مشاريع القاع وجوارها | 33 | بهاء محمد كرنبة | 76-356 989 | التعاونية (مشاريع القاع) |
|  |  | 34 | كمال شحادة بو فارس | 03- 116 134 | التعاونية (مشاريع القاع) |
|  | حوش السيد علي وجوارها | 35 | علي حسين الهق | 71- 026 869 | التعاونية (حوش السيد علي) |
|  |  | 36 | حسين مرتضى | 03-376 308 | التعاونية (الهرمل) |
|  |  | 37 | فرنسوا شدياق | 70-142 992 | وزارة الزراعة البترون (البترون) |

Annex 4 D: List of Participant to Artificial Insemination (Akkar, North & Mont Lebanon)

| المنطقة Area | الإسم Name | التلفون Telephone | صفة Origin |
| --- | --- | --- | --- |
| حلبا | 1 | فادي الحلبي (حلبا) | 76- 092 628 | مربّي |
| القبيات | 2 | محمد العلي (عيدمون) | 03- 413 998 | مهندس زراعي |
|  | 3 | وائل محمد ضاهر (وادي خالد) | 71- 947 891 | مربّي |
|  | 4 | عمّار هشام سرّاج (القبيات) | 76- 311 193 78- 905 388 | مربّي |
|  | 5 | فادي حمود (عكّار العتيقة) | 03- 563 605 | مربّي |
| الجومة | 6 | فادي محمد محمود اسماعيل (حي زوق) | 03- 563 605 | مساعد فنّي بيطري |
|  | 7 | رشيد ناصر عثمان (الفنيدق) | 03- 339 691 | مربّي |
|  | 8 | عبد الرزّاق شعبان (مشحا) | 71- 180 835 | مساعد فنّي بيطري |
|  | 9 | عبد الهادي الرافعي | 71- 218 427 | مساعد فنّي بيطري |
|  | 10 | عبد الكريم محمد عل(الدورة) | 70-365 336 | مربّي |
|  | 11 | طعّان عبدالله | 71- 766 825 | مربي |
| الدريب | 12 | ربيع عبدالله (سفيرة دريب) | 71- 828 136 | مربّي |

| المنطقة | الإسم | التلفون | صفة |
| --- | --- | --- | --- |
| زغرتا | 13 | طوني جبريل (زغرتا) | 03- 886 974 | مربّي |
|  | 14 | بشير نعّوم (زغرتا) | 71- 509 999 | مربّي |
|  | 15 | سايد نكد (زغرتا ) | 03- 456 991 | مربّي |
| الكورة | 16 | شادي الناهوم )الكورة) | 70- 190 215 | طبيب بيطري |
|  | 17 | غاوي غاوي (الكورة) | 03- 016 731 | طبيب بيطري |
|  | 18 | سمعان الهندي | 70- 238 454 | تلميذ بيطري |
| البترون | 19 | فرنسوا شدياق (البترون) | 70 - 142 992 | مهندس زراعي |
|  | 20 | أمين منذر (البترون( | 03 - 657 530 | مربّي |
|  | 21 | جريس قبريانوس | 71- 995 807 | مربي |
| الضنيّة | 22 | جميل ديب (بيت الفقس) | 03- 071 833 | مساعد فنّي بيطري |
|  | 23 | ربيع الضناوي ( دير نبوح) | 70- 347 354 | مربّي |
|  | 24 | هيثم جمال (بخعون) | 70-379 389 | مربّي |

| سهل عكار | 25 | إبراهيم ديب (بيت ايوب) | 70- 106 635 | مساعد فني |
| --- | --- | --- | --- | --- |
|  | 26 | عبد الرحيم كيلاني (بيت الحاج كوشا) | 70- 198 730 | مساعد فني |
|  | 27 | أحمد حسين (العبّودية) | 71- 887 086 | مساعد فني |
| طرابلس | 28 | فراس محمد ياسين (طباع) | 71- 239 154 | طبيب بيطري |
|  | 29 | فادي شحادة (طرابلس) | 03- 186 587 | مربي |
|  | 30 | جاد النشار | 03- 960530 | تلميذ بيطري |
| بيروت | 31 | جورج رعد | 70- 097 361 | مهندس زراعي |
| جبيل | 32 | بدوي المصري (جبيل) | 03- 730 532 | مربي |
|  | 33 | أنطونيوس غوش (جبيل) | 03- 875 598 | مساعد فني |
|  | 34 | فريدريك خليفة | 03- 03 6977 | طبيب بيطري |
|  | 35 | فيصل خضر(اللقلوق) | 71- 097 290 | تلميذ بيطري |
|  | 36 | ماريّا معلّم (جبيل) | 03- 398 002 | تلميذة بيطرية |
| المنطقة | الإسم | التلفون | الصفة | الوصول الساعة الامضاء |
| جبل لبنان | 37 | يوسف صالح (المتن) | 03- 091 455 | طبيب بيطري |
|  | 38 | مروان العربضي (عاليه) |  | طبيب بيطري |
|  | 39 | ناجي صعب (بكفيّا) | 70- 295 253 | طبيب بيطري |
|  | 40 | مايكل المصري صليما المتن الاعلى) (كفرسلوان حمّاتة) | 70- 144269 | تلميذ بيطري |
| زحلة | 41 | شربل صقر | 03- 002361 | تلميذ بيطري |
| رأس بعلبك | 42 | إيهاب عبدو منصور | 70- 106 781 | تلميذبيطري |

Annex 4 E: List Of Artificial Inseminators Equiped with AI kits (Beqaa)

| الجمعية التعاونية لإنتاج الحليب في Dairy Coop | الإسم Name | التلفون Telephone | معدّات Equipment |
| --- | --- | --- | --- |
| خربة روحا وجوارها | أيمن يوسف | 03- 015 640 | عدّة كاملة |
| كفرمشكي وجوارها | يوسف أحمد صبح | 03- 683 854 | عدّة كاملة |
| الصويري وجوارها | محمد زيتون | 03- 841 491 | عدّة كاملة |
| غزة وجوارها | عبدو المجذوب | 70- 449 262 | عدّة كاملة |
|  | بلال أحمد خليل | 03- 092 238 |  |
|  | عبدالله سعيد المجذوب | 71- 649 747 |  |
| المرج وجوارها | أحمد زياد شمّوري | 71- 729 658 | عدّة كاملة |
|  | لؤي بو عثمان | 03- 653 118 |  |
| زحلة وجوارها | عباس فقيه | 71- 328 619 | عدّة كاملة |
| منطقة تربل وجوارها | جاد سعيد معكرون | 03- 931 452 | عدّة كاملة |
| الناصرية وجوارها | علي ملحم الترشيشي | 76- 667 501 | عدّة كاملة |
|  | علي محمد الترشيشي | 76- 769 897 |  |
| منطقة غربي بعلبك | علي النجار | 03- 690 625 | عدّة كاملة |
| حوش النبي وجوارها | حسين القرصيفي | 71- 178 246 | عدّة كاملة |
| بعلبك وجوارها | زاهر صلح | 70- 547 509 | عدّة كاملة |
|  | علي الذكرى | 03- 182 807 |  |
| رسم الحدث وجوارها | د. علي رستم | 76- 044 149 | عدّة كاملة |
|  | د.عماد صوان | 03- 562 394 |  |
| اللبوة – البزالية وجوارها | بلا ل نزهة | 70- 545 055 | عدّة كاملة |
| مشاريع القاع وجوارها | كمال شحادة بو فارس | 71- 870 421 | عدّة كاملة |
|  | بهاء محمد كرنبة | 76- 356 989 |  |
| حوش السيد علي وجوارها | علي حسين الهق | 71- 026 869 | عدّة كاملة |

Annex 5

Delivery Of Dairy Equipment & Lists Of Project Beneficiaries (LRF 26)

| List of Project Beneficiaries for 100 Milking Machines |
| --- |
| P.O. Nb :5201074 ORSO/LEB/201/UNJ - 14 August 2013 |
| Quantity Received = 100 Milking Machines |
| Caza | Village | Names | Telephone | Registration No | Qty |
| Zgharta | Kfardlakos | Wadad Bachir Naoum | 06-667403 |  | 1 |
|  | Alma | Rachid Ahmad Addouj | 70-207847 | 3 | 1 |
|  |  | abdala Kaysar Wehbi (Naziha Youssef) | 06-685186 |  | 1 |
|  |  | Mahmoud Mhamad El-Masri | 71-583691 |  | 1 |
|  |  | Houriyye Erslen | 71-583691 |  |  |
|  | Meryata | Taha Ali obayd | 71-934090 | 13 | 1 |
|  | Bchennin | Leiba Fadel | 70-473406 |  | 1 |
| Sub Total Zgharta : | 6 |
| Caza | Village | Names | Telephone | Registration No | Qty |
| Batroun | Chebtin | charbel Youssef Najm (Chadia) | 76-580007 | 50 | 1 |
|  | Niha | Youssef Atiyeh (Wasten) | 06-775432 |  | 1 |
|  | Batroun | Pierre Tanios Samarani | 71- 152833 | 1 | 1 |
|  | Bjdarfel | Amin Monzer |  |  | 1 |
| Sub Total Batroun : | 4 |
| Caza | Village | Names | Telephone | Registration No | No |
| Koura | Kfarkahol | Nicolas Elias Semaan | 03-532647 | 9 | 1 |
|  | Al-Majdel | Moussa Chalouhi (Georgina Alam) | 70-834011 | 18 | 1 |
|  | Habbouch | Miled Jabbour (Hiyam) | 06-950205 |  | 1 |
|  |  | Elias Tawk (Odette) | 06-950205 |  | 1 |
| Sub Total Koura : | 4 |
| Caza | Village | Names | Telephone | Registration No | Qty |
| Donniyeh | Beit AlFakes | Mhamad Yehiya (Hend Yehiya) | 03-790157 | 22 | 1 |
|  |  | Khadija Mahmoud Dib+Khadija Khoder Hassoun | 03-821518 |  | 1 |
|  |  | Hayat + Ali Yehiya | 03-405839 |  | 1 |
|  |  | Emna + Ahmad Hamad Yehiya |  |  | 1 |
|  |  | Chafic Mhamad Yehiya | 70-565747 | 44 | 1 |
|  |  | Ayman Abd el Malak Hajj | 70-186344 | 44 | 1 |
|  |  | Abed el ghafar abed lmalak lhaj (ramia) |  | 44 | 1 |
|  |  | Imane ahmad dib | 70-252781 |  | 1 |
|  |  | Salima Ahmad Dib(abed el aziz) | 70-252781 | 25 | 1 |
|  |  | Nada mohamed Omar (abed el ghafour) | 70-252781 | 25 | 1 |
|  |  | Rokiya khoder Hassoun | 71-459335 | 25 | 1 |
|  |  | Abed lmawla Hamad (Mariam) | 70-345603 |  | 1 |
|  | Assoun | Abed el kader Khoder (Honayda) | 06-490939 |  | 1 |
|  |  | Khoder + Abd Hamid Khoder | 06-491161 |  | 1 |
|  |  | Ali mohamed hussein el sheikh(Salima) | 03-368093 | 49 | 1 |
|  |  | Omar mohamed kanj | 03-430561 | 20 | 1 |
|  | Nemrin | Samira Mahmoud Obeid (Mehdi Hassan Merei) | 71-909188 | 79 | 1 |
| Caza | Village | Names | Telephone | Registration No | Qty |
| Donniyeh | Karsita | Mariam ahmad hussein issa | 76-002015 |  | 1 |
|  |  | Fatme hamad el hayek | 71-864074 | 13 | 1 |
|  |  | Khaled Rachid Alwan (Diba) | 70-569152 | 55 | 1 |
|  |  | Fattoum (mohamed zeinedine el hajj) ) | 71-325175 | 84 | 1 |
|  |  | Mohamed mahmoud el hayek (Abir) | 70-589044 | 3 | 1 |
|  |  | Mohamed khaled aloush(Hamda) | 70-251786 | 85 | 1 |
|  | Karsita | Jamal mohamed Gharib(Fatme) | 70-539067 | 64 | 1 |
|  |  | Ali ahmad hussein aloush | 03-603882 |  | 1 |
|  |  | Ahmad mohamed aloush(ghedwa) | 03-195821 | 85 | 1 |
| Caza | Village | Names | Telephone | Registration No | Qty |
| Donniyeh | Assafira | Amira essayed (ahmad mahmoud el yakhne) | 03-961581 |  | 1 |
|  |  | Saada khaled Harmouch | 70-014237 |  | 1 |
|  |  | Ahmad Melhem Melhem (fatiya) | 06-490298 |  | 1 |
|  |  | Jamila Daher (Mahmoud Daher) | 71-943407 |  | 1 |
|  | Ein eltine | Khaled ahmad khaled+mohamed ahmad khaled+naziha khaled+Joumana khaled | 06-260155 06-260175 |  | 1 |
|  |  | Hussein mehssen obeid (Aziza) | 76-502368 |  | 1 |
|  |  | Soad (Khodermahmoud obeid) |  | 8 | 1 |
|  |  | Zeina mehsen obeid |  |  | 1 |
|  | Taran | Mostafa hussein Kassem (Fatme) |  | 23 | 1 |
|  | betromaz | Mhamad Zantar(hanaa) | 71-745931 |  | 1 |
|  | Al- rawda | Zoulfikar seif eddine al ouweid (Amira) |  |  | 1 |
|  |  | ismail mostafa al ouweid |  |  |  |
|  |  | Naser Diab El ouweid |  |  | 1 |
|  |  | Saad Diab El ouweid |  |  |  |
|  | Kafarhabo | Mahmoud Fouad Mahmoud(Hawdi) | 03-275884 | 14 | 1 |
|  | Bakhoun | Ali ahmad el ahmad (Dalia) | 06-241031 | 898 | 1 |
|  | El kottein | Ahmad ibrahim ahmad (Naimeh) | 03-531916 | 40 | 1 |
|  | Dabaal | Aysha hassan Nasser | 03-615912 |  | 1 |
|  |  | Naser Abdul Kader Fares (Khadija) | 03-339541 |  | 1 |
|  |  | Ahmad Kamal din (kamila Chami) | 03-491429 | 12 | 1 |
| Caza | Village | Names | Telephone | Registration No | Qty |
| Donniyeh | Izzal | Ahmad hussein el maghshoush (Fatme) | 06-495036 |  | 1 |
|  |  | Mostafa hussein khaled (el maghshoush) |  |  |  |
|  |  | Mohamed Ahmad Abed el Aziz Ramadan (Fatme) |  |  | 1 |
|  |  | Ali Nadim Abed El aziz(Bariaa) |  |  | 1 |
|  |  | Mostafa Ali El maghshoush(Rahifa+ his sun Ali ) | 70-595302 | 23 | 1 |
|  |  | Mahmoud mhamad Amoun(shahida) | 70-382534 | 26 | 1 |
|  |  | Mahmoud hassan nadah(Dalla) |  | 78 | 1 |
|  |  | Halime Abd El-Hadi | 06-495128 |  | 1 |
|  |  | Ahmad Abed El Rahim Kamal eddine (Fatme) | 70-088736 |  | 1 |
|  |  | Nawaf mhamad Kamal eddine (Nahda) |  |  | 1 |
|  |  | Mostafa Ahmad Abed el Rahman(Samiha) |  |  | 1 |
|  | Ezki | Mostafa mahmoud el sherkawi | 03-766735 | 30 | 1 |
| Caza | Village | Names | Telephone | Registration No | Qty |
| Donniyeh | Bakarsona | Ahmad mhamad mouna | 70-146905 | 35 | 1 |
|  |  | Mahmoud Hassan nadah(Amina chawk) |  |  | 1 |
|  |  | Mhamad Mahmoud shawk (Terez) | 71-201940 | 102 | 1 |
|  |  | Nayef Abed el Hamid Moumen |  |  | 1 |
|  |  | Youssef Mahmoud Shawk |  |  | 1 |
|  |  | Ahmad mhamad Shandab(Salma Allam ) | 03-273890 | 20 | 1 |
|  | Harf el sayad | Naser Mostafa Hamdan | 06-240633 | 6 | 1 |
|  | El Hazmieh | Mariam Mostafa Eldirani | 70-667277 | 9 | 1 |
|  | Beit hawik | Fatme Khalil (Mohamad khoder Terekmani) | 03-184759 |  | 1 |
|  |  | Abed El Hamid Khoder Naser (Majida) | 03-196837 |  | 1 |
|  |  | Ali khoder Naser (Sououd) | 03-196837 |  | 1 |
|  |  | Ali Abed El Kader Fares | 03-395849 |  | 1 |
|  | Hawara | Fadia (Mohamad Terekmani) | 03-920494 |  | 1 |
|  |  | Fadia (Ahmad Terekmani) |  |  |  |
|  |  | Khadija (mostafa terekmani) | 03-739016 |  | 1 |
|  |  | Ali Ahmad Terekmani | 76-185775 |  |  |
| Caza | Village | Names | Telephone | Registration Nb | Qty |
| Donniyeh | Hawara | Ahmad khoder Khalil (Zeina) | 71-692365 |  | 1 |
|  |  | Soukayna(Ziad mhamad Terekmani | 70-155949 |  | 1 |
|  |  | Aysha Khalil Terekmani |  |  |  |
|  | Terbol | Najwa Jreish (Elias Jreish) | 03-411620 |  | 1 |
|  | Beit Dawood | Mahmoud Khoder Naddah (Halima) | 03-499437 |  | 1 |
| Sub Total Donniyeh | 73 |
| Menniyeh | Hay El Douhour | Mhamad Mostafa essayed ahmad (Sanaa) | 03-183242 | 2 | 1 |
|  | El menyi | Samer Ahmad Alam eddine | 70-296050 | 13 | 1 |
|  |  | Ammar Ahmad El kheir (Nada) | 70-427658 | 513 | 1 |
|  |  | Mhamad hussein Farasha | 06-462737 | 196 | 1 |
|  |  | Karam merae El Kassab (Layla) | 06-460023 | 83 | 1 |
|  | Lnabi kozeiber | Waleed Hassan El Beyrouti (Rana) | 03-737604 | 379 | 1 |
|  |  | Mostafa Mohamad Dandan (Maha) | 71-932988 | 383 | 1 |
| Sub Total Menniyeh | 7 |
| Caza | Village | Names | Telephone | Registration Nb | Qty |
| Baalbeck | Tofikiye | Nayef Kayed Bazzal | 70- 085 974 | 3 | 1 |
|  |  | Ali assaad Bazzal | 71- 409 262 | 1 | 1 |
|  |  | kasem assaad bazzal | 08- 233 253 | 2 | 1 |
|  |  | Ali Ahmad Bazzal | 08- 233 414 | 2 | 1 |
|  |  | Mhamad Ali bazzal | 76- 722 538 | 50 | 1 |
|  |  | Mehdi Ali kHayel | 03- 261 311 | 79/5 | 1 |
| Sub Total Baalbeck | 6 |
| Grand Total Distributed |
| Cazas | Qty |
| A | Zgherta | 6 |
| B | Batroun | 4 |
| C | El -Koura | 4 |
| D | Donniyeh | 73 |
| E | Menniyeh | 7 |
| F | Baalbeck | 6 |
| TOTAL | 100 |
| FINAL BALANCE |
| Quantity Received | 100 |
| Quantity Distributed | 100 |
| BALANCE | 0 |
| N.B: The Delivery Notice for each beneficiary with his phone number, ID card copy, ID number and his signature is available in LRF 26 dairy Project recording files at the FAO offices in Zahleh. |

| List of Project beneficiaries for 50 mini dairy processing units. |
| --- |
| P.O : 5 201 056 ORSO/LEB/201/UNJ - Dated 11 Avril 2013 |
| Quantity Received = 50 mini units |
| Caza | Village | Names | Telephone | Registration No | Qty |
| Zgharta | Ein Taroun | Domet Abd ahald (Katia Chhade) | 06-575103 |  | 1 |
|  | Alma | Rachid Addouj (Chahide) | 70-207847 | 3 | 1 |
|  |  | Mahmoud El-Masri | 71-583691 |  | 1 |
|  |  | Houriyyi Ahmad Erslan | 71-583691 |  |  |
| Sub Total Zgharta | 3 |
| Caza | Village | Names | Telephone | Registration No | Qty |
| Batroun | Beit Kassab | Jeanette Jerji | 06-770052 | 54 | 1 |
|  | Chbtin | Charbel Youssef Najem (Chadia) | 76-580007 | 50 | 1 |
|  | Niha | Youssef Khouri (Wasten) | 06-775432 |  | 1 |
|  | Sghar | Georges Matta (Roksan) | 03-390921 |  | 1 |
|  | Kfarhalda | Georges Saad (Alice Saba) | 03-345486 06-780070 |  | 1 |
|  | Zan | Antoine Hanna (Rita) | 03-096491 |  | 1 |
|  | Douma | SALIME Chalhoub (Elie Chalhoub ) | 06-520225 |  | 1 |
| Sub Total batroun | 7 |
| Caza | Village | Names | Telephone | Registration No | Qty |
| Bcharri | Hasroun | Marie Therese Mereib (Georges) | 06-591219 |  | 1 |
|  | Hadchit | Rita Hatchiti (Marcelle) | 70-401636 06-645245 |  | 1 |
|  | Bekaa Kafra | Nissrine Barrak (Charbel Nakad) | 70-120568 | 96 | 1 |
| Sub Total bcharri | 3 |
| Caza | Village | Names | Telephone | Registration No | Qty |
| Koura | kfarHazir | Hanaa Mkhayel (khalil) |  |  | 1 |
|  | Khan Bziza | Rafqa Sekkar | 71-432 046 |  | 1 |
|  | Bsarma | Toni Botros Hanna | 71-630278 |  | 1 |
| Sub Total koura | 3 |
| Caza | Village | Names | Telephone | Registration No | Qty |
| Donniyeh | beit alfakes | Sabah Ahmad Hamad | 03-484523 | 3 | 1 |
|  |  | Khadije Mhamad Dib + Khadiji Hassoun | 03-821518 |  | 1 |
|  |  | Hayat +Ali ahmad Yehiya | 03-405839 |  | 1 |
|  |  | Emna + ahmad hamad Yehiya |  |  | 1 |
|  |  | Salime Ahmad Dib (abd Aziz Dib) | 70-252781 | 25 | 1 |
|  |  | Nada Mhamad Omar (Abd Ghafour Dib) | 70-252781 | 25 |  |
|  |  | Roukayya Khoder Hassoum | 71-459335 | 25 |  |
|  |  | Mhamad Awada (Khadiji) | 70-713826 |  | 1 |
|  | Nemrin | Emna Hammoud (Khoder) | 06-491161 |  | 1 |
|  | karsita | Fattoum Hajj (Mhamad EL-Hajj) | 71-325175 | 84 | 1 |
|  |  | Hatem Zein Din | 03-281644 | 51 | 1 |
|  | Safira | Hoda Hassoun (Mostafa Hassoun) | 03-768717 |  | 1 |
| Donniyeh | Ein Tini | Jouma &Naziha Khaled (Ahmad khaled) | 06-260155 06-260175 |  | 1 |
|  | Taran | Sanaa Trad (Mhamad Trad) | 70-793195 |  | 1 |
|  |  | Emna Handouch (Mhamad Handouch) | 06-490519 | 33 | 1 |
|  | Kfarbanin | Assia Sayed (Khoder Sayyed) | 70-260905 |  | 1 |
|  | Debael | Aicha Ahmad Nasser | 03-615912 |  | 1 |
|  |  | Khadija Fares (nasser Fares) | 03-339541 |  | 1 |
|  | Izzal | Fatme Maghchouch (Ahmad Maghchouch) | 06-495036 |  | 1 |
|  |  | Noura Maghchouch (mostafa Maghchouch) |  |  |  |
|  |  | Fatme Youssef (Mahmoud Youssef) | 71-988550 |  | 1 |
|  |  | Baria Abd Rehmen (Ali Abd Rehmen) | 71-758398 |  | 1 |
|  |  | Halime Maghchouch (mostafa Maghchouch) | 06-495133 | 9 | 1 |
|  |  | Rahife Maghchouch | 70-595302 | 23 | 1 |
|  |  | Maha Maghchouch (Mostafa Maghchouch) | 06-495093 |  | 1 |
|  |  | Joumana Khaled Yassin | 71-648366 |  | 1 |
|  |  | Nawaf + Nahda Kamal Din |  |  | 1 |
| Donniyeh | Bkarsouna | Dam el-Hana Chowk (Khoder chowk) | 03-129374 |  | 1 |
|  | Berit Haweek | Majida Nasser (Abd El-hamid Nasser) | 03-196837 |  | 1 |
|  | Houwara | Fadia Terkamni (Ahmad Terkmeni) | 03-920494 |  | 1 |
|  |  | Fadia Terkamni (MostafaTerkmeni) |  |  |  |
|  |  | Khadija Terkmene | 03-739016 |  | 1 |
|  |  | Ali Ahmasd Terkman | 76-185775 |  |  |
|  |  | Soukayna Terkmene (Mother of ziad Terkmani) | 70-155949 |  | 1 |
|  |  | Aicha khalil Terkmene |  |  |  |
|  | Deir Nbouh | Fatme Ahmad Mhamad | 03-835866 | 12 | 1 |
| sub total of DONNIYEH | 30 |
| Menniyi | Nabi Youchaa | Awsaf El-Masri (Ali Masri) | 06-462602 | 100 | 1 |
|  | Mennyi | Layla Kassab (son : Karam Kassab) | 06-460023 | 83 | 1 |
| sub total of menniyeh | 2 |
| Caza | Village | Names | Telephone | Registration No | Qty |
| Akkar | Halba | Fadi Mhamad el-Halabi |  |  | 1 |
|  | Halba | Halba Coop |  |  | 1 |
| sub total of Akkar | 2 |
| Grand Total Distributed |
| Cazas | Qty |
| A | Zgharta | 3 |
| B | Batroun | 7 |
| C | Bcharri | 3 |
| D | Kourra | 3 |
| E | Donniyi | 30 |
| F | Menniyi | 2 |
| j | Akkar | 2 |
| Total | 50 |
| FINAL BALANCE |
| Quantity Received | 50 |
| Quantity Distributed | 50 |
| Balance | 0 |
| List of Project beneficiaries from the Distribution Of 15 Additional MINI dairy Units |
| P.O : 5 201 103 ORSO/LEB/201/UNJ - Dated 7 August 2013 |
| Quantity Received : 15 additional MINI dairy units |
| Caza | Village | Coops | Names | Telephone |
| Akkar | Fnaydek | Fnaydek | Fatme Ahmad Zakhia | 03- 342 916 |
|  | Fnaydek | fnaydek for fabrication of animal and vegetal production | Fadwa Rachid Zahramen | 03- 125 584 |
|  | Fnaydek | Union Municipality of Jerd Kaytae | Rana EL-Sayed | 03- 531 489 |
| Donniyeh | bkarsouna | N.A. | mazhar rachid chawk | 03- 433 073 |
| Batroun | Bchaele | N.A. | Therese Romaniyos | 76- 079782 |
| Baalbak | Bdnayel | N.A. | Ibrahim Sleiman | 76-030329 |
| Aley | Bhamdoun | N.A. | Nada jerji Kheir Alla | 03-708 981 |
| donniyeh | beit el fakes | N.A. | Jamil Dib | 70-252 781 |
| Batroun | Bjerdefil | N.A. | Vergeni Salam | 03-836 805 |
| Baalbak | Nabi chit | baalbak | Sawsan melhem Abd Sater | 70-710665 |
| Baalbak | Charawni | baalbak | Iman Askar | 70- 506 343 |
| Baalbak | baalbak | baalbak | Hala Mahmoud Soleh | 71- 398 209 |
| Baalbak | Tarayya | Tarayya | Fatme Hamiye | 70- 912 164 |
| Akkar | Halba | Halba Coop | Hajj Baker Naim | 03- 436 392 |
| Akkar | Halba | Halba Coop | Hajj Baker Naim | 03- 436 392 |
| FINAL Balance |
| Quantity Received | 15 |
| Quantity Distributed | 15 |
| Total Stock of additional MINI Dairy | 0 |
| N.B: The Delivery Notice for each beneficiary with his phone number, ID card copy, ID number and his signature is available in LRF 26 dairy Project recording files at the FAO offices in Zahleh. |

Milk Cans distribution

| List of Project beneficiaries from 2000 milk cans and 3000 milk filters (procedure under Dairy Project - LRF 26) |
| --- |
| P.O. = 5201031 – Dated 10 April 2013 |
| Quantity Received: 1000 Milk Cans 20 L. 1000 Milk Cans 40 L. 3000 Plastic Food Grade Milk Filters |
| Caza | COOP | Center | The recipient | QTY of 40 liters can | QTY of 20 liters Can | QTY Filters | Nb of farmers |
| Central Bekaa | Zahleh | Dalhamiye | Nawwar Hamdi Ibrahim | 25 | X | 50 | 25 |
|  |  | Jalala | Mamdouh and Ali El Radi | 20 | X | 50 | 20 |
|  |  | Khalil Akl | Georges Sawaya | 1 | 1 | 2 | 1 |
|  |  | Karak | Rodwan Adnan Salhab | 25 | X | 70 | 25 |
|  | Nasriya | Nasriya | Hossein Tarshishi | 50 | X | 80 | 50 |
|  |  | Hosh El Nabi | Khaled El Tannousi | 30 | X | 45 | 30 |
|  | Kab Elias | Kab Elias | Mahmoud Kassem EL Mahmoud | 15 | X | 25 | 15 |
| Sub Total CENTRAL BEKAA | 166 | 1 | 322 | 166 |
| West Bekaa | Ghaza | Ghaza | Ibrahim El Majzoub | 50 | X | 60 | 50 |
|  |  | El Khyara | Hassan Ali Kerdi | 15 | X | 25 | 15 |
|  |  | Ghaza | Soaad Melhem Darwish | 2 | 2 | X | 4 |
|  |  | Ghaza | Moseada Abou hammin | 2 | 3 | X | 5 |
|  | Sawira | Sawira | Diab Janbein | 20 | X | 30 | 20 |
|  | Khirbet Kanafar | Mashghara | Hassan Bjeiji | 30 | X | 50 | 30 |
|  |  | Masabki | Bassam Hajjar | 30 | X | 40 | 30 |
|  | El Marej | Marej1 | Khoder Oweid El Asaad | 40 | X | 50 | 40 |
|  |  | Marej2 | Abed El hamid Abbas | 10 | X | 20 | 10 |
| Sub Total WEST BEKAA | 199 | 5 | 275 | 204 |
| Caza | COOP | Center | The recipient | QTY of 40 liters can | QTY of 20 liters Can | QTY Filters | Nb of farmers |
| Baalbek | Bazaliya | Labwa | Abbas Mashhour Abdo | 30 | X | 150 | 30 |
|  | Bazaliya | Labwa 2 | Bilal Rabah | 20 | X | 40 | 20 |
|  | Bazaliya | Bazaliya | Ali Kassem Bazal | 20 | X | 150 | 20 |
|  | Hosh El Nabi | Bednayel | Khalil Abaas Haydar | 5 | X | 3 | 5 |
|  | Shlifa | shlifa | Rabih Botros Rahme | 10 | X | 25 | 10 |
|  |  | shlifa | Dani and Elham Jaajaa | 5 | 5 | 3 | 2 |
|  | Baalbek | baalbek | Omar El Zokra | 30 | X | 160 | 30 |
|  | Mashariea El Kaa | Mashariea El Kaa | Shehade Abou Fares | 40 | 20 | 80 | 60 |
|  |  |  | Mohamad Hassan Khalaf | 20 | 5 | 130 | 25 |
|  | AL Rida | Brital | Abbas Ali Mazloum | 5 | X | 5 | 5 |
|  | Baalbek | Bednayel | Mohamad Ajaj Akil | 2 | X | 1 | 2 |
| Sub Total BAALBECK | 187 | 30 | 747 | 209 |
| Hermel | Hosh El Sayed Ali | Hosh El Sayed Ali | Hassan Hamed Bazal | 30 | X | 150 | 30 |
| Sub Total HERMEL | 30 |  | 150 | 30 |
| Rashaya | Kherbet Roha | Rfeid | Sawsan Faraj Osman | 4 | X | 4 | 4 |
|  | Kfarmechki | Kfarmeshki | Rola El Ferkh Saaid | 20 | X | 35 | 20 |
|  |  | Lebbaya | Mohamad Ali Khatib | 1 | X | 1 | 1 |
| Sub Total RASHAYA | 25 |  | 40 | 25 |
| Caza | COOP | Village | The recipient | QTY of 40 liters can | QTY of 20 liters Can | QTY Filters | No. of farmers |
| Baalbeck | Baalbeck | Nayef Kayed Bazzal | 1 |  | 2 |  |
|  |  | Ali assaad Bazzal | 1 |  | 2 |  |
|  |  | kasem assaad bazzal | 1 |  | 2 |  |
|  |  | Ali Ahmad Bazzal | 1 |  | 2 |  |
|  |  | Mhamad Ali bazzal | 1 |  | 2 |  |
|  |  | Mehdi Ali kHayel | 1 |  | 2 |  |
| GRAND TOTAL distributed in BEKAA : | 613 | 36 | 1546 | 635 |
| Caza | COOP | Village | The recipient | QTY of 40 liters can | QTY of 20 liters Can | QTY Filters | No. of farmers |
| AKKAR | Jouma COOP and its environs | Beino | Pascal Kafrouni | 3 | 3 | 6 | 6 |
|  |  |  | Georgette Kafrouni | 2 | 2 | 5 | 4 |
|  |  |  | Jamil Dib | 1 | 1 | 2 | 2 |
|  |  |  | Pascal Kafrouni | 20 | 20 | 40 | 40 |
|  |  |  | Mahmoud Mostafa Mahmoud | 15 | 15 | 30 | 30 |
|  |  | Borej | Khaled Yassin | 1 | 2 | 3 | 3 |
|  |  | Dawra | Mahmoud El Ghani | 2 | 2 | 5 | 4 |
|  |  | Rahba | Mounir Khouri | 2 | 2 | 5 | 4 |
|  |  | Ilat | Hanna Jdid Hanna | 9 | 9 | 20 | 18 |
|  | Halba COOP and its environs | Mshha | Akram Shaaban | 15 | 15 | 30 | 30 |
|  |  | Arka | Youssef Ahmad Taleb | 12 | 12 | 30 | 24 |
|  |  | Halba | Hajj Baker Naim | 23 | 23 | 50 | 46 |
|  |  |  | Salem Ahmad Salem | 15 | 15 | 40 | 30 |
|  | Kobayat COOP and its environs | Kobayat | Joseph Daher | 25 | 4 | 80 | 29 |
|  |  |  | Hosam El Asaad | 50 | 50 | 125 | 100 |
|  |  |  | Mohamad Khoder | 10 | 30 | 40 | 40 |
|  |  |  | Talal El Hosni | 10 | 10 | 20 | 20 |
|  |  | Rmah | Joseph Abdallah | 10 | 10 | 20 | 20 |
|  | Dreib COOP | Dreib | Joseph Botros Abdallah | 25 | 25 | 70 | 50 |
| TOTAL distributed in AKKAR : | 250 | 250 | 621 | 500 |
| Caza | Village | Names | Telephone | Registration No | QTY of 40 liters can | QTY of 20 liters Can | QTY Filters |
| Zgharta | Zgharta | Elie Salim Mouawad | 03-133633 |  | 2 | 5 | 3 |
|  |  | Youssef Gerious Batour | 70-233317 | 153 |  | 2 | 1 |
|  | Kfardlakos | Botrous Youssef Feniyenos | 03-268926 | 288 |  | 2 | 1 |
|  |  | Antoine Feniyenous |  |  | 2 | 2 | 2 |
|  |  | Nadim Maroun Mjalleh | 06-665734 |  | 2 | 2 | 2 |
|  |  | Mansour El beyea | Milk Dealer |  | 5 | 5 | 10 |
|  |  | Bachir Sarkis Naoum | 70-509992 71-509999 |  | 2 | 2 | 2 |
|  |  | Anwar Hares Franjiye | 03-471962 |  | 2 | 2 | 3 |
|  |  | Wadad Bachir Naoum | 06-667403 |  |  | 4 | 2 |
|  | Iael | Mounif Ayoub | 03-960404 |  | 2 | 2 | 2 |
|  | Karem Saddeh | Monstry St Jacob | 06-595425 |  | 2 | 2 | 2 |
|  | Ein Taroun | Doumit Abd El Ahad | 06-575103 |  |  | 4 | 2 |
| Caza | Village | Names | Telephone | Registration No | QTY of 40 liters can | QTY of 20 liters Can | QTY Filters |
| Zgharta | Alma | Fawzi Chheb Abdalla | 70-442578 |  |  | 2 | 1 |
|  |  | abdala Kaysar Wehbi (Naziha Youssef) | 06-685186 |  | 2 |  | 1 |
|  |  | Bilal Ahmad Erslan | 71-583691 |  |  | 2 | 1 |
|  |  | Mahmoud Mhamad El-Masri | 71-583691 |  |  | 5 | 3 |
|  |  | Houriyye Erslen | 71-583691 |  |  |  |  |
|  | Meryata | Taha Ali obayd | 71-934090 | 13 |  | 2 | 1 |
|  |  | Mhamad Ali Zreik | 70-355219 | 7 | 2 | 2 | 2 |
|  |  | Tarek Mahmoud Asaad | 71-969791 |  |  | 3 | 2 |
|  | Fouar | Abd Aziz Houayek | 71-063226 | 34 |  | 2 | 1 |
|  | Darayya | Toni Khosse El alam | 03-453894 | 84 | 4 | 8 | 15 |
|  | Bchennin | Leiba Fadel | 70-473406 |  |  | 2 | 1 |
| Sub Total ZGHARTA : | 27 | 62 | 60 |
| Caza | Village | Names | Telephone | Registration No | QTY of 40 liters can | QTY of 20 liters Can | QTY Filters |
| Batroun | Bchaele | therese romaniyos | 76-079782 | 96 |  | 2 | 2 |
|  | Mhermech | Najib Elias Attiyeh |  |  |  | 5 | 2 |
|  | Beit kassab | Jeanette Elias Jerji | 06-770052 | 54 |  | 3 | 2 |
|  | Chebtin | charbel Youssef Najm (Chadia) | 76-580007 | 50 | 1 | 5 | 3 |
|  | Niha | Youssef Atiyeh (Wasten) | 06-775432 |  | 3 |  | 2 |
|  | Sghar | Georges Nadim Matta | 03-390921 |  |  | 5 | 2 |
|  | Ebrin | Mariam Chahine | 03-625311 | 23 | 3 | 2 | 2 |
|  | Hadchit | Marcelle Hadchiti | 70-401636 06-645245 |  | 2 |  | 2 |
|  | Kfarhalda | Georges hanna saad | 03-345486 06-780070 |  | 2 | 3 | 2 |
|  | Kfarhayy | Charbel Rizk | 03-646273 |  |  | 5 | 4 |
|  | kfarhatna | Dani Tanios | 03-004184 |  | 1 | 3 | 2 |
|  | Zan | Antoine Hanna Hanna | 03-096491 |  | 1 | 3 | 1 |
|  | Douma | Elie Youssef Chalhoub | 06-520225 |  | 2 | 2 | 2 |
|  | Kesrwen (mont Liban) | Joseph Najem |  |  |  | 4 | 2 |
|  | Bjerdarfil | Vegeni Salam | 03- 836 805 | 15 |  |  | 3 |
|  | Bhamdoun (Aley) | Nada kheiralla | 03- 708 981 | 38 |  | 2 | 2 |
| Sub Total BATROUN: | 15 | 44 | 35 |
| Caza | Village | Names | Telephone | Registration No | QTY of 40 liters can | QTY of 20 liters Can | QTY Filters |
| Bcharri | Hasroun | Georges Meraeb | 06-591219 |  | 2 |  | 2 |
|  | Bekaa Kafra | Charbel Nakad | 70-120568 | 96 | 2 | 3 | 2 |
| Sub Total BCHARRI : | 4 | 3 | 4 |
| Caza | Village | Names | Telephone | Registration No | QTY of 40 liters can | QTY of 20 liters Can | QTY Filters |
| Koura | Kfarhazir | Khalil Mkhayel |  |  |  | 2 | 1 |
|  | bterram | Elie Andraous | 03-436493 |  |  | 2 | 1 |
|  |  | Salim Dib Sleiman |  |  |  | 2 | 1 |
|  | Bchmezzin | Ibrahim Said Makhlouta | 70-163882 | 173 | 5 | 6 | 15 |
|  | Kosba | Nicolas Zeidan | 71-834114 |  | 10 | 0 | 15 |
| Caza | Village | Names | Telephone | Registration No | QTY of 40 liters can | QTY of 20 liters Can | QTY Filters |
| Koura | Metrit | Yaakoub Tedros | 06-952431 |  |  | 2 | 1 |
|  | Bsarma | Toni Hanna Botrous | 71-630278 |  |  | 2 | 2 |
|  | Habbouch | Miled Jabbour (Hiyam) | 06-950205 |  |  | 3 | 2 |
|  |  | Elias Tawk (Odette) | 06-950205 |  |  | 3 | 2 |
|  |  | Hanna el Alam |  |  |  | 2 | 1 |
|  |  | Youssef Loulou Tawk | 70-578649 |  |  | 3 | 2 |
|  | Kfarkahol | Nicolas Elias Semaan | 03-532647 | 9 |  | 3 | 2 |
|  | Al-Majdel | Moussa Chalouhi (Georgina Alam) | 70-834011 | 18 |  | 4 | 2 |
| Sub Total AL KOURA: | 15 | 34 | 47 |
| Caza | Village | Names | Telephone | Registration No | QTY of 40 liters can | QTY of 20 liters Can | QTY Filters |
| Doniyeh | Assafira | Amira Essayed (ahmad mahmoud el yakhne) | 03-961581 |  |  | 2 | 1 |
|  |  | Ahmad El Yakhani | 03-961581 |  |  | 2 | 1 |
|  |  | Ali Mostafa el Yakhani | 70-560411 |  | 2 | 10 | 12 |
|  |  | Saada khaled Harmouch | 70-014237 |  |  | 2 | 1 |
|  |  | Hoda Hassoun | 03-768717 |  |  | 10 | 10 |
|  |  | Ahmad Melhem Melhem (fatiya) | 06-490298 |  |  | 4 | 2 |
|  |  | Jamila Daher (Mahmoud Daher) | 71-943407 |  |  | 2 | 1 |
|  |  | Maha El Yakhani |  |  |  | 25 | 30 |
|  |  | Waddah Harmouch |  |  |  | 10 | 10 |
| Donniyeh | Beit Al Fakes | Sabah Ahmad Hamad | 03-484523 | 3 |  | 2 | 1 |
|  |  | Amine Ahmad Erslan | 03-484523 | 3 |  | 2 | 1 |
|  |  | Ali Mhamad Yehiya (Hend Yehiya) | 03-790157 | 22 |  | 2 | 1 |
|  |  | Khadija Mahmoud Dib+Khadija Khoder Hassoun | 03-821518 |  |  | 2 | 1 |
|  |  | Hayat Ahamd Yehiya | 03-405839 |  |  | 2 | 1 |
|  |  | Emna + Ahmad Hamad Yehiya |  |  |  | 2 | 1 |
|  |  | Chafic Mhamad Yehiya | 70-565747 | 44 |  | 2 | 1 |
|  |  | Ayman Abd Malak Hajj | 70-186344 | 44 |  | 4 | 2 |
|  |  | Abed el ghafar abed lmalak lhaj (ramia) |  | 44 |  | 2 | 1 |
|  |  | Mhamad Abd El Kader | 70-240108 |  |  | 2 | 1 |
|  |  | Imane ahmad dib | 70-252781 |  |  | 2 | 1 |
|  |  | Salima Ahmad Dib(abed el aziz) | 70-252781 | 25 |  | 3 | 2 |
|  |  | Nada mohamed Omar (abed el ghafour) | 70-252781 | 25 |  | 3 | 2 |
|  |  | Rokiya khoder Hassoun | 71-459335 | 25 |  | 3 | 2 |
|  |  | Mhamad Ahmad Osman | 03-915773 | 30 |  | 2 | 1 |
|  |  | Adnan Ahmad Ismail | 70-140486 | 1000 |  | 2 | 1 |
|  |  | Mhamad Hussein awada | 70-713826 |  |  | 2 | 1 |
|  |  | Mhamad Ahmad abd El kader | 71-053650 | 6 |  | 2 | 1 |
| Caza | Village | Names | Telephone | Registration No | QTY of 40 liters can | QTY of 20 liters Can | QTY Filters |
| Donniyeh | Nemrin | Samira Mahmoud Obeid (Mehdi Hassan Merei) | 71-909188 | 79 |  | 2 | 1 |
|  | Bakarsona | Mezher rachid chawk | 03- 433 075 | 51 |  | 10 | 5 |
|  |  | hussein ali chandab | 03-079563 | 20 |  | 3 | 2 |
|  |  | mhamad ali chandab | 70-571219 | 20 |  | 3 | 2 |
|  |  | ali mhamad chawk | 03- 433073 | 95 |  | 2 | 2 |
|  |  | mhamad hussein chandab | 70-032022 | 8 |  | 3 | 2 |
|  |  | Ahmad mhamad mouna | 70-146905 | 35 |  | 2 | 1 |
|  |  | Mahmoud Hassan chawk |  |  |  | 2 | 1 |
|  |  | Mhamad Mahmoud shawk (Terez) | 71-201940 | 102 |  | 3 | 2 |
|  |  | Nayef Abed el Hamid Moumen |  |  |  | 4 | 2 |
|  |  | khoder said chawk (Dam el hana) | 03-129374 |  |  | 3 | 2 |
|  |  | Youssef Mahmoud Shawk |  |  |  | 3 | 2 |
|  |  | Ahmad mhamad Shandab(Salma Allam ) | 03-273890 | 20 |  | 2 | 1 |
|  |  | hassan mhamad chandab | 76-045183 |  |  | 2 | 1 |
|  |  | Ali Chandab (PILOT) | 70-571219 |  |  | 1 | 1 |
|  | Assoun | Mhamad Mostafa Abou Zeid | 06-490918 |  |  | 2 | 1 |
|  |  | Khoder &Abd El hamid Hammoud | 06-491161 |  |  | 4 | 2 |
|  |  | Khaled& Ahmad Diab | 70-376219 |  |  | 4 | 2 |
|  |  | Hussein Mhamad Cheikh | 03-368093 |  |  | 2 | 1 |
|  |  | Ali mohamed hussein el sheikh(Salima) | 03-368093 | 49 |  | 3 | 2 |
|  |  | Omar mohamed kanj | 03-430561 | 20 |  | 3 | 2 |
| Donniyeh | Karsita | Fatme hamad el hayek | 71-864074 | 13 |  | 1 | 1 |
|  |  | Khaled Mhamad Hayek | 70-569152 | 55 |  | 3 | 2 |
|  |  | Fattoum (mohamed zeinedine el hajj) ) | 71-325175 | 84 | 2 | 20 | 22 |
|  |  | Mohamed mahmoud el hayek (Abir) | 70-589044 | 3 |  | 2 | 1 |
|  |  | Ahmad Radwan |  |  |  | 2 | 1 |
|  |  | Mariam ahmad hussein issa | 76-002015 | 13 |  | 2 | 1 |
|  |  | Mhamad Ahmad Znoub | 03-902723 | 122 |  | 2 | 1 |
|  |  | Hatem Zein Din (milk dealer) | 03-281644 | 51 | 2 | 15 | 7 |
|  |  | Ahmad Mostafa Kaddour | 03-944525 | 3 |  | 2 | 1 |
|  |  | Mohamed khaled aloush(Hamda) | 70-251786 | 85 |  | 2 | 1 |
|  |  | Mhamad Hussein Kaddour | 70-271217 | 3 |  | 2 | 1 |
|  |  | Jamal mohamed Gharib(Fatme) | 70-539067 | 64 |  | 2 | 1 |
|  |  | Bandar Hussein Agha | 03-931643 |  | 0 | 20 | 25 |
| Caza | Village | Names | Telephone | Registration No | QTY of 40 liters can | QTY of 20 liters Can | QTY Filters |
| Donniyeh | Karsita | Ali ahmad hussein aloush | 03-603882 |  |  | 10 | 10 |
|  |  | Ali Mhamad Issa (milk dealer) | 03-085597 | 37 | 0 | 35 | 22 |
|  |  | Ahmad mohamed aloush(ghedwa) | 03-195821 | 85 |  | 2 | 1 |
|  |  | Khaled Rachid Alwan (Diba) | 70-569152 | 55 |  | 3 | 2 |
|  | Ein EL-Tini | mhamad &khaled Ahmad Khaled | 06-260155 06-260175 |  |  | 8 | 4 |
|  |  | Hussein mehssen obeid (Aziza) | 76-502368 |  |  | 2 | 1 |
|  |  | Soad (Khoder mahmoud obeid) |  | 8 |  | 2 | 1 |
|  |  | Zeina mehsen obeid | 70-415378 |  |  | 2 | 1 |
|  | Taran | Mhamad trad | 03-512487 | 11 |  | 2 | 1 |
|  |  | Mostafa hussein Kassem (Fatme) | 71-843726 | 23 |  | 2 | 1 |
|  |  | Mhamad Rachid Trad | 70-793195 |  |  | 3 | 2 |
|  |  | Mhamad Handouch | 06-490519 | 33 |  | 3 | 2 |
| Donniyeh | Btermez | Bandar Hussein El Agha | 71-745931 |  |  | 2 | 1 |
|  | Al- rawda | Zoulfikar seif eddine al ouweid (Amira) | 70-341931 |  |  | 2 | 1 |
|  |  | ismail mostafa al ouweid |  |  |  | 2 | 1 |
|  |  | Naser Diab El ouweid | 76-113098 |  |  | 2 | 1 |
|  |  | Saad Diab El ouweid |  |  |  | 3 | 2 |
|  | Kfarhabou | Mahmoud Fouad Mahmoud(Hawdi) | 03-275884 | 14 | 3 | 2 | 2 |
|  |  | carlos ibrahim Mekdsi | 70-154151 | 32 | 2 | 2 | 2 |
|  | Kfar Banin | khoder mhamad El sayed | 70-260905 |  |  | 3 | 2 |
|  |  | Abd el hay hussein Saade | 71-868840 |  |  | 2 | 1 |
|  | Bekaa Safrein | moatasam Mahmoud Kanj | 03-175062 | 53 |  | 2 | 1 |
|  | Kafarhabo | Ali ahmad el ahmad (Dalia) | 06-241031 | 898 |  | 4 | 2 |
|  | Mrah Sraj | Samir Hussein Mereai | 70-706121 | 41/27 |  | 3 | 2 |
|  |  | Ahmad ibrahim (Kamila) | 03-531916 | 40 |  | 3 | 2 |
|  | Dabaal | Aysha hassan Nasser | 03-615912 |  |  | 4 | 2 |
|  |  | Naser Abdul Kader Fares (Khadija) | 03-339541 |  |  | 6 | 3 |
|  | El kottein | Ezz el Din Chafchk | 70-570907 | 36 |  | 2 | 1 |
|  | El kottein | Ahmad Kamal din (Naima) | 03-491429 | 12 |  | 3 | 2 |
| Donniyeh | Harf el sayad | Naser Mostafa Hamdan | 06-240633 | 6 |  | 2 | 1 |
|  | beit zoud | mhamad machhour Zoud | 71-067338 | 60 |  | 2 | 1 |
|  | El Hazmieh | Mariam Mostafa Eldirani | 70-667277 | 9 |  | 3 | 2 |
|  | Beit hawik | Fatme Khalil (Mohamad khoder Terekmani) | 03-184759 |  |  | 2 | 1 |
|  |  | Abed El Hamid Khoder Naser (Majida) | 03-196837 |  |  | 3 | 2 |
|  |  | Ali khoder Naser (Sououd) | 03-196837 |  |  | 2 | 1 |
|  |  | Ali Abed El Kader Fares | 03-395849 |  |  | 2 | 1 |
| Caza | Village | Names | Telephone | Registration No | QTY of 40 liters can | QTY of 20 liters Can | QTY Filters |
| Donniyeh | Izzal | Aicha Abd rehman |  |  |  | 2 | 1 |
|  |  | Mahmoud kassem Maghchouch | 70-852074 |  |  | 2 | 1 |
|  |  | ahmad hussein Maghchouch | 06-495036 |  |  | 4 | 4 |
|  |  | Mostafa Hussein Maghchouch |  |  |  |  |  |
|  |  | Mostafa Abed El Rahim Kamal eddine (Fatme) |  |  |  | 1 | 1 |
|  |  | Mhamad Ahmad Youssef (Fatme | 71-988550 |  |  | 2 | 1 |
|  |  | mhamad Ahmad Yassin | 70-546535 |  |  | 2 | 1 |
|  |  | mostafa hussein Khaled Maghchouch |  |  |  | 1 | 1 |
|  |  | mostafa Mhamad Abd Rehman | 70-328375 | 27 |  | 2 | 1 |
|  |  | Ali Khoder abd Rahman | 71-772896 |  |  | 2 | 1 |
|  |  | mhamad Ahmad Abd Rehman |  |  |  | 4 | 2 |
|  |  | Ali Nadim Abd Rehman | 71-758398 |  |  | 6 | 3 |
|  |  | Hssan Mahmoud Kamal din |  |  |  | 2 | 1 |
|  |  | mostafa Mhamad Maghchouch | 06-495133 | 9 |  | 3 | 2 |
|  |  | Mostafa Ali El maghshoush (Rahifa+ his son Ali ) | 70-595302 | 23 |  | 3 | 2 |
|  |  | Mahmoud mhamad Amoun(shahida) | 70-382534 | 26 |  | 3 | 2 |
|  |  | Mahmoud hassan nadah(Dalla) |  | 78 |  | 2 | 1 |
|  |  | Maha el Maghchouch | 06-495093 |  |  | 2 | 1 |
|  |  | halimi abd el hadi | 06-495128 |  |  | 2 | 1 |
|  |  | Ahmad Abed El Rahim Kamal eddine (Fatme) | 70-088736 |  |  | 2 | 1 |
|  |  | Joumana Ali Yassine | 71-648366 |  |  | 2 | 1 |
|  |  | hassan mhamad Maghchouch | 70-328375 |  |  | 2 | 1 |
|  |  | Abd Rahim Ali Maghchouch |  |  |  | 2 | 1 |
|  |  | Abdel latif Maghchouch |  |  |  | 2 | 1 |
|  |  | Nawaf mhamad Kamal eddine |  |  | 1 | 4 | 2 |
|  |  | hassan ali Radwan |  |  | 1 | 2 | 1 |
|  |  | Mostafa Ahmad AbdRahman(Samiha) |  |  | 1 | 2 | 1 |
| Donniyeh | Hawara | Fadia (Mohamad Terekmani) | 03-920494 |  | 1 | 2 | 1 |
|  |  | Fadia (Ahmad Terekmani) |  |  |  | 2 | 1 |
|  |  | Khadija (mostafa terekmani) | 03-739016 |  |  | 2 | 1 |
|  |  | Ali Ahmad Terekmani | 76-185775 |  |  | 2 | 1 |
|  |  | Ahmad khoder Khalil (Zeina) | 71-692365 |  |  | 2 | 1 |
|  |  | Soukayna(Ziad mhamad Terekmani | 70-155949 |  |  | 4 | 2 |
|  |  | Aysha Khalil Terekmani |  |  |  | 3 | 2 |
| Donniyeh | Terbol | Najwa Jreish (Elias Jreish) | 03-411620 |  |  | 3 | 2 |
|  | Deir Nbouh | fatme ahmad yassin | 03-835866 | 12 |  | 3 | 2 |
|  | Beit Dawood | Mahmoud Khoder Naddah (Halima) | 03-499437 |  |  | 2 | 1 |
|  | jerd el kaytaa | huussein alwan | 06-895033 |  |  | 10 |  |
|  | Ezki | Mostafa mahmoud el sherkawi | 03-766735 | 30 |  | 3 | 2 |
| Sub Total Donniyeh | 15 | 461 | 327 |
| Meniyeh | AL Nabi Youchaa | ali Ahmad El MASRI | 06-462602 | 100 |  | 3 | 2 |
|  |  | Said Mhamad El kalal | 03-144573 | 12 |  | 3 | 2 |
|  |  | Mostafa khoder Beker | 03-182430 | 135 |  | 2 | 1 |
|  |  | Abd El karim Omar Dhaybi | 06-463438 | 176 |  | 2 | 1 |
|  |  | Ahmad Abd RAHMAN Dhaybi | 70-582680 | 7 |  | 2 | 1 |
|  |  | Hassan Abd Sater Dhaybi | 06-461859 | 46 |  | 2 | 1 |
|  |  | Khaled Mhamd Dib Masri | 06-463005 | 106 |  | 2 | 1 |
|  |  | Omar Mhamad El kalal | 03-414624 |  |  | 2 | 1 |
|  | Bhannin | Marwan Mhamad Taha | 71-639498 | 32 |  | 2 | 1 |
|  | Hay El blat | Mostafa Khoder Beker | 76-171936 | 3 |  | 2 | 1 |
|  | Hay El Douhour | khoder Ali sayed Ahmad | 03-238462 | 22 |  | 3 | 2 |
|  |  | Mhamad Mostafa essayed ahmad (Sanaa) | 03-183242 | 2 |  | 2 | 1 |
|  | El menyi | Samer Ahmad Alam eddine | 70-296050 | 13 |  | 2 | 1 |
|  |  | Mahmoud Ghezzawi | 70-308295 | 366 |  | 2 | 1 |
|  |  | yehia mhamad Achrafi | 06-464173 | 90 |  | 4 | 2 |
|  |  | Ammar Ahmad El kheir (Nada) | 70-427658 | 513 |  | 2 | 1 |
|  |  | Mhamad hussein Farasha | 06-462737 | 196 |  | 2 | 1 |
|  |  | Karam merae El Kassab (Layla) | 06-460023 | 83 |  | 2 | 1 |
|  | Hay Hamdoun | Mostafa Said Malas | 06-464838 | 498 |  | 2 | 1 |
|  |  | Said Hussein Malas | 03-539665 | 498 |  | 2 | 1 |
|  |  | Khaled Refaet Matar | 03-937643 | 264 |  | 2 | 1 |
|  |  | Abd el Kader Srour | 03-227014 | 231 |  | 2 | 1 |
|  | Hay Jdidi | Zeinab Dandan | 70-097350 | 135 |  | 3 | 2 |
|  |  | Salem Ahmad el Kheir | 06-460720 | 508 |  | 3 | 2 |
|  | Hay el Heker | Hassan ahmad katiae | 06-461208 | 108 |  | 2 | 1 |
|  | Hay Farhat | Mhamad Zreika | 03-372391 | 207 |  | 2 | 1 |
|  | Trablos | Fayez Akra |  |  | 5 | 5 | 10 |
|  | Deir Omar | Abd El Hafiz Dhaybi | 06-430386 | 71 |  | 2 | 1 |
|  |  | Nabih Dhaybi | 70-512159 | 90 |  | 2 | 1 |
|  | Lnabi kozeiber | Waleed Hassan El Beyrouti (Rana) | 03-737604 | 379 |  | 3 | 2 |
|  |  | Mostafa Mohamad Dandan (Maha) | 71-932988 | 383 |  | 3 | 2 |
| Sub Total Menniyeh | 5 | 74 | 48 |
| Grand Total Distributed |
| Caza | COOP | Center | The recipient | QTY of 40 liters can | QTY of 20 liters Can | QTY Filters | No of farmers |
| Doniyeh Minyeh | N/A |  | 36 | 543 | 376 | 160 |
| Zgharta |  |  | 27 | 62 | 54 | 32 |
| Batroun |  |  | 15 | 44 | 35 | 52 |
| Bsharri |  |  | 4 | 3 | 2 | 3 |
| Koora |  |  | 15 | 34 | 47 | 12 |
| TOTAL distribution in NORTH: | 87 | 686 | 514 | 228 |
| South | Majdel Silm | Majdel Silm | Hajj Ali Sabra | 15 |  | 15 | 15 |
| TOTAL distribution in South : | 15 | X | 15 | 15 |
| Metn | Georges Shahid Khalil | Feitron | Meiroba | 8 | 7 | 20 | 8 |
| TOTAL distribution in Metn: | 8 | 7 | 20 | 8 |
| AKKAR | Hajj Bakr | COOP Halba | COOP Halba | 27 |  | 84 | 35 |
|  | Fadi El-halabi |  | COOP Halba |  | 21 | 200 | 100 |
| TOTAL distribution in Akkar: | 27 | 21 | 284 | 135 |
| Region | QTY of 40 liters can | QTY of 20 liters Can | QTY Filters | Nb of farmers |
| BEKAA | 613 | 36 | 1546 | 642 |
| AKKAR | 250 | 271 | 905 | 500 |
| NORTH | 114 | 686 | 514 | 363 |
| SOUTH | 15 |  | 15 | 15 |
| METN | 8 | 7 | 20 | 8 |
| GRAND TOTAL DISTRIBUTED | 1000 | 1000 | 3000 | 1528 |
| FINAL BALANCE | QTY of 40 liters can | QTY of 20 liters Can | QTY Filters |  |
| Quantity Received | 1000 | 1000 | 3000 |  |
| Quantity Distributed | 1000 | 1000 | 3000 |  |
| Balance | 0 | 0 | 0 |  |
| N.B: The Delivery Notice for each beneficiary with his phone number, ID card copy, ID number and his signature is available in LRF 26 dairy Project recording files at the FAO offices in Zahleh. |  |  |

| List of Project beneficiaries from 14 Medium Size (250 Kg) Dairy Units Distribution |
| --- |
| P.O. : 5201055 - DATED 11 APRIL 2013 : Qt received : Batch Pasteurizer = 10 , Working Table = 10, Labne Bag Hanger = 10, Cheese Press =15 |
| P.O. : 5201087 - DATED 14 August 2013 : Qt received : Batch Pasteurizer = 4 , Working Table = 4, Labne Bag Hanger = 4, Cheese Press =4 |
| Total Qt Received : Batch Pasteurizer =14 , Working Table =14, Labne Bag Hanger =14, Cheese Press =19 |
| Casa | COOP | Village | Name | Tel | Working Table | Batch Pasteurizer 250 L. | Labneh BagHanger | Cheese Press |
| Baalbak | Rawda | Britel | Abbas Ali Mazloum | 03-948319 | 1 | 1 | 1 | 1 |
| West Bekaa | Ghazza | Ghazza | Mesaede Majzoub | 70-311149 |  | 1 |  |  |
| Metn | al-Baladi | Faytroun | Gerious Chahid Khalil | 03-847849 | 1 |  |  |  |
| Rashaya | Kherbet Rouha | Rafid | Sawsan Faraj | 70/828627 |  |  |  | 1 |
| Baalbak | Chlifa | Deir Ahmar | Rabih Botrous Rahme | 70/862953 | 1 | 1 | 1 | 1 |
| Akkar | Jouma | Bayno | Georgette Kafrouni | 70/225341 |  |  |  | 1 |
| baalbak | Rasm Hdath | bazzaliya | Ali Bazzal | 03-170602 | 1 | 1 | 1 | 1 |
| Akkar | Kobayyat | Kweshra | Mhamad Khoder | 03-257879 | 1 |  | 1 | 1 |
| Donniyeh | N.A. | Karsita | Bandar Agha (Mahmoud Hayek) | 03-931643 | 1 | 1 | 1 | 1 |
|  |  |  | Fatme Issa (Ahmad Issa) | 03-085597 | 1 | 1 | 1 | 1 |
|  |  | Sfiri | Maha harmouch (Mahmoud Harmouch ) | 03-834029 | 1 | 1 | 1 | 1 |
|  |  |  | Wafaa Harmouch (Son: Rabih Harmouch) |  | 1 | 1 | 1 | 1 |
| Zgharta |  | Zgharta | Maria Mouauad ( Elie Mouawad) | 03-133633 | 1 | 1 | 1 | 1 |
|  |  | Darayya | Toni El-Alam | 03-453894 | 1 | 1 | 1 | 1 |
| Casa | COOP | Village | Name | Tel | Working Table | Batch Pasteurizer 250 L. | Labneh BagHanger | Cheese Press |
| Koura | N.A. | Bchmezzin | Jeanette Makhlouta (Ibrahim Makhlouta) | 70163882 | 1 | 1 | 1 | 1 |
| Batroun | N.A. | Beit Kassab | Jeanette elias Daoud | 70-473406 |  |  |  | 1 |
| Zahle | Zahle | Terbol | Georges Dib El 5ouri | 03-074330 | 1 | 1 |  | 1 |
| Baalbak | Baalbak | Ras Baalbak | Affaf Mhanna | 70- 494492 | 1 | 1 | 1 | 1 |
| Akkar | Kobayyat | Kobayyat | Antoinette Moussa | 03- 350219 |  |  |  | 1 |
|  | Fnaydek | Fnaydek | Fadwa Rachid Zahraman | 03- 125 584 |  |  |  | 1 |
|  | halba | jerd el kaytaa | Hussein abd el wahed alwan | 06-895 033 |  | 1 | 1 | 1 |
|  | Halba | Halba | Fadi mhamad el-Halabi |  |  |  | 1 |  |
| GRAND TOTAL distributed : |
| Quantity Received | 14 | 14 | 14 | 19 |
| Quantity Distributed | 14 | 14 | 14 | 19 |
| FINAL BALANCE | 0 | 0 | 0 | 0 |
| N.B: The Delivery Notice for each beneficiary with his phone number, ID card copy, ID number and his signature is available in LRF 26 dairy Project recording files at the FAO offices in Zahleh. |

| LIST of project beneficiaries from (6) reception TANKS DISTRIBUTED IN NORTH , AKKAR AND BEKAA (oct 2013) |
| --- |
| P.O No : 5 20 1 055 ORSO/LEB/201/UNJ -11 april 2013 Qt Received = 6 |
| CAZA | Village | Name Of Manager | Center | Mobile | COOPS | Qty |
| Donnieh | karsita | bandar Agha |  | 03-931643 | Not Available | 1 |
|  | Sfira | Maha el-Yakhani |  | 70/225341 |  | 1 |
|  |  | Ali Issa |  | 03-834029 |  | 1 |
| Akkar | Kobayyat | Hussam El Assaad | Kobayyat | 03-193808 | Kobayyat | 1 |
|  | Kweshra | Mhamad Khoder | Kweshra | 03-257897 | Kweshra | 1 |
|  | Bayno | Pascal Kafrouni |  | 70/225341 | Jouma | 1 |
| Grand Total Distributed |  |  |  |  |  |
| Quantity Received | 6 |  |  |  |  |  |
| Quantity Distributed | 6 |  |  |  |  |  |
| FINAL Balance | 0 |  |  |  |  |
| N.B: The Delivery Notice for each beneficiary with his phone number, ID card copy, ID number and his signature is available in LRF 26 dairy Project recording files at the FAO offices in Zahleh. |  |  |  |  |  |

| LIST OF Project beneficiaries from COOLING TANKS DISTRIBUTED IN NORTH , AKKAR AND BEKAA |
| --- |
| P.O No : 5 20 1 064 ORSO/LEB/201/UNJ - 2013 |
| Distribution of (5) milk Cooling TANKS 2000 Liters |
| CAZA | Village | Name Of Farmers | Center | Mobile | COOPS | QTY |
| 1 | Hermel | Hoch Sayed Ali | Hassan Bazzal | Hoch Sayed Ali | 03 - 730 540 | Hoch Sayed Ali | 1 |
| 2 | Baalbak | Baalbak | Omar Zekra | Baalbak | 03-412852 | Baalbak | 1 |
| 3 |  | Mchariae el Qaa | Mhamad Kromba | Mchariae el Qaa | 70-126139 | Mchariae el Qaa | 1 |
| 4 |  | Labwe 2 | Bilal Rbeh | Labwe 2 | 03-771655 | Bezzaliya | 1 |
| 5 | Zahle | Nassriye | Hussein Tarchichi | Nassriye | 03-817367 | Nassriye | 1 |
| FINAL BALANCE |  |
| Quantity Received | 5 |  |
| Quantity Distributed | 5 |  |
| Balance | 0 |  |
| N.B: The Delivery Notice for each beneficiary with his phone number, ID card copy, ID number and his signature is available in LRF 26 dairy Project recording files at the FAO offices in Zahleh. |

| LIST OF project beneficiaries from THE COOLING TANKS DISTRIBUTED IN NORTH , AKKAR AND BEKAA |  |
| --- | --- |
| P.O No : 5 20 1 064 ORSO/LEB/201/UNJ - 2013 |  |
| List of (5) Cooling TANKS 1000 Liters distributed |  |
| CAZA | Village | Name Of Manager | Center | Mobile | COOPS | QTY |
| Baalbeck | Tarayya | Fatme Hamiye | Tarayya | 70- 912 164 | Tarayya | 1 |
|  | Bezzaliyi | Ali Bazzal | rasm el-Hdath | 03-170602 | Rasm el-Hdath | 1 |
| Akkar | Wadi Khaled | Hussam Hussam | Wadi Khaled | 03-193808 | Kobayyat | 1 |
|  | al - korneh | nasser osman | al - korneh | 03-339691 | Jouma | 1 |
|  | Bayno | Pascal Kafrouni | bayno | 70-225341 | Jouma | 1 |
| FINAL BALANCE |  |  |  |  |  |
| Quantity Received | 5 |  |  |  |  |  |
| Quantity Distributed | 5 |  |  |  |  |  |
| Balance | 0 |  |  |  |  |  |
|  | N.B: The Delivery Notice for each beneficiary with his phone number, ID card copy, ID number and his signature is available in LRF 26 dairy Project recording files at the FAO offices in Zahleh. |

| LIST OF project beneficiaries from Milk reception TANKS DISTRIBUTED |  |
| --- | --- |
| P.O No : 5 20 1 064 ORSO/LEB/201/UNJ - 2013 Qt Received = 8 |  |
| List of distribution of (8) Milk Reception Tanks 250 Liters |  |
| CAZA | Village | Name Of Manager | Center | Mobile | COOPS | QTY |
| West Bekaa | Ghazza | Mesaede Majzoub | Ghazza | 70-311149 | Ghazza | 1 |
| Baalbak | tarayya | Fatme Hamiye | Tarayya | 70- 912 164 | Tarayya | 1 |
|  | Bezzaliyi | Ali Bazzal | rasm el-Hdath | 03-170602 | Rasm el-Hdath | 1 |
| Zahle | Nassriye | Hussein Tarchichi | Nassriye | 03-817367 | Nassriye | 1 |
| akkar | halba | hajj baker naim | halba | 03- 436 392 | halba | 1 |
|  | Al - korneh | nasser osman | al - korneh | 03-339691 | Jouma | 1 |
| West Bekaa | Marj | abd el hamid abbas | Marj |  | Marj | 1 |
|  | Machghara | Bassam hajjar | Machghara | 03-732632 | Kherbet kanafar | 1 |
| FINAL BALANCE |  |  |  |  |  |
| Quantity Received | 8 |  |  |  |  |  |
| Quantity Distributed | 8 |  |  |  |  |  |
| Balance | 0 |  |  |  |  |  |
| N.B: The Delivery Notice for each beneficiary with his phone number, ID card copy, ID number and his signature is available in LRF 26 dairy Project recording files at the FAO offices in Zahleh. |

| LIST OF project beneficiaries from THE MILK PUMP DISTRIBUTED IN NORTH , AKKAR AND BEKAA |  |
| --- | --- |
| P.O NO : 5 20 1 064 ORSO/LEB/201/UNJ - 2013 |  |
| Grand Total of 8 milk pumps distributed |  |
| CAZA | Village | Name Of Manager | Center | Mobile | COOPS | Qty |
| Donniyeh | Karsita | Ali Issa | Karsita | 03-085597 |  | 1 |
|  | Sfira | Maha Yakhani | Sfira | 03-834029 |  | 1 |
| Akkar | Kobayyat | Hussam El Assaad | Kobayyat | 03-193808 | Kobayyat | 1 |
|  | Kobbayat | Joseph Daher | Kobayyat | 70- 125362 | Kobayyat | 1 |
|  | Kweshra | Mhamad Khoder | Kweshra | 03-257897 | Kweshra | 1 |
| Baalbak | Bezzaliyi | Ali Bazzal | rasm el-Hdath | 03- 170602 | Rasm el-Hdath | 1 |
| Zahle | Nassriye | Hussein Tarchichi | Nassriye | 03-817367 | Nassriye | 1 |
| Baalbak | Tarayya | Fatme Hamiye | Tarayya | 70- 912 164 | Tarayya | 1 |
| FINAL BALANCE |  |  |  |  |
| Quantity Received | 8 |  |  |  |  |
| Quantity Distributed | 8 |  |  |  |  |
| Balance | 0 |  |  |  |
| N.B: The Delivery Notice for each beneficiary with his phone number, ID card copy, ID number and his signature is available in LRF 26 dairy Project recording files at the FAO offices in Zahleh. |

| LIST OF project beneficiaries from THE EKOMILK DISTRIBUTED IN NORTH , AKKAR AND BEKAA |
| --- |
| P.O.No : 5 201 083 - 5 july 2013 Qt received : 10 Units |
| List of Distribution of 10 Automatic Milk Analyzers " EKOMILK " |  |
| CAZA | Village | Name Of Manager | Center | Mobile | COOPS | No |
| 1 | Akkar | Kobayyat | Hussam El Assaad | Kobayyat | 03-193808 | Kobayyat | 1 |
| 2 |  | Kweshra | Mhamad Khoder | Kweshra | 03-257897 | Kobayyat | 1 |
| 3 |  | Wadi Khaled | Salem Salem | kobayyat |  | Kobayyat | 1 |
| 4 | Baalbak | Bezzaliyi | Ali Bazzal | Rasm el-Hdath | 03- 170602 | Rasm el-Hdath | 1 |
| 5 |  | Mchariae el Qaa | Chhade bou Fares | Mchariae el Qaa | 03- 116 134 | Mchariae el Qaa | 1 |
| 6 |  | Tarayya | Fatme Hamiye | Tarayya | 70- 912 164 | Tarayya | 1 |
| 7 | Zahle | Nassriye | Hussein Tarchichi | Nassriye | 03-817367 | Nassriye | 1 |
| 8 | Donniyeh | Karsita | Ali Issa | Karsita | 03-085597 | N.A. | 1 |
| 9 |  | Karsita | Bandar El Agha | Karsita | 03-931643 | N.A. | 1 |
| 10 |  | Sfira | Maha Yakhani | Sfira | 03-834029 | N.A. | 1 |
| FINAL BALANCE |  |  |  |  |  |
| Quantity Received | 10 |  |  |  |  |  |
| Quantity Distributed | 10 |  |  |
| Balance | 0 |  |  |
| N.B: The Delivery Notice for each beneficiary with his phone number, ID card copy, ID number and his signature is available in LRF 26 dairy Project recording files at the FAO offices in Zahleh. |  |

# Footnotes

FAO organized a meeting for problems associated with milk price disputes and solutions sought with participation of three ministries (see Annex 1)