Lebanon Recovery Fund

MPTF OFfice GENERIC ANNUAL programme NARRATIVE progress report

REPORTING PERIOD: 1 january – 31 December 2013

| Programme Title & Project Number |  | Country, Locality(s), Priority Area(s) / Strategic Results |
| --- | --- | --- |
| Programme Title: National Action Programme to Mainstream Climate Change into Lebanon’s Development Agenda (Climate Change Coordinating Unit – CCCU) Programme Number (if applicable) MPTF Office Project Reference Number: |  | (if applicable) Country/Region Lebanon |
|  |  | Priority area/ strategic results Governmental institutions/national coverage |
| Participating Organization(s) |  | Implementing Partners |
| Organizations that have received direct funding from the MPTF Office under this programme |  | Ministry of Environment Ministry of Finance National Council for the Environment |
| Programme/Project Cost (US$) |  | Programme Duration |
| Total approved budget as per project document: USD 500,000 MPTF /JP Contribution: by Agency (if applicable) |  |  | Overall Duration (months) | 24 months |
| Agency Contribution by Agency (if applicable) |  |  | Start Date (dd.mm.yyyy) | 15 March 2013 |
| Government Contribution (if applicable) |  |  | Original End Date (dd.mm.yyyy) | 31 March 2015 |
| Other Contributions (donors) (if applicable) |  |  | Current End date(dd.mm.yyyy) |  |
| TOTAL: |  |  |  |  |
| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| Assessment/Review - if applicable please attach Yes No Date: dd.mm.yyyy Mid-Term Evaluation Report – if applicable please attach Yes No Date: dd.mm.yyyy |  | Name: Vahakn Kabakian Title: Climate Change Portfolio Manager Participating Organization (Lead): Email address: vahakn@moe.gov.lb |

# NARRATIVE REPORT FORMAT

# Purpose

Project Summary and linkage to national priorities:

The project aims at mainstreaming climate change concepts into the different governmental development agendas by climate proofing the relevant plans and actions of the various ministries. The proposed project is in line with the Government of Lebanon’s plan of action, as mentioned in the first national communication report to the UNFCCC, and reiterated in the Second National Communication report to the UNFCCC.  Furthermore, the proposed project builds on the on-going renewable energy and energy efficiency objectives of the Ministry of Energy and Water and the Sustainable Energy Strategy project of the Ministry of Finance as well as Ministry of Agriculture’s adaptation efforts.  Overall, this project will work to meet the national priority of achieving the 12% renewable energy mix target by 2020 to move towards a Low Carbon/Emission Economy, as well as provide a directive for national adaptation activities leading to a national low emission climate resilient development strategies.

Project Outputs:

- Output 1: Engagement of ministries and governmental and national institutions in continuous planning/decision making on climate change issues

- Output 2: Identify and develop nationally appropriate mitigate actions (NAMAs) and pilot demonstration adaptation projects

- Output 3: Engagement of Lebanon in the international climate change arena and promoting new national and international climate financial mechanisms

Objectives

In order to improve climate change governance and meet the challenges that will face Lebanon as a result of climate change, there is a need to mainstream climate change concepts into national and sectoral development plans and to coordinate on-going climate change initiatives that are scattered. To achieve this, the proposed project presents a comprehensive coordination mechanism involving strategic planning, and close and effective communication with national, regional and international partners, as well as the recommendation of financial mechanisms needed at the national level.

With the recent Council of Ministers’ decision during its session dated March 28, 2012, the Decree (8157/2012) establishing the National Council for the Environment (NCE) has been enacted. The NCE is made of 14 members representing 7 ministries (the Ministry of Environment – Head of the NCE; and the ministries of Finance, Interior and Municipalities, Agriculture, Public Works and Transport, Energy and Water, and Industry) and 7 non-public entities (Order of Physicians, Order of Engineers and Architects, The Bar Association, Association of Banks, Association of Insurance Companies, representative of NGOs, representatives of the Academic sector).

Given the above, and knowing that proper climate change governance needs to build on on-going and planned national activities, the proposed project seeks to strategically align all national activities by coordinating and bringing them under the NCE. To achieve this, the proposed project aims to engage ministries and governmental institutions in planning and elaborating effective national adaptation (and pilot demonstration of adaptation technologies) and mitigation action plans (including NAMAs). The project will also address the institutional and legal barriers for the development of the national and international financial mechanisms and will improve the engagement of Lebanon in the international climate change arena.

# Results

- Narrative reporting on results:

- Project Management

- Preparation of regular progress reports and financial management of expenditures;

- Organization of stakeholder meetings (with regular meetings with the Ministry of Finance);

- Daily follow-up with project staff;

- Coordination with all national stakeholders and beneficiaries;

- Providing technical and policy advice to decision-makers on climate change negotiations and other climate related issues (primarily to MoE).

- Coordinate work with CEDRO project and Ministry of Finance and the Lebanese Center for Energy Conservation on clarifying Lebanon’s 12% renewable energy strategy.

Output 1: Engagement of ministries and governmental and national institutions in continuous planning/decision making on climate change issues

- This output involves the establishment of a network of climate change focal points among ministries, embedded in the NCE (as mandated by the NCE Decree 8157/2012) governmental, academic and private institutions to facilitate the interaction and coordination between the different actors involved in climate change issues.  This will lead to the establishment of the Government Group (GG) and the Research and Technical Support Group (RTSG).

Achievements:

Focal Points meetings under the CCCU:

The second meeting of the focal points of the Climate Change Coordination Unit (CCCU) was held on March 27th, 2014. The first session of the meeting, held for the newly appointed focal points, allowed the newcomers to get acquainted with the issues of climate change in general, its impacts in Lebanon, and the objective and structure of the CCCU and their respective TORs and roles. The second session of the meeting, gave an overview of the activities that the climate change team has undertaken and what is planned for the next quarter.

The third meeting of the focal points of the CCCU was held on November 14th, 2014 (see Annex 1 for list of participants and photos). The first session of the meeting,  summarized the main activities of the CCCU at the Ministry of Environment. The second session of the meeting presented the inception of Institutional Mapping for Climate Change Activities project. The third session included information sharing of climate-related activities held at the different member institutions. It summarized the submissions of focal points of project sheets asking for three climate change-related activities achieved by their institutions during the past three years, and the main planned activities for the future. The final session closed with a round-table discussion for the CCCU in 2015.

The first draft of the mapping database was submitted by the consultant and reviewed by the project team. The database includes information on various nationally- and internationally-funded projects that have climate change or climate change related components. This mapping presents a comprehensive coordination mechanism involving strategic planning, and close and effective communication with national, regional and international partners, as well as the recommendation of financial mechanisms needed at the national level  This also can be used in turn, as an indication of the priority given to climate change within the country.  The mapping output is expected to be ready by March 2015.

Coordination under the working groups:

- This output also involves the provision of capacity building and information dissemination to governmental focal points in order to promote public sector capacity and capability to tackle climate change issues in their sectoral plans and policies.

The engagement process will include:

- Focal points designation

- Focal points training

- Inter-ministerial and inter-institutional agreements preparation

Achievements:

Partner Ministry/agency involvements – focal points:

Additional nominations were received from the Litani River Authority, World Health Organization, Food and Agriculture Organization, Prime Minister’s Office and the Economic and Social Commission for Western Asia (ESCWA). The total number of focal points from various ministries and agencies were 32 nominations (List of agencies can be found in annex 1).

Focal Points’ Training:

The unit has established contacts with experts and institutions to conduct trainings for certain groups of focal points in four proposed areas. These areas, as identified by the focal points, are (1) Meteorological Climate Modeling, (2) Effective Writing & Communication Skills, (3), Climate Change Finance and (4) Cost-benefit Analysis and Cost-Effectiveness Analysis in appraising energy and environment projects.

The training on Meteorological Climate Modeling took place in  Italy, from 28 to 30 April, 2014. The participants from Lebanon were representatives from the Lebanese Agricultural Research Institute and the Lebanese Meteorological Services from the Directorate General of Civil Aviation.

Two Effective English Writing Skills training took place on June 12 and 26, 2014 respectively. Representatives from various institutions were present (see list in Annex 2). Also, these series of trainings were followed with an Arabic Writing Skills training that took place on July 16, 2014.

The training on Climate Change Finance was conducted on 7th and 8th July 2014 by the Frankfurt School of Finance & Management. Training sessions provided an overview on (1) Climate Finance architecture, (2) Climate Finance readiness, (3) recent/current experience in Lebanon with Climate Finance, (4) opportunities, barriers, and risks, and (5) Climate Finance instruments. Also, discussions were initiated in an attempt to map Lebanon’s climate finance architecture (were examples from other countries were provided), and a roadmap was given with detailed next steps to better structure Lebanon’s national climate finance architecture ( see Annex 3).

Also, the training on CBA and CEA in appraising energy and environment projects took place on 19th and 20th August, 2014 by Dr. Tobias Schmidt (researcher at the Chair of Sustainability and Technology at ETH Zurich). The two-day training included theoretical as well as applied information on two decision support tools: CBA and CEA. It also aimed at triggering discussions among the participants on how these methods could be useful to inform Lebanese policy decisions in general, and in energy related decisions in specific. The overarching approach included de-risking renewable energy investments. Participants included the Ministry of Finance, Ministry of Energy and Water, Ministry of Agriculture, Lebanese Petroleum Authority, Lebanese Center for Energy Conservation, Higher Council for Privatization, Council for Development and Reconstruction, Central Bank of Lebanon, in addition to representatives from the academic/research sector and private consultants (see Annex 4).

- Training and capacity building of other ministries in issues related to climate change is also envisaged. Needs for any legislative changes will be reviewed and changes proposed to the NCE (such changes include tariff restructuring (for e.g., RE and EE). It will also serve to undertake the assessment on how to reach the 12% RE national target as an integrated and holistic approach.

Achievements:

Legislative at the fiscal/financial side at Ministry of Finance:

The study related to the Optimal Renewable Energy mix and its impact on the macro-economy in Lebanon has been finalized and published online (climate change website). The full report can be accessed on the following web-link:

http://climatechange.moe.gov.lb/Library/Files/Uploaded%20Files/Renewable%20Energy%20-%20Investment%20Cost%20-%20Final%20Version.pdf

The above results were included as a main section of the Strategic Environmental Assessment (SEA) of Lebanon’s Renewable Energy scoping report, to serve as an alternative analysis to the National Renewable Energy Strategy (NRES) that is not existent yet. Therefore the SEA studies the impacts of the proposed RE optimal mix with respect to environmental, social and economic indicators.

Also, a document summarizing the existing loan schemes and eligibility criteria, as well as the planned loan schemes in Lebanon that can be considered as climate finance was finalized and prepared to be published in Q4 of 2014. These incorporate five main loan schemes with a number of implementing agencies and funders and/or guarantors.

The Mobility Cost study for Lebanon has been finalized and published online (http://climatechange.moe.gov.lb/newsmobility). The study provides an approach from the cost side of mobility to generate recommendations in order to move the Lebanese passenger transport sector towards sustainable ground. An average conservative figure for mobility cost was calculated: one passenger travelling one kilometer in a passenger vehicle, including externality components of pollution, travel time, congestion, and crashes, costs around US¢ 50. Moreover, sustainable transport indicators are set to find that the most critical ones were not emissions or safety-related, but mostly pointed to an excessive energy consumption by the passenger transport sector.

The study concludes with a set of recommendations and policies to improve certain aspects of the passenger transport sector. This was achieved upon analyzing cost components and referring to sustainable mobility indicators incepted throoughout the case study.

Additionally, the first draft of the study on Fossil Fuel Subsidies in Lebanon was finalized and distributed to relevant stakeholders for a round of comments. The aim of the study is to highlight the inefficient fossil-fuel subsidies that distort markets, impede investment in clean energy sources and undermine efforts to deal with climate change. This study evaluates the impact of fossil-fuel subsidies on the Lebanese economy, fiscal balances, and the environment, while accounting for equity and poverty alleviation concerns.  The study will be uploaded on the project website once it is completed.

Furthermore, the ToRs of the Climate Public Expenditure and Institutional Review (CPEIR) for Lebanon were prepared ad finalized. The CPEIR aims at supporting the Government of Lebanon in improving its climate public expenditure efficiency, as well as its climate governance. With a high debt-to GDP ratio at 140% at end-2013 and a primary fiscal deficit at USD 4.24 billion in 2013, national and international climate finance should be used efficiently and effectively. The CPEIR is a methodology utilized to assess the use of funds that are primarily dedicated to addressing climate change issues. It reviews how climate change related expenditures are integrated into national budgetary processes and is considered as a first step to building a climate fiscal framework. This study is expected to be undertaken by an international institution specializing in expenditure reviews and climate finance, while working closely with a national Public Financial Management expert. The overall expected duration of the assignment is one year and will be funded (USD 100,000) by the Arab Climate Resilience Initiative (ACRI).

Training on Climate Change negotiations:

Building on the basic training on climate change negotiations that was held in December 2013, a more advanced training to enhance the skills of the Lebanese negotiators was conducted on 24th and 25th September, 2014.  The general objective is to further enhance the negotiation capacity of the negotiations' contact group and other stakeholders. This in turn will provide effective participation of the Lebanese Climate Change negotiators at the UNFCCC sessions (see Annex 5). It is important to note that this training was conducted through a grant from the German Ministry of Foreign Affairs, through the German Embassy in Lebanon (value €25,000).

Output 2: Identify and develop nationally appropriate mitigate actions (NAMAs) and pilot demonstration adaptation projects

- This output builds on the assessment of the country’s vulnerability and impacts of climate change and the identification and analysis of the key emitter sectors to consequently propose detailed viable actions (short, medium and long-term) to reduce national emissions, increase resilience, and adapt to climate change.

In this output, various scenarios, opportunities, and approaches will be investigated and viable modalities, policies/regulations and mechanisms will be developed to ultimately facilitate the development of integrated and comprehensive plans for NAMAs.  This will be achieved through a systematic coordination process between the public sector (GG) and the academic and private sector (RTSG) with the assistance of the Coordination Unit. Sectoral working groups will be established to allow a focused and continuous interaction between the stakeholders. The developed action plans will be consequently submitted to the CoM for approval following the endorsement of the NCE.

Achievements:

Strategic Environmental Assessment of the National Renewable Energy Strategy:

Work under the Strategic Environmental Assessment (SEA) of Lebanon’s Renewable Energy scoping report was finalized. The final round comments from various stakeholders were consolidated and shared with the consultants. The results of the “Optimal Renewable Energy Mix in Lebanon” study conducted under the CCCU served as an alternative analysis to the National Renewable Energy Strategy (NRES) that is not existent yet. Also, the Consultation Workshop for the SEA was held on 24th October 2014, with working groups on Windpower, Solar power and Hydropower.

Nationally Appropriate Mitigation Actions:

The inception reports of the provision of professional services for the development of NAMAs for the waste/strategy and the transport sectors were submitted and reviewed. The two inception reports submitted by the international consultant institution G + H, and the national consultant ECODIT, included the overall objective and methodology of the assignment, risk management and mitigation, team composition and scope of work, as well as a delivery schedule.

- Pilot demonstration adaptation projects are envisaged based on the results obtained from the UNEP/UNDP/MoE Technology Needs Assessment project and other national assessments.  The scope and number of pilot projects will be determined once the project is initiated and based on the prioritization set out by the NCE.

Achievements:

Agriculture Demonstration Pilot Project:

The final review of the national guidelines for greenhouse rainwater harvesting systems in Lebanon has been finalized, and a few alterations to the three chosen pilot sites have been completed, and the continuous recording of collected water is being taken at the three chosen sites (photos in Annex 6).

This particular assignment is based on the technology action plan of the Technology Needs Assessment report for the water sector. The specific adaptation technology under consideration is the rainwater harvesting from greenhouse tops (RWHG), which is expected to increase water harvesting and reduce the pressure on pumping from the underground water, therefore increasing water availability during critical months of late summer and early autumn, reducing the risk of salinity in both soil and water, and increase the resileince of crops to prolonged drought and to some fungal outbreaks.

Output 3: Engagement of Lebanon in the international climate change arena and promoting new national and international climate financial mechanisms

- This output includes all activities required to reinforcing the role of Lebanon in international climate change negotiations and to enable the country to play a proactive role within the Group of 77 and China, the Cartagena Dialogue as well as the Arab League. This will be achieved through the strengthening, work organization and capacity building, of the official delegation that represents Lebanon in the UNFCCC negotiations.

- This output will also involve the preparation of national negotiating positions within the Ad Hoc Working Group on the Durban Platform for Enhanced Action (ADP), building blocks and the submission of these positions to the UNFCCC Secretariat.

- Based on the UNFCCC negotiations and the international climate financing trends, the project will work on setting up an enabling environment in Lebanon that would promote financing mechanisms.  This would include NAMA financing mechanisms, available national financing options and official development assistance or credit line programmes that fit into the low emission development strategy.  This would bridge the gap in funding of climate change related development and strengthen the national financial institutions in climate issues.

Climate Change Negotiations:

The first negotiations’ contact group meeting was held on April 28, 2014 with invitations extended to Ministry of Finance, Ministry of Agriculture, American University of Beirut – Issam Fares Institute, University of Balamand – Institute of the Environment, Green Party, Climate Action Network and IndyAct. The group was updated on the UNFCCC negotiating session of March 2014, and the important negotiation developments for the remaining of the year. It was highlighted the importance of Lebanon in preparing for the subsequent meetings and getting involved in the discussions related to Intended Nationally Determined Contributions (INDCs) and UpFront Information under the negotiation. A workplan was drafted depicting the roles and activities that the contact group has agreed upon with specific deadlines for  submission.

The second negotiations’ contact group meeting was held on August 6, 2014.  The group was updated on the developments which occurred in the June ADP session and discussed the expectations for the Conference of Parties (COP) 21 in Lima in December 2014. The meeting prioritized the elements which should be addressed by Lebanon in parallel with the UNFCCC scheduled meetings. The contact group agreed to remain persistent on addressing mitigation and adaptation with the same level of priority in the INDCs since Lebanon is highly vulnerable to the adverse impacts of climate change. Moreover, the meeting stressed on the importance of the differentiation methodology and agreed on the next steps to address this sensitive issue. As far as political voicing/messaging goes, it was decided that Lebanon’s carbon-reducing plans and strategies be put forward to show ambition.

The third negotiations’ contact group meeting was held on November 14, 2014.  The group was updated on the developments which occurred in the October ADP session. This was followed by a discussion session focusing on Lebanon’s position on the INDCs, Adaptation in the 2015 Agreement, as well as the main focus points for Lebanon in the Climate Finance track.  Also, the group was given the essential Logistics and Coordination guidelines for attending the UN Climate Change Conference (COP20) in Lima, Peru.

The climate change team took a leading role at the COP20 meeting in Lima, Peru as part of the official Lebanese delegation. Coordination meetings and contact group meetings were held with the League of Arab States (LAS), the Cartagena Dialogue group, and the G77 + China group. Lebanon also hosted a side event during the first week of the negotiations, on the Economic Repercussions of Climate Change on Vital Sectors of the Lebanese Economy. The team introduced the event, underscoring the economic repercussions of climate change and the need to effectively address them (see Annex 7 for media coverage). Also the study on the optimal renewable energy mix for Lebanon was presented and discussed.

The Lebanese delegation followed on official and non-official negotiation sessions on Climate finance, the Subsidiary Body for Implementation (SBI) on NAMAs, SBI on National Adaptation Plans, and ADP sessions.

Also, the institutional  process to assign a National Designated Authority (NDA) to act as an interface between Lebanon and the Green Climate Fund (GCF), was concluded with the choice of the Ministry of Environment as an NDA. The GCF has been established as an operating entity of the financial mechanism of the UNFCCC by a consensus decision of more than 190 countries that are Parties to the Convention. The Fund will promote a paradigm shift towards low-carbon and climate-resilient development pathways by supporting developing countries to address their climate change mitigation and adaptation needs. The Fund is expected to play a significant role in the mobilization of climate finance, which is planned to increase over time to reach USD 100 billion per year by 2020.

- Describe any delays in implementation, challenges, lessons learned & best practices:

- Qualitative assessment:

The project resulted in the creation of momentum on coordination on climate change among the stakeholders. The advanced negotiations training was again highly appreciated, as some of the stakeholders are looking forward to closer coordination on that matter.

The work with the Ministry of Finance on climate change issues has been taken to a new level, whereby close collaboration is underway in studying various fiscal and financial incentives for energy efficient and renewable technologies (including transport vehicles). The CPEIR process will also strengthen this collaboration.

Using the Programme Results Framework from the Project Document / AWP - provide an update on the achievement of indicators at both the output and outcome level in the table below. Where it has not been possible to collect data on indicators, clear explanation should be given explaining why, as well as plans on how and when this data will be collected.

|  | Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification |
| --- | --- | --- | --- |
| Outcome 1: National Coordination on climate change issues Indicator: (1) Engagement of ministries and governmental institutions in continuous planning/decision making on climate change issues; (2) Identification and development national sectoral NAMAs and pilot demonstration adaptation plans; and (3) Engagement of Lebanon in the international climate change arena and promoting new national and international climate finance mechanisms. Baseline: Limited coordination and participation in climate change issues Planned Target: See outputs | Targets (year 2) - Coordination mechanism established - Adaptation pilot sites chosen and National guidelines for rainwater harvesting from greehouses completed - Training sessions for the focal points conducted - Fiscal/financial mechanisms identified and assessed through a number of studies in collaboration with the Ministry of Finance - Climate negotiations trainings conducted - Participation in the climate summit (COP 20) |  |  |
| Output 1 Engagement of ministries and governmental institutions in continuous planning/decision making on climate change issues Indicator(s) 1.1. Assignment of focal points from ministries, governmental institutions, academia, and the private sector to establish GG and RTSG 1.2. Establishment of a cooperation scheme between ministries and governmental institutions for efficient communication and data sharing 1.3. Training of designated focal points for skills and knowledge improvement Baseline: weak coordination among ministries on matters related to climate change Planned Target: Coordination scheme established and strengthened (year 1) Training of the focal points (year 1, 2) | 2014 implementation TORs shared and discussed with nominated focal points Coordination scheme established First, second and third CCCU meetings between GG and RTSG focal points were conducted Trainings on the areas of CBA/CEA in environmental projects, climate finance, effective writing and communications skills, and climate modeling were conducted Inception of the instituional mapping project |  | TORs of Focal Points Letters of nominations CCCU meetings summary reports Trainings summary reports |
| Output 2 Identification and development of national sectoral NAMAs and pilot demonstration adaptation plans Indicator(s): 2.1.: Situation analysis and preparation of sector specific NAMAs 2.2.: Situation analysis and selection of location of pilot demonstration adaptation projects sites Baseline: availability of few NAMAs and adaptation projects Planned Target: 2.1: Situation analysis conducted (year 1, 2) 2.2.: NAMAs prepared (year 2) 2.3.: Adaptation pilots project underway (year 2) | 2014 accomplishments Finalized the SEA for the renewable energy sector in Lebanon, with the recruited consultants The inception reports of the provision of professional services for the development NAMAs for the waste/strategy and the transport sectors were submitted and reviewed Work for the preparation of guidelines completed to climate proof the EIA process National guidelines for rainwater harvesing from greehouses completed |  | SEA final document NAMA contracts awarded National guidelines for RWH document |
| Output 3 Engagement of Lebanon in the international climate change arena and promoting new national and international climate area and promoting new national and international climate financial mechanisms Indicator(s): 3.1.: Strengthening Lebanon’s role in international climate change negotiations and obligations 3.2.: Identifying new financing mechanisms for climate change Baseline: Weak role of Lebanon in the UNFCCC negotiations Planned Target: 3.1.: Participation in the climate change negotiations (years 1, 2) 3.2.: Financial mechanisms promoted (years 1, 2) | 2014 accomplishments Advanced climate change negotiations training conducted A national contact group for the negotions is established, with three meetings held in 2014 Participation in Arab Group negotiations meetings and Cartagena Dialogue meetings Participation in the COP20 Fund has been received from the UNDP-RBAS Arab Climate Resilience Initiative (ACRI) Project to conduct a CPEIR for Lebanon. Recruitment of consultants to conduct CPEIR is underway and the work will start in 2015 with close cooperation of the Ministry of Finance. |  | Advanced negotiations training reports Climate negotiations analysis report List of participants of the COP 20 and media coverage Fiscal/financial study reports prepared and published online |

iii) A Specific Story (Optional)

- This could be a success or human story. It does not have to be a success story – often the most interesting and useful lessons learned are from experiences that have not worked. The point is to highlight a concrete example with a story that has been important to your Programme in the reporting period.

- In ¼ to ½ a page, provide details on a specific achievement or lesson learned of the Programme. Attachment of supporting documents, including photos with captions, news items etc, is strongly encouraged. The MPTF Office will select stories and photos to feature in the Consolidated Annual Report, the GATEWAY and the MPTF Office Newsletter.

Problem / Challenge faced: Describe the specific problem or challenge faced by the subject of your story (this could be a problem experienced by an individual, community or government). Programme Interventions: How was the problem or challenged addressed through the Programme interventions? Result (if applicable): Describe the observable change that occurred so far as a result of the Programme interventions. For example, how did community lives change or how was the government better able to deal with the initial problem? Lessons Learned: What did you (and/or other partners) learn from this situation that has helped inform and/or improve Programme (or other) interventions?

III.	Other Assessments or Evaluations (if applicable)

•	Report on any assessments, evaluations or studies undertaken.

IV.	Programmatic Revisions (if applicable)

•	Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place.

V. 	Resources (Optional)

•	Provide any information on financial management, procurement and human resources.

•	Indicate if the Programme mobilized any additional resources or interventions from other partners.

Mobilized Financial Resources:

€ 35,000 from the Federal Ministry of Foreign Affairs, Germany to conduct the advanced climate negotiations training.

USD 100,000 from the Arab Climate Resilient Initiative, UNDP-RBAS, to conduct the Climate Public Expenditure and Institutional Review.

Human Resources:

  - National Project Staff:

- Project Coordinator - economist (x1)

Expenditures to date

USD 432,571.59

Abbreviations and acronyms:

| ACRI | Arab Climate Resilience Initiative |
| --- | --- |
| ADP | Ad hoc working group on the Durban Platform for enhanced action |
| CCCU | Climate Change Coordinating Unit |
| CEDRO | Community Energy efficiency and Renewable energy Demonstration |
| COP | Conference of Parties |
| CPEIR | Climate Public Expenditure and Institutional Review |
| EDL | Electricite Du Liban |
| EE | Energy Efficiency |
| ESCWA | Economic and Social Commission for Western Asia |
| GCF | Green Climate Fund |
| GG | Government Group |
| GHG | Greenhouse Gas |
| INDCs | Intended Nationally Determined Contributions |
| LAS | League of Arab States |
| MoE | Ministry of Environment |
| NAMA | Nationally Appropriate Mitigation Action |
| NCE | National Council for the Environment |
| NDA | National Designated Authority |
| NGOs | Non-Governmental Organization |
| NRES | National Renewable Energy Strategy |
| RE | Renewable Energy |
| RTSG | Research and Technical Support Group |
| RWHG | Rainwater Harvesting from Greenhouse Tops |
| SBI | Subsidiary Body for Implementation |
| SEA | Strategic Environmental Assessment |
| SEA | Strategic Environmental Assessment |
| UNDP | United Nations Development Programme |
| UNFCCC | United Nations Framework Convention on Climate Change |

# Annex 1. List of Focal Points/organizations to the climate change coordinating unit

Confirmed Nominations

- Association of Banks in Lebanon

- Directorate of Civil aviation (DGCA) - Beirut International Airport

- Association of Lebanese Industrialists

- American University of Beirut – Issam Fares Institute

- University of Balamand – Institute of Environment

- Council of Development and Reconstruction

- Électricité Du Liban

- Industrial Research Institute

- IndyAct

- LARI

- Middle East Airlines

- Ministry of Agriculture

- Ministry of Education

- Ministry of Finance

- Ministry of Foreign Affairs

- Ministry of Industry

- Ministry of Interior and Municipalities

- Ministry of Public Health

- Ministry of Public Works and Transport -  التنظيم المدني

- Ministry of Public Works and Transport -  المديرية العامة للنقل البري و البحري

- Ministry of Energy and Water – Water Resources

- National Council of Scientific Research

- Order of Engineers

- Litani River Authority

- World Health Organization

- Food and Agriculture Organization

- Prime Minister’s Office

- Economic and Social Commission for Western Asia (ESCWA)

Partners

- Disaster Risk Management Unit in Lebanon

- CEDRO

- Lebanese Center for Energy Conversation (LCEC)

- Lebanese Center for Water Conservation and Management (LCWCM)

# Annex 2. List of attendees of the two training sessions

June 12th: English Effective Writing and Communication Skills – Part I

|  | Name | Organization | Email |
| --- | --- | --- | --- |
| 1 | Rana Youssef | Ministry of Environment/UNDP | R.Youssef@moe.gov.lb |
| 2 | Mary Awad | Ministry of Environment/UNDP | m.awad@moe.gov.lb |
| 3 | Ahmad Harb | Lebanese Petroleum Authority | ahmad.harb@lpa.gov.lb |
| 4 | Carla Nassab | CEDRO | carla.nassab@undp-lebprojects.org |
| 5 | Sawsan Nassredine | Ministry of Finance | sawsanna@finance.gov.lb |
| 6 | Cynthia Kayem | Ministry of Environment/UNDP | cynthia.kayem@undp-lebprojects.org |
| 7 | Mireille Jazi | Balamand University | Mireille.Jazi@balamand.edu.lb |
| 8 | Patricia Haydamous | Issam Fares Institute - AUB | ph16@aub.edu.lb |
| 9 | Vahakn Kabakian | Ministry of Environment/UNDP | Vahakn@moe.gov.lb |
| 10 | Yara Daou | Ministry of Environment/UNDP | y.daou@moe.gov.lb |
| 11 | Alaa Bashir | IndyAct | comms@indyact.org |
| 12 | Tala Moukaddem | Society for the Protection of Nature in Lebanon - SPNL | t.moukaddem@spnl.org |
| 13 | Lea Hakim | Ministry of Finance/UNDP | LeaH@finance.gov.lb |
| 14 | Kourken Kadehjian | Ministry of Environment/UNDP | Kerk92@gmail.com |
| 15 | Nohal Al Homsi | World Health Organization | alhomsin@who.int |
| 16 | Lara Haidar | Ministry of Environment/UNDP | L.Haidar@moe.gov.lb |
| 17 | Aya El Hajj | Ministry of Environment/UNDP | a.elhajj@moe.gov.lb |
| 18 | Lea Aboujaoude | Ministry of Environment/UNDP | l.kai@moe.gov.lb |
| 19 | Nada Mneimneh | Ministry of Finance | nadamnh@gmail.com |
| 20 | Ali Shaar | Directorate General of Civil Aviation | ali.shaar@hotmail.com |
| 21 | Ihab Jomaa | Agricultural Research Institute of Lebanon - LARI | ijomaa@lari.gov.lb |

June 26th: English Effective Writing and Communication Skills – Part II

|  | Name | Organization | Email |
| --- | --- | --- | --- |
| 1 | Rana Youssef | Ministry of Environment/UNDP | R.Youssef@moe.gov.lb |
| 2 | Mary Awad | Ministry of Environment/UNDP | m.awad@moe.gov.lb |
| 3 | Ahmad Harb | Lebanese Petroleum Authority | ahmad.harb@lpa.gov.lb |
| 4 | Leila El Sayyed | Ministry of Environment/UNDP | leila.el-sayed@undp-lebprojects.org |
| 5 | Sawsan Nassredine | Ministry of Finance | sawsanna@finance.gov.lb |
| 6 | Cynthia Kayem | Ministry of Environment/UNDP | cynthia.kayem@undp-lebprojects.org |
| 7 | Mireille Jazi | Balamand University | Mireille.Jazi@balamand.edu.lb |
| 8 | Patricia Haydamous | Issam Fares Institute - AUB | ph16@aub.edu.lb |
| 9 | Vahakn Kabakian | Ministry of Environment/UNDP | Vahakn@moe.gov.lb |
| 10 | Yara Daou | Ministry of Environment/UNDP | y.daou@moe.gov.lb |
| 11 | Alaa Bashir | IndyAct | comms@indyact.org |
| 12 | Abed El Rahman Zawawy | Directorate General of Civil Aviation | zawawyabed@gmail.com |
| 13 | Lea Hakim | Ministry of Finance/UNDP | LeaH@finance.gov.lb |
| 14 | Kourken Kadehjian | Ministry of Environment/UNDP | Kerk92@gmail.com |
| 15 | Nohal Al Homsi | World Health Organization | alhomsin@who.int |
| 16 | Lara Haidar | Ministry of Environment/UNDP | L.Haidar@moe.gov.lb |
| 17 | Aya El Hajj | Ministry of Environment/UNDP | a.elhajj@moe.gov.lb |
| 18 | Lea Aboujaoude | Ministry of Environment/UNDP | l.kai@moe.gov.lb |
| 19 | Jad Stephan | Ministry of Environment/UNDP | jadstephan@live.com.au |
| 20 | Ali Shaar | Directorate General of Civil Aviation | ali.shaar@hotmail.com |
| 21 | Ihab Jomaa | Agricultural Research Institute of Lebanon - LARI | ijomaa@lari.gov.lb |

# Annex 3    Climate Finance Seminar Final Report can be accessed at the following web-link:

http://climatechange.moe.gov.lb/Library/Files/Uploaded%20Files/CF%20Seminar%20Lebanon%20Report.pdf

Agenda

| Climate Finance Seminar (07.07 – 08.07.2014) |
| --- |
| Monday, 07.07.2014 – The national and international climate finance architecture |
| 9:00-9:30 | Registration |
| 9:30-9:45 | Welcoming words (MoE-UNDP) |
| 9:45-11:15 | Session 1: Introduction to Climate Finance This session introduces the current debate on climate finance and provides an overview about available international funding sources and eligibility criteria, as well as the importance of national sources. It is to help participants to get an insight into institutional arrangements and political framework for mobilizing, managing and monitoring of climate finance. (Presentation) |
| 11.15-11:30 | Break |
| 11:30-13:00 | Session 2: Lebanon’s Experience in Climate Finance Lebanon has already experience in climate finance. By addressing the question - who needs to be involved and why - the important stakeholders for climate finance in Lebanon will be elaborated. Moreover, based on the experience and knowledge of the participants, existing climate finance mechanism and instruments will be discussed. The focus will lie hereby on lessons learned and the perceived impact. (Interactive session) |
| 13:00-14:00 | Lunch |
| 14:00–16:30 | Session 3: Getting Ready for Climate Finance Countries want to prepare for climate finance readiness. This requires on national level to decide on an institutional set up (with different players and roles). This session introduces different options (e.g. selecting an existing or establishing a new institution) for getting ready – e.g. by introducing the institutional arrangements in other countries. Together, the important steps will be elaborated to prepare for climate finance readiness. (Presentation and interactive session) |
| 16:30–17:00 | Summary of day one and introduction to the next day |
| Tuesday, 08.08.2014 - Climate finance instruments |
| 16:00-16:15 | Recap of day 1 and introduction of day 2 |
| 16:15-17:45 | Session 4: Barriers for Climate Investments This session introduces the major barriers with regard to investments in mitigation and adaptation projects. Together, the participants will categorise the major barriers experienced in Lebanon. (Presentation and interactive session to elaborate the context in Lebanon) |
| 17:45-18:00 | Break |
| 18:00-19:30 | Session 5: Policy Incentives for Climate Finance Various public policy incentives and financial instruments are suitable to address GHG emissions reductions and mobilise investments in adaption and mitigation. With reference to the previous session and together with good practice samples from other countries, an overview of different instruments and criteria that define effective policy incentives will be discussed. (Presentation and interactive session to elaborate the context in Lebanon) |
| 19:30-20:00 | Wrap up, evaluation and Closing words |
| 20:00 | Iftar |

List of Attendees

Climate Finance Seminar

July 7th & 8th, 2014

Gefinor Rotana Hotel – Clemenceau Beirut

| Name | Institution | Email | Phone |
| --- | --- | --- | --- |
| Christine Gruening | Frankfurt School of Finance and Management | C.Gruening@fs.de | - |
| Carola Menzel | Frankfurt School of Finance and Management | C.Menzel@fs.de | - |
| Joseph Saade | NATCAZ | joseph.a.saade@gmail.com | 03-080818 |
| Jessica Obeid | CEDRO | jessica.obeid@undp-lebprojects.org | 03-404741 |
| Jihan Seoud | UNDP | Jihan.seoud@undp.org | 03-161370 |
| Catherine Abdo | V4 Advisors | cabdo@v4advisors.com | 03-590779 |
| Walid Sayegh | UNDP/MoF | walid.sayegh82@gmail.com | 70-299672 |
| Tarek Bsat | Bank Audi | tarek.bsat@asib.com | 76-888318 |
| Yasmine Ibrahim | UNDP/MoF | yasminei@finance.gov.lb | 03-957565 |
| Patil Mesrobian | LCEC | patil.mesrobian@lcecp.org.lb | 03-103979 |
| Russel Frost | Streg Project/EU/GFA | r-f121@yahoo.co.uk | - |
| Patricia Haydamous | IFI/AUB | ph16@aub.edu.lb | 70-811267 |
| Cherine Daoud | BLOM Bank | cherine_daoud@hotmail.com | 03-782234 |
| Carla Nassab | CEDRO | carla.nassab@undp-lebprojects.org | 03-397361 |
| Celina Andrioti | JP Morgan | celina-andrioti@jpmchase.com | 03-777984 |
| Kourken Kadehjian | UNDP/MoE | kerk92@gmail.com | 71-754073 |
| Tala Moukaddem | SPNL | tala.moukaddem@gmail.com | 03-187479 |
| Majd Fayyad | Green Future | majdfayyad89@gmail.com | 03-948642 |
| Jaoudat Abou Jaoude | CDR | jawdata@cdr.gov.lb | 03-346890 |
| Isabelle Naoum | BLOM Bank | i.naoum@blom.com.lb | 03-359454 |
| Georges Abi Saleh | ABL | gas@abl.org.lb | 03-628188 |
| Lamia Chamas | PCM | lchamas@pcm.gov.lb | 03-705800 |
| Nina El Hajj Srour | Credit Libanais | nelhajj@cl.com.lb | 03-771321 |
| Zeina Majdalani | PCM | zmajdalani@pcm-gov.lb | 03-245416 |
| Elie Zanaty | BLOM Bank | elie.zanaty@gmail.com | 03-953045 |
| Rawad Massoud | V4 Advisors | rmassad@v4advisors.com | 71-139943 |
| Jad Stephan | UNDP/MoE | jadstephan@live.com.au | 03-423836 |
| Krystel Rizk | CEDRO | krystel.rizk@undp-lebprojects.org | 03-833087 |
| Lea Hakim | UNDP/MoF | leah@finance.gov.lb | 01-981057 |
| Maya Damaj | Byblos Bank | mdamaj@byblosbank.com.lb | 03-616089 |
| Lara Haidar | UNDP/MoE | l.haidar@moe.gov.lb | 03-024284 |
| Souraya Srage | BDL | ssrage@bdl.gov.lb | 03-733162 |
| Hassan Harajli | CEDRO | hassan.harajli@undp-lebprojects.org | 71-222555 |
| Tarek Kazoun | KAFALAT | tarekkazoun@hotmail.com | 03-963443 |
| Khaled Bohsali | BDL | kbohsali@bdl.gov.lb | 03-359930 |
| Vahakn Kabakian | UNDP/MoE | vahakn@moe.gov.lb | 03-527679 |
| Lea Kai Aboujaoude | UNDP/MoE | l.kai@moe.gov.lb | - |
| Yara Daou | UNDP/MoE | y.daou@moe.gov.lb | 03-312501 |
| Leila El Sayed | UNDP/MoE/MoF | leila.el-sayed@undp-lebprojects.org | 03-940506 |
| Mary Awad | UNDP/MoE | m.awad@moe.gov.lb | 03-394326 |

# Annex 4    Training on Cost-Benefit and Cost-Effectiveness Analysis in Appraising Energy and Environmental Projects Final Report

Cost-Benefit Analysis & Cost-Effectiveness Analysis Training

The Ministry of Environment in cooperation with the United Nations Development Programme organized a hands-on training on “Cost-Benefit Analysis and Cost-Effectiveness Analysis for Environmental and Energy Projects. The event took place on Tuesday 19 and Wednesday 20, 2014, and was delivered by Dr. Tobias Schmidt.

The aim was to provide the participants with theoretical as well as applied information on two decision support tools: Cost-Benefit Analysis (CBA) and Cost-Effectiveness Analysis (CEA). It also aimed at triggering discussions among the participants on how these methods could be useful to inform Lebanese policy decisions.

During the first day, participants were given an overview and introduction to basic financial principles. Important concepts that were discussed were the principle of time-value of money and how it can be implemented in finance through discounting.

Then, the CBA and CEA tools were introduced highlighting the key differences between the two concepts. Also, the participants were asked to perform their own CEA in groups as to get a better understanding of the sensitivities of life-cycle costs to certain input parameters and assumptions.

Main discussions revolved around:

- the height of the discount rate (CBA);

- the idea of pricing in non-monetary values (CBA);

- aligning different policy targets (CEA);

- the usefulness and various procedures of multi-criteria assessment;

- the principle of the Levelized Cost of Electricity (LCOE);

- interpretation of negative abatement costs;

- cross-subsidizing of risk through public grants;

- the role of fossil subsidies; and

- the role of discounting.

Sessions of the second day focused on the effects of risk on private discount rates, the role of risks for cost-effectiveness, different risk categories typically present in energy projects and three different derisking mechanisms to increase cost-effectiveness: risk reduction (policy derisking), risk transfer (financial derisking), and increasing of returns (risk compensation). To put the idea in context, post-Kyoto climate policy – specifically the role of Nationally Appropriate Mitigation Actions (NAMAs) – was introduced.

The participants also engaged in a policy derisking exercise, the Derisking Renewable Energy Investment (DREI) tool, that was originally developed by UNDP (with Tobias Schmidt being one of the authors).

Conclusions and discussions focused on:

- whether risk categories can be isolated or whether correlations between these categories are too strong;

- the fact that investing in derisking measures upfront can reduce the long-term costs of a policy to the public sector substantially;

- risk analysis is specifically important in low-carbon technologies as they typically rely on more upfront finance than high-carbon projects; and

- in the case of policy derisking, a higher leverage can be achieved, as each project that follows that derisking measure profits from the derisking effect, whereas financial derisking is limited to individual projects.

Agenda

Hands-On Training on Cost-Benefit and Cost-Effectiveness Analysis in Appraising

Energy and Environmental Policies – Day 1

Tuesday, August 19th, 2014

Sheraton Four Points Hotel

| Time | Session | Description |
| --- | --- | --- |
| 9:00 – 9:15 | Registration and Welcoming Note |
| 9:15 – 10:15 | Basic Terms and Principles in Finance Presentation & Interactive Elements | This session introduces the basic terms and principles in finance such as nominal versus real value, discounting and selecting discount rates, net present value (NPV), and internal rate of return (IRR). |
| 10:15 – 10:45 | Coffee Break |
| 10:45 – 12:45 | Introduction to Cost-Benefit Analysis (CBA) and Cost-Effectiveness Analysis (CEA) Presentation & Q&A | The definitions, purpose and principles of both CBA and CEA will be given, highlighting the different methodologies, difficulties and caveats of both methods. Examples of CBA & CEA will be presented. |
| 12:45 – 13:30 | Lunch |
| 13:30 – 16:00 | Exemplary Case Study: Feed In Tariff Policy for Wind Power Group Exercise | A case study on CBA and CEA for a feed-in tariff (FiT) policy for wind will be used as a practical exercise (baselines, discount rates, sensitivity analysis, etc.) |

Hands-On Training on Cost-Benefit and Cost-Effectiveness Analysis in Appraising

Energy and Environmental Policies – Day 2

Wednesday, August 20th, 2014

Sheraton Four Points Hotel

| Time | Session | Description |
| --- | --- | --- |
| 9:00 – 9:15 | Registration & Recap of Day 1 & Introduction of Day 2 |
| 9:15 – 10:15 | Risk and Public Policy Presentation | This extends the learning of previous sessions by focusing on the role of risk for the cost-effectiveness of public policies. Examples of typical risks from the fields of energy and environment will be provided and discussed. |
| 10:15 – 11:15 | De-risking as a Way to Improve the Cost-Effectiveness of Public Policies Presentation | This session introduces de-risking methods and how de-risking can increase the cost-effectiveness of public policies. Specifically, de-risking is discussed in the context of Nationally Appropriate Mitigation Action policies (NAMAs) as established under the UNFCCC and the Green Climate Fund. |
| 11:15 – 11:45 | Coffee Break |
| 11:45 – 13:45 | De-risking Case Study on a hypothetical Wind FiT NAMA Group Exercise | This session will implement a de-risking case study on a on a feed-in tariff (FiT)-based NAMA policy for wind. Many of the key issues of de-risking will be discussed and the participants will have to create a policy mix spurring wind investments, which include de-risking elements. |
| 13:45 – 14:00 | Clinique – Q&A Open Discussion | An open discussion with questions and answers covering all topics treated in the training. CBA/CEA issues specific to Lebanon’s situation will be discussed. |
| 14:00 | Lunch |

List of Attendees

Hands-On Training on Cost-Benefit and Cost-Effectiveness Analysis in Appraising

Energy and Environmental Policies

August 19 & 20, 2014

Four Points Sheraton Hotel - Verdun

| Name | Institution | Email |
| --- | --- | --- |
| Hassan Harajli | CEDRO | hassan.harajli@undp-lebprojects.org |
| Marc Haddad | LAU | mhaddad@lau.edu.lb |
| Pierrette Zouein | LAU | pzouein@lau.edu.lb |
| Karim Osseiran | Ministry of Energy and Water | karim.m.osseiran@gmail.com |
| Michel-Ange Medlej | Ministry of Energy and Water | michelange.medlej@gmail.com |
| Hadi Tabbara | Consultant | haditabbara@yahoo.com |
| Patil Mesrobian | Lebanese Center for Energy Conservation | patil.mesrobian@lcecp.org.lb |
| Elie Abou Jaoudeh | Lebanese Center for Energy Conservation | eaboujaoudeh@lcecp.org.lb |
| Assem Abou Ibrahim | Lebanese Petroleum Authority | assem.abouibrahim@lpa.gov.lb |
| Rola Sheikh | Lebanese Petroleum Authority | rola.sheikh@lpa.gov.lb |
| Walid Nasr | Lebanese Petroleum Authority | walid.nasr@lpa.gov.lb |
| Mada Arslan | Banque du Liban | marslan@bdl.gov.lb |
| Helena Haddad | Banque du Liban | hahaddad@bdl.gov.lb |
| Maya Mhanna | Ministry of Agriculture | mayamhanna@gmail.com |
| Diala Chaar | Higher Council for Privatization | dchaar@hcp.gov.lb |
| Maya Chamli | Higher Council for Privatization | mchamli@hcp.gov.lb |
| Jaoudat Abou Jaoudeh | Council for Development and Reconstruction | jawdata@cdr.gov.lb |
| Jean Stephan | Food and Agriculture Organization | jean.stephan@fao.org |
| AbdelRahim Ayoubi | UNDP/Ministry of Finance | Abdelrahim.ayoubi@gmail.com |
| Walid Sayegh | UNDP/Ministry of Finance | walidsa@finance.gov.lb |
| Nadim Farajalla | Issam Fares Institute – American University of Beirut | nf06@aub.edu.lb |
| Rana El Hajj | Issam Fares Institute – American University of Beirut | re15@aub.edu.lb |
| Nabil Amacha | Litani River Authority | nabilamacha@hotmail.com |
| Vahakn Kabakian | UNDP/Ministry of Environment | vahakn@moe.gov.lb |
| Lea Kai Aboujaoude | UNDP/Ministry of Environment | l.kai@moe.gov.lb |
| Yara Daou | UNDP/Ministry of Environment | y.daou@moe.gov.lb |
| Leila El Sayyed | UNDP/Ministry of Environment | leila.el-sayed@undp-lebprojects.org |
| Mary Awad | UNDP/Ministry of Environment | m.awad@moe.gov.lb |
| Kourken Kadehjian | UNDP/Ministry of Environment | kerk92@gmail.com |
| Jad Stephan | UNDP/Ministry of Environment | jadstephan@live.com.au |

# Annex 5    Advanced UNFCCC Negotiations Training

Agenda

National Workshop on Climate Change Negotiations

Training to Enhance the Skills of the Lebanese Negotiators

Beirut, 24 September – 25 September 2014

Day 1 – Wednesday 24 September 2014

| Programme |
| --- |
| 09.00 – 10.00 | Welcome and Introduction Where do the negotiations stand |
| Session I: Negotiating in practice |
| 10.00 – 10.20 | Gathering information Where to get useful information in short time; which sources to use and why they are important. |
| 10:20 – 10.30 | Negotiation Exercise Part I: Introduction |
| 10.30 – 11.00 | Coffee Break |
| 11.00 – 11.20 | How to work effectively as a delegation Information flow within a delegation; attribution of tasks; using resources effectively; insights from the EU and Lebanon |
| 11.20 – 12.20 | Back channels for influencing the negotiations How to use the media, NGOs, other parties, the Secretariat, Chairs and the Presidency |
| 12.20 – 13.20 | Lunch Break |
| 13.20 – 14.10 | How to say what you want where, when and how (I) Choosing the right meeting and the right moment in the negotiations, creating the right atmosphere, which people to approach Statements in Plenary Contact groups and informals Group meetings |
| 14.10 – 15.00 | How to say what you want where, when and how (II): Formal bilaterals |
| 15.00 – 15.30 | Coffee Break |
| 15.30 – 16.30 | Moderated discussion: Who to approach to strengthen the Lebanese position? |
| 16.30 – 16.40 | Problem 1 and how to solve it Difficult situations that negotiators might encounter in the negotiations, and possible solutions |
| 16.40 – 17.00 | Negotiation Exercise Part II: Opening Plenary |

Day 2 – Thursday 25 September 2014

| Programme |
| --- |
| Session II: Understanding and influencing text |
| 09.00 – 09.30 | Understanding codes Understanding the most relevant negotiation codes in the context of the negotiations on the 2015 climate agreement |
| 09.30 – 09.50 | Working with text I: Formalities and Practicalities How to bring text into the negotiations; with whom to work on text etc. |
| 09.50 – 10.30 | Working with text II: Language to watch out for in decision text Preambular and operative paragraphs and the key words at the start; slippery negotiation words; references to past decisions; cross-check with other agenda items |
| 10.30 – 11.00 | Coffee Break |
| 11.00 – 11.30 | Negotiation Exercise Part III: Contact Group |
| 11.30 – 11.45 | Problem 2 and how to solve it Difficult situations that negotiators might encounter in the negotiations, and possible solutions |
| 11.45 – 12.15 | Using and pleasing your Minister How to effectively use your minister; how to navigate your minister through the negotiations |
| 12.15 – 13.15 | Lunch Break |
| 13.15 – 13.45 | Negotiation Exercise Part III: Final Plenary + Reflections on the exercise |
| 13.45 – 14.45 | Analysis of draft INDC decision text I – group work Analysing the draft decision on intended nationally determined contributions that was presented by the ADP Co-Chairs |
| 14.45 – 15.15 | Coffee Break |
| 15.15 – 16.15 | Analysis of draft INDC decision text II – presentation and discussion of results Analysing the draft decision on intended nationally determined contributions that was presented by the ADP Co-Chairs |
| 16.15 – 16.30 | Problem 3 and how to solve it Difficult situations that negotiators might encounter in the negotiations, and possible solutions |
| 16.30 – 17.00 | Wrap up Feedback on the workshop and open questions |

List of Attendees

| Name | Institution | Email | Phone |
| --- | --- | --- | --- |
| Laura Sisco | AUB | lbs05@mail.aub.edu | 76-530866 |
| Julia Strobl | AUB | jms23@mail.aub.edu | 78-907886 |
| Hanan Abdul Rida | German Embassy | hanan.abdul-rida@auswaertiges-amt.de | 04-935015 |
| Vahakn Kabakian | UNDP/MoE | vahakn@moe.gov.lb | 03-527679 |
| Lea Kai | UNDP/MoE | l.kai@moe.gov.lb | 03-744252 |
| Christophe Maroun | IndyAct | cmaroun@indyact.org | 03-060933 |
| Ali Shaar | DGCA | ali.shaar@hotmail.com | 03-287819 |
| Rana El Hajj | AUB/IFI | re15@aub.edu.lb | 03-404625 |
| Mary Awad | UNDP/MoE | m.awad@moe.gov.lb | 03-394326 |
| Carla Jamous | Ministry of Agriculture | jamous.carla@gmail.com | 71-330834 |
| Yara Daou | MoE/UNDP | y.daou@moe.gov.lb | 03-312501 |
| Talal Salman | MoF/UNDP | talal.salman@finance.gov.lb | - |
| Sabine Saba | IoE/Balamand | sabine.saba@fty.balamand.edu.lb | 03-985469 |
| Suzanne Baaklini | L’Orient le Jour | suzannebaaklini@lorientlejour.com | 03-363811 |
| Leila El Sayed | UNDP/MoE/MoF | leila.el-sayed@undp-lebprojects.org | 03-940506 |
| Bjorn Jakobson | AUB | bjornbangjakobson@gmail.com | 76-953522 |
| Marc Wehaibe | DGCA | wehaibem@beirutairport.gov.lb | 03-613283 |
| Bassam Kantar | Al Akhbar | bassam.kantar@gmail.com | 03-350956 |
| Lara Haidar | UNDP/MoE | l.haidar@moe.gov.lb | 03-024284 |
| Majed Soufi | AUB | mks30@mail.aub.edu | 70-199127 |
| Camilla Bausch | Ecologic | camilla.bausch@ecologic.eu | - |
| Lena Donat | Ecologic | lena.donat@ecologic.eu | +4915785200866 |

# Annex 6. Photos of  Greenhouse Rainwater Harvesting Systems (Site: Kfarmashoun)

# Annex 7     Media Coverage of Lebanon’s Side Event Agenda at COP20

Video coverage:

https://www.youtube.com/watch?v=Hb9UwVyKt9A

International Institute for Sustainable Development (IISD) article:

http://www.iisd.ca/climate/cop20/enbots/6dec.html#event2

# Footnotes

The term “programme” is used for programmes, joint programmes and projects.

Strategic Results, as formulated in the Strategic UN Planning Framework (e.g. UNDAF) or project document;

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as  “Project ID” on the project’s factsheet page the MPTF Office GATEWAY

The MPTF or JP Contribution, refers to the amount transferred to the Participating UN Organizations, which is available on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

# Text boxes

ii) Indicator Based Performance Assessment: