Lebanon Recovery Fund

MPTF OFfice GENERIC ANNUAL programme NARRATIVE progress report

REPORTING PERIOD: 1 january – 31 December 2014

| Programme Title & Project Number |  | Country, Locality(s), Priority Area(s) / Strategic Results |
| --- | --- | --- |
| Programme Title: Reviving Farmers’ Livelihood in South Lebanon Programme Number: LRF 28 MPTF Office Project Reference Number: 00086602 |  | Lebanon / Nabatieh - South Region |
|  |  | Local governance structures in target under-served regions strengthened for better representation, participation, and basic local services delivery. |
| Participating Organization(s) |  | Implementing Partners |
| UNDP |  | National counterparts: Ministry of Agriculture Municipality of Nabatieh |
| Programme/Project Cost (US$) |  | Programme Duration |
| Total approved budget as per project document: USD 700,000 MPTF /JP Contribution: USD 700,000 |  |  | Overall Duration (19 months) |  |
| Agency Contribution UNDP: USD 69,300 in-kind |  |  | Start Date (01.05.2013) |  |
| Government Contribution Ministry of Agriculture: USD 111,000 in-kind Municipality of Nabatieh: USD 600,000 Cash USD 83,000 In-kind |  |  | Original End Date (31.12.2014) |  |
|  |  |  | Current End date(31.05.2015) |  |
| TOTAL: USD 1,563,300 |  |  |  |  |
| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| Assessment/Review - if applicable please attach Yes No Date: dd.mm.yyyy Mid-Term Evaluation Report – if applicable please attach Yes No Date: dd.mm.yyyy |  | Name: Hussein Nasrallah Title: Project Manager Participating Organization (Lead): UNDP Email address: hussein.nasrallah@undp-lebprojects.org |

### List of Acronyms

BOQ: 		Bill of Quantities

CDR:		Council of Development and Reconstruction

MoA: 		Ministry of Agriculture

MoN: 		Municipality of Nababtieh

TOR:		Terms of Reference

UNDP: 	United Nations Development Program

# NARRATIVE REPORT FORMAT

# EXECUTIVE SUMMARY

- The Municipality of Nabatieh and the Ministry of Agriculture have conducted a preliminary needs assessment of the site. Engineers developed the architectural, structural, electronic and mechanical executive maps before the preparation of the BOQ of quantities and price. Accordingly, TOR was prepared and shared with UNDP HQ for approval. The MoA focal point met with the MoN and agreed on the structure of the agricultural extension services that the Market will provide.

# Purpose

Intended Outcome as stated in the Country Programme Results and Resource Framework: Local governance structures in target under-served regions strengthened for better representation, participation, and basic local services delivery.

Output indicators as stated in the Country Programme Results and Resources Framework: Capacities of institutions and community groups strengthened for effective formulation and implementation of decentralized policies and regional and local development plans including women and youth.

The overall aim of the project is to sustain and strengthen the agricultural sector and support rural development in South Lebanon, specifically Nabatieh Muhafazat. The project will contribute to expand livelihood opportunities for vegetable farmers in South Lebanon through the establishment of a market place. This will contribute to reducing transaction costs and strengthen access to extension services to improve post-production stages which are at the heart of sector’s vulnerability. The project will benefit 426,000 Lebanese residents, including 8,000 fruit and vegetable producers, and will serve as a pilot model to be replicated in other rural areas in Lebanon.

The project aims at reducing farmer poverty and vulnerability in South Lebanon, focusing on Nabatieh as a pilot area. The immediate overall objective of the project is to promote rural development and alleviate poverty through overcoming agricultural constraints and assisting the small and poor farmers in reducing the production costs, increasing its quality and overcoming post-harvesting barriers. The integrated intervention will serve a double purpose:

- The establishment of a wholesale vegetable and fruit farmers’ market in Nabatieh city granting a safe and regulated place for the direct sale by the farmers,

- The provision of essential extension services to improve post-production stages.

# Results

Expected Result 1: A farmers’ market in Nabatieh city is established.

- Preparation of technical feasibility study for the market site

The Municipality of Nabatieh and the Ministry of Agriculture have conducted a preliminary needs assessment of the site. The wholesale vegetable and fruit market requires the following elements: a cement wholesale building, a cement administrative building, a corridor tent, a hangar, asphalting for car and truck paths, a fence, a herbs garden and accessible footpaths, in addition to the extension services.

A comprehensive study is required prior to proceeding with the contracting process. Engineers will develop the architectural, structural, electronic and mechanical executive maps before the preparation of the BOQ of quantities and price.

- Initiation of procurement process

Contractors will be invited to bid according to the specifications set out in the tender. This process will be fair and competitive guaranteeing best value for money, according to UNDP rules and regulations.

- Establishment of market management structure

While the Municipality of Nabatieh will be responsible for the overall management and maintenance of the market upon project completion, a cost-recovery mechanism will be in place to safeguard the financial sustainability of the market. The system will be based on fee-for-service which will enable the Municipality to hedge itself against foreseen and unforeseen maintenance costs. This will also incentivize the farmers to access the market and related extension facilities as professional services.

The project also seeks to establish transparent mechanisms promoting inclusion and accountability. Hence, a “market managerial board” will be created and will include the Municipality of Nabatieh, the Ministry of Agriculture, farmer representatives and others as necessary based on a series of consultations at the local level with stakeholders. Based upon UNDP’s expertise in developing national capacities to fulfill development aspirations and goals, the UN programme will provide technical assistance enabling the managerial board members to be operational, autonomous and sustainable beyond the project life cycle.

- Monitoring and evaluation

Continuous monitoring and evaluation will occur during the project, with the UNDP project team directly based in Tyre near the project site, with easy access to Nabatieh. Field visits will be regular and thoroughly documented. A post-implementation evaluation survey will be conducted to ensure the project objectives vis-à-vis usage.

Expected Result 2: Access to agricultural extension services is improved

- Establishment of information centre in the market

In order to promote the Nabatieh market place as a one-stop information centre where farmers can go to sell their products in addition to finding a wide range of accessible extension services, a small information area will be created.  This space will require furnishing, and will contain information products such as thematic brochures, leaflets and contact books of agricultural professional services, for the farmers to freely consult. As exposed earlier, the Ministry of Agriculture will be responsible for running this centre.

- Establishment of storage and refrigerating facility

Equipment towards establishing a storage and cooling room in the market will also be purchased. Storage limits waste and is thus paramount, particularly for farmers coming from remote locations. Access to refrigeration is not widespread in rural areas of Lebanon but is nonetheless important to extend the life of fragile products such as vegetables and to increase their selling value. This will be an in-kind contribution from the Ministry of Agriculture.

- Thematic and technical trainings for farmers and cooperatives

Thematic and technical trainings for farmers and cooperatives of the region will be organized by the Ministry of Agriculture to enhance linkages. These will be arranged with a variety of partners based upon their area of expertise. Topics to be identified could include marketing, handling and transportation, food quality, water management, credit schemes, cash crops, organic market, linkages with agro-food processing industry and export avenues amongst others.

- Narrative reporting on results:

The Market TOR and maps where approved by UNDP HQ, and the bid was posted online on the UNDP website. Interested bidders are contacting the Project Manager and site visits are executed to ensure that the applicants are responding to the identified technical specifications. The dead line for submitting the offers is on the 27th of May 2014. The MoN representative is also joining the site visits and discussing the needs with the potential bidders in order to ensure that farmers will have a comfortable place to sell their products.

On the deadline, 8 companies submitted the technical and financial proposals, of which 4 offers were rejected during the preliminary examination due to the below reasons:

| BID 2 | Kabboud for Construction | Missing Implementation Timetable, No List of Shareholders, No Ranking from CDR or MPW, No CV of Staff, No Financial Statements, Some Reservations and additions to the BOQ |
| --- | --- | --- |
| BID 6 | LED | Missing Implementation Timetable, No Ranking from CDR or MPW, No Financial Statements, No Certificate of Latest Tax Payment, No Method Statement |
| BID 4 | United Infrastructure | No Ranking from CDR or MPW, No Certificate of Latest Tax Payment, No Organigram CV of Staff |
| BID 1 | Delta Eng | Missing Implementation Timetable, No Organigram, No CV of Staff, No Company Profile, No Financial Statements, No Method Statement |

The panel members were:

1.	Nada Sweidan, UNDP Programme Officer

2.	Hussein Nasrallah, UNDP Project Manager

3.	Vatche Boyadjian, UNDP Engineer - Consultant

4.	Mirvat Hammoud, UNDP Procurement Associate

The panel evaluated the four technically responsive offers and ranked the companies as follows:

| Name of Offerors | Country of Origin | Technical compliance (“Yes/No”) | Original Offer Price excluding VAT (US$) | Final/ Corrected Price excluding VAT (US$) | Ranking |
| --- | --- | --- | --- | --- | --- |
| 1. MEAMAR for Engineering and Development S.A.R.L. | Lebanon | Yes | US$ 768,221.11 | US$ 768,569.83 | 1 |
| 2.Lebanese Engineering Masonry Co. “LEMCO” | Lebanon | Yes | US$ 926,836.20 | US$ 926,836.20 | 2 |
| 3. Hanna Khoury and Brothers Co. s.a.r.l | Lebanon | Yes | US$ 1,071,858.00 | US$ 1,071,858.00 | 3 |
| 4. Al Bonyan Co. for Engineering and Contracting | Lebanon | Yes | US$ 1,085,051.00 | US$ 1,226,017.00 | 4 |

MEAMAR for Engineering and Development S.A.R.L is a Lebanese limited liability company specialized in contracting, operating since 1988 with an annual turnover of USD 15.6 million in 2012 and USD 17.6 million in 2013. MEAMAR has an Attestation/Certificate from the Ministry of Public Works as a Class B Buildings prequalified contractor by the ministry and an Attestation/Certificate from the CDR confirming that MEAMAR is prequalified by CDR for more than 1 million USD projects.  MEAMAR latest projects include: Solid Waste Treatment Plant in Nabatieh, Al Fakiha School and Public Gardens in Ghobairy. MEAMAR has 56 registered staff. The proposed project team consists of registered engineers. It is important to highlight that the evaluation was cleared by UNDP HQ after a thorough review and clearance of an independent engineer.  The contract was signed and excavation works started.

After several technical meetings with MEAMAR Company, they submitted all maps and documents requested by the UNDP engineer. The construction started by the beginning of September 2014 and all excavations works are finished. Furthermore, weekly visits to the site are being carried out by the UNDP engineer and Project team to ensure the full implementation of the project. UNDP Engineer is following up closely with MEAMAR on the advancements and implementation of the project on the ground. There is a close attention to all technical aspects of the projects from structural, electrical, mechanical and electrical details.

The latest results achieved on the construction site are the following: foundation finished and steel columns erected in Block B. In Block C the construction of the second floor is completed and inside works started. In Block D, the construction of the first floor is finalized. MEAMAR started the construction of the second floor. In addition, the list of needed equipment is prepared and procurement will start in the next quarter. The following pictures provide a visual on the progression of the project:

Figure - Block B: Excavations and foundation construction completed

Figure 2 - Block C: Construction of the second floor is completed.

Figure 3 - Block D: First roof finished and columns for the second roof erected.

To ensure the improvement of the agricultural extension services, UNDP project team is working closely with the Ministry of Agriculture and the Municipality of Nabatieh to schedule the training to farmers as well as procuring the needed equipment. In this respect:

- The Ministry of Agriculture representatives prepared the agenda for the training of the farmers and the cooperatives (Agenda attached).

- The Map of the cooling room was submitted to the Ministry of Agriculture in order to start the procurement process.

- The management board meeting as agreed with municipality of Nabateih and Ministry of agriculture will take place in the first quarter of 2015.

- Describe any delays in implementation, challenges, lessons learned & best practices: The process was delayed due to following factors:

  - The approval of TOR and maps from UNDP HQ was delayed

  - MEAMAR started the works mid of August 2014

  - The security situation in the area before and after Ashoura restricted the movement of the workers

  - To ensure proper delivery and installation of the requested equipment, the procurement process were delayed until the construction works are finalized.

Using the Programme Results Framework from the Project Document / AWP - provide an update on the achievement of indicators at both the output and outcome level in the table below. Where it has not been possible to collect data on indicators, clear explanation should be given explaining why, as well as plans on how and when this data will be collected.

|  | Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification |
| --- | --- | --- | --- |
| Outcome 1 | Local governance structures in target under-served regions strengthened for better representation, participation, and basic local services delivery |
| Output 1.1 Capacities of institutions, local authorities and community groups strengthened for effective formulation and implementation of social, environment and economic development plans in South Lebanon Indicator 1.1.1 Baseline: No farmers’ market is available in the region Planned Target: - Establishment of a wholesale vegetable and fruit farmers’ market in Nabatieh. - At least 175 farmers will benefit from the market. - Extension services accessible to farmers. - At least 4 thematic and technical trainings will be conducted. | Activity 1: A farmers’ market in Nabatieh is established Procurement process finalized and MEAMAR signed the contract with UNDP and started the works. Several technical meetings with MEAMAR company were held MEAMAR submitted all maps and documents requested by UNDP engineer Excavations works finished and construction started Weekly visits to the site Preliminary list of equipment prepared with the Municipality for procurement | Maps were changed based on the request of the Minister of Agriculture; The BOQs were changed based on the available budget for constructing the market; TOR and technical maps are still pending UNDP HQ approval. |  |
|  | Activity 2: Access to agricultural extension services is improved The Ministry of Agriculture representatives prepared the agenda for the training of the farmers and the cooperatives Several meetings with representative of MoA in Nabatieh. The Map of the cooling room was submitted to the Ministry of Agriculture in order to start the procurement process. The management board meeting as agreed with municipality of Nabateih and Ministry of agriculture will take place in the first quarter of 2015. |  |  |

# Footnotes

The term “programme” is used for programmes, joint programmes and projects.

Strategic Results, as formulated in the Strategic UN Planning Framework (e.g. UNDAF) or project document;

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as  “Project ID” on the project’s factsheet page the MPTF Office GATEWAY

The MPTF or JP Contribution, refers to the amount transferred to the Participating UN Organizations, which is available on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

Figures from the Agricultural Census 2011, Ministry of Agriculture and FAO

The extension service centre informs farmers about good agricultural practices such as how to improve the quality of crops, the control of pest and diseases, packaging, etc.

# Text boxes

ii) Indicator Based Performance Assessment: