[Name of Fund or Joint Programme]

MPTF OFfice GENERIC ANNUAL programme NARRATIVE progress report

REPORTING PERIOD: 1 january – 31 December 2014

| Programme Title & Project Number |  | Country, Locality(s), Priority Area(s) / Strategic Results |
| --- | --- | --- |
| Programme Title: Family support, justice and security. Programme Number: P1-02 MPTF Office Project Reference Number: 00081992 |  | (if applicable) Country/Region Iraq, Baghdad , Basra, and Erbil |
|  |  | Priority area/ strategic results Governance and Human Rights |
| Participating Organization(s) |  | Implementing Partners |
| Organizations that have received direct funding from the MPTF Office under this programme UNDP UNICEF |  | National counterparts (government, private, NGOs & others) and other International Organizations Family Protection Units at central level, Directorate for Combating Violence Against Women at Regional level. |
| Programme/Project Cost (US$) |  | Programme Duration |
| Total approved budget as per project document: USD 5,467,880 MPTF /JP Contribution: by Agency (if applicable) UNDP: USD 3,967,880 UNICEF: USD 1,500,00 |  |  | Overall Duration (months) 36 months |  |
| Agency Contribution by Agency (if applicable) |  |  | Start Date 9 March 2012 |  |
| Government Contribution (if applicable) |  |  | Original End Date 31 March2015 |  |
| Other Contributions (donors) (if applicable) |  |  | Current End date 30 September 2015 |  |
| TOTAL: |  |  |  |  |
| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| Assessment/Review - if applicable please attach Yes No Date: dd.mm.yyyy Mid-Term Evaluation Report – if applicable please attach Yes No Date: dd.mm.yyyy |  | Name: Nahid Hussein Title: Project Manager / Rule of Law, Human Rights and Access to Justice Participating Organization (Lead): UNDP Email address: nahid.hussein@undp.org |

# EXECUTIVE SUMMARY

In 2014, UNDP Iraq, as part of its larger programme addressing access to justice for women and survivors of Domestic and Gender-based Violence (DGBV), has achieved key milestones that resulted in significant progress of work which has positively contributed to the improvement of the delivery of justice services to/, refuge for/ and reintegration of victims of domestic and gender based violence which can be summarized as follows. The GOI and KRG capacity to combat DGBV has significantly strengthened through the provision of technical expertise, institutional development and capacity building programme. Through this support UNDP has contributed to the establishment of 7 Directorates for Combating Violence Against Women (DCVAW) in the KRG, in addition to 27 offices at provincial level in Kurdistan Region of Iraq, 1 Family Protection Directorate (FPD) and 16 Family Protection Units (FPUs) in each Governorate at the central level. As a result; the domestic and gender based violence national data-base for tracking cases of domestic and gender-based violence has been finalized and is now fully operational on both federal and regional levels where different reports can be generated to inform government policies and strategy. The Ministry of interior has sustainable allocations and human resources within its structure to ensure the continuity of the work. As a result of UNDP support, there has been a significant increase in the reported cases to FPUs and DCVAW, which have received a total of 13,998 cases in 2014 alone.

Capacity building programmes have been conducted targeting DCVAW and FPU staff and other stakeholders. Trainings have capacitated a total of 185 staff in different specialized areas relevant to data-base, provision of services to DV and GBV cases, communications and the role of legislations in combating violence against women. In addition, UNDP provided technical advisory support to DCVAW in the establishing training units within the Ministry of Interior (MOI). These training units will continue to provide capacity building to the newly deployed staff.

UNDP worked very closely with Ministry of Woman Affairs (MOWA) at federal level and Ministry of Labor and Social Affairs   (MOLSA) at regional level to assist with the adoption of the Shelter policy and strategy, through substantial support in drafting policy and strategy, which has been shared with the Ministry and CSOs for discussion and comments. Adopting shelter policy will help GOI and KRG to provide more protection for the survival of DGBV.

The project continued its technical advisory support aiming at policy reform and as a result the adopted Domestic Violence Bill in KRG is under revision, and a Draft of DV Law at federal level has submitted to the Parliament for adoption.

With regards to access to justice, significant progress has also been achieved through UNDP support. This includes the establishment of 6 court-based legal aid helpdesks in 5 cities of Iraq, in addition to the 6 legal assistance centers inside the IDPs and Refugees camps in KR-I and Anbar governorate as a part of UNDP response to the crisis situation and in direct collaboration with DCVAW. UNDP provided technical advisory and capacity building support to the CSOs and the Kurdistan Bar Association to ensure the relevant capacity for the free provision of legal aid support to vulnerable groups with special focus on women and children.  UNDP also assisted with the establishment of the referral system between KBA and DCVAW. This referral system will contribute to the institutionalization of the provision of these servicesto vulnerable groups and communities in Iraq. As a result of this effort and during 2014, 15,423 people have benefitted from the services of the legal help-desk throughout Iraq – 935 received full legal representation, 3,001 received one-one-on legal consultation and follow up, 1487 received  social services and 10,000 people received legal awareness and information.

Similarly, through technical and advisory support, UNDP assisted the drafting of the Legal Aid Law in KR-I, this law, once adopted, will ensure the institutional sustainability of the services.

UNICEF

UNICEF engagement in supporting the Ministry of Labor and Social Affairs in National Child Protection Policy has reached with significant milestone in 2014. UNICEF and MoLSA have engaged with an institutional contact with American University of Beirut (AUB) to develop National Child Protection Policy. The policy development has different phases. Notable results achieved is 2014 are a) Child Protection Situation Analysis completed b) Draft Child Protection Policy document completed.

# Purpose

Relevant NDP Goal(s): 9.1.4 Reform the economic and legal institutions to ensure equality in rights and opportunities for men and women (family laws, protection from violence, property ownership, employment, political rights and inheritance). Relevant UNDAF Priority Area Outcome: Priority Area 1: Improved governance, including protection of human rights. Outcome 1.3: Iraq has an improved legal and operational Rule of Law framework for administration and access to justice. Priority Area 5: Investment in human capital and empowerment of women, youth and children. Outcome 5.1: The Iraqi state has improved knowledge, attitude and practices regarding the roles and rights of women, youth and children in line with international conventions, the Iraqi Constitution and legislation. Outcome 5.5: The Iraqi state has institutionalized preventive and protective mechanisms to combat gender-based violence. UNDP Country Programme Outcome 2: Enhanced rule of law, protection and respect for human rights in line with international standards.

- In March 2009 the UNDP programme in the Kurdistan Region reported, while divorce may not be widespread, anecdotal evidence reveals that self-harm and suicide rates among girls and women are linked to gender-based violence. There are currently few public entities that are able to receive and support victims of gender-based violence, something, which this programme sought to address through the proposed Family Protection Directorates.

- In 2010 a survey conducted by OXFAM International, in collaboration with the Iraq Al-Amal Association of Iraqi women, revealed that approximately 60% of women in the sample of 1,700 indicated that safety and security continued to be their main concern; 40% indicated that their security had actually worsened compared to 2006 and 2007; 35% of the sample were female household heads; 55% of them stated that they had been a victim of violence; 22% had experienced domestic violence; and 45% indicated their income situation had worsened compared with previous years, with access to water, electricity and health care cited as major problems by most of the women respondents.

- UNDP Iraq, in coordination with the Bureau of Crisis Prevention and Recovery formulated the Family Support, Security and Justice in Iraq programme to further support the Government’s efforts in creating a strategy to ensure that survivors of domestic, gender based violence and trafficking are offered refuge and support. This project provides comprehensive technical and advisory support combined with extensive capacity development interventions of known key stakeholders in Iraq including the Ministry of Interior, Ministry of Labour and Social Affairs, Ministry of Woman as well as with non-governmental and civil society organizations and international support missions.

- This project is within Outcome 2 of the UNDP Country Programme 2011-2014 which is Enhanced rule of law, protection and respect for human rights in line with international standards and responds to three outputs within the CPAP 2011-2014 document.

| Outputs | Output 1: Policy and legislative reform supported for improved access to justice for gender based violence (GBV) survivors. Output 2: Enhanced law enforcement response to combating GBV and supporting GBV survivors and victims of trafficking. Output 3: National institutions strengthened to undertake social and economic empowerment and protection of GBV survivors. |
| --- | --- |
| Activities | Output 1: Policy and legislative reform supported for improved access to justice for GBV survivors. 1.1 Central Government and Kurdistan Regional Government are provided with legislative and policy support for improved family protection and law enforcement. 1.1.1 Specific advice and training for the core working group on how to address violence against women and children and victims of trafficking provided. 1.1.2 Support the promotion and activities of committee 80 to ensure their impact on the legislative reform in moving forward the agenda of family support, justice and security. 1.1.3 Support the core working group in the development of action plans and annual work and budget plans to further strategy on family support, justice and security. 1.1.4 Support awareness raising activities to promote the KRG strategy and to ensure their impact and moving forward the agenda of family support, justice and security. 1.2 Child Welfare Commission is supported with the development of Child Protection Policy. Output 2 Enhanced law enforcement response to combating GBV and supporting GBV survivors and victims of trafficking. 2.1 Central Government and Kurdistan Regional government are supported with the referral mechanism for the new Family Protection Directorates, police support units and CSOs. 2.1.1 Targeted training for Police from the Central Government and the Kurdistan Region. Training focuses on SOPs on how to run Family Protection Units (including study tours). 2.1.2 Empowerment of female police officers working in the newly established Directorates through targeted training courses and increased awareness. 2.1.3 Support the establishment of victim support units in police stations (Baghdad) to act as referral centres for the established Family Protection Directorates. 2.1.4 Develop/adapt training material on combating violence against women and children for police officers and social workers working in Directorates to ensure continuous training and sustainability. 2.1.5 Linkages developed between the Directorates and the criminal courts in their areas to ensure chain of evidence, i.e. testimony, preservation of physical evidence, necessary for successful prosecution - work with Criminal Court and the Social Research Department staff for capacity building in following up and handling cases. 2.1.6 Develop advocacy strategy highlighting the role of family support, justice and security. 2.1.7 Assess performance and impact of Directorates. 2.1.8 Organize multi-stakeholder workshops to disseminate lessons. 2.1.9 Support the development of an effective data base for newly established Directorates (design and training). 2.2 Relevant service providers have an enhanced capacity to deal with GBV cases. 2.2.1 Training for police, in particular female police officers, in interview techniques, investigations, forensics, chain of evidence, and how specifically to process cases of violence against women and children. 2.2.2 Trainings and advocacy for Ministry staff, Parliamentary staff, judges, lawyers and judicial staff on gender sensitive/human rights based approach methodology to addressing violence against women and children in relation to the workings of the Family Protection Directorates. 2.2.3 Organize awareness raising workshops on combating violence against women and children and the link with human rights and the rule of law. Encourage target groups to participate in policy reviews and improved legislative frameworks. 2.2.4 Trainings for health care workers, i.e. medical staff, counsellors, psychologists, on dealing with victims of violence. This includes developing of referrals protocols that will support the implementation of the CVAW programme and link up with the Directorates. 2.2.7 Organize trainings on the revised JTI and Police Academy curricula and train ToTs in the respective rule of law institutions on GBV and role of FPDs. 2.3 NGOs working on providing legal aid have an enhanced capacity on family protection and violence prevention. 2.3.1 Initial mapping and capacity assessment of NGOs providing legal aid nationwide to victims of violence. This includes the Iraqi Bar Association. 2.3.2. Support establishment of an effective referral system linking NGOs with Directorates and prosecution services which includes provision of financial and logistical support to NGOs offering legal aid to victims of all forms of GBV. 2.4. Relevant NGOs have an enhanced capacity on child protection issues Output 3: National institutions strengthened to undertake social and economic empowerment and protection of GBV survivors. 3.1 Development of shelter policy to the development of shelter policy at central and KRG level supported, participation of civil society ensured. 3.1.1 Policy advice and technical support given on shelter policy in both Central Level and the Kurdistan Region and the development of plan of action. 3.1.2 Develop a policy framework based on a situational analysis to facilitate the reintegration of shelter clients back into the community. 3.2 Female shelters and safe houses supported through institutional strengthening and capacity development. 3.2.1 Mapping of NGOs providing shelter or refuges to victims of violence, including advocacy and workshops. 3.2.2 Support to existing NGO managed shelters for victims of violence including a national conference for lessons learned. 3.2.3 Capacity building provided to shelter staff on management, budgets, resource mobilization, etc. 3.2.4 Develop/adapt training material on working with victims of violence for shelter staff (also to GoI). 3.2.5 Specialized training provided to shelter staff on dealing with victims of violence. 3.3 NGOs offering shelter support to women strengthened to provide referral support. 3.3.1 Provision of capacity building, financial and logistical support to NGOs providing support to women and women victim of violence that can act as referral centres. 3.3.2 Develop linkages with on-going UNCT economic empowerment/private sector development programs. |
| Procurement (major items) | Too early in the life cycle of the project. |

# Results

- Narrative reporting on results:

At the outcome indicators level, this project is showing a positive impact on the ground and adequate changes at policy and community levels. All development efforts through this project have positively impacted the policies related to combating violence against women as well as improving the lives of communities. The evidence for this change is best illustrated by the establishment of total of 16 FPUs, 1 FPD and 7 DCVAWs, as well as 12 legal aid helpdesks at federal and regional levels, defining the provision of services to women, including women and girls survivors of SGBV and Trafficking among Syrian Refugee and IDPs, as it provides a concrete model for the GOI and KRG to respond to DGBV. It has also led to the revision and improvement of Domestic Violence Bill in KRG, a draft of DV Bill in Baghdad, and a draft legal assistance Law in KR-I National capacity, especially of the of the FPUs and DCVAWs, as well as the law enforcement officers at the Ministry of Interior, have been significantly improved through trainings, development of strategic action plans, and most importantly the development of the national data-base for GBV and DV at the federal and regional levels. UNDP, through the implementation of this project, helped create the visibility and the focus needed for abused women and girls through the adoption of the adequate and relevant legal instruments to ensure the prevention and protection measures.

UNDP’s work has institutionalized part of the mechanisms to protect women survivors of DV and GBV; this is considered a significant step forward in the legal and institutional recognition of the need to protect the victim of DV and GBV. This has been achieved through drafting the shelter policy for vulnerable women with UNDP support, supporting MOLSA and MOWA in KRG and Baghdad with drafting and the adoption of shelter strategic framework, as well as the establishment of the first shelters for the survivors of GBV in both Baghdad and Basra governorates. Also drafting the first legal assistance law in KR-I targeting vulnerable groups and with special focus on victims DV and GBV is considered and significant step in this regard.

Output 1: Policy and legislative reform supported for improved access to justice for GBV survivors

UNDP continued to provide technical advisory support to the Domestic Violence Bill. On federal level UNDP continued to follow up on the progress made by the Committee of Expert, chaired by MOWA, the Draft of DV Law at federal level is submitted to the Parliament for adoption.  At regional level, UNDP organized number of meetings with the DCVAW, MOI, Kurdistan Judicial Council and selected members of the Regional Parliament to discuss the revision of Domestic Violence Bill, as a result and with UNDP support forum has been established between Judiciary and DCVAW for regular meeting and discussion on DV law and required amendment.

In 2014, the first national database for tracking cases of domestic and gender-based violence in Kurdistan region, as well as in central and southern Iraq has been finalized and launched which is now fully operational. The database is a milestone in Iraq’s efforts to tackle violence against women. Evidence-based information is pivotal to bringing changes at policy and community levels. The national database will constitute the single detailed source of information on domestic and gender-based violence to inform law enforcement, regional statistics and policy-making.

Remarkable steps have been taken to institutionalize the provision of the free legal aid services in Kurdistan Region, through the development and finalization of Legal Aid Law in KR-I, which is expected to be submitted and adopted by Kurdistan Parliament in 2015.  This will ensure the institutional sustainability of legal assistance by law. The law has been developed in close coordination and consultation with relevant counterparts including; Judicial Counsel, Ministry of Justice, Judge Union, KBA, DCVAW, Human Rights Board, legal committee at Kurdistan Parliament and CSOs.

UNICEF

UNICEF support to the Ministry of Labor and Social Affairs in developing National Child Protection Policy has reached with significant milestone in 2014. UNICEF and MoLSA have engaged with an institutional contact with American University of Beirut (AUB) to develop National Child Protection Policy. The policy development has different phases. Notable result achieved is 2014 are a) Child Protection Situation Analysis completed b) Policy option paper developed.

In partnership with American University of Beirut (AUB), the development of National Child Protection Policy (NCP) for Iraq is still in progress. As a crucial step in the development of the policy, MOLSA commissioned a situation analysis with support from AUB with the aimed of ensuring that policy development is informed by the situation of children in Iraq and lessons from previous policy development exercises, such as documentation and review of relevant legislations for children. Based on the outcome of the situational analysis, a consultative workshop aimed at discussing the identified gaps of the situation analysis, deliberating on other models of Child Protection Policies, including the need to take a system approach for the Iraq’s policy was organized by UNICEF and AUB on 27 February 2014 in collaboration with the members of the Child Welfare Commission (CWC).  The meeting resulted into:

- A discussion on four options model of policy from other countries which are similar in context, laws and cultural context like Iraq;

- It was agreed that MOLSA will study these four options policies and use the lessons from these policies to inform the development of the Iraq’s policy;

- AUB was requested to develop a Policy Options paper through the Iraq Situation analysis for children, literature reviews, collections of relevant data, deliberation with key stakeholders, including government, Civil Society and UN agencies in Iraq

As a follow up the recommendations above, AUB conducted the relevant consultations, reviews and developed a Policy Option paper. The Policy Option paper has been shared with UNICEF and MOLSA for review and consideration as contributing document to the development of the Iraq Child Protection policy. Both the Policy Option paper and the learning from the four options Child Protection from other countries will inform the working modality for the drafting of the Iraq Child Protection Policy.

Monitoring and Reporting Mechanism (MRM) on the grave violations of children’s rights in armed conflict.

In 2014, UNICEF, in collaboration with UNAMI, UNHCR and other agencies, supported the strengthening of networks of facilitators through the country and the capacity building of 1,548 (188 NGO staffs, 1320 MRM focal points from NGOs and volunteers, and 40 facilitators), including NGOs that are part of the USAID Access to Justice Programme. Through this extensive network, 825 incidents of grave violations reported, which constitutes 33% of the target, of which 690 were verified. The limited target of cases of grave violations monitored and reported is mainly due to limited access to ISIL controlled areas where the highest number of violations are taking place. As a result of the functional MRM system in all Governorates of the country, UNICEF has strengthened its capacity to monitor, document and verify gross child rights violations and to provide real-time information interventions and advocacy. Through the extensive networks of facilitators and services provided by UNICEF and other agencies, the 20% target for provision of appropriate services was achieved.

Output 2: Enhanced law enforcement response to combating GBV and supporting GBV survivors and victims of trafficking.

In 2014 UNDP extended its support at regional level to enhance the institutional capacity to combat domestic violence and GBV within the context support to MOI to establish training unit. Through this support UNDP worked to ensure that this training unit has the adequate organizational structure and required capacity to perform their duty, and UNDP initiated providing six trainings in different specialized areas relevant to data-base, provision of services to DV and GBV cases, communications and the role of legislations in combating violence against women targeting 158 male and female staff of DCVAW, in which 82 were police officers (26 female and 56 male police officers), 31 psychological and social workers (15 female and 16 male), 25 statistic and data analysis staff (7 female and 18 male) as well as 20 staff of the communication section (6 female and 14 male). The purpose of the training was to enhance the capacity of the staff in recording and reporting DV and GBV cases using the professional database developed by UNDP, providing service to DV and GBV cases and communication strategy through providing awareness raising about their services and outreach capacity. At the federal level UNDP organized a three day training on the Rights of Women and the Role of Legislations in combating Violence against Women, given by an international expert, that targeted Judiciary, Investigative Judges and Public Prosecutors that are assigned to deal with domestic violence cases. 27 participants benefited from the training (11 Female and 16 Male) out of them 11 Judges, 8 Public Prosecutors, 5 social workers and 3 DGs representatives of Judicial council.

As a result of the enhanced capacity of both FPUs and DCVAWs, particularly for recording and reporting DV and GBV cases, as well as on communication strategy a total of 13,998 cases have been reported during 2014 by all FPUs at federal level DCVAW at regional level.

In 2014, UNDP supported the implementation of the MoU signed with Kurdistan Bar Association (KBA), and the development of similar MoU with Iraqi Bar Association (IBA) in Basra. and as a result, a legal aid committee was established inside the bar associations.  UNDP supported the provision of legal assistance services by KBA and IBA through 4 court based legal help desks, targeting vulnerable groups with special focus on victims of GBV and DV. Discussion and negotiation is curretly ongoing with Union Jurists in Baghdad to sign similar MoU for the provision of legal assistance through the 2 court based legal help desks.  In addition UNDP facilitated the signing and supported the implementation of two MoUs between KBA and DCVAW in Duhok and Erbil governorates, and facilitated the establishing of a coordination and cooperation mechanism in Basra between IBA and FPU. The purpose of these MoUs and coordination mechanisms is to establish and strengthen an institutionalized referral system between these institutions. The KBA in KR-I and IBA in Basra are now providing free legal assistance to the survivors of domestic and gender based violence that are referred by DCVAW and FPUs. This practice will contribute to raising awareness of the lawyers on issues related to DGBV and ensure the engagement between relevant institutions to combat violence against women.

As a part of UNDP’s response to the crisis situation in the KR-I and Anbar governorates, 6 additional legal assistance centers have been established and are fully operational inside Refugee and IDP camps, targeting women and girls survivors of SGBV and Trafficking among the Refugee and IDPs. In the KR-I the legal centers are providing services in direct collaboration and involvement of DCVAWs through the deployment of specialized SGBV investigation officers providing follow up and investigation to the SGBV incidents when required. As a result, and with UNDP support, the capacity of DCVAW has been strengthened and their presence ensured for emergency response targeting women and girls survivors of SGBV among IDPs and Refugees.

In 2014, and through 12 court based legal helpdesks and legal center inside IDPs and Refugee camps, 15,423 people have benefitted from the services of the legal help-desk throughout Iraq – 935 received full legal representations (791 Female, 144 Male), 3,001 received one-one-on legal consultation and follow up (1952 Female, 1049 Male), 1487 received social services (1316 Female, 171 Male) and 10,000 people received legal awareness and information.

UNICEF

Effective referral system and legal assistance: In 2014, UNICEF implementing partner Human Rights Defenders Organisation has established a referral pathway between NGOs, Directorates and prosecution office. In total 132 children received legal assistance while 79 children provided with legal representation.

Output 3: National institutions strengthened to undertake social and economic empowerment and protection of GBV survivors

UNDP worked very closely with MOWA at federal level, and MOLSA at regional level, to assist the adoption of the Shelter policy. UNDP is also supporting MOLSA and MOWA in KRG and Baghdad with the drafting and the adoption of shelter strategic framework. At federal level, with UNDP support, MOWA has agreed to establish the first shelters for the survivors of GBV in both Baghdad and Basra governorates, an MoU has been developed by UNDP and signed with MOWA that provides a framework for cooperation and identifies the supports needed from UNDP regarding the shelter initiative such as developing the operation guidelines and referral system and capacity development support. At regional level, a committee has been established from relevant institutions which are Ministry of Education, Ministry of Health and High Council of Women, chairing by both MoLSA and UNDP to follow up on the adoption of the policy. The committee identified the shelter needs and agreed action plan for the adoption of the policy.

- Challenges, lessons learned & best practices:

The main challenge during 2014 was the political and security situation resulting from the ISIS conflict and the subsequent emergency and crisis situation (The Emergency Relief Coordinator of the UN declared a Level 3 emergency in mid-2014, the highest level of humanitarian emergencies) that imposed serious limitations and delay in the implementation of some activities. In addition to this, the parliamentary elections in Iraq and delay in the formation of Kurdistan Government impacted the timely implementation of some activities of the project.

The support to the development of the shelter policy targeting the victims of the domestic and gender-based violence continued to be a major challenge, particularly during the first half of 2014. Due to cultural barriers, the progress of the GOI in this particular area of work took longer than expected. Fortunately during the 4th quarter of 2014, UNDP efforts succeeded in making significant progress in this regard through MOWA agreement to establish the first shelters for the survivors of GBV in both Baghdad and Basra governorates, and the signature of MoU between UNDP and MOWA that provides a framework for cooperation and identify the supports needed from UNDP regarding the shelter initiative.

In Baghdad, the IBA represented a major challenge for the work of the legal aid helpdesks, as there is limited understanding of the legal aid concept within the IBA.  This has resulted in limited cooperation between Civil Society Organizations and Iraq Bar Association lawyers. To overcome this challenge, UNDP is continuing its discussion with IBA to find agree on a mechanism for cooperation and also working with other relevant counterparts such as Union Jurists in Baghdad to support the legal aid work.

UNICEF

The development of the Child Rights Law and Child Protection Policy encountered a major challenge since its inception.  A notable challenge was to identify qualified national policy advisor to support the process and the ongoing challenge with the changing political development and security situation in the country. It has delayed the drafting process. In order to address this challenge, UNICEF engages with American University of Beirut.  During a recent Annual Work Plan meeting on November 2014, UNICEF has agreed with the government to priorities finalisation of national child protection policy in 2015. Consultation with children, community and stakeholders is expected to be carried out in early 2015. Government of Iraq and UNICEF, together with American University of Beirut, have identified Al Rafdaeen University Baghdad to carry out the consultation with children, community and stakeholders at different level. American University of Beirut will work together with Al Rafdaeen University to provide technical guidance, training and analyse the result of the consultation. This process will lead to the finalisation of the Child Protection Policy in 2015.

- Qualitative assessment:

Key Achievements:

- Training course targeted 185 DCVAW and FPU staff and other stakeholders in different specialized areas relevant to database, provision of services to DV and GBV cases, communication and role of legislations in combating violence against women.

- National database launched and fully operational for both FPUs and DCVAWs.

- 6 courts based legal helpdesks established in Erbil, Duhok, Sulymaniah, Basra and Baghdad and 6 legal assistance and DCVAW centers established in main IDPs and Refugee camps in Erbil, Duhok, Sulaimany and Anbar governoartes and 15,423 people served.

- Referral mechanisms established between KBA and DCVAWs in KR-I and between FPU and IBA in Basra.

- Draft Domestic Violence Law at federal level is finalized submitted to the Parliament for adoption.

- Draft of Legal Aid Law finalized in KR-I.

- The first shelters for the survivors of GBV in both Baghdad and Basra governorates have been established and a MoU has been signed with MOWA.

- Shelter policy is finalized and adopted.

The Family Protection Units at the federal level and the DCVAW at the Regional level have gained adequate capacities to provide services to Iraqi survivors of DGBV and they are the sole	reporting mechanism for DGBV cases for the GOI and KRG. This has been ensured through series of trainings organized under this project and launching the first DGBV national database that enables MOI to share trusted information with other institutions such as MOLSA, MOWA, COR, MOP and CSOs.

As result of the implementation of this project, FPUs and DCVAW managed to attract the attention of the GOI, KRG and other actors, and increased numbers of reported cases, police female officers and female civilian staff have been confirmed.

UNDP finalized the draft of legal assistance law and is now advocating for the adoption of the law in KRG, upon its adoption the Regional Government financial resources will be allocated for such services.

Through the implementation of the MoU with KBA and IBA as a strategic partner, as well as establishment of referral mechanisms between KBA and DCVAW in KR-I, IBA and FPUs in Basra, institutional capacity of national institutions has been built and institutional mechanisms developed for the provision of legal assistance to vulnerable groups with special focus on survivors of GBV and DV which is crucial for the sustainability of legal aid work.

UNDP worked very closely with MOWA and MOLSA to assist the adoption of the Shelter policy and strategy, through the MoU signed with MOWA at federal level and coordination committee established between different relevant actors in KRG a strategic partnership and cooperation ensured for the adoption and implementation of shelter policy.

Using the Programme Results Framework from the Project Document / AWP - provide an update on the achievement of indicators at both the output and outcome level in the table below. Where it has not been possible to collect data on indicators, clear explanation should be given explaining why, as well as plans on how and when this data will be collected.

| JP Title | Family Protection, Support, Justice and Security for Survivors of Domestic and Gender Based Violence |
| --- | --- |
| UNDAF Priority Area | Priority 1: Improved governance, including protection of human rights. |
| Relevant MDG(s) | MDG 3: Promote gender equality and empower women. MDG 8: Develop a global partnership for development. |
| Relevant NDP goals | 9.1.4 Reform the economic and legal institutions to ensure equality in rights and opportunities for men and women (family laws, protection from violence, property ownership, employment, political rights and inheritance). |
| Relevant UNDAF Priority Area Outcome: 1.3: Iraq has an improved legal and operational Rule of Law framework for administration and access to justice. Outcome 5.5: The Iraqi state has institutionalized preventive and protective mechanisms to combat gender-based violence. |
| JP Outputs | UN Organization Specific Output (Applicable in case of JP) | Performance Indicators | Baseline | Target | Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Means of Verification |
| JP Output 1: Policy and legislative reform supported for improved access to justice for GBV survivors | 1.1 Central Government and Kurdistan Regional Government are provided with legislative and policy support for improved family protection and law enforcement | 1.1.1 Number of Family protection units staff trained on How to address violence against women and children and victims of trafficking | 1.1.1 0 | 300 | 393 FPUs and DCVAWs staff, senior management and law enforcement officers, have been trained on GBV and DV. . |  | 1.1.1 Training Report |
|  |  | 1.1.2 Percentage of trainees satisfied with the usefulness and relevance of training provided | 1.1.2 NA | 80% | 80% |  | 1.1.2 Trainees feedback and evaluation form |
|  |  | 1.1.3 Policy to address Family Protection and GBV drafted. | 1.1.3 No policy exists. | 1.1.3 Policy drafted and submitted for GoI/ KRG endorsement. | Anti-domestic Violence Bill is endorsed and adopted in KRG. Draft Anti Domestic Violence is submitted for endorsement in at Federal level. Strategic framework and action-plan for the FPUs at federal levels are endorsed and adopted. Shelter policy is developed at federal and regional level adopted by MOLSA and MOWA, 4 MoUs signed between UNDP, KBA, DfCVAW and IBA institutionalizing free legal aid services and establishing referral system. Legal Assistance Law drafted and being submitted to Parliament in KR-I. |  | 1.1.3 Policy document |
|  |  | 1.1.4 Number of raising awareness campaigns on the legislations related to family protection | 1.1.4 0 | 18 | 19 |  | 1.1.4 Programme Progress Report |
|  | 1.2 Child Welfare Commission is supported with the development of Child Protection Policy | 1.2.1 A study on violence against children completed | 1.2.1 No | 1.2..1 Yes | Child protection situation analysis completed |  | 1.2.1 Study report |
|  |  | 1.2.2 Child Protection Policy drafted | 1.2.2 No | 1.2.2 Draft Child Protection policy developed and ready to be submitted for endorsement. | Draft National Child Protection Policy paper developed. Country wide consultation planned in the finalization |  | 1.2.2 Policy document |
| JP Output 2 Enhanced law enforcement response to combating GBV and supporting GBV survivors and victims of trafficking | 2.1 Central Government and Kurdistan Regional government are supported with the referral mechanism for the new Family Protection Directorates, police support units and CSOs | 2.1.1 Standard Operating Procedures (SOPs) and Protocols. Manuals for Family Protection developed | 2.1.1 No SOPs and Protocols exist | 2.1.1. SOPs, manuals developed | Intake- forms have been developed at federal and regional levels, endorsed and adopted by FPUs in Iraq. Draft SOPs developed and adopted by FPUs. MoUs signed between DfCVAW and KBA have been signed to establish first institutionalized referral system between the two institutions. Training materials have been developed |  | 2.1.1 SOPs document |
|  |  | 2.1.2 Number of police staff (disaggregated by Sex) in central government and KRG trained on the Family Protection Units standard operating procedures | 2.1.2 0 | 2.1.2 300 | The Total of 126 Police officers have been trained (36 female and 90 male). Through the training units established within DCVAW additional trainings will be organized to reach the target by the end of the project. |  | 2.1.2 Training report |
|  |  | 2.1.3 Percentage of trainees satisfied with the usefulness and relevance of training provided | 2.1.3 NA | 2.1.3 80% | 80% |  | 2.1.3 Feedback forms |
|  |  | 2.1.4 Number of female police staff trained on how to respond to GBV and domestic violence | 2.1.4 0 | 2.1.4 100 | The Total of 36 female police staff have been trained. The trained cadre will conduct trainings targeting female police officer. |  | 2.1.4 Training report |
|  |  | 2.1.5 Percentage of trainees satisfied with the usefulness and relevance of training provided | 2.1.5 NA | 2.1.5 80% | 80% |  | 2.1.5 Feedback forms |
|  |  | 2.1.6 Number of victim support units in Police stations in Baghdad established, and referral centres | 2.1.6 0 | 2.1.6. 18 | 10 Units established in KRG. This target is on track. | Discussion is ongoing at federal level | 2.1.6 Programme progress report |
|  |  | 2.1.7 Number of CSO participating in the new Referral system at CSO level | 2.1.7 0 | 2.1.7 20 | 25 |  | 2.1.7 Programme progress report |
|  |  | 2.1.8 A Coordination process to establish Linkages between the Family Protection Directorates and existing Monitoring and Reporting Mechanism for Grave Child Right’s Violations (MRM) referral mechanism in place | 2.1.8 No | 2.1.8 Yes | 1538 825 gross violation of children rights reported in which 690 verified. |  | 2.1.8 Programme progress report |
|  | 2.2 Relevant service providers have an enhanced capacity to deal with GBV cases | 2.2.1 Number of Family protection units and directorates staff of disaggregated by sex) trained on how address to violence against women and children cases | 2.2.1 0 | 2.2.1 250 | 393 (176 female and 220 male) FPUs and DCVAWs staff, senior management and law enforcement officers, have been trained on GBV and DV. |  | 2.2.1 Training report |
|  |  | 2.2.2 Percentage of those trained satisfied with relevance and usefulness of training. | 2.2.2 NA | 80% | 80% |  | 2.2.2 Trainees feedback forms |
|  | 2.3 NGOs working on providing legal aid have an enhanced capacity on family protection and violence prevention | 2.3.1 Mapping and capacity assessment of NGOs providing legal aid to victoms of violence completed | 2.3.1 No | 2.3.1. Yes | Yes |  | 2.3.1 Assessment report |
|  |  | 2.3.2 Number of NGOs providing supported to provide legal aid services | 2.3.2 0 | 2.3.2. Fifteen (15) NGOs providing legal aid services 20 | 13 |  | 2.3.2 Programme progress report |
|  | 2.4. Relevant NGOs have an enhanced capacity on child protection issues | 2.4.1 Number of NGOs staff trained on child protection issues | 2.4.1 0 | 2.4.1 300 (100 social workers trained, 200 MRM Focal Persons monitoring and reporting child rights violations) | 1,548 (188 NGO staffs, 1320 MRM focal points from NGOs and volunteers and 40 facilitators) trained. |  | 2.4.1 Training report |
|  |  | 2.4.2 Percentage of trainees satisfied with the usefulness and relevance of training provided | 2.4.2 NA | 2.4.2 80% | 70 % |  | 2.4.2 Trainees Feedback forms |
| JP Output 3: National institutions strengthened to undertake social and economic empowerment and protection of GBV survivors | National institutions strengthened to undertake social and economic empowerment and protection of GBV survivors | 3.1 Number of CSOs involved in drafting of the Shelter Policy | 3.1 0 | 3.1 Five (5) NGOs working on shelter policy | 5 at federal and regional level. |  | Programme progress report |
|  |  | 3.2 Percentage of CSOs involved in the drafting fully satisfied with their level of engagement in drafting of shelter policy | NA | 3.2 80% | 80% | Rolled out to 2013 | 3.2 NGOs feedback forms |
|  |  | 3.3 Shelter policy reviewed and re-drafted in a participatory manner | 3.3 No | 3.3 Policy drafted | Shelter policy has been drafted in KRG and submitted for approval to MOLSA. Draft Shelter strategy has been shared with federal government |  | 3.3 Policy document |
|  |  | 3.4 Number of advocacy initiatives undertaken | 3.4 0 | 3.4 6 | Two High level meetings organized at federal and Regional level to discuss the Roadmap for the adoption of the Shelter policy | It is expected that the policy will be adopted by MOLSA by the end of the project. | 3.4 Programme progress report |
|  |  | 3.5 SOPs to provide effective shelter support and services re-drafted | 3.5 No | 3.5 SOPs drafted | Policy and strategic action plan for shelter developed and shared with MOLSA. other relevant offices and CSOs | It is expected that this activity will be completed by end of the project no-cost extension in 30 September 2015 | 3.5 SOPs document |
|  |  | 3.6 Number of government staff trained on shelter SOPs | 3.6 0 | 3.6 50 | Rolled out to 2015 | It is expected that this number will be reached upon the adoption of the shelter policy | 3.6 Training report |
|  |  | 3.7 Percentage of those trained satisfied with relevance and usefulness of training | 3.7 | 3.7 | Rolled out to 2015 | It is expected that this number will be reached by end of the project no-cost extension in 30 September 2015 | 3.7 |
|  |  | 3.8 Number of NGOs trained in providing shelter services to victims of violence | 3.8 0 | 3.8 15 | Rolled out to 2015 | This activity depends on the GOI decision to adopt shelter policy for GBV and DV victims. Discussion is ongoing | Training report |
|  |  | 3.9 Percentage of those trained satisfied with relevance and usefulness of training | 3.9 NA | 3.9 80% | Rolled out to 2015 | It is expected that this number will be reached by end of the project no-cost extension in 30 September 2015 | 3.9 Trainees Feedback forms |
|  |  | 3.10 Number of NGOs offering shelter support to women supported to providing referral service | 3.10 0 | 3.10 15 | Rolled out to 2015 | It is expected that this number will be reached by end of the project no-cost extension in 30 September 2015 | 3.10 Programme progress report |

iii) A Specific Story (Optional)

# Launch of the First Domestic and Gender based Violence Database in Kurdistan Region of Iraq

UNDP IRAQ and KRG Ministry of Interior during the launching Ceremony. Photo by UNDP Iraq 2014

UNDP and the Ministry of Interior launched the first database for tracking Domestic and Gender based Violence cases in Kurdistan.

During the last three years UNDP provided support to the Directorate for Combatting Violence against Women. The Directorate is the only regional institution mandated to receive and investigate domestic violence cases and provide services to the survivors. The UNDP support takes different forms that entail the institutional development of the Directorate as well as the long-term capacity building of the staff. The outcome of this initiative demonstrated positive impact on the ground and adequate changes at policy and community levels that offer new opportunities to explore how UNDP and the Ministry of Interior can strengthen their joint efforts to adopt a forward-looking and expanded support to enhance the capacity of the Ministry of Interior.

The database is considered a milestone in that it will constitute the only accurate source of information on domestic and gender based violence and informs the regional statistics and polices on issues related to domestic and gender based violence. Staffs are trained to effectively and efficiently manage and operationalize the database towards the institutionalization of using evidence based information.

His Excellency, Mr. Karim Sinjary, the Minister of Interior acknowledged and appreciated the strategic partnership with UNDP, highlighting the importance of “expanding the current support to different departments within the Ministry of Interior.”

UNDP will continue to provide support to the Ministry, the Directorate and the communities in Kurdistan to ensure that institutional capacities “are in place to respond to those who genuinely demand these critical services”, as stated by Dr. Adam Abdelmoula, UNDP Country Director.

------------------------------------------------------------------------------------------------------------------------------------

Launch of the first national database on domestic and gender-based violence

The first national database for tracking cases of domestic and gender-based violence in central and southern Iraq was today launched in Baghdad by the Ministry of Interior (MoI), the State Ministry of Women Affairs and the United Nations Development Programme (UNDP).

"Her excellency emphasized on the importance of the Domestic and gender based violence database program to helps all the relevant actors who are working on ending the domestic violence to update their annual plans, and evaluate and review their programs, which were missing in the planning over the past years."

The database is a milestone in Iraq’s efforts to tackle violence against women. Evidence-based information is pivotal to bringing changes at policy and community levels. The national database will constitute the single detailed source of information on domestic and gender-based violence to inform law enforcement, regional statistics and policy-making.

"We are strongly committed to strengthen the essential role the Iraqi institutions play to combat violence against women," Dr Adam Abdelmoula, UNDP Country Director said. “Access to proper information is key to policy and legislative reforms in this field.”

Since 2011 the UN development agency supported the Iraqi Family Protection Directorate, which is the reporting mechanism of the government for receiving and investigating cases of violence against women, and provides assistance to victims.

UNDP helped the directorate set strategies for implementing policies on gender-based violence, and trained staff and other stakeholders such as judges, legal professionals and civil society organizations in database management and use of evidence-based information.

In the future, UNDP and the Ministry of Interior will continue and join forces to strengthen the role of the Family Protection Directorate, to ensure that domestic and gender-based violence is combatted through a policy and legislative framework that is in line with international standards.

# Footnotes

The term “programme” is used for programmes, joint programmes and projects.

Strategic Results, as formulated in the Strategic UN Planning Framework (e.g. UNDAF) or project document;

The MPTF or JP Contribution, refers to the amount transferred to the Participating UN Organizations, which is available on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

# Text boxes

ii) Indicator Based Performance Assessment: