# Iraq UNDAF Fund

# Project # 82046: P1-03

# Date and Quarter: 1 April to 30 June 2015

# 2nd  Quarter 2015

| Participating UN Organisation: UNDP | Sector: Governance and Human Rights |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: The Iraqi Commission of Integrity |

| Title | Institutional Development of the Iraqi Anti-Corruption Academy |
| --- | --- |
| Geographic Location | Baghdad |
| Project Cost | $2,827,273 USD (including $ 100,000 UNDP TRAC) |
| Duration | 45 months |
| Approval Date (SC) | 08 February 2012 | Starting Date | 09 March 2012 | Completion Date | 31 December 2016 |
| Project Description | Considering that the legal and institutional anti-corruption framework has only recently been established in Iraq, there is a need to strengthen the institutional framework, and to streamline the laws and regulations that govern the mandates, powers, and interaction between the various anticorruption agencies. Legislative reform on its own will not be sufficient to combat corruption in Iraq, particularly if the personnel that are responsible for enforcing the law are not equipped with up-to-date knowledge and skills. This project will provide administrative and technical assistance to the newly established Anti-Corruption Academy, particularly with a view to enabling capacity building and knowledge development for the country’s anti-corruption agencies. |

Development Goal and Immediate Objectives

UNDAF: Priority 1 Improved Governance, including the protection of human rights. UNDP CPAP: Outcome 3 Strengthened regulatory frameworks, institutions and processes in place for accountable, transparent and participatory governance at national and local levels.

Output 1: Anti-Corruption Academy has sustainable organizational arrangements. Output 2: Relevant resources in place for the Anti-Corruption Academy. Output 3: Anti-Corruption Academy ability and capacity to deliver training established.

| Outputs, Key Activities and Procurement |
| --- |
| Outputs | 1. Anti-Corruption Academy has sustainable organizational arrangements. 2. Relevant resources in place for the Anti-Corruption Academy. 3. Anti-Corruption Academy ability and capacity to deliver training established. |
| Activities for Output 1: | A needs assessment carried out to determine the Academy’s administrative, operational, financial and sustainable requirements. Working session conducted to determine the Academy’s organizational structure |
| Activities for Output 2: | 2.1 Working session conducted to determine each faculty and centre’s requirements and staffing levels. 2.2 Various faculties set up and equipped. 2.3 Various centres set up and equipped. |
| Activities for Output 3 | 3.1 Sufficient and experienced national staff employed. 3.2 Programme curricula developed. 3.3 Training courses established. 3.4 Training sessions based on new training courses and curricula conducted. 3.5 Training session conducted for the Academy staff. 3.6 Training courses developed on line. |
| Procurement (major items) |  |

| Funds Committed as of 30 June 2015 | USD 1,320,524.33 1,311,975.53 + 8548) | % of approved of Tranche 1 & 2 including$ 100,000 UNDP Core Funds | 46.7 % |
| --- | --- | --- | --- |
| Funds Disbursed as of 30 June 2015 | USD 1,165,950,.52 | % of approved of Tranche 1 & 2 including$ 100,000 UNDP Core Funds | 41.24 % |
| Forecast final date | 31 December 2016 Approved no-cost extension | Delay (months) | 30 |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Oversight agencies in Iraq | 2,000+ |  |

| Quantitative achievements against objectives and results |
| --- |
| Output 1 Anti-Corruption Academy has sustainable organizational arrangements. | Anti-Corruption Academy structure identified. Needs assessment carried out The Anti-Corruption Academy official Directorate of the Commission of Integrity | % of planned | 100% |
| Output 2 Relevant resources in place for the Anti-Corruption Academy | Working sessions completed Setting up and equipping centers is still underway | % of planned | 69% |
| Output 3 Anti-Corruption Academy ability and capacity to deliver training established. | 20 curricula approved and textbooks published. The needs assessment to determine requirements for online training courses and IT applications completed. | % of planned | 74% |

Qualitative achievements against objectives and results

Output 1: Anti-Corruption Academy has sustainable organizational arrangements. Output 1 at the end of Q2 2014 The Commission of Integrity has approved the structure of the Anti-Corruption Academy (ACA). The ACA is an official Directorate of the Federal Commission of Integrity. Output 2: Relevant resources in place for the Anti-Corruption Academy. Output2 during Q2 2015 As a result of the revision of the needed IT applications which is the change of the application list, the allocated budget of this output had to be revised accordingly. Checking the approximate cost of the selected applications in the light of the financial ability of the ACA to maintain the licenses of the applications, and as per to prioritizing the needs of the ACA to implement its mandate, only two items from the original list remain, the ECM and the BlackBoard, that is after excluding the E-library one. The project management has designed a simplified pilot trials of the two applications to be partially implemented within the ACA for a period of month for each. A criteria were established to evaluate the pilot process in the middle and the end. Due to the mid evaluation, there was a necessity to extend each pilot for another month. Basically, the main reason for extending the ECM pilot was that the current approved organigram of the ACA was not applicable to be reflected on the system applying the delegations and the authorizations for the senior management, the system used to crash. This organigram was very different version from the one developed by the project at the early stages, unfortunately. The two pilots were concluded at the mid of June. Currently, the project team is working on the conclusions and recommendations after the pilot as well as waiting for the feedback from the ACA and the application provider. Output 3: Anti-Corruption Academy ability and capacity to deliver training established. Output 3 during Q2 2015 The CoI-ACA have finalized the second revision of the curricula at the end of the Q1 and recommended to be deposited for a specialized Arabic proofreading. Also, the CoI has formally requested the MoHE to form a committee to conduct a final revision of the curricula. Two national proofreading experts were hired for this purpose, the proofreading process will be started mid of April for a month (20 curricula) The final version of the curricula was received from the ACA. Then the curricula went through the process of the proofreading which is ongoing now. The specs of the books production were discussed with the ACA to comply with the ACA-CoI corporate standards of printing and found compatible with UNDP’s guidelines. The ToR for the print RFQ is under drafting. Board meeting took place on the 19 June 2015 where progress was reviewed. Outputs are in line with the original.

Main implementation constraints & challenges

Some major changes within the Iraqi public administration body affects the decision making process in the CoI/ACA. The recent change of the CoI commissioner caused delays in taking some decisions which are directly related to the project activities. The ACA remained open during the insecurity in 4th Quarter 2014. The unstable security and escalation of violence in Iraq has impeded access for students. Alternate locations for training of trainers may be either Erbil (if acceptable to the Federal Government) or Turkey. Alternative arrangements and close attention to security especially into the International Zone are being monitored.