RUNO ANNUAL PROJECT REPORT		TEMPLATE 4.4

PEACEBUILDING FUND (PBF)

ANNUAL PROJECT progress report

COUNTRY: South Sudan

REPORTING PERIOD: 1 january – 31 December

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: SKills and Employment for Peace Programme Number (if applicable) 00087878 MPTF Office Project Reference Number: |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UNIDO & ILO |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: National Ministry of Labour, Public Service and Human Resource Development State Ministry of Labour, Ministry of Cooperatives and Ministry of Youth Non Governmental Organizations |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) 1,553,886 |  |  | Overall Duration (months) 18 |  |
|  |  |  | Start Date (dd.mm.yyyy) 1 October 2014 |  |
| Government Contribution (if applicable) |  |  | Original End Date (dd.mm.yyyy) | 30 April 2015 |
| Other Contributions (donors) (if applicable) |  |  | Current End date(dd.mm.yyyy) 31 December 2015 |  |
| TOTAL: | 1,553,886 |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Assessment/Review - if applicable please attach Yes No Date: Mid-Term Evaluation Report – if applicable please attach Yes No Date: |  | Name: Ram Kishore Prasad SINGH Title: Chief Technical Advisor Participating Organization (Lead): UNIDO Email address: R.SINGH@unido.org |

PART 1 – RESULTS PROGRESS

  - Assessment of the current project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project is contributing:

Priority Plan Outcome to which the project is contributing. Improved economic and emloyment for young people.

Priority Plan Outcome indicator(s) to which project is contributing. access to business opportunities, income generation activities and employment , # of cattle-related inter-communal conflicts, # of youth and women with access to economic opportunities and income generation

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  Young men and women are more engaged in diversified economic opportunities based on skills gained

Rate the current status of the outcome:

| Indicator 1: Number of youth, men and women with access to business opportunities and income generation activities and employment. Indicator 2: # of target beneficiaries (youth and women benefiting from mobile/static training programme Indicator 3: # of new micro enterprises established or existing ones upgrated | Baseline: Youth men and women currently have extremely limited access to skills training and employment opportunities (data unavaliable) Target: 1,500 young men and women access learning and skills training opportunities Progress:79.33% (1,190 Young men and women trained). Baseline: No vocational and livelihood centres are currently fully operational in Jonglei State. Target: 1,500 beneficiaries trained Progress:79.33% (1,190 Young men and women trained). Baseline: Very few registered enterprises exist in Jonglei Target: 10 new micro industries established or existing ones upgrated Progress:0% |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

263 Young men and women (180 women and 83 men) trained in Dairy  in Jonglei State (Bor County) and Greater Pibor Administrative Area (GPAA) (Pibor, Gumuruk and Pochalla South Counties). 257 participant’s fishermen (209 men and 48 women) trained in fish processing and preservation in Jonglei State (Bor County) and Greater Pibor Administrative Area (GPAA) (Pibor, Gumuruk and Pochalla South Counties).

343 Young women and men (286 women and 57 men) trained in food processing and hospitality in Jonglei State (Bor County) and Greater Pibor Administrative Area (GPAA) (Pibor, Gumuruk and Pochalla South Counties). 182 participants (all 182 are men) trained in hides and skin in Jonglei State (Bor County) and Greater Pibor Administrative Area (GPAA) (Pibor, Gumuruk and Pochalla South Counties). 145 Young women and men (141 men and 4 Woman) trained in Solar energy concentrated primarily on installing solar panels, wiring of solar panel and system designer in Pibor, Gumuruk and Pochalla (GPAA).

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Vocational Technical skills training has strengthened capacity of young South Sudanese men and women in food processing & hospitality, milk processing; fish processing and preservation; processing of hides and skins and installation and maintenance of solar equipment.The training has created and promoted financial discipline among members in relation to proper planning, and proper utilization of regular savings. The training  has generated many business active groups, John Garang group, Bor town, and Peace group, Pibor, Gumuruk, Kornyice and Takbieth etc. Some groups are operating home based whereas some took it on full dimension with a small venue. In Pibor the group of women from food processing upon receiving the startup kits started bakery business in Pibor main market. The Minister of Culture, Youth and Sport admitted that the quality of bread in the market had improved due to the training received by this group of women.

In Gumuruk, the commissioner has confirmed the positive echo of the training in the Market. He affirmed that the community were handling the milk wrongly and now they have seen how valuable is the milk and how it can be processed to yoghurt and some high value products. He also said that the food processing group are appreciated for the good quality bread they produce and people like it more than the other types of bread in the market.

The engagement of fishermen in fish processing and preservation to gain a sound knowledge of basic principles of hygiene and sanitation in the processing of fish had certainly brought a positive change in the environment of fishing in the target area. The training has  given to the beneficiaries a better understanding of value addition fish products through hygiene and sanitation and improved processing at fishing location in Jonglei State and GPAA. Increased awareness of fishermen members about the importance of a sound handling of the fish and extended knowledge on fish conservation and transformation to important by products have contributed to more comfortable profit margins and better quality fish in the markets.

Linking knowledge to attitude and attitude to behavior and behavior to practice has been behind the noticeable change of the participants. They were exposed to sanitizing practice of the milking equipment using appropriate sterilizing liquids for milk equipment, the cattle keepers and traders experienced the benefits of working together in a team and gained an understanding of the requirements and benefits of a consistent joint approach to milk production. They were taught how to collectively operate in a value chain in order to sustain their businesses and consolidate their respective income and profit.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

The project was in its inception phase when violent conflict erupted and spread through various parts of the country in December 2013. The suspension of recovery and development work that resulted from the conflict caused a delay of over nine months to UNIDO and ILO's operations in the project. An assessment mission led by the UN RCO in June 2014 to newly created Greater Pibor Administrative Area (GPAA) from Jonglei State, as well as a more detailed UNIDO assessment of local conditions in the specific target areas of the project in July 2014 allowed for operations to start again. Since then, sustained and satisfactory progress has been made in project implementation. In addition, the long rainy season and inaccecibility to the project villages due to the poor road infrastructure constrained implementation of other planned activites.

Outcome Statement 2:  Economic opportunities and employment is generated for young men and women

Rate the current status of the outcome:

| Indicator 1: Number of youth and women with access to economic opportunities and income generation Indicator 2: # Youth and women benefit from the business training Indicator 3: # producer associations/cooperative societies provided training and support | Baseline: Youth and women currently have extremely limited access to skills training and employment opportunities (data unavailable) Target: 1,500 young men and women access learning and skills training opportunities Progress:25% Baseline: Significant business training has been undertaken in Jonglei State Target: 30 GET Ahead and GYI trainers 1,500 young men and women trained Progress:130% (39 GET Ahead and GYI trained) and 20% (300 young men and women trained) Baseline: 65 registered cooperatives in Jonglei State Target: 10 cooperative trainers and 20 new youth and women economic associations created and or supported to expand Progress:125% (25 Cooperatives Trainers trained in Jonglei State) 15% (3 new youth and women economic associations created) |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Market surveys, income generation and market-relevant business training and support to outreach services

Livelihood, employment and market opportunities baseline study conducted in the counties of Pibor, Pochalla, Bor, Twic East and Akobo, Jonglei state.

During September, a total of 15 young men and women ( 2 female and 13 Men)  trained on the ILO Module of Get Your Business Ideas (GYBI) in Juba selected from Jonglei State and GPAA (9 from Bor, 5 from Pibor and 2 from Pochalla).

Moreover, 24 young women trainers were trained on GET Ahead Module to Start Your Business in Juba. These participants were drawn from the Central Eqatoria (6) Jonglei State (7) and GPAA (Pibor 6 and Pochalla 5).

250 Young women entrepreneurs  trained on GET Ahead to Start Your Business in Pibor, Pochalla and Bor Counties (125 Bor, 75 Pibor and 50 Pachalla)

50 Young men and women trained in Bor & Pibor 25 each on Generate Your Business Idea (GYBI)

25 cooperative trainers trained in in Bor, Pibor and Pochalla.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Development of livelihood, employment and market opportunities baseline study document.

The training of trainers on business skills training has strengthened capacity of young South Sudanese men and women to transfer the knowledge and skills for the capacity building to others enterpreneurs in Jonglei and GPAA .The training has created and promoted business skills training discipline among members in relation to proper planning, and proper training techniques. The trainers have aspirations of starting the training on their own. Through the training programs of young men & women the social cohesion enhanced which is key to rebuilding tolerance and trust. Examples include trainers of trainers from Jonglei State and Greater Pibor Administrative Area (GPAA) interacting in training conducted has brought some truth telling within the group and interacted together during free hours.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

The ILO had duly initiated work prior to December 2013. In the face of spreading violence in Jonglei State, the ILO expert took cover within the UNMISS base of Akobo. On 17 December 2013 he was killed in the attack suffered by the base. Following such a tragic event, the ILO Director General ordered the departure of all ILO personnel from the country and the suspension of all ILO work in South Sudan. An internal investigation into the case was undertaken, in collaboration with DSS and UNMISS. At the conclusion of the investigation, an ILO security field assessment took place in April 2015 and ILO senior management decided to resume ILO's engagement in South Sudan.

While ILO had therefore initiated work on this project in a timely manner, this tragic incident and ensuing investigation and suspension in South Sudan caused a 16 months delay on ILO operations under this project. As soon as the suspension was lifted, a technical mission from its regional office in Cairo visited South Sudan at the end of April. The mission therefore approved the resumption of activities and determined the requirements of a No-Cost Extension to be submitted to PBF.

Measures taken by ILO:

ILO has fully established office in Juba, recruited staff to monitor the implementation, trained 39 GET Ahead and GYI trainers, 25 cooperative trainers to spear a head the training programs and employed backup consultant.

Outcome Statement 3:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 4:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender in the reporting period

| Evidence base: What is the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | The mobile livelihood skills training had created awareness among the beneficiaries on how to effectively utilize the available resources at their reach (animal and agricultural products, fish and sun power etc.) as sources of income. This training had changed the community behavior in the way of handling the daily lives and improves their hygiene practices. New business have been created because many bebneficiairies have already started their own business and those who were doing business had increased quality and production. Awareness created in regards to value added on animal products such as hide and skins. Peace and consistence among various communities enhanced through daily interactions during training hours. Team work and cooperation between various age groups created. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | The project filled critical funding gaps in peace building in the country because the initiative subscribes to the peace building support plan in support of the South Sudan Development Plan actions towards delivering technical and business skills training for young women and men. The low levels of socio economic development has directly contributed to involvement of youth in conflict. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | The Project could benefit only a limited number of participants where as the demand for vocational and business skills training is so high in the target community. Particularly with the fact that the area of GPAA has entered a peace phase that need to be consolidated by development programs. The important flux of demobilized children from the military groups advocates for more funding of youth training. UNICEF is willing to bring supplementary funds or advocate for more substantial support in order to work with UNIDO to enroll more Demobilized children soldiers. Moreover, UNIDO in partnership with FAO is planning to implement a new joint project on "Sustainable Food Security Through Community Based Livelihood Developnment" in the GPAA area effective early 2016. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | Engaging the services of line Ministries, developing wider partnerships with local authorities often identifed by their low capacities was innovative. Project tried to utilise services of the locally available human resources and build capacity of the local government for effective monitoring of the beneficiary groups. Organising a common training programme involving participants from different ethinic groups who were in conflict in the past helped achieve reduction in conflict and enhanced peace. |
| Gender: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | The original gender marker is still intact, the project will still assist young women empowering them and enable them increase their decision making and enhancing their capacities to enter into small trade and business activities through Mobile and static technical and business skills. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) |  |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (250 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Young men and women are more engaged in diversified economic opportunities based on skills gained | Indicator 1.1 # youth and women with access to economic opportunities and income generation | Young men and women currently have extremely limited access to skills training and employment opportunities (data unavailable) | Increase by 30% number of youth currently taking literacy classes in target counties 1,500 young men and women access learning and skills training opportunities |  | The suspension of recovery and development work due to Dec 15, 2913 caused a delay of over nine months to UNIDO and ILO's operations in the project. | Training will be finalised during the 1st quarter of 2016 |
|  | Indicator 1.2 |  |  |  |  |  |
|  | Indicator 1.3 |  |  |  |  |  |
| Output 1.1 Youth and women are provided with marketable technical skills | Indicator 1.1.1 # of target beneficiaries (youth and women) benefiting from mobile/static training programme | No vocational and livelihood centres are currently fully operational in Jonglei | 1,500 young men and women access learning and skills training opportunities | 1,190 young men and women with technical skills | As above | Training will be finalised during the 1st quarter of 2016 |
|  | Indicator 1.1.2 |  |  |  |  |  |
| Output 1.2 Appropriate support systems for the development of micro-industries that are tailored to the needs of groups and own account workers established | Indicator 1.2.1 # of new micro-enterprises established or existing ones upgraded | Very few registered enterprises exist in Jonglei | 10 new micro-industries established or existing ones upgraded | Not commenced | As above | Establishment will be finalised during the 1st quarter of 2016 |
|  | Indicator 1.2.2 |  |  |  |  |  |
| Output 1.3 | Indicator 1.3.1 |  |  |  |  |  |
|  | Indicator 1.3.2 |  |  |  |  |  |
| Outcome 2 Economic opportunities and employment is generated for young men and women | Indicator 2.1 # youth and women with access to economic opportunities and income generation | Youth and women currently have extremely limited access to skills training and employment opportunities (data unavailable) | 1,500 young men and women access learning and skills training opportunities | 25% young men and women with business skills | During 15 Dec 2013 conflict an ILO consultant was killed in Akobo. The Director General ordered the departure of all ILO personnel from the country and the suspension of all ILO work in South Sudan, causing delays. | Training will be finalised during the 1st quarter of 2016 All |
|  | Indicator 2.2 |  |  |  |  |  |
| Output 2.1 Income generation and market-relevant business training and outreach services | Indicator 2.1.1 # youth and women benefit from the business training | No significant business training has been undertaken in Jonglei State | 30 Get Ahead & GYI trainers 1,500 young men & women trained | 39 GET Ahead and GYI ToTs trained in business skills 300 young men and women with bussiness skills | As above | Training will be finalised during the 1st quarter of 2016 |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 Cooperative education and finance training | Indicator 2.2.1 |  |  |  |  |  |
|  | Indicator 2.2.2 # cooperative group undergoing training | Not available | At least 10 new cooperative established among women | 25 cooperative trainers trained with Cooperative skills 3 new youth and women economic groups | As above | Training and creation of groups will be finalised during the 1st quarter of 2016 |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | Women in Jonglei State (Bor County) and Greater Pibor Administrative Area (GPAA) (Pibor, Gumuruk and Pochalla South Counties) have a lot of useful ethno-knowledge of dairy that blend and compares very well with contemporary principles of milk processing. It was realized during this training that the communities especially the Bor community follows same principles of cheese making while preserving milk. It was therefore easy to learn together on these issues. |
| --- | --- |
| Lesson 2 (1000 character limit) | Hygiene and sanitation are huge issues in Jonglei State (Bor County) and Greater Pibor Administrative Area (GPAA) (Pibor, Gumuruk and Pochalla South Counties), direct observations and focused group discussions, histories and stories indicated that, a lot of work needs to be done to ensure observance of simple hygiene practices like using handkerchieves, covering mouth while coughing, excusing to step aside while sneezing, washing cow udder while milking etc. |
| Lesson 3 (1000 character limit) | Keep it simple. Strive to keep the project and technologies simple, inexpensive, and replicable with the least dependence on outside assistance as possible. This means using local materials and resources. This can result in lower production results but with less risk to fishermen and greater applicability. |
| Lesson 4 (1000 character limit) | Promote Self Reliance. The focus of projects is on what the community can do, not what the project can do for them. Caution is needed not to offer assistance until all local resources and initiatives are tried and prove to fall short. 'Ask not how can I help but how can you, the community, do this?' This adopted approach will nurture self-reliance and a “can do attitude” and keep away from the dependency syndrome which is all too common in South Sudan. It is important to highlight that the project is making clear from the start that we only provide technical assistance and facilitate accessing employment or business openings through some tool kits and entrepreneurial assistance. No allowance for attending or direct funds after training is provided. Although difficult, setting this tone early paid off by discarding the participants who requested such funds. This also helped to maintain in the program those with serious committment. |
| Lesson 5 (1000 character limit) | Engaging the community in all processes including selection of participants ensures sustainability. Results reveal that for peace building processes to be realized, communities need to be empowered and involved throughout the entire Program/Project processes. The involvement should not only be for those in leadership, or those with means but rather all stakeholders. Participatory development emphasizes that the people to whom a service is offered ought to be empowered to demand for their entitlements and need to be involved in all decision-making processes regarding the development action. The level to which an individual is active in particular community events and issues reflects the extent to which he/she is involved or included in advancing issues of common interest. It is through such collective efforts that community members share a sense of ownership of achievements realized. The community’s ability to build formal and informal networks is critical in realizing this goal. |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

The TOT on Generate Your Business Idea (GYBI) and GET A Head with Your Business (GYB) have been very effective in shifting the knowledge and attitude of the participants to peace building as it brought together communities who do not interact all the time. Trainings were very helpful for them to start friendships with other youth from other communities. At the start of the training, they not interested in talking to each. Training gave them a chance to speak with people outside of their community circle. The training helped them to realize that they were part of the society and as ordinary youth as others in the other communities. During those days of training it was clearly observed that the trainees were treating them equally and it helped them to build their confidence.

In Bor: Anyang Makuach Aluel is 33 year old lady and is a member of the John Garang group. Before this training she used to help her husband in their shop in Bor town. She occasionally used to make tea for customers. In the course of this training she went home with doughnuts and bread made during the learning process. The husband and children were very delighted with them. She started buying every time from the baking group. After the training the husband supported her to start producing bread and doughnuts along with the tea. Her business is taking off nicely. These are example of tangible outcomes of the practical training in the food processing and hospitality training.

In Pochalla: Two female business women Roda Gilo Obany (35) and Sham Bony Ajwany (37) said they were doing business of producing buns (mandazi) and the business was not making profit. When they joined this training they learnt how to make mandazi using good procedures. Production had improved.  With the same quantity of ingredients they produced double what we have been doing before. They are very happy because through the training, they are making more money with less cost.

Ojo Omot Deng (28) said he had been making bread long before but had a challenge on how to mix the right quantities of ingredients.  He said “I went to a neighboring country for a bakery course but I was not taught on how to use the right procedure and quantity especially when it comes to putting yeast and proofing process and timing” he was frustrated and returned home. Then he learnt about this course. In the course he was taught and shown the right procedures of making bread. And now he said “I am getting double profit”. Before with 50 kg of wheat flour he produced 13 trays, about 500 pieces of bread and now after the training he produce 25 trays that is about 1000 pieces of bread from the same quantity. He said “My costumers are very happy from the bread quality and I make more money too. I am very glad for UNIDO and the government for coming down to us and giving us this chance to learn skills”.

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures are on track, slightly delayed, or off track:

If expenditure is delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of expensed project budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: Young men and women are more engaged in diversified economic opportunities based on skills gained |
| Output 1.1 | Youth and women are provided with marketable technical skills | UNIDO | 713,369 | 628,008 |  |
| Output 1.2 | Appropriate support systems for the development of micro- industries that are tailored to the needs of groups and own account workers established | UNIDO | 184,361 | 124,191 |  |
| Output 1.3 |  |  |  |  |  |
| Outcome 2: Economic opportunities and employment is generated for young men and women |
| Output 2.1 | Market surveys, income generation and market- relevant business training and support to outreach services | ILO | 304,693 | 127,116.50 |  |
| Output 2.2 | Cooperative education and training, financial literacy and support to outreach services | ILO | 351,463 | 14,000 |  |
| Output 2.3 |  |  |  |  |  |
| Outcome 3: |
| Output 3.1 |  |  |  |  |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total: |  |  | 1,553,886 | 893,315.5 |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when); or whether any changes are envisaged in the near future (2000 character maximum):

ILO/UNIDO partners and public institutions have demonstrated their commitment to the project goals and planned results.

During the start-up of the project planning phase, the involvement and ownership of the National Ministry of Labor, Public Services and Human Resources Development and state government (Ministry of Labor and Human Resources Development, Ministry of Cooperatives and Rural Development and Ministry of Youth, Sports, Culture and Heritages has been exemplary.

ILO/UNIDO implements a vocational training skills initiative and works closely with public institutions partnering in this PBF grant to build linkages and leverage resources.

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.