RUNO ANNUAL PROJECT REPORT		TEMPLATE 4.4

PEACEBUILDING FUND (PBF)

ANNUAL PROJECT progress report

COUNTRY: Yemen

REPORTING PERIOD: 1 january – 31 December

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: IRF-71: Addressing grievance in the South (Yemen) Programme Number (if applicable) 00087896 MPTF Office Project Reference Number: |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UNOPS |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: UNOPS, Office of the Special Advisor to the Secretary General |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) $1,089,709.00 |  |  | Overall Duration (months) 12 |  |
|  |  |  | Start Date (dd.mm.yyyy) 01.10.2013 |  |
| Government Contribution (if applicable) |  |  | Original End Date (dd.mm.yyyy) | 01.10.2014 |
| Other Contributions (donors) (if applicable) |  |  | Current End date(dd.mm.yyyy) 31.03.2015 |  |
| TOTAL: |  |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Assessment/Review - if applicable please attach Yes No Date: Mid-Term Evaluation Report – if applicable please attach Yes No Date: |  | Name: Hasan Abujaber Title: Project Coordination Support Officer Participating Organization (Lead): OSASG Email address: HasanA@unops.org |

PART 1 – RESULTS PROGRESS

  - Assessment of the current project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project is contributing:

Priority Plan Outcome to which the project is contributing.

Priority Plan Outcome indicator(s) to which project is contributing.

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  Active, peaceful and constructive engagement of Southern factions in political transition

Rate the current status of the outcome:

| Indicator 1: Consistent participation of Southern delegates in National Dialogue and Constitutional Process, measured by withdrawal rate of Southern delegates Indicator 2: Southern support for National Dialogue and political process Indicator 3: | Baseline: N/A Target: <10% average across all WGs Progress:Achieved Baseline: N/A Target: Over 50% of political factions at the end of the National Dialogue Progress:In progress Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

First output: increased analytical/monitoring capacity to understand grievances, anticipate conflict. Second: increased engagement with Southern factions (meetings, facilitation). The Senior Political Affairs Officer (SPAO) consistently produced analytical reports covering major events relating to the transition progress, especially with regard to ermerging signs of conflict. The SPAO also produces regular updates each week. In August 2014 a Project Assistant was recruited in order to identify crucial gaps in the office coverage in terms of geography and key personalities involved in politics/civil society. The assistant makes regular visits across the South that the SPAO can not travel to for security reasons. These activities are key to producing a comprehensive stakeholder map of Southern political groups and personalities. Only two minor Hirak factions supported the NDC outcomes publically one year ago but now perhaps 1/3rd support the outcomes in private with guarantees.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Previously there had been little political engagement of Southern political actors. A number of the high profile, historic leaders based outside of the country were known to the OSASG and the international community but the street leadership, the popular forces and figures in society that were the real personalities behind the Southern movement had largely been ignored. This was due to a number of reasons, not least of which security, but also that engaging with separatist forces was feared to give them a large amount of legitimacy. As events moved ahead on the ground people became increasingly disillusioned with the international communtiy's interest or ability to bring any resolution to their political demands. This project has seen great efforts to engage with the whole spectrum of leadership in the South ranging from those figures aligned with the previous president, those with the current (both against separation), to those parties and people who reject anything but total independece for the South. In between, perhaps where the great majority of society lies, are tribal groups and leaders, civil society activists, local dignitaries - all of whom have been engaged by this office. This office contends that in itself this represents a major victory as its establishment has given an outlet to those forces to speak to a hitherto distant and disinterested international community. The legal basis for the activity of the office has been the outputs of the National Dialogue Conference. This has given no small amount of legitimacy and credibility for the office when engaging with actors from across the wide political spectrum. It is important to note that thus far not one faction has ever refused to meet with or speak to the representatives of the office. That in itself should be marked up as a major achievement in a fractious and emotionally charged, politically divided South.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Excellent progress is being made for this outcome.

Outcome Statement 2:  Tangible progress in concluding on solutions to Land and civil service related grievances implemented and accepted (and some high profile cases resolved)

Rate the current status of the outcome:

| Indicator 1: By end December 2013, xx high profile land cases and xx dismissal cases are resolved. Indicator 2: Indicator 3: | Baseline: Zero Target: 1,000 for both commissions Progress:As of Dec 2014, 8,000 cases fully processed, 2,000 cases ratified in total, out of estimated 250,000 received Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Two outputs: 1) Capacity of the Land Commission augmented and 2) Capacity of the Civil Service Commission augmented.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Both commissions have been supported by the provision of equipment, including furniture and CCTV equipment. A number of international experts have been sent on short missions to Aden to provide capacity building. Other UN agencies have also contributed to this effort, notably IOM and UNDP. The concept of establishing the two commissions was to grasp two of the primary concerns that had most contributed to fuelling the sense of grievance in the South. The problems surrounding the theft of prime real estate and agricultural land and the dismissal of thousands without recognition of their service or of adequate pensions were correctly identified as key to resolving the issues at the core of Southern feelings of marginalistion. The Dismissals Commission has worked very well to finalise cases (now in excess of 8,000) while the Land Commission has worked at a slower pace. Each commission has received in excess of 125,000 cases each. Of these 8,000 have been processed and ratified by the Dismissals Commission, and around 1,000 for the Land Commission.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

The primary block is the government. At this point they have not paid the salaries or running costs for the two commissions for the last quarter. The unpaid staff are also getting restless that they will become the object of people's frustration for lack of progress. The government was supposed to establish a supervisory body with a steering committee, including representatives of the OSASG and UNOPS but it has prevaricated. In addition, donor money was sent to the Yemen Central Bank and was agreed to then send it on to the UNOPS account to be under international supervision. The Central Bank have failed to forward this sum ($200 million) and the government has refused to expedite the process of setting up the mechanism and bodies to deal appropriately with the claims presented by the commissions. It is clear that there is a lack of political will from the various stakeholders in Sana'a to implement this. Thus far pressure from the OSASG has resulted in limited results and the office is aware that much more pressure needs to be applied to the Office of the President or the commissions will fail in their task.

Outcome Statement 3:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 4:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender in the reporting period

| Evidence base: What is the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | The OSASG had held a number of meetings with a few representatives from the South prior to the National Dialogue but there had been no clearly separated goal to engage them as a separate entity. This had led to a gap in knowledge of what groups, figures and organisations were out there as well as the gap that the people of the South felt in regards to international engagement. Many Southerners felt completely excluded from the NDC while the majority believed that the international community and the government in Sana'a did not want real representation to take part. That OSASG has met several hundred people representing a wide range of organisations that include meetings in every single governate from East to West in the South since the Senior Political Affairs Officer started work in May 2014 is a huge achievement. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | This Project does fill a critical funding gap and is the only Project that seeks to engage with political representation of leadership of the Southern movement |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | The project has not (yet) sought or achieved additional funding commitments. It is hard to quantify the effect of the efforts of the project in terms of accelerating the peace process. It is more accurate to say that the declining political situation in the South has been somewhat slowed by OSASG efforts. Without engagement the voices for separation would undoubtedly have grown louder. In the component supporting the capacity of the two commissions, the Project has identified interfaces with support provided by UNDP and IOM (with funding outside the Peacebuilding Fund) and regularly coordinates activities so to avoid overlap and to ensure synergies where possible. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | In and of itself, engaging with leadership within the Southern movement was risky enough. There are many players involved in the transition and certain groups fear that inclusive participation of representative groups in the NDC, the National Body and other official state institutions will lessen their grip on their own interests in the South. There are also many disparate factions of the Southern movement, each fighting for the right to say they are the legitimate voice. In reality they are trying to control the message and controlthe access of the international community to alternative voices, some of which are more popular than they would like to give them credit for. Thus from many sides the OSASG has many spoilers against their engagement with the broader society and the alternative groups. This engagement strategy is one which is highly risky for those reasons mentioned above. The pay off has been the formation of links and relations to popular voices and groups across the whole of the South. |
| Gender: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | There were no markers set down for gender in this project. However the OSASG has made every effort to engage with women's groups and has also listened to the voices of women academics and women representatives of the main Southern movement political parties. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) | At this point there are no other issues that have arised that need to be shared with PBSO. The idea is to build on the excellent progress made thus far. |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | The earlier that political engagement is sought the better the chances of success for peace building will be. Engagement with the Southern movement was late. Despite starting late on in the game, the OSASG has managed to rapidly build up a large amount of credibility among the various players in the South. |
| --- | --- |
| Lesson 2 (1000 character limit) | Manage expectations. Because this is the first time that there has been any concerted diplomatic efforts made at seriously engaging the Southern movement, people became very hopeful that the international community would address their issues by supporting calls for independence. From the start it was made clear that the basis for engagement was on the outcomes of the NDC rather than supporting independence. Nevertheless the OSASG was their to listen to their concerns. This early reality check ensured that hopes were not raised only to be dashed later. Even small mistakes in this regard would have crushed the credibility of the OSASG and ensured the office would not have been welcome to operate. |
| Lesson 3 (1000 character limit) | First of all conduct a stakeholder mapping exercise to be sure that all of them are engaged with so no one feels a sense of exclusion. There are many potential spoilers in the South and if any one of them felt particuarly excluded then they had the potential to make OSASG work almost impossible. This included the parties/people representing the North from the GPC and Islah, as well as the local, more extreme groups demanding immediate secession. |
| Lesson 4 (1000 character limit) |  |
| Lesson 5 (1000 character limit) |  |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures are on track, slightly delayed, or off track:

If expenditure is delayed or off track, please provide a brief explanation (500 characters maximum):

56% of the total budget has been disbursed with $474,870.

Please provide an overview of expensed project budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: Active, peaceful and constructive engagement of Southern factions in political transition |
| Output 1.1 | Consistent participation of Southern delegates in National Dialogue and Constitutional Process, measured by withdrawal rate of Southern delegates |  |  |  |  |
| Output 1.2 | Southern support for National Dialogue and political process |  |  |  |  |
| Output 1.3 |  |  |  |  |  |
| Outcome 2: Key high profile grievances in the South are resolved through a legitimate, non-discriminatory system |
| Output 2.1 | By end December 2013, xx high profile land cases and xx dismissal cases are resolved. |  |  |  |  |
| Output 2.2 |  |  |  |  |  |
| Output 2.3 |  |  |  |  |  |
| Outcome 3: |
| Output 3.1 |  |  |  |  |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total: |  |  |  |  |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when); or whether any changes are envisaged in the near future (2000 character maximum):

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.