RUNO END PF PROJECT REPORTING		TEMPLATE 4.5

PEACEBUILDING FUND (PBF)

END OF PROJECT report

COUNTRY: YEMEN

REPORTING PERIOD: END OF PROJECT REPORT

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: Woman & Youth engagement in Yemen's Political transition Programme Number (if applicable) PBF/IRF-73 MPTF Office Project Reference Number: 00087974 |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UNOPS, UNFPA, UN Women |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: OSASG as coordinating entity for UNOPS, UNFPA and UN Women |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) USD 95,559 for UN Women, USD 290,787 for UNFPA, USD 614,435 for UNOPS |  |  | Overall Duration (months) 15 months |  |
|  |  |  | Start Date (dd.mm.yyyy) 11 Oct 2013 |  |
| Government Contribution (if applicable) |  |  | Original End Date (dd.mm.yyyy) | 10 Jul 2014 |
| Other Contributions (donors) (if applicable) |  |  | Final End date(dd.mm.yyyy) 31 Dec 2014 |  |
| TOTAL: | $ 1,000,781 |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Mid-Term Evaluation / Review - if applicable please attach Yes No Date: End of project Evaluation– if applicable please attach Yes No Date: |  | Name: Hasan Abujaber Title: Project Coordination Support Officer Participating Organization (Lead): Office of the Special Adviser to the Secretary-General on Yemen (OSASG) Email address: HasanA@unops.org |

PART 1 – RESULTS PROGRESS

  - Assessment of the project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project has contributed:

Priority Plan Outcome to which the project has contributed. n/a

Priority Plan Outcome indicator(s) to which project has contributed. n/a

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  National Dialogue process concludes with outcomes that strengthen women’s rights and their political participation; reflected in the subsequent milestones in the political transition (Constitution, and post ND legislation) protecting these gains. This outcome falls under PBF outcome area "Promote coexistence and peaceful resolution of conflict"

Rate the current status of the outcome:

| Indicator 1: Final ND outcome document adequately reflects women’s concern(s) and ideas Indicator 2: Constitution contains provisions that strengthen women’s political participation and confirm to CEDAW Indicator 3: Electoral reforms contain provisions for women’s increased representation | Baseline: ND final report contains a provision on a quota for women in elected bodies Target: Yes Progress:Yes Baseline: 50% of CEDAW provisions enshrined in the new Constitution Target: 50% Progress:Consistution drafting process is still ongoing. Also, some CEDAW provisions were mentioned in the Rights & Freedom final outcome document for the ND. Baseline: Legislation to implement the outcomes of the ND and complete the political transition that contains adequate provision relevant to women’s rights, interests and representation is passed Target: Yes Progress:No. Due to the delays in the NDC, legislation to implement NDC outcomes and political transition process have not been completed at the time of the Project's end |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

- Women and Youth Forum was established to bring together women, youth and CSO components. The Forum held weekly meetings and focus group discussions for women from inside and outside the NDC, facilitated by international and national consultants

- Several workshops and conferences were conducted in and outside Sana’a in collaboration with NDI and FES on citizenship advocacy, supporting NDC outcomes in relation to women rights, youth and CSOs demands, and a women demands document from NDC outcomes was drafted to be submitted to the Constitution Drafting Committee;

- Drafted a road map for post NDC period for women, which was submitted to ND-Secretary General;

- A monitoring plan was developed to track the adoption of the demands document, recommendations and NDC outcomes during the constitutional process;

- Formal submission of recommendations on new and amended legislation not made, as the political process had not yet advanced to that stage.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

The project established a network of 62 national NGOs from all governorates to deliver and participate in the WYF activities. Commencement of the project during the NDC phase enabled the Forum to achieve direct impact on the work of the women constituency inside the NDC.

WYF, with UNOPS and OSASG support, provided administrative and logistical support for the activities. Weekly meetings started in August 2013 to discuss NDC women related outputs. Women from different political affiliations, independent women and women activists attended these meetings to ensure engagement of women from outside the dialogue and to ensure that all women issues were addressed and fed into the NDC working groups discussions. These meetings were facilitated by national and international experts on women issues and constitutional reforms.

With the early start that OSASG managed to cover, the inclusion of women rights and and political participation in the NDC was achieved. The project had a direct impact on the women constituency participation in the NDC, fruitful meetings with women from outside the dialogue summarised and captured issues which were fed into discussions of the NDC by the women constituency. Providing technical expertise on women issues and advocacy enabled the constituency to inline the women issues and create strategic plans for advocating women demands for constitution drafting. In all, this has contributed to legitimizing the outcome document of the dialogue among the women activists and civil society and will also have an impact on supporting peaceful political transition.

Mainly during the period after the successful conclusion of the NDC, five conferences and workshops were held in Sana’a and Aden covering different aspects including citizenship advocacy, constitution, support NDC outcomes and defining the women demands and a workplan advocating for the related ouputs to the NDC and constitutional process. Four of those conferences and workshops targeted women and youth constituencies. Two trainings were conducted in Sana’a and Aden, for civil society and women on dialogue and mediation and another training on communication and advocacy facilitated by international and national experts.

Two national consultants worked with the women constituency throughout the period and produced a document on the women demands, stating all women issues in the NDC outcome document and the key issues and concerns to be submitted to the NDC's General Secretary. The document was presented in two large conferences - one for the preliminary document and then for the mid-review.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

More outreach and advocacy in the governorates was planned for the project during the NDC phase through coordinating OSASG activities with UNFPA. This was not achieved because the funds were received only in mid-October when a large part of the conference was already completed and when the UNFPA/UN Women annual work plans were already closed. More engagement of civil society in other provinces started early in 2014 continued throughout the remainder of the project period.

Outcome Statement 2:  National Dialogue process concludes on outcomes that strengthen the political participation of youth; reflected in the subsequent milestones in the political transition (Constitution, and post ND legislation) protecting these gains./ This outcome falls under PBF outcome area "Promote coexistence and peaceful resolution of conflict"

Rate the current status of the outcome:

| Indicator 1: Final ND outcome document adequately reflects youth concern(s) and ideas Indicator 2: Constitution contains provisions that strengthen youth political participation Indicator 3: Electoral reforms contain provisions for women’s increased representation | Baseline: Recommendations for stronger youth political participation in NDC final Outcomes document Target: 5 Progress:Yes Baseline: Constitution specifies youth as a target for strengthened participation in elected bodies Target: Yes Progress:Constitution drafting process is still ongoing. Baseline: Electoral legislation that contains adequate provision is passed Target: Yes Progress:No, electoral legislation will only be prepared after the constitutional referendum, now scheduled for March 2015 |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

- Regular weekly meetings for the youth constituency from inside and outside the NDC facilitated by national and international consultants to determine the outputs relevant to the NDC and Constitutional process.

- Several workshops were conducted and  facilitated by national and international consultants to discuss the proposals for the new constitutional process and positions for the constitution to address.

- A final document for Youth vision on the new constitution was produced in tandem with the outcome document  to be submitted to the CDC in the next stage. A monitoring plan is developed to ensure implementing the youth recommendations and NDC outcomes document during the constitution drafting.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

With the early start which OSASG managed to cover through other PB funds, the project had a direct impact on the youth constituency participation during the NDC and made the participation more transparent and inclusive, key issues of youth political participation were addressed in the dialogue and included in the outcome document, which has participated directly to the peaceful political transition plan of the GCC Initiative. With ensuring the successful engagement of the youth and NGOs working on the youth concerns, coherent understanding of the peaceful political transition and citizenship will evolve among the youth constituency, which will also have greater impact on the next phases of drafting the constitution and elections.

With technical support from OSASG and operational support from UNOPS the WYF hosted regular weekly meetings for the youth constituency from inside and outside the NDC starting in July 2013. Structured discussion were facilitated by national and international consultants on youth, communication and constitutional law.  Discussions were around youth concerns and representation in the NDC working groups and with the guidance of the technical expertise, messages and platforms were developed. Those meetings assisted in harmonizing and articulating the youth constituency participation in the different working groups and inclusion of the youth visions from outside the dialogue.

Under this project, 3 workshops and conferences on the NDC outcomes, youth visions of the new constitution, advocacy and constitution were conducted for the youth constituency. The network took part in most of the youth activities to advance the youth voices. Conceptions were received through other activities targeting youth in Sana’a and other governorates.

Training on creating advocacy and communication campaign plans was conducted to build the youth and civil society capacity to enable them create an advocacy plan and design a communication campaign and to set out a mechanism to reach out to youth on the constitution and the NDC outcomes document in the next phase.

A document articulating the youth vision for the constitution was developed by the youth constituency during the WYF regular meetings with the guidance of national and international consultants. This document was developed in tandem with the outcome document of the NDC with the youth recommendations to be submitted to the CDC in the constitution drafting process. A committee of youth has been established to monitor the implementation of the NDC outcomes document and youth recommendations in issues related to youth rights and political participation.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

More outreach and advocacy in the governorates was planned for the project during the NDC phase with OSASG in coordination with UNFPA. This was not achieved due to the late project approval and transfer of funds. More engagement of civil society in other provinces will start early in 2014 and will continue throughout the project.

Outcome Statement 3:  National Dialogue Conference (NDC) outcomes, draft Constitution and subsequent related legislation reflect the concerns of women and young people across all regions of Yemen and all social profiles./ This outcome falls under PBF outcome area "Promote coexistence and peaceful resolution of conflict"

Rate the current status of the outcome:

| Indicator 1: Percentage of eligible voters voting in the referendum (disaggregated by gender). Indicator 2: Indicator 3: | Baseline: 65.1% of registered voters (in Presidential election) Target: 65% (of which 45% women) Progress:The referendum has been delayed beyond the end date of this Project. Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

UNFPA started project implementation under outcome #3 of the IRF project document since January 2014. Its related outputs is aiming at reflecting the views of women and youth through a survey, conducted network of NGOs/CSOs, by feeding into the NDC and especially in relation to the Constitution. The implementation focused on achieving the following:

1- The views of women and men on the  National Dialogue recommendations are collected.

2- The capacities of implementing partners and CSOs at the governorate level are improved in terms of collecting opinions from specific targeted groups, outreaching specific targeted groups of the population.

3- Women and youth are informed about the recommendations of the National dialogue, issues related to women and youth. In addition to the identified output, UNFPA supported the CDC with legal expertise on women rights and the Constitution.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

The relevant networks of NGOs/CSOs are identified and provided assistance to adequately relay women and youth concerns at decision high making level.

The  implementing partner,  All Girls and their network, have a previous track record in supporting UNFPA collecting voices of women and youth for the National Dialogue Conference; they have the ability to ensure quality data collection and analysis of the issues at hand. Their skills were deepened through trainings provided by an expert in order to ensure good quality of data collection. UNFPA Yemen has been providing technical guidance and coaching the IPs to setting up focus group meetings with  the women and youth at governorates level.  The selection of the sample, the methodology, the manual, and the questionnaire of the polling were developed with the support of a national expert and several trainings were conducted to the field workers from different CSOs at governorates level. The polling survey was conducted throughout Yemen, covering all governorates and targeting 4500 men and women (42% male and 58% women). Only one polling survey was conducted instead of the two envisioned as it was more relevant to the project implementation to quickly gather information on population opinions. The polling results report is about to be finalized.

Based on the results of the polling survey, manual were developed in order to conduct outreach information  campaign at governorates level, on women and youth rights. A ToT training in coordination with the General Secretariat for the National Dialogue targeted 46 trainees from across the country.  The trainees were selected based on certain criteria to make sure that they have the capability to conduct the same training at their governorate.therfore, the trainess will replicate the same training at the governorate level to train community educators from the district level to raise their awarness of women rights.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

While initial delays in funding meant that UNFPA was able to commence activities only in early 2014, this was accomplished through a no-cost extension, also benefitting from the delays on the political front.

A second challenge was the absence of UN Women in Yemen. Relevant project inputs were shifted and absorbed by UNFPA.

Outcome Statement 4:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender at the end of the project

| Evidence base: What was the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | In this project all of the conferences and workshops had intensive media coverage. National and international TV, news websites and newspapers releases. Attached is a list of some articles on line and a list of the media covering the WYF activities. Photos of workshops and events are available (three selected ones are attached), in addition to the attendance sheets and minutes of meetings. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | Yes, the project filled a gap in funding. Structuring the women and youth participation as caucuses in the dialogue was essential and no one had interest in providing support of any type to help the constituencies come together. On the other hand, other constituencies had resources and expertise to unify their participation and structure the two constituencies participation. Without the IRF Funding for the activities conducted by this Project in 2013, essential activities to strengthen women and youth participation in the political discussions would not have taken place. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | The Project did achieve some catalytic effects within the short period of implementation in 2013. At this stage, no additional funding commitment was attracted, even though the UNFPA/UN Women activities were programmed within the larger funding framework of both agencies for 2014, so that synergies and other catalytic effects are anticipated. Project activities did contribute to on-going dialogue and negotiations directly relevant to the political transition process by bringing the women and youth from inside and outside the NDC together to participate as caucuses. Engaging women and youth from outside the dialogue and civil society in those discussions through the WYF enabled exchanging experiences and opened space for women and youth to identify their needs and views to create unified platforms for their participation. By building their capacity to advocate their demands and the outcome document and assisting them to monitor the implementation, the women and youth awareness and support to the peaceful transition will definitely increase all around Yemen. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | The Project did not support any innovative activities. A challange was to keep the two constituencies neutral, constructive and focused on the benefit for Yemen women and youth and put aside the political affiliations position. WYF found itself caught up in the middle of heated political debates. By losing transparency and neutrality regarding women and youth related issues, a risk was that women and youth around the country rejecting the final demands documents . As a consequence, the demands documents will lose crediblility to be advanced to the CDC when those demands are not agreed upon among the women and youth of different affiliations. To overcome that, the forum ensured cross-sector participation of women and youth. Some of the most difficult situations were having to deal with strong confrontations and debates between activists who are against for-change and their opponents. Especially the women component , sub-side meetings took place between the forum and those members to resolve the issues and find common ground and language to use that suits both sides. This also happened continuously during the smaller discussions with youth and women who were in the constituency but had a political affiliation and was solved. With all these efforts the forum managed to produce the final documents of the women and youth demands and visions after consultations and acceptance of women and youth as a caucuses;in dependants and politically affiliated and activists all together. |
| Gender marker: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | The project gender marker has not changed. The targeted group is women and youth and both groups have benefited from the project activities. The classification is still on level 2 for the gender marker. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) |  |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | Joined outreach coordination of the UN and international actors: In July 2013 while the NDC was ongoing and the women and youth participation was notably out of structure, the project proposal was still under revision and was not approved yet. Thus the need for an intervention to assist women and youth constituencies was still critical. The OSASG had some resources to establish the Women and Youth Forum but with limited capacities. The forum identified national and international partners like Friedrich-Ebert-Stiftung and the NDI project who had some resources and developped joint interventions. |
| --- | --- |
| Lesson 2 (1000 character limit) | Women and youth affiliations and mediation: Most of the women and youth constituencies had a political affiliation, and by representing the women and youth constituency in the dialogue, it was essential that the women and youth representations should not be politically driven. It was therefore necessary to design and organize workshops and meetings in a way that would anticipate political agendas and to incorporate elements to allow for negotiation and for focus on technical aspects. |
| Lesson 3 (1000 character limit) |  |
| Lesson 4 (1000 character limit) |  |
| Lesson 5 (1000 character limit) |  |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures were on track, slightly delayed, or off track:

If expenditure was delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of project expensed budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: National Dialogue process concludes with outcomes that strengthen women’s rights and their political participation; reflected in the subsequent milestones in the political transition (Constitution, and post ND legislation) protecting these gains. This outcome falls under PBF outcome area "Promote coexistence and peaceful resolution of conflict" |
| Output 1.1 | Regular and substantive participation of a representative cross-section of women in Women and Youth Forum activities. | UNOPS | $65,368.00 | $85,368.00 |  |
| Output 1.2 | Women’s concerns and common positions raised through the Forum appropriately fed into the political process. | UNOPS | $183,458.00 | $163,458.00 | exprts cost was less than planeed because it was covered from other projects to save additional funds for the Forum activities |
| Output 1.3 | Recommendations on strengthened women’s participation fed into the constitutional drafting process and all legislative follow-up to the National Dialogue. | UNOPS | $40,646.00 | $40,646.00 |  |
| Outcome 2: National Dialogue process concludes on outcomes that strengthen the political participation of youth; reflected in the subsequent milestones in the political transition (Constitution, and post ND legislation) protecting these gains./ This outcome falls under PBF outcome area "Promote coexistence and peaceful resolution of conflict" |
| Output 2.1 | Regular and substantive participation of a representative cross-section of youth in Women and Youth Forum activities | UNOPS | $65,368.00 | $97,273.00 |  |
| Output 2.2 | Youth concerns and common positions raised through the Forum appropriately fed into the political process. | UNOPS | $216,651.00 | $186,651.00 | exprts cost was less than planeed because it was covered from other projects to save additional funds for the Forum activities |
| Output 2.3 | Recommendations on strengthened youth participation fed into the legislative process and all legislative follow-up to the National Dialogue. | UNOPS | $40,646.00 | $40,646.00 |  |
| Outcome 3: National Dialogue Conference (NDC) outcomes, draft Constitution and subsequent related legislation reflect the concerns of women and young people across all regions of Yemen and all social profiles./ This outcome falls under PBF outcome area "Promote coexistence and peaceful resolution of conflict" |
| Output 3.1 | Views of women and youth throughout Yemen surveyed fed into the NDC (through scaled up outreach, survey and canvassing of views of women and young people across the country), through a network of NGOs/CSOs | UNFPA | $ 290,787.00 | $ 290,787.00 |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total |  |  |  |  |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when) (2000 character maximum):

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.