RUNO ANNUAL PROJECT REPORT		TEMPLATE 4.4

PEACEBUILDING FUND (PBF)

ANNUAL PROJECT progress report

COUNTRY: Nepal

REPORTING PERIOD: 1 january – 31 December

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: Increasing the Safety of Journalists Programme Number (if applicable) PBF/NPL/A-3 MPTF Office Project Reference Number: 00085992 |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: United National Educational, Scientific and Cultural Organization (UNESCO) |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: Ministry of Information and Communications (MoIC), National Human Rights Commission (NHRC), Federation of Nepali Journalists (FNJ), Freedom Forum, Sancharika Samuha, Association of Community Radio Broadcasters(ACORAB), Informal Sector Service Centre (INSEC), Women's Rehabilitation Centre (WOREC), Nepal International Media Partnership (NIMP) |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) USD 566,000 |  |  | Overall Duration (months) 24 |  |
|  |  |  | Start Date (dd.mm.yyyy) 01/03/2013 |  |
| Government Contribution (if applicable) |  |  | Original End Date (dd.mm.yyyy) | 30/02/2015 |
| Other Contributions (donors) (if applicable) |  |  | Current End date(dd.mm.yyyy) 30/12/2015 |  |
| TOTAL: | USD 566,000 |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Assessment/Review - if applicable please attach Yes No Date: Mid-Term Evaluation Report – if applicable please attach Yes No Date: |  | Name: J.B. Biswokarma Title: Project Coordinator Participating Organization (Lead): UNESCO Email address: jb.biswokarma@unesco.org |

PART 1 – RESULTS PROGRESS

  - Assessment of the current project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project is contributing:

Priority Plan Outcome to which the project is contributing. Citizen’s confidence in security sector institutions has increased as a result of these institutions becoming more capable, accountable and responsive to Nepal’s diverse society

Priority Plan Outcome indicator(s) to which project is contributing. 1. Decrease in practice of self-censorship on reporting of sensitive cases and topics in project districts. 2. Media professionals believe there is increased freedom of expression because of diminishing security threats in project districts.

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  The NHRC, professional media associations, state agencies and civil society (including political parties) join hands to establish a nationally owned mechanism that ensures a safe environment for journalists.

Rate the current status of the outcome:

| Indicator 1: a. An independent mechanism for safety of journalists and free expression evolves to be an efficient node for dealing with the safety of journalists and impunity, and to investigate violations of freedom of expression in a gender sensitive way. Indicator 2: b. Professional institutions have the capacity to enhance the safety of journalists and deal with cases of impunity. Indicator 3: | Baseline: NHRC unable to implement original concept developed in 2012 to establish a mechanism for the protection of journalists. The current concept note for the mechanisms includes protection only for journalists Target: The concept note elaborated to stakeholders by applying recommendations of the national and regional consultations. Progress:Concept note on functioning of the independent mechanism prepared, discussed and revised, discussions and consultations ongoing on institutional design and creation. NHRC officials discussed on international experiences of the such mechanism. Baseline: No cases received. Target: 0% of the registered cases be investigated by the mechanism. Progress:Status and capacity of established media rights violation monitoring and response desks of professional organizations analyzed. Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

UNESCO along with the International Media Mission consulted along with the various stakeholders to establish an independent mechanism dealing with safety of journalists and the issue of the impunity. A term of reference, participation modalities, rules of procedures, funding etc. has been prepared. Code of conduct for handling cases related to attaches on media and journalists for security agencies have made, and an operational guidelines for the rapid intervention task force (RITF) for safety of journalists and free expression in coordination has made in partnership with the concern stakeholders. The policies related to the free expression and safety of journalists and complain handling process and guideline for the mechanism were reviewed. The regulation for enabling NHRC to establish the proposed mechanism was drafted and a policy document on creating and operationalizing the Rapid Task Intervention Force (RTIF) at NHRC under the proposed mechanism was drafted.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

The National Human Rights Commission (NHRC) has endorsed the agenda of establishing an independent nationally owned mechanism to address the issues of impunity and increasing the safety of journalists in the five years strategic planning. The ToR of the mechanism has accepted by the all stakeholder that was finalized after the regional and national consolation including the International Media Mission in Nepal in 2015. It has seen that the mechanism which is being established in Nepal, and which is the first of its kind in South Asia, could serve as a model for other countries. The mechanism has foreseen that will contribute to increase the security of journalists, promote the freedom of expression and deal the issues related to the impunity which contributes the peacebuilding process.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

A mechanism for security of journalists and address the issues of impunity has endorsed by the NHRC in the strategic planning which has opened the door to establish the mechanism. The policies, guidelines and operation modalities of the mechanism have already prepared. However, it took time to establish the mechanism due to the priority of the national politics which was the promulgating new constitution and the political instability also affected for establishing the mechanism.

Outcome Statement 2:  The capacity of state authorities, including security sector institutions and the courts, to better protect journalists is enhanced with the support of civil society, political parties and the public at large.

Rate the current status of the outcome:

| Indicator 1: a. Courts conduct impartial, speedy and effective hearings of cases of impunity of violence against journalists in project districts. Indicator 2: Police provide pro-active preventive measures to protect journalists from potential violence in project districts. Indicator 3: c. % of journalists from project districts are better enabled to access fair and effective security and justice institutions (UNDAF 4.2) | Baseline: % of court cases hearing allegations of alleged acts of violence against journalists. Target: 25% increase of court cases hearing allegations of alleged acts of violence against journalists. Progress:The stat is still undergoing through the political transition. The cases of the impunity are not in priority yet. As per the record of Federation of Nepali Journalists (FNJ) has filed 39 cases of violence against journalist out of them 35 were killed and 4 were disappeared. I those cases of killed journalists has registered in the district court and appeal the court and verdict to jailed to the perpetrators. The project has contributed to sensitized to the judiciary on the safety of journalists and the issues of impunity which has reflected in those cases. In addition UNESCO could get additional funds to study the status of journalists who were killed and disappared. Baseline: # of district level FIRs and cases registered with police Target: 25% increase of district level FIRs and cases registered with police Progress:The FIR registration will be started after the establishment and functioning of the mechanism. In the meantime the concern stakeholders are aware on the FIR registration process. Polices of the project area (19 district) and Human Rights Cell of Nepal Police in center were sensetized on UN Plan of Action on Safety of Journalists and the Issues of Impunity. Baseline: % of journalists satisfied with the courts, police and prosecutors Target: 25% increase of journalists satisfied with the courts, police and prosecutors Progress:TSeveral dialogue and discussion in district, regional and central level with the journalists were organized to make them enable to deal with the judiciary and security sectors. In the meantime, dialogue among the journalists, security sector and judiciary also organized in the district, regional and national level which has contributed for better enable access fair and effective security and justice institutions. |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

A) Organized dialogue with security sector institutions on the role of free expression in a democracy and the responsibility of police for protecting free expression, particularly journalists at the district level.

b) Establish a scheme of “gender and inclusion champions for journalists’ security” and train members of security sector institutions on issues of vulnerability and gender  equality, and

c) Organize dialogue among prosecutors, police, government and judicial officials at local level and engage them in dialogue to advocate for justice and protection of free expression and for safety of journalists.

d) Support dialogue between the independent mechanism for protecting journalists and free expression and political parties/political interest groups to seek their public commitments on ending impunity.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

The following progress were achieved through the activities carried-out in the period:

a) Local level members of the executive and judiciary have a good understanding of the importance to enhance the safety of journalists and their role in this context. The project activities have reached to the more than 1,000 stakeholders across the country and they participated on different dialogue, discussion programmes which have contributed them to enrich their knowledge on the safety of journalists and the issues of impunity in Nepal.

b) Scheme of “gender champions for journalists’ security” is established among members of the security sector. Around 200 security, judiciary and administrators have trained on gender sensitivity in 19 districts of project area. They have been advocating on the districts promoting freedom of expression, gender equality and safety of journalists.

c) Support dialogue between the independent mechanism for protecting journalists and free expression and political parties/political interest groups to seek their public commitments on ending impunity. The dialogue with political parties was organizes as a part of International Mission. That was done as a strategy to have a large impact by concerning the political parties the international concerns on safety of journalists as a large group. The dialogue with political parties was held on April 2015 and was attended by one representative each from the major political parties. The issues discussed were related to safety of journalists, the need for proper legislation and need for establishing an independent mechanism for protection and safety of journalists.

d) Political parties/political interest groups act in compliance with their public commitment to end insecurity and impunity.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 3:  Journalists and media houses have enhanced capacity to protect themselves.

Rate the current status of the outcome:

| Indicator 1: Journalists implement personal safety measures Indicator 2: Women journalists implement gender safety measures. Indicator 3: Media houses implement appropriate means to protect their female/ male staff. | Baseline: Journalists are insufficiently equipped to deal with the high number of security threats and do not systematically implement proven protection measures. Target: Journalists utilize new capacity and utilize tools to protect themselves against threats. Progress:Journalists were trained on the UN Plan of Action on the Safety of journalists and the Issue of Impunity, a study on the self-protection capacity of the journalists, assessment on the capacity of media rights violation monitoring desks including inception context analysis and Do No Harm workshop etc. have increased the sensitivity of the project partners on the importance of the safety of journalists. A dedicated website on the issues of safety of journalists has been operating by the umbrella organization of journalists Federation of Nepali Journalists. The journalists of the target areas have been aware on the physical and professional safety issues and media rights violence. In addition, the code of conduct for journalists has revised in coordination with Press Council Nepal along with the concern stakeholders. Baseline: No comprehensive, gender specific approach to increase the safety of women journalists, only a variety of individual training initiatives. Target: Women journalists have access to gender-specific techniques and utilise to protect their safety. Progress:Around 200 women journalists were trained under the project on the personal and professional security. The trainings were led by the national and international facilitators. A Guideline for the women journalists concerning the safety of women journalists published consulting with national and international experts. The published 1,000 copies of guideline have distributed the working women journalists that has been utilizing in their day to professional life. Baseline: No systematic implementation of security measures by media owners so far Target: Media owners are aware of the issue and put in place tools to contribute to increase the security of journalists Progress:About 200 media owners and managers were sensitized on gender sensitivity and safety of women journalists. They are now aware on the gender sensitive issues and practice those measures in their institutions. The national and international experts which were engaged to sensitize them on the issues of gender sensitivity and safety of women journalists. |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

A) Carried-out an independent review of the existing Code of Conduct for journalists against international standards, with particular consideration of gender aspects, and support a consultative process for enhancing and making it enforceable

b) Organized a NIMP mission including discussions and press conferences to assess the safety mechanisms and advocate for ending impunity on some emblematic cases.

c) Developed practical guidelines/toolkits on issues related to the safety of journalists.

d) Developed a handbook on safety for women journalists.

e) Trained female journalists on personal safety and professional journalism.

f) Organized workshops with media owners on their responsibility for the safety of journalists.

g) Organized dialogue between media owners and professional associations of journalists to develop a safety protocol for dealing with the safety issues, include that of workplace safety and responsiveness to gender concerns.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

A) made a self-regulatory framework for journalists at par with international standards.

b) reviewed of the existing Code of Journalistic Ethics by the national and international experts which is going to be released by Press Council Nepal.

c) Published a practical guidelines on issues related to the safety of journalists which has been used by the women journalists on their daily professional life.

d) Female journalists have enhanced their capacity on safety issues. They were trained by the national and international gender and media experts. About 200 female journalists were trained. They were trained on freedom of expression and media freedom, professionalism, journalits code of ethics, working journalist act, professional and physical safety of journalists etc.

f) The media owners are sensetized on the issues of journalist safety, work place safety and response and gender concerns. IMS/NIMP, Freedom Forum, FNJ organized consulation meetings on their responsibility for safety of journalists. The meeings were organized with professional associations and media owners for developing a protocol dealing with safety, workplace safety and responses and gender concerns.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 4:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender in the reporting period

| Evidence base: What is the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | There were various activities done under the project. Some studies concerning the safety of journalists have done under the project. Study report on the self-protection capacity of the journalists, assessment on the capacity of media rights violation monitoring desks including inception context analysis, and media monitoring reports etc. There were various consolation meeting with the different stakeholders in different levels; consolation meeting with police and judiciary in regional level, meeting with the media owners and managers on the safety of journalists and gender sensitive issues, regional and national consolation among the stakeholder to establish an independent mechanism protecting the journalists, finalize the ToR and working modalities. Meetings for revising the code of conducts for journalists, training to the women journalists on the their professional and physical safety, guidelines for women journalists on safety issues etc. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | Yes, the project filled the gap on peacebuilding process. The safety of journalists and the issue of impunity were not in the priority of the Nepal government due to the political transition. The government has formed a Truth and Reconciliation Commission which hasn't addressed these issues yet. In the cases of impunity against journalists, the government has formed some commission to find the reality however most of the cases are still not investigated. This shows the government hasn't prioritized and funding in these cases. Therefore, this project has contributed to sensitize security and judiciary on the journalist safety and issues of impunity. It also supported to create an environment to establish an independent mechanism protecting journalists and end the impunity which which definitely contributes peacebuilding process in Nepal. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | This project has been catalytic in reviving the proposal of establishing a nationally owned mechanism to protect free expression in Nepal. Due to the efforts of this mechanism the proposal which has been inactive for the last two years is now in a stage of being implemented with the agreement that it will be housed in the National Human Rights Commission. The headquarter of UNESCO has supported on the additional funding for sustainability of the project. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | There are not such specific and innovative activities considering the peace building context, however there were some challenges to achieve intended goal in the political transition. There were not commissioners in National Human Rights Commission that affected that affected to carry-out the activities in an intensive way. |
| Gender: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | The project has some specefic activities concedering the gender issue. Preparing guidelines for women journalists on safety and conducted dialouge and discussion particularly focused on professional as well as workplace safety issues with the concern stakeholders. The gender score-card is used in the implementation of the project. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) |  |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (250 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 The NHRC, professional media associations, state agencies and civil society (including political parties) join hands to establish a nationally owned mechanism that ensures a safe environment for journalists. | Indicator 1.1 An independent mechanism for safety of journalists and free expression evolves to be an efficient node for dealing with the safety of journalists and impunity, and to investigate violations of freedom of expression in a gender sensitive way. | NHRC unable to implement original concept developed in 2012 to establish a mechanism for the protection of journalists The current concept note for the mechanisms includes protection only for journalists | The concept note elaborated to by applying recommendations of the national and regional consultations The new revised concept note also includes human rights defenders and other key civil society actors as target groups to be protected | Concept note on functioning of the independent mechanism prepared, discussed and revised, discussions and consultations ongoing on institutional design and creation NHRC officials discussed on international experiences of the such mechanism. | The retirement of NHRC commissioners and the government's failure to identify their successors pose a big challenge towards achieving this target Delayed as there was no endorsement letter of NHRC available at UNESCO or UNPFN. |  |
|  | Indicator 1.2 Professional institutions have the capacity to enhance the safety of journalists and deal with cases of impunity |  |  |  |  |  |
|  | Indicator 1.3 |  |  |  |  |  |
| Output 1.1 An independent mechanism for safety of journalists and free expression evolves to be an efficient node for dealing with the safety of journalists and impunity, and to investigate violations of freedom of expression in a gender sensitive way. | Indicator 1.1.1 Ownership of all stakeholders for project implementation ensured | Scattered knowledge of stakeholders of the project strategies and activities | Stakeholders have full ownership of project and understand their role in its implementation | All stakeholders are on board with full ownership and role |  |  |
|  | Indicator 1.1.2 Inception context analysis (including assessment of the overall safety situation of journalists, inclusion at the district and regional levels, and analysis of past and on-going actions and institutions addressing this issue) and conflict analysis. | No analysis of current situation available | Stakeholders have comprehensive knowledge about status quo. | Inception context analysis carried out, recommendations included |  |  |
| Output 1.2 Professional institutions have the capacity to enhance the safety of journalists and deal with cases of impunity | Indicator 1.2.1 Status and capacity of established media rights violation monitoring and response desks of professional organizations analyzed. | Present desks operate in an incoherent, hence ineffective way. | 1 In-depth knowledge of existing desks supports the planning of more efficient desks |  |  |  |
|  | Indicator 1.2.2 Agreement reached coordination and improving monitoring documentation among the various media rights violation monitoring activities | Unequal quality of media rights violation monitoring activities | Common approach of monitoring activities documented in a written agreement. | Activity carried-out (NIMP and National Implementation partners) |  |  |
| Output 1.3 | Indicator 1.3.1 |  |  |  |  |  |
|  | Indicator 1.3.2 |  |  |  |  |  |
| Outcome 2 The capacity of state authorities, including security sector institutions and the courts, to better protect journalists is enhanced with the support of civil society, political parties and the public at large | Indicator 2.1 Courts conduct impartial, speedy and effective hearings of cases of impunity of violence against journalists in project districts. | 30% of court cases hearing allegations of alleged acts of violence against journalists Average time to complete hearing of cases is protracted. | 25% increase of court cases hearing allegations of alleged acts of violence against journalists 25% reduction in time to conclude hearing of cases. | Consultations at district & regional levels organized, assessment on role of judges and courts carried out and the role identified. Nearly 200 persons including security personals, members of judiciary become aware on the FoE and safety of journalist |  |  |
|  | Indicator 2.2 Police provide pro-active preventive measures to protect journalists from potential violence in project districts. | 10% district level FIRs and cases registered with police 4% of district level police investigations into alleged cases No monthly security meetings with media stakeholders No measures taken by police to prevent violence against journalists. | 25% increase of district level FIRs registered with police, 25% increase of district level police investigations into alleged cases, 25% increase of security meetings with media, 25% increase in measures taken by police on violence against journ | Better understanding on national and international instruments of Freedom of Expression and issues concerning safety of journalists among police. |  |  |
| Output 2.1 Security sector institutions and courts have increased capacity to enhance protection of journalists and prosecute violence against journalists in a gender sensitive and inclusive manner. | Indicator 2.1.1 Training institutions of justice organs extend the scope of training to enable an increasing number of judicial officers to conduct hearings in line with legal standards. | No such trainings available (based on consultations with Judiciary) | 25% increase in number of judicial officers trained to conduct hearings in line with legal standards. | Activity carried out (NIMP and National Implementation partners Activity ongoing (NIMP and National Implementation partners) |  |  |
|  | Indicator 2.1.2 Security sector institutions have increased capacity through training of trainers in security training institutions. | Insufficient trainings for security sector on the protection of journalists (based on pre-assessment Feb, 2014) | Training bodies of security sector institutions conduct trainings. | Activity carried-out (NIMP and National Implementation partners) |  |  |
| Output 2.2 Key representatives of civil society including political parties/political interest groups take action to reduce the number of threats and violence, determined by public demands for freedom of the press and the progress in the peace process | Indicator 2.2.1 Representatives of political parties/political interest groups act with respect for freedom of the press and the safe conduct of journalism | Political parties may behave in contradiction to their responsibility to guarantee freedom of the press, thereby jeopardizing secure working environment for journalists | Political parties including their youth wings accept and follow public demands for non-interference in reporting and potential investigations into media right violations through perception polls and data | Activity carried-out (NIMP and National Implementation partners) |  |  |
|  | Indicator 2.2.2 The public determines political parties/political interest groups to enable impartial news coverage | Public recognition of political interference does not lead to tangible change in behaviour of involved actors | Public opinion is given influence to contribute to increased security of journalists | Activity carrie-out (NIMP and National Implementation partners |  |  |
| Output 2.3 | Indicator 2.3.1 Public at large creates an atmosphere conducive to increasing the safety of journalists in peace building and the understanding of the importance of a free and safe environment for journalists. | Public in general is not aware of the issues concerning safety of the journalists | Public understands its role to contribute to enhance journalists’ security | The project reached to 1000 persons with several activities focused on creating awareness about the understanding of the importance of a free and safe environment for journalists |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 Journalists and media houses have enhanced capacity to protect themselves | Indicator 3.1 Journalists implement personal safety measures | Journalists are insufficiently equipped to deal with the high number of security threats and do not systematically implement proven protection measures | Journalists utilize new capacity and utilize tools to protect themselves against threats | Activity carried-out (NIMP and National Implementation partners) |  |  |
|  | Indicator 3.2 Women journalists implement gender safety measures | comprehensive, gender specific approach to increase the safety of women journalists, only a variety of individual training initiatives | Women journalists have access to gender-specific techniques and utilize to protect their safety) | Activity carried-out (NIMP and National Implementation partners |  |  |
| Output 3.1 Journalists have means at hand to enhance their personal protection | Indicator 3.1.1 Self-protection capacities of journalists including functioning and efficiency of ‘Hotlines’ maintained by press freedom protection organizations are available | Existing self-protection capacities and methodologies for the individual media professional have not been reviewed regarding their efficiency and scope (Assessment, 2014) | Overview of existing tools and lessons learned regarding efficiency, implemented | Report produced identifying roles and responsibilities of the stakeholders |  |  |
|  | Indicator 3.1.2 Additional hotlines established, where required | Existing hotlines do not have the capacity to cover all potential beneficiaries (Assessment, 2014) | A sufficient number of hotlines are in place to cover as many cases as possible | Activities carried out |  |  |
| Output 3.2 Women journalists have gender specific approaches regarding their personal safety | Indicator 3.2.1 Women journalists will be better equipped to increase their personal safety | No comprehensive, gender specific approach to increase the safety of women journalists | Women journalists have access to gender-specific techniques and approaches to protect their safety | Activity carried out (NIMP and National Implementation partners) |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | One of the lessons learned have been that large stakeholders discussions need to be carried out to select implementing partners. For example, it was important to get engaged with stakeholders with extended national presence because the project will have impact beyond the selected districts via its mechanism to protect free expression. With this realization the project has now partnered with six more human rights and media advocacy groups. |
| --- | --- |
| Lesson 2 (1000 character limit) | It would be better if the approval taken with the ministry of information and communication before the project started. It took long time to convince the concern authorities and take approval to kick-off the activities. |
| Lesson 3 (1000 character limit) | The safety of journalist is also related or influenced by the content they produce. The project did refer to content tangentially but had no activities aimed at assisting to professionally conduct their business that could also contribute towards reducing threats. While the project did attempt to address the improvements in law and policy, and the code of conduct for journalists, the next steps would be to train them on how to uphold the professional in conduct. This could call for focused capacity development interventions in the future. |
| Lesson 4 (1000 character limit) |  |
| Lesson 5 (1000 character limit) |  |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures are on track, slightly delayed, or off track:

If expenditure is delayed or off track, please provide a brief explanation (500 characters maximum):

94% of total budget has expanded while implementing the project

Please provide an overview of expensed project budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: |
| Output 1.1 |  |  | 81,500.00 |  |  |
| Output 1.2 |  |  | 58,000.00 |  |  |
| Output 1.3 |  |  |  |  |  |
| Outcome 2: |
| Output 2.1 |  |  | 65,000.00 |  |  |
| Output 2.2 |  |  | 40,500.00 |  |  |
| Output 2.3 |  |  | 37,500.00 |  |  |
| Outcome 3: |
| Output 3.1 |  |  | 74,000.00 |  |  |
| Output 3.2 |  |  | 30,000.00 |  |  |
| Output 3.3 |  |  | 25,000.00 |  |  |
| Outcome 4: |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total: |  |  |  | 94% |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when); or whether any changes are envisaged in the near future (2000 character maximum):

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.