|  | SUN Movement Multi-Partner Trust Fund |  |
| --- | --- | --- |

PROGRAMME1 QUARTERLY PROGRESS UPDATE

as of September  2014

| Participating UN Organization: | World Health Organization |
| --- | --- |
| Implementing Partner(s): | World Vision Uganda |
| Programme Number: | Program number – SUN – Window 2-010 |
| Programme Title: | Programme title – Strengthening Uganda Civil Society capacity to strengthen the scaling up Nutrition (SUN) |
| Total Approved Programme Budget: | US$___ USD 321,000______________ |
| Location: | Uganda |
| MC Approval Date: |  |
| Programme Duration: | 3 years | Starting Date: | March 2013 | Completion Date: | March 2016 |
| Funds Committed: | US$_________________ | Percentage of Approved: |  |
| Funds Disbursed: | US$_________________ | Percentage of Approved: |  |
| Expected Programme Duration: | 3 years | Forecast Final Date: | March 2013 | Delay (Months): | 6 months |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| A functional CSO platform with harmonised information and capacity to influence nutrition policy and action in favour of mothers and children by 2014 | As part of the process of establishing sub-regional information platform in Lango and Acholi sub-region, UCCOSUN amd other actors mobilized communities during the International Breast Feeding Week in Kitgum. In addition to creating on breast-feeding, about 45 mothers who had practiced exclusive breast-feeding were recorgnized publicly. | 20 |
| An effective policy and legal frame-work from national level to the grassroots for improved nutrition governance by 2014 to support the scale-up o f proven interventions in country | In collaboration with other actors, UCCOSUN supported a media dialogue to strengthen advocacy for nutrition. About 35 journalists and reporters from different media houses acquired knowledge and skills in nutrition advocacy as well as basic facts. From the information acquired, the media profiled key messages on nutrition during the International day of Breast feeding. |  |
| A stronger and sustainable multi-stakeholder dialogue from national level to the grassroots for better government accountability on nutrition investments by 2014 | At the beginning of the quarter, UCCOSUN mobilized and trained 56 nutrition multi-stakeholders from Tooro Kingdom, in nutrition advocacy. The people trained later acted as champions in mobilizing and sharing information on scaling-up nutrition among rural households. During the report period, UCCOSUN and other Civil Society actors in Tooro Kingdom hosted the King of Tooro and the Prime Minister (PM) of Uganda, in Kyegeggwa district. During the event attended by slightly over 900 people, the King and PM laid a foundation stone for construction of a children’s ward where services to scale up nutrition would be a major component. |  |
| A constituency with capacity to demand for the scale up of nutrition activities at the grassroots by 2014 | The secretariat continued with monitoring and sharing reports with members and the SUN secretariate |  |

Qualitative achievements against outcomes and results:

The major qualitative achievement during the quarter was the commitment made by the cultural leaders – The King of Tooro, to continue mobilizing his subjects for taking collective actions to scaling up nutrition. Similarly, the Tooro Kingdom became an additional sub-regional regional information platform coordinated bya UCCOSUN member organization called Kabarole Research Centre

The term “programme” is used for projects, programmes and joint programmes.