|  | SUN Movement Multi-Partner Trust Fund |  |
| --- | --- | --- |

PROGRAMME1 QUARTERLY PROGRESS UPDATE

as of March  2015

| Participating UN Organization: | World Health Organization |
| --- | --- |
| Implementing Partner(s): | World Vision Uganda |
| Programme Number: | Program number – SUN – Window 2-010 |
| Programme Title: | Programme title – Strengthening Uganda Civil Society capacity to strengthen the scaling up Nutrition (SUN) |
| Total Approved Programme Budget: | US$___ USD 321,000______________ |
| Location: | Uganda |
| MC Approval Date: |  |
| Programme Duration: | 3 years | Starting Date: | March 2013 | Completion Date: | March 2016 |
| Funds Committed: | US$_________________ | Percentage of Approved: |  |
| Funds Disbursed: | US$_________________ | Percentage of Approved: |  |
| Expected Programme Duration: | 3 years | Forecast Final Date: | March 2013 | Delay (Months): | 6 months |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| A functional CSO platform with harmonised information and capacity to influence nutrition policy and action in favour of mothers and children by 2014 | Organized and conducted on sub-regional meeting for multi-stakeholders forum Gulu, Arua, Kitgum and Oyam towards the end of February. About 700 people participated in the public action where awareness was created on issues of child malnutrition and its impact on the well being of children as well as it linkages ton other social determinants like child marriages. District leaders committed to invest more in scaling up nutrition. | 20 |
| An effective policy and legal frame-work from national level to the grassroots for improved nutrition governance by 2014 to support the scale-up of proven interventions in country | UCCOSUN supported processes of reviewing the advocacy strategy for rolling out UNAP. For the period under review, members participated in three UNAP coordination meetings to review progress and also recommend improvements. UCCOSUN developed a concept note for the second national nutrition and it was adopted by the Nutrition Focal Point – Office of the Prime Minister. On January, 2015, UCCOSUN joined the Global Action/2015 movement to mark the beginning of the Inter-Governmental Negotiations for the Post22015 development frame-work. Over 1000 people participated in the national campaign launch of the Action/2015 campaign in Uganda. | 30 |
| A stronger and sustainable multi-stakeholder dialogue from national level to the grassroots for better government accountability on nutrition investments by 2014 | The Steering Committee reviewed the draft and the Consultant is currently working on finalizing the report to be launched by the end of April. At the beginning of March, UCCOSUN members partnered with NTV and conducted a people’s parliament on nutrition, maternal and child health at Mpigi District headquarters. About 45 people participated in the live TV show including District leaders, MPs, children, Government officials and CSO representatives. | 25 |
| A constituency with capacity to demand for the scale up of nutrition activities at the grassroots by 2014 | Monitoring of UCCOSUN activities continued throughout the quarter and lesson learnt documented and shared with all stakeholders. In Amuru district, stakeholders interfaced with local leaders on the access to health services including support to scale-up nutrition. The district leaders committed to increase investment in nutrition. | 30 |

Qualitative achievements against outcomes and results:

During the quarter, UCCOSUN members actively participated in 4 stakeholders workshops and contributed to shaping the nutrition component in Health goal, target and indicators. Specifically, we submitted our contribution to the national negotiating team emphasising the importance of including indicators on stunting and breast-feeding.

The term “programme” is used for projects, programmes and joint programmes.