# RUNO Half Yearly Reporting 					TEMPLATE 4.3

[COUNTRY: Kyrgyzstan]

PROJECT HALF YEARLY PROGRESS UPDATE

PERIOD COVERED: JANUARY – JUNE 2015

| Project No & Title: | PBF/KGZ/A-1: Strengthening capacities of LSGs for peacebuilding |
| --- | --- |
| Recipient Organization(s): | UNDP, UNICEF |
| Implementing Partners (Government, UN agencies, NGOs etc): | Department for Ethnic and Religious Policy and Collaboration with Civil Society (Office of the President), State Agency on Local Self-Governance and Inter-Ethnic Relations, Inter-Agency Commission to coordinate implementation of the Concept for National Unity and Interethnic Relations, State Commission on Religious Affairs, Assembly of People of Kyrgyzstan, Local Self-Governance (LSG) bodies in selected districts |
| Total Approved Budget : | 1,728,877 - UNICEF: USD 228,876 - UNDP: USD 1,500,001 - Total: |
| Preliminary data on funds committed : | UNICEF: USD 80,469 UNDP: USD 724,002 Total: USD 804,471 | % of funds committed / total approved budget: | UNICEF: 35% UNDP: 48.27% Total: 46.53% |
| Expenditure: | UNICEF: USD 57,969 UNDP: USD 697,120 Total: USD 755,089 | % of expenditure / total budget: (Delivery rate) | UNICEF: 25.3% UNDP: 46.47% Total: 43.68% |
| Project Approval Date: |  | Possible delay in operational closure date (Number of months) |  |
| Project Start Date: | 01.01.2014 |  |  |
| Expected Operational Project Closure Date: | 30.06.2016 |  |  |
| Project Outcomes: | Outcome 1: State institutions and LSGs collaborate to bridge local divides and implement the Concept for National Unity and Inter-Ethnic Relations Outcome 2: State institutions and LSGs jointly reduce local tensions through gender-responsive peacebuilding initiatives and promotion of religious diversity |
| PBF Focus Area (select one of the Focus Areas listed below) |  |

# Qualitative assessment of progress

| For each intended outcome, provide evidence of progress during the reporting period. In addition, for each outcome include the outputs achieved. (1000 characters max per outcome.) | Outcome 1: The Office of the President allocated funds to the Agency for Local Self-Government Affairs and Interethnic Relations (GAMSUMO) to support peacebuilding projects of LSGs and Cultural Centers (representing ethnic groups), thereby contributing to the implementation of the policy on national unity and interethnic relations. With UNDP support GAMSUMO set up a grant facility. UNDP experts in the Monitoring Center have built capacities of GAMSUMO specialists to monitor and mentor 12 already selected projects. After a UNDP training on project development for LSGs, GAMSUMO regional representatives, and civil society, 75 peacebuilding project ideas were submitted in response to GAMSUMO’s call for proposal. GAMSUMO assisted the Inter-Agency Commission (IAC), that steers the implementation of the interethnic policy, to monitor the status of its implementation. A progress report was prepared by the IAC that also adopted a resolution on further policy implementation. Outcome 2: As the result of participatory analysis of conflict causes with LSGs, 24 project ideas to address local conflict drivers were developed in 14 pilot municipalities in close collaboration of LSGs and civil society (now being considered for receiving grants). Communication between local institutions of GAMSUMO (public reception centers, consultative councils on inter-ethnic relations) has been strengthened through joint working meetings. The Government developed an action plan on the implementation of the recently approved religious policy that was developed with UNDP support. UNICEF has facilitated policy dialogue and advocacy and helped building consensus among stakeholders and getting political buy-in for a governmental regulation that was agreed upon and currently is with the Prime Minister for endorsement. The regulation introduces a multi-sectorial and inter-ministerial mechanism to detect vulnerable families and provide social support and/or referral (case management). Outcome 3: Outcome 4: |
| --- | --- |
| Do you see evidence that the project is having a positive impact on peacebuilding? (1000 characters max.) | During meetings to discuss conflict drivers/ possible responses at local level, LSGs tried to exclude women engaged in protests (OBON) and individuals perceived as “opposition”. Individual meetings with LSGs on the importance of their participation to voice grievances and dissatisfaction were held. As a result such groups were included and protest women started to share their views and ideas. OBON women in Maevka (previously in confrontation with LSG), initiated a project on multi-cultural exchanges of different ethnicities, to be implemented jointly with the LSG. In Vasilievka OBON women who have initiated protest groups against LSG have been identified as project leaders. As the result of legal consultations/trainings of local council members, disputes over land and water have been resolved in four pilot municipalities in Batken. GAMSUMO responded to a conflict situation in Bazar-Korgon and Vasilievka. Agreements were reached and preventive actions helped preventing escalation. |
| Were there catalytic effects from the project in the period reported, including additional funding commitments or unleashing/ unblocking of any peace relevant processes? (1000 characters max.) | 15 amendments were introduced to the laws on LSGs and on Local State Administrations that makes the heads of local administrations and LSGs directly responsible on inter-ethnic relations in communities. GAMSUMO started to initiate and lobby for this as a result of working with UNDP Monitoring Centre experts, facing difficulties in getting regular and systematic information on inter-ethnic dynamics from 64 LSGs. With adoption of mentioned changes, LSGs will be held more accountable and will engage in conflict prevention efforts more actively. More than USD 80,000 were allocated from local budgets in 14 pilot LSGs for projects aiming at strengthening inter-ethnic relationship and empowering women (co-funded 20% - 70% of 24 project budgets). Additionally, the Office of the President provided funds to GAMSUMO to provide small grants to LSGs and ethnic communities for the same purpose, making financial support for such activities no more entirely dependent on donor support. |
| If progress has been slow or inadequate, provide main reasons and what is being done to address them. (1000 characters max.) | UNICEF (Output 2.3): Field-level activities have been lagging behind due to a delay in approval of the respective governmantal regulation introducing a mechanism to detect vulnerable families and provide social support and/or referal. Elections to local parliament in two pilot municipalities in Batken, and elections of head of LSG in one municipality in Chui partly effected timely completion of some activities and decreased the level of involvement of municipalities. In order to increase the sustainability of the Monitoring Centre and strengthen the capacity of the National Institute for Strategic Studies of Kyrgyz Republic (NISS) it was initially decided to provide cash transfer to NISS through HACT modality upon successful completion of an assessment. Since NISS did not qualify for HACT, it was decided to proceed with issuing an institutional contract. Related delays affected the work of the Monitoring Centre in the beginning of 2015. |
| What are the main activities/expected results for the rest of the year? (1000 characters max.) | - Monitoring progress of 24 grant projects along with coaching of LSGs. - Support implementation of the religious policy by assisting the State Commission on Religious Affairs (adoption of Action Plan for policy implementation, capacity building, etc.) - Expansion of Monitoring Center work (preparation of analytical notes for GAMSUMO on inter-ethnic dynamics in the country to take preventive measures; capacity building for GAMSUMO to establish mobile response group); - Measures to strengthen the capacity of LSGs, local councils in conflict prevention, mediation, facilitation and responding to emerging tensions; - Involvement of vulnerable women in decision-making processes and peacebuilding activities to prevent their recruitment into women protest movements (OBON). - Work with the Inter-Agency Commission on implementation of the policy for national unity and interethnic relations (addressing the issue of underrepresented groups in public and state service). |
| Is there any need to adjust project strategies/ duration/budget etc.? (1000 characters max.) | As part of the project activities on capacity building of the Inter-Agency Commission (IAC) in conflict monitoring, early preventive action, gender-responsive peacebuilding, coordination, and monitoring of policy implementation had originally been planned. Due to the fact that the IAC is represented by high level officials and has formalized arrangements, initially planned activities seem to be unrealistic because it is difficult to ensure their participation in field conflict monitoring and response visits, study tours or trainings. Therefore it was decided in close consultation with OHCHR and HCNM OSCE decided to support an international conference under the leadership of IAC on global practices of minority representation and diversity management. |
| What is the project budget expenditure to date (percentage of allocated project budget expensed by the date of the report) – preliminary figures only? (1000 characters max.) | USD 755,089 (48.68%) |
| Any other information that the project needs to convey to PBSO (and JSC) at this stage? (1500 characters max.) | N/A |

INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (250 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Project Outcome 2.3: State Institutions and LSGs collaborate to bridge local divides and implement the Concept for National Unity and Interethnic Relations | Indicator 1.1 Number of cases relating to conflicts that LSGs targeted in the project have addressed with support of the Agency for LSG Affairs and Interethnic Relations and their affiliated structures (with breakdown of how many of those were resolved) | • The level of cooperation between GAMSUMO and LSGs in cases related to conflicts is 19% (21 cases - 12 resolved) • The level of effectiveness of GAMSUMO and LSGs joint work in addressing conflict cases is 47% | At least 10 % increase by June 2016 | 3 conflict cases were targeted with support from GAMSUMO and affiliated structures (intervention to a conflict); 12 missions to communicate with people and mitigate tensions perfomerd jointly with GAMSUMO and Osh City Mayor's Office. |  |  |
|  | Indicator 1.2 Number of joint initiatives carried out by the Agency for LSG Affairs & Interethnic Relations in collaboration with other state bodies and /or civil society to increase the percentage of under-represented groups in LSG-led local grievance resolution | The number of joint initiatives of GAMSUMO and LSG to increase the percentage of under-represented groups in LSG-led local grievance resolution mechanisms and decision-making bodies is 0%. | At least 20 % increase by June 2016 | 0 | Efforts meets great resistance from State Agencies including IAC |  |
| Output 1.1 State Agency for Local Self-Governance and Inter-Ethnic Relations effectively mentors and supports LSGs and other partners to bridge divisions and reduce tensions at the national and local levels. | Indicator 1.1.1 Number of cases where Agency provided services to LSGs to bridge the divisions and reduce tensions | 0 | At least 8 in 2014; 12 in 2015; 8 until end of June | 3 cases (Agency provided small grants to 3 LSGs to bridge the divisions). 12 LSGs were mentored by Monitoring Centre experts on implementation of peacebuilding projects (Provided by GAMSUMO) |  |  |
|  | Indicator 1.1.2 |  |  |  |  |  |
| Output 1.2 Agency for Local Self-Governance and Inter-Ethnic Relations effectively supports LSGs and civil society to monitor local conflicts and inter-ethnic relations and engage in early preventive action | Indicator 1.2.1 Preventive measures taken by LSGs and national actors (in response to conflict monitoring results) that have mitigated tensions (documented through case studies documented by authorities) | The level of cooperation between GAMSUMO and LSG in cases related to conflicts is 19%. • The level of effectiveness of GAMSUMO and LSG joint work in addressing conflict cases is 47% | At least 8 in 2014; 12 in 2015; 8 until end of June | 24 action plans (projects within rapid response funds) in response to conflict analysis reports developed in pilot LSGs, implemented by LSGs in close collaboration with public preventive centers, CSO, rayon administration, local parliament, etc; |  |  |
|  | Indicator 1.2.2 |  |  |  |  |  |
| Output 1.3 The Inter-Agency Committee effectively coordinates the implementation of the Concept for National Unity and Inter-Ethnic Relations | Indicator 1.3.1 % of planned measures that were actually implemented through coordination in the inter-agency commission (co-chaired by the Agency) | Action plan on Concept was adopted in October 2013. January 2014 was the planning phase of IAC work. | At least 30% in 2014; 40% in 2015; 50% in 2016 | According to the report of Monitoring Centre, Ministry of Culture has taken 9 measures from the Concept on Unity Action Plan; Minsitry of Eduaction implemented 4 measures and National Comission on State Language implemented 9 measures. |  |  |
|  | Indicator 1.3.2 |  |  |  |  |  |
| Outcome 2 State institutions and LSGs jointly reduce local tensions through gender-responsive peacebuilding initiatives and promotion of religious diversity | Indicator 2.1 % of women in LSG-led local grievance resolution mechanisms and decision-making bodies | % of women in LSG-led local grievance resolution mechanisms and decision-making bodies is 41% | At least 10 % increase by June 2016 | 1 women from Vasilievka (participant of Women Leadership School organized by UNDP) has been elected as the head of LSG; 1 women from Tokmok was elected as the local parliament member. |  |  |
|  | Indicator 2.2 National policy on religious affairs in place, providing a framework for the promotion of religious diversity and freedom Baseline: No such policy in place | There is no Religious Policy | Policy approved by June 2016 | Religious Policy approved; and Action plan on implementation of Policy has been developed. |  |  |
| Output 2.1 LSGs and local communities in selected districts support gender-responsive local peacebuilding | Indicator 2.1.1 Number of LSG-led initiatives that address gender based violence and integrate gender aspects into their agenda | 4 LSGs works on addressing gender based violence (LSG-led). 14 LSGs has established Gender Councils within Implementation of Action Plan on 1325 | at least one in each LSG targeted | In 4 pilot AO in Chui oblast and 1 municipality in Karakol raised the issue of gender based violence, 2 municipalities submitted project proposals on establishing women centers, in Osh & Jalal-Abad; 3 women centers established. |  |  |
|  | Indicator 2.1.2 Number of state/LSG-led initiatives that have promoted ethnic and religious freedom and diversity (documented by authorities) in a well coordianted manner, involving a variety of different stakeholders | 0 | at least one in each LSG targeted | 5 projects submitted to UNDP by LSGs though wide public discussions on promoting ethnic diversity; Sulaiman-Too - Symbol of Peace & Cohesion - Festival has started with joint initiative of Osh city Mayor's office,UNDP,Osh State University & others. |  |  |
| Output 2.2 Selected LSGs and related state institutions (district state administration and social protection) detect vulnerabilities and reduce tension via direct service delivery and refer to specialized support (social cash transfers and services) | Indicator 2.2.1 |  |  |  |  |  |
|  | Indicator 2.2.2 # vulnerable and poor [families with children, youth and minorities] identified and assisted at local level | # of appeal to LSG for support | 10 % increase in number over baseline | No progress | Nearly eith-month delay in governmental approval of the respective ordinance/regulation instituting LSG and state bodies to detect and provide social support to vulnerable children, youth and their families | No adjustment planned. Upon approval of regulation accelerated implementation will take place |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

# Footnotes

Please note that where there are multiple agencies, only one consolidated project report should be submitted.

Approved budget is the amount transferred to Recipient Organisations.

# Funds committed are defined as the commitments made through legal contracts for services and works according to the financial regulations and procedures of the Recipient Organisations. Provide preliminary data only.

# 4 Actual payments (contracts, services, works) made on commitments.

5 PBF focus areas are:

PBF Focus Areas are:

1: Support the implementation of peace agreements and political dialogue (Priority Area 1):

(1.1) SSR, (1.2) RoL; (1.3) DDR; (1.4) Political Dialogue;

2: Promote coexistence and peaceful resolution of conflicts (Priority Area 2):

(2.1) National reconciliation; (2.2) Democratic Governance; (2.3) Conflict prevention/management;

3:Revitalise the economy and generate immediate peace dividends (Priority Area 3);

(3.1) Employment; (3.2) Equitable access to social services

4) (Re)-establish essential administrative services (Priority Area 4)

(4.1) Strengthening of essential national state capacity; (4.2) extension of state authority/local administration; (4.3) Governance of peacebuilding resources (including JSC/ PBF Secretariats)