# RUNO Half Yearly Reporting 					TEMPLATE 4.3

[COUNTRY: Kyrgyzstan]

PROJECT HALF YEARLY PROGRESS UPDATE

PERIOD COVERED: JANUARY – JUNE 2015

| Project No & Title: | PBF/00088670 PDP PBF Youth |
| --- | --- |
| Recipient Organization(s): | UNDP, UNICEF, UNFPA |
| Implementing Partners (Government, UN agencies, NGOs etc): | Ministry of Labour Migration and Youth, Ministry of Education and Science, Ministry of Social Development, Agency for Local Self-Governance and Interethnic relations, State Commission on Religious Affairs of the Kyrgyz Republic, LSG bodies, Defense Council. |
| Total Approved Budget : | 605825 |
| Preliminary data on funds committed : | UNICEF:USD 224,719 UNDP: USD 110,422 Total: USD 335,141 | % of funds committed / total approved budget: | UNICEF: 92.36% UNDP: 30.46% Total: 55.32% |
| Expenditure: | UNICEF:USD 214,164 UNDP: USD 110,421 Total: USD 324,585 | % of expenditure / total budget: (Delivery rate) | UNICEF: 88.02% UNDP: 30.46% Total: 53.58% |
| Project Approval Date: | December 12th, 2013 | Possible delay in operational closure date (Number of months) |  |
| Project Start Date: | 07.03.2014 |  |  |
| Expected Operational Project Closure Date: | 30.06.2016 |  |  |
| Project Outcomes: | Outcome 1: Vulnerable young women and young men at-risk have better opportunities to acquire civic participation skills to positively engage in society and develop respect for diversity. Outcome 2: Vulnerable young women and young men at-risk express their concerns, participate in decision-making at various levels and have better access to economic opportunities to reduce the likelihood of youth involvement in violent conflict. |
| PBF Focus Area (select one of the Focus Areas listed below) |  |

# Qualitative assessment of progress

| For each intended outcome, provide evidence of progress during the reporting period. In addition, for each outcome include the outputs achieved. (1000 characters max per outcome.) | Outcome 1: UNICEF: 28 young civil society leaders trained on youth work curriculum and involved 1553 young people of different background into skills building and advocacy (46 % women/girls). UNICEF with GIZ brought a multi-ethnic group of youth workers to Germany to gain experience of youth work. UNDP: The project built/ rehabilitated sports grounds and organized cultural events bringing youth from different backgrounds together (300 young leaders held national forum on peacebuilding in Alabuka; sports event in Batken for over 1,000 participants (300 women)). In order to ensure transparency and youth’s access to services and benefits of the project (e.g. sports facilities), an agreement was reached between UNDP and LSGs that all assets created by the project will be transferred to municipal government that ensure that members of the community will have access to these assets. Grants have been provided in the North to promote youth entrepreneurship, social activities, and vocational trainings.. Outcome 2: With the help of young leaders attending the youth curricula trainings, youth committees have started working under local LSGs in at least 4 pilot communities. Curriculum attendants initiated the development of youth plans in 6 pilot communities. Outcome 3: Outcome 4: |
| --- | --- |
| Do you see evidence that the project is having a positive impact on peacebuilding? (1000 characters max.) | Based on the knowledge and instruments gained at the course youth workers created at least 5 services for youth in partnership with the local authorities as a part of institutionalization of planning in youth sector. They implemented 12 social projects aiming for addressing key social issues that concern youth of different background. Youth workers involved around 1000 young people people of different background into the local skill building and advaocy excrsises with over 58 % of those being young women and girls. UNICEF joined reources with GIZ to bring a multi-ethnic group of youth workers from around the country to gain experiences in Germany. |
| Were there catalytic effects from the project in the period reported, including additional funding commitments or unleashing/ unblocking of any peace relevant processes? (1000 characters max.) | In three of the pilot communities municipalities have created youth committees as a specific department attached to them. Since respective communities did not have a strong engagement with youth before, the creation of these committees has been catalytic to advance the voice of youth in their community. |
| If progress has been slow or inadequate, provide main reasons and what is being done to address them. (1000 characters max.) | According to the initial design, youth leaders from civil society were supposed to attend youth work curriculum in parallel with the youth affairs specialists coming from municipalities and state administrations. However because of major reshuffling in the Academy under the President of the Kyrgyz Republic their participation in the course has been delayed. |
| What are the main activities/expected results for the rest of the year? (1000 characters max.) | UNICEF will organize youth work curricula training for youth affairs specialists and build their links with the civil society youth leaders who have already finalized the course. These links will be organized through local joint skill building, outreach and advocacy activities. The project will continue supporting youth leaders and youth specialist in launching new youth development projects as well as in improving youth services. Agencies will help young people to mobilize for introducing youth development projects and services into local development planning. Young people will have an opportunity to learn from the Serbian experience of youth participation in local development. |
| Is there any need to adjust project strategies/ duration/budget etc.? (1000 characters max.) | N/A |
| What is the project budget expenditure to date (percentage of allocated project budget expensed by the date of the report) – preliminary figures only? (1000 characters max.) | USD 324,585 (53.58%) |
| Any other information that the project needs to convey to PBSO (and JSC) at this stage? (1500 characters max.) | N/A |

INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (250 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 2.9: Vulnerable young women and young men at-risk have better opportunities to acquire civic participation skills to positively engage in society and develop respect for diversity | Indicator 1.1 2.9.1 Number of youth in LSGs targeted by the project who advocate for equal access to services together with youth from other ethnic groups | 61% | 20% increase in number over baseline by end of 2016 | n/d |  |  |
|  | Indicator 1.2 |  |  |  |  |  |
| Output 1.1 Output 1: Vulnerable young women and young men at-risk express their concerns, participate in decision-making at various levels and have better access to economic opportunities to reduce the likelihood of youth involvement in violent conflict | Indicator 1.1.1 Number of youth in LSGs targeted by the project who advocate for equal access to services together with youth from other ethnic groups | 61% | Target: 10% increase in number over baseline | n/d |  |  |
|  | Indicator 1.1.2 |  |  |  |  |  |
| Output 1.2 Youth work curricula for youth in and out of school have been piloted in selected districts and relevant institutions have the capacity to replicate the delivery of the curricula elsewhere | Indicator 1.2.1 # of languages in which the curricula available | 0 | 3 | 1 |  |  |
|  | Indicator 1.2.2 # of youth workers complete TOT | 0 | 40 | 28 |  |  |
| Output 1.3 | Indicator 1.3.1 |  |  |  |  |  |
|  | Indicator 1.3.2 |  |  |  |  |  |
| Outcome 2 2.10: Vulnerable young women and young men at-risk express their concerns, participate in decision-making at various levels and have better access to economic opportunities to reduce the likelihood of youth involvement in violent conflict | Indicator 2.1 2.10.1 % increase in constructive participation of youth in decision-making processes at all levels 2.10.2 % of vulnerable young women and young men that are optimistic (think positively) about their future (and their future opportunities) | At the basic level recorded 44 non-constructive conflict events involving young people. 44 facts - it is 100%. At the final stage decreasing of number of conflicts (less than 44) will indicate a positive trend. 2.10.2 63% | 10% increase in number over baseline by end of 2016 2.10.2 10% increase in number over baseline by end of 2016 | Only in one of the pilots (Vasilevka, Chui, January 2015) was recorded the fact of participation of young people in violent conflict. 2.10.2 The growing number of youth involved into the project events (about 2700 people)…(see outc-3, outp indic112 |  |  |
|  | Indicator 2.2 2.10.3 # of development strategies and policies with inclusion and guaranteed budgetary stipulation addressing needs and priorities of young men and young women | 3 | at least 13 local and national level | There were developed 7 action plans in total (1 in Osh, Chui-4, Batken-2). But budgetary stipulation at now has only 3 (Osh-1, Batken-2). |  |  |
| Output 2.1 | Indicator 2.1.1 |  |  |  |  |  |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 | Indicator 2.2.1 |  |  |  |  |  |
|  | Indicator 2.2.2 |  |  |  |  |  |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

# Footnotes

Please note that where there are multiple agencies, only one consolidated project report should be submitted.

Approved budget is the amount transferred to Recipient Organisations.

# Funds committed are defined as the commitments made through legal contracts for services and works according to the financial regulations and procedures of the Recipient Organisations. Provide preliminary data only.

# 4 Actual payments (contracts, services, works) made on commitments.

5 PBF focus areas are:

PBF Focus Areas are:

1: Support the implementation of peace agreements and political dialogue (Priority Area 1):

(1.1) SSR, (1.2) RoL; (1.3) DDR; (1.4) Political Dialogue;

2: Promote coexistence and peaceful resolution of conflicts (Priority Area 2):

(2.1) National reconciliation; (2.2) Democratic Governance; (2.3) Conflict prevention/management;

3:Revitalise the economy and generate immediate peace dividends (Priority Area 3);

(3.1) Employment; (3.2) Equitable access to social services

4) (Re)-establish essential administrative services (Priority Area 4)

(4.1) Strengthening of essential national state capacity; (4.2) extension of state authority/local administration; (4.3) Governance of peacebuilding resources (including JSC/ PBF Secretariats)