RUNO END PF PROJECT REPORTING		TEMPLATE 4.5

PEACEBUILDING FUND (PBF)

END OF PROJECT report

COUNTRY: Colombia

REPORTING PERIOD: 2014-2015 Communication for Peace

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: Communication for Peace Programme Number (if applicable) MPTF Office Project Reference Number: 00089169 |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UNICEF |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: Government of Colombia (through the office of the High Commisioner for Peace) and Government of Norway. |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) US $2,000,000 |  |  | Overall Duration (months) January 2014 - Ten months duration |  |
|  |  |  | Start Date (dd.mm.yyyy) 10.01.2014 |  |
| Government Contribution (if applicable) US $300.000 (in kind) |  |  | Original End Date (dd.mm.yyyy) | )31.12.2014 |
| Other Contributions (donors) (if applicable) US $500.000 government Norway |  |  | Final End date(dd.mm.yyyy) 31.03.2015 |  |
| TOTAL: | 2,800,000 |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Mid-Term Evaluation / Review - if applicable please attach Yes No Date: End of project Evaluation– if applicable please attach Yes No Date: |  | Name: Carolina Plata Title: Chief Communications UNICEF Colombia Participating Organization (Lead): UNICEF Email address: cplata@unicef.org |

PART 1 – RESULTS PROGRESS

  - Assessment of the project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project has contributed:

Priority Plan Outcome to which the project has contributed.

Priority Plan Outcome indicator(s) to which project has contributed.

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  At the of end of the national communication campaign, at least 70% of a representative sample of the national public opinion, demonstrates higher awareness on how to contribute to a culture of sustainable peace and reconciliation.

Rate the current status of the outcome:

| Indicator 1: Percentage of people who demonstrate better knowledge of peacebuilding in Colombia (The sample will be representative for the national level, with disaggregation for urban and rural areas). Indicator 2: Qualitative analysis of key informant interviews at the national level, on the issues of peacebuilding and reconciliation Indicator 3: | Baseline: After recalculation the initial survey, showed that 29.5% of the population interviewed showed awareness and positive attitudes towards building peace and reconciliation in Colombia. Target: 5,800 men and women aged 18 years, residing in 80 municipalities. Progress: For the second measurement the same indicator was 58.2%. There was an increase of almost 98% in the proportion of people that have a positive view on peace building and reconciliation. Baseline: Ten focus groups were developed with community members in municpalities both most and less affected by the armed conflict. Topics treated were: Coexistence, respect for differences and for others, gender equity, civic culture, social justice, reconciliation, community participation, peaceful mobilization and using mass media to promote peace. Target: There is a positive notion on resolving conflicts peacefully and the importance of reconciliation. Progress:The result of 10 different focus groups confirmed that key community actors and civic leaders expressed greater interest in participating in various activities and groups that promote a culture of peace reducing aggression and solving conflicts without violence. Qualitative analysis also included 15 interviews with key informants. Baseline: Target: Progress: |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

The UNCT in Colombia jointly defined the process to select the advertising agency and the M&E Company to carry out the campaign. The message focused on generating a culture of peace and not supporting any political agenda. The campaign was launched on July 16th 2014 with 7 TV and Radio commercials, a song produced for the campaign, a website and social media strategy and innovative outreach activities.  More than 39 million people have been exposed to the commercials; and at the local level the campaign reached at least 25,000 people directly with activities. A mobile cinema combining the campaign message with the showing of "Mateo", Colombia's foreign film entry for the Oscars awards reached 153 municipalities, with particularly strong participation by women and youth. Five radio dramas were produced and broadcast in 107 local stations. In the final phase, national actors have agreed to carry on the Respira Paz message through strategic alliances with the UN.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

The Breathe Peace campaign unfolded at a time of great relevance for its message to register with Colombia's target population, coming amid continued progress in peace negotiations aimed at ending the country's 50 year armed conflict, and just following a hotly contested presidential election in which peace was the central issue in the campaign.  It is encouraging that there was an increase from 29.5% to 58.2% in the proportion of people that were aware on how to contribute to a culture of peace and sustainable reconciliation. This is not only higher than expected, but especially noteworthy given that the investment and the duration of media exposure has been relatively short in comparison with most advertising campaigns. The evidence suggests not only that the campaign is coming at a propitious time for its message to the general population, but also that field activities such as the mobile cinema presented in different municipalities are contributing to evolving attitudes about the connection between peace and actions that can be taken on a personal level to respect differences, coexist more peacefully with fellow citizens and contribute to a civic culture focused on reconcilation and forgiveness.  Interviews with opinion leaders confirm this growing recognition, and it is reaffirming to note in this regard that the Breathe Peace campaign has been complemented by a campaign introduced by Colombia's business community over the same period that encourages people to envision their individual contributions to a future in peace.

The campaign's invitation to Breathe Peace is accompanied by innovative activities that have made it possible to reach conflict-affected communities and victims. Some 200 activities have been carried out at the local level through which local governments, civil society organizations, schools and universities, and UN agencies have incorporated the campaign into their activities.  The diverse elements of the Campaign have facilitated social mobilization for peace. The campaign is contributing in the manner anticipated, by solidifying positive attitudes towards peace through an indirect message focusing on personal responsibility and cultural change, with the Theory of Change being that such a contribution on a cultural level will increase the chances for explicit support for peace processes in Colombia and decrease opposition.

The successful implementation of the campaign has enabled the UNCT to raise supplementary funds from a bilateral donor, the Government of Norway, to extend the campaign for several months beyond the time frame of the PBF donation. The focus of this final phase of Breath Peace as a UN-spearheaded campaign, expected to run through mid-2015, is on national sustainability, by synthesizing the campaign in a readily-accessible format (as kits) and constructing strategic alliances with national counterparts who will carry on the campaign message in the future.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

The last available survey information reflects data only through December 2014, however it is a reasonable assumption that the positive trend in public attitudes has continued through to the end of the period of the grant. The survey data would not capture the impact of the use of a portion of grant funds used in 2015. Even with the positive results achieved, it is important to underscore the limitations imposed by the relatively short term presence of the campaign and resource levels which remain modest compared to comparable commercial or governmental campaigns of typically longer duration and budgets many times the size. It has to be noted also that the campaign is unfolding in a political environment that remains highly polarized around the peace process. While the presidential elections and gradual progress in the peace negotiations helped to establish an environment conducive to the message of the campaign, Colombia's population is also subject to persistent armed conflict and a steady stream of negative messaging about peace by opponents of the peace process. This analysis both underscores the need for campaigns such as Breathe Peace, and serves as a reminder of the challenging environment for their success in the country. There is more detailed information about the activities and coverage of the campaign and about the topics associated to culture of peace as results of M&E report but can’t be included in this report due to the limited space in the template.

Outcome Statement 2:  More than 50% of representative sample of women and youth in two of the most affected regions by the armed conflict in the country are more prone to promote peace and reconciliation in their communities.

Rate the current status of the outcome:

| Indicator 1: Percentage of women and youngsters –in all prioritized municipalities- who exhibit more positive perceptions and better knowledge on how to build peace and promote reconciliation. Indicator 2: Type of perceptions of sampled groups of women and youngsters, regarding conflict, peacebuilding and reconciliation. Indicator 3: Proportion of surveyed people (most and less affected by the armed conflict) that have an explicit orientation to participate with their own initiative in peacebuilding and reconciliation activities. | Baseline: 46% of women and youth in Nariño and Norte de Santander show positive attitudes and interest in participating in community activities that contribute to a peaceful coexistence and inclusion of people who once belonged to illegal armed groups. Target: Youth 18 to 25 years and women living in Norte de Santander and Nariño. Progress:60% of women and youth interviewed in Nariño and Norte de Santander show positive attitudes and interest in participating in community activities that contribute to a peaceful coexistence and inclusion of people who once belonged to illegal armed groups. Baseline: The data of this indicator is already measured in the indicator 1. Both indicators measured positive perceptions towards the peaceful resolution of conflicts and reconciliation. A new indicator is proposed which measures additional results (See indicator 3). Target: Progress: Baseline: 47.4% for most affected people by the armed conflict. 47.7% for less affected people by the armed conflict. Target: 70% for both types of population. Progress:69.9% for most affected people by the armed conflict. 69% for less affected people by the armed conflict. |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

There were public and private events involving women and youth, mostly sharing the campaign message and media material produced in tandem with the traveling cinema, "Mateo". A typical event involved showing the TV commercials, conducting the group breathing exercise and inviting children to play with the comic book that also transmits the campaign's central message about how breathing can be an instrument to control emotions of anger and avoid negative violent reactions. Five episodes of a radio-drama, with a strong focus on women and youngsters issues, were produced were broadcast in 107 local radio stations following the route of the mobile cinema which not only covered the departments but many other war-affected areas of the country. 4 out of the 7 references of TV and radio spots had women as the role to communicate the message.  The song of the campaign was created by one of the most popular music groups lead by a young woman and the Olympics BMX gold medal woman was a supporter.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

The assessment data indicates that the "Breathe Peace" campaign has motivated women and youth in the regions with greater violence levels to take part in generating awareness about the culture of peace. The campaign fomented participation of young people in many activities promoted by the local authorities with cultural and sports organizations, for example, and is encouraging them to look for new opportunities to promote reconciliation and forgiveness actions inside their communities. Additionally, results of the surveys revealed that a sample number of women are becoming more involved in activities for their communities, creating opportunities and spaces for personal growth and community reconciliation.

The campaign extended beyond the prioritized regions, having reached with the mobile cinema 153 municipalities in 17 out of Colombia’s 32 departments: Sucre, Bolívar, Magdalena, Atlántico, La Guajira, Cesar, Santander, Tolima, Boyacá, Cundinamarca, Nariño, Cauca, Valle del Cauca, Caldas, Risaralda, Guaviare, and Antioquia; with a total of 172 cinema showings.  In addition, the campaign featured as part of many events and activities with young people and women, such as: an online course conducted by UNICEF and UNFPA (3,000 youth); International Day for the Elimination of Violence against Women activities with artists and theatre in Bogotá and other cities; UN Model simulations in Bogotá and Medellin (4,000 young people).  Local authorities and private companies incorporated the concept of "Breathe Peace" through activities in schools, universities, libraries, and sports at the local level as part of the national "Week for Peace" celebrations.

The Department of Nariño, a war-affected region in southern Colombia, launched a local peace program called: "Nariño breathes Peace", supported by the local UN presence to spread the message of the campaign; and in Bogotá, the local office on sports and recreation has agreed to incorporate Breath Peace materials into a sports and peace public policy with  UN technical assistance.  Youth were among the active users of social media platforms to reflect upon, and spread, the message of the campaign.  The theory of change remains relevant for this outcome because through this strategy the campaign was able to impact and to mobilize youngsters and women to participate and support peace initiatives in their communities.

On the base line 47.7% of women and youth in Antioquia, Cordoba, Meta, Nariño, Norte de Santander and Vichada showed a positive view to participate in community activities that contribute to a peaceful coexistence and inclusion of people who once belonged to illegal armed groups.   And the progress showed:  69.1% of women and youth interviewed in Nariño and Norte de Santander show positive attitudes and interest in participating in community activities that contribute to a peaceful coexistence and inclusion of people who once belonged to illegal armed groups.

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Outcome Statement 3:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

Outcome Statement 4:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress at the end of project

List the key outputs achieved under this Outcome (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress at the end of project

Describe progress made toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress was not made, what were the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How were they addressed (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender at the end of the project

| Evidence base: What was the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | An M&E framework was developed based on qualitative and quantitative data including base line and final surveys for 5,800 men and women aged 18 years, residing in 80 municipalities. Ten focus groups were held with youngsters and women in the municipalities of: Nariño (Pasto and Tumaco), and Norte de Santander (Cúcuta y Sardinata). Additionally 15 opinion leaders were interviewed on all the issues related to peace building. All this information has been used to implement an evaluation of the campaign according to two DAC-OECD criteria: effectiveness and relevance. Considering that all activities just finished in late March 2015, the evaluation is still in progress. Findings, conclusions, lessons learned and recommendations, based on available data, will be ready for late April 2015. The writing of the report will be funded through UNICEF own funds. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | There is the first communications campaign of its kind with a nationwide reach and a clear call to action to the general public to contribute in their daily lives to a culture of peace. A complementary campaign promoted by the private sector has also helped to fill the gap during this period. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | Due to the high level of polarization caused during the electoral process in the first semester, we decided to launch the campaign after the elections, delaying the timing of its initial impact. After the launch, the campaign achieved important effects. The campaign reached at least 82% of the national public through TV and radio networks, and at least 15 million people through free-press media reports. The impact on social media has also been relevant with more than 50 million impressions on social media platforms and the internet. Local authorities are are incorporating the campaign into their activites.The successful implementation of the campaign has enabled the UNCT to raise supplementary funds from a bilateral donor, the Government of Norway, to extend the campaign for several months beyond the time frame of the PBF donation. This final phase of Breath Peace as a UN-spearheaded campaign is expected to run through mid-2015. Its focus is on national sustainability, by synthesizing the campaign in a readily-accessible format (as kits) and constructing strategic alliances with national counterparts who will carry on the campaign message in the future. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | The Breath Peace campaign is a highly innovative campaign with its unusual call to adopt breathing as an instrument that ordinary Colombians can use to achieve greater inner peace and peace within their communities. The message to stop, take a breath, and breathe peace was also understood at a metaphorical level as a message to the country as a whole. More conventional, lower-risk proposals could have been chosen, and there was considerable discussion internally as to whether the Breathe Peace campaign would be considered too "light" of a concept, given the deep structural challenges to building sustainable peace in Colombia that go beyond personal and cultural transformation. However the UN system chose this "out-of-the box" campaign concept, and it has been validated by the positive response received. |
| Gender marker: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | The campaign had a gender approach in content and language, as well as in its target. TV commercials as well as figures who have participated in the campaign were mostly women. The campaign also supoorted events with UN Women, UNFPA and UNICEF, among others UN agencies, for the promotion of gender as well as the fight against gender violence. In actions in the regions, women and women's organizations were highly represented. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) | The main activity in the field was the presentation of the campaign content in tandem wiht "Mateo", a colombian movie selected to run for Colombia for the Oscars Academy Award for Best Foreign Language Film. This allowed us to reach more than 25,000 people directly in field and 153 municipalities in 20 departments covering half of the main areas in the country as well as small towns. The movie estimulated reflection locally about the message of the film of how youth can escape violene through theatre and community. The UN system is current setting the stage to hand over the key elements of the RespiraPaz campign to national actors who can sustain its message beyond the life the UN campaign. Local authorities have already incorporated the message, as well as private companies and NGOs. Additionally, discussions are on going with the National Government and the complementary peace campaign beign promoted by the private sector (Soy Capaz). The existence in parallel, of this campaign, made it more difficult than anticipated to strike up individual alliances with businesses. As part of the free-press impact, the campaign produced more than 183 notes published in national and local media, that can be calculated in a Return On Investment (ROI) - editorial value of around the 1.7 million dollars. The TV comercials and other videos posted on the campaign's YouTube channel have over 400,000 views and a high rate of viewing of 15%. |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | Peace is an issue that continues to cause high polarization linked to political issues in the country. In order to achieve more impact towards a culture of peace, it is required to continually work to bring on board the widest possible range of influential actors of society: businesses, politicians, social organizations, churches, media leaders, etc. Fifty years of conflict has deeply degraded the value of life and permeated the society with violence, as seen not only the armed conflict, but in the even higher levels of violence not directly associated with it. Building a culture of peace in Colombia is thefore an enormous task. |
| --- | --- |
| Lesson 2 (1000 character limit) | Expectations of the impact of any communications campaign will depend on the duration and size of investment, particulary in a country the size of Colombia and with deeply ingrained tendencies towards skepticism and indifference towards peace. While we are confident that the Breach Peace campaign is making a memorable and noteworthy contribution to a culture of peace and the national discussion about peace at a critical time in Colombia, there will need to be more such efforts, well funded and sustained at the national and regional level, as well as increased coordination and partnerships, to have a deep and lasting impact. |
| Lesson 3 (1000 character limit) | This peace campaign has made possible first ever joint UN system-wide communication strategy in Colombia, strengthening the visibility of the UN system and its contribution towards peace issues. One of the challenging elements in this regard has been to maintain the active participation and interest of the widest possible number of UN agencies, funds and programmes, some of which more fully embraced the campaign than others. A strengthened outreach to UN agencies is paying important dividends in establishing the alliances for sustainability sought during 2015. |
| Lesson 4 (1000 character limit) | The campaign relied on a close partnership with one of Colombia's leading advertising agencies, Sancho BBDO. This infused the campaign with creative energies and high production values that marked all of its key moments and phases. At the same time, the vastly different institutional cultures and experiences between the two partners made for a constant challenge in ensuring that the campaign content was consistent with UN values and sensitivities, and that its limited resources, when compared to those available to typical commercial campaigns, were spent efficiently. |
| Lesson 5 (1000 character limit) |  |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

In 2015, the department of Nariño, southwestern of Colombia, promoted the campaign with the support of UN agencies, local and departmental entities and partners and local NGOs, joined in the initiative "Nariño Breathe Peace" (Nariño Respira Paz in Spanish), a platform for activities around peacebuilding and development in the region.  In February, the initiative commemorated World Wetlands Day (February 2) in the rural suburb of El Encano, out of Pasto, Nariño´s capital.

More than 300 children together with a visitors group, actively took part of activities such as puppets, music, painting, an ecological walk and forest restoration which were specially designed part to raise public awareness about the importance and value of the wetlands and the environment related to peace building.

In March, the initiative commemorated International Women's Day (March 8). In the El Encano suburb also, with 50 women leaders of peasant and indigenous community who participated in a forum with the movie "Mateo", part of the Breathe Peace campaign. In the event, the initiative recognized the work of rural women in main issues as food security, stability in rural areas, promotion of economic, environmental and social changes needed to achieve sustainable development and peace building from the territories.

Also, on Women's Day was officially launched "Breathe Nariño Peace" in Pasto with the presentation of the theater project "My body is a song of peace" which represents a key opportunity to make visible women as an example in peacebuilding. Over a thousand people enjoyed the play, produced by UNDP, in collaboration with UN Women, UNHCR and UNFPA, the Municipality and the Government of Nariño. "The play is a scenic adventure into the intricate world of women in times of storm, uprooting and pain of the territory. Women who travel illuminating hope, women laden with stories, memories and meanings for life traveling across the river memory to illuminate with their words and actions the life of the world ", say the playmakers.  The initiative has developed an events calendar to keep spreading the Breathe Peace campaign across the year commemorating special days to raise public awareness on peacebuilding issues.

Nariño initiative has spread to neighboring department of Cauca, where it was launched "Cauca Breathe Peace", also is expected soon other departments in the southwestern region of Colombia, one of the most affected by the armed conflict. The region is in the border with Ecuador and is on the Pacific coast, making it a corridor towards the area of Putumayo and Amazons with large plantations of coca and high presence of illegal armed groups. This region also has also been affected by high impact natural disasters events.

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures were on track, slightly delayed, or off track:

If expenditure was delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of project expensed budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: At the of end of the national communication campaign, at least 70% of a representative sample of the national public opinion, demonstrates higher awareness on how to contribute to a culture of sustainable peace and reconciliation. |
| Output 1.1 | Massive Media |  | USD 2,000,000.00 - 130.841.12 (indirect support costs UNICEF) 1,869,159 (Programmable amount) | USD 1,077,538 | Budget has been divided by outcomes but not by outputs since it is an integral massive campaign, as media mix normally suggests. |
| Output 1.2 |  |  |  |  |  |
| Output 1.3 |  |  |  |  |  |
| Outcome 2: More than 50% of representative sample of women and youngsters in two of the most affected regions by the armed conflict in the country are more prone to promote peace and reconciliation in their communities. |
| Output 2.1 | BTL Bellow The Line communication (community events) activites in prioritized territories. |  |  | USD 791,082 | Budget has been divided by outcomes but not by outputs since it is an integral massive campaign, as media mix normally suggests. |
| Output 2.2 |  |  |  |  |  |
| Output 2.3 |  |  |  |  |  |
| Outcome 3: |
| Output 3.1 |  |  |  |  |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total |  |  |  |  |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when) (2000 character maximum):

The campaign was lead by a UN Peace Committee integrated by the RCO, UNICEF, UNIC and UNDP, with the support of UNHCR, UNWOMEN, UNFPA, UNHCHR, and other agencies in Colombia.

The Government participated donating radio spaces in the main national public radio network rated as agreed for the project on USD300,000 in kind.

All UN stakeholders were involved in the campaing, such as private sector, academy, media, opinion leaders, celebrities and sports women and me, also NGO's and national and regional goverments.

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.