## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | SUPPORT TO JOBS, THE RESILIENCE OF THE SMALL ENTERPRISES AND INFORMAL WORKERS DURING AND BEYOND THE COVID19 IN CAMEROON | Overall Duration (months) | 12 Months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 01.01.2021
MPTF Office Project Reference Number: | MPTF_00209: UN COVID-19 MPTF | Original End Date (dd.mm.yyyy) | 01.01.2022
Country | CAMEROON | In case of NCE Current End date(dd.mm.yyyy) | 01.04.2022
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | ILO, UNFPA, UN HABITAT, UNESCO | National counterparts (government, private, NGOs & others) and other International Organizations |  The Ministry of Employment and Vocational Training (MINEFOP)  The National Employment Fund (FNE),  The Ministry of SMEs (MINPMEESA)  The Ministry of Women and Family Promotion(MINPROFF)  Ministry of Housing and Urban Development (MINHDU)  The Ministry of Public Health (MoH)  The Ministry of Youth and Civic Education (MINJEC)  The Ministry of Scientific Research (MINRESI)  The Ministry of Environment, Nature Protection and Sustainable Development (MINEPDDED)  The Ministry of Arts and Culture (MINAC)  Ministry of Communication (MINCOM)  Ministry of Territorial Administration (MINAT)  The municipalities  FEICOM  Employers' organizations  Workers' organizations  Civil society organizations (CSOs), Women Associations (National Chapter of the Organization for Women in Science for the Developing World), youth associations and networks (PAYNCoP, LOYOC, Youth National Council, Youth Connekt Cameroon, StrawAcademy, Accord Parfait, AfricAvenir-G54, DMJ)  Media, community radios
Report Cleared By
o Name: | Matthias Z. NAAB
o Title: | Coordonnateur Résident
o Email address: | matthias.naab@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | The overall goal of the project was to reduce the vulnerability of women and youth by contributing to the socio-economic response plan through supporting the creation and protection of jobs, small businesses and co-operatives for a better build back from the COVID-19 in Cameroon. The COVID-2019 MPTF II project has attracted the full support of institutional partners and Decentralized Territorial Authorities, who have mobilized in its implementation, with the technical assistance of UN Stakeholder Agencies. The Decentralized Local Authorities have become involved in the action demonstrating the role they can play with the population in a context of health crisis that has produced devastating effects on young people and women. Actions have increased people’s access to help and accurate information on COVID-19 protection measures, Family Planning and the fight against Gender-Based Violence (GBV) In particular, the following results were obtained: • 12 businesses owned by vulnerable youth have been created, • 317 women merchants and 4,800 women were educated about GBV and COVID-19, some of whom received COVID19 protection kits; • 48 leaders from youth and women’s organizations have had strengthened capacity to promote sexual and reproductive health, fight against COVID-19, and participate in decision-making. • 235 abused women and girls trained in coconut transformation; • 35 midwives trained in tracking Reproductive Sexual Health targets in the context of COVID-19 and the continuity of adolescent sexual and reproductive health (ARDS) services, prevention and management of COVID-19 for pregnant women. The synergy between the different actors has enabled the strengthening of the capacities of the target populations, in particular: . to achieve the empowerment of the population, mainly women and youth, including people with disabilities and local authorities through: - 16 training courses on behavioural change for 197 people, as well as 52 awareness sessions involving 477 participants. -media capacity building, Civil Society Organizations, purchasing and equipping of materials for the production and dissemination of content, dissemination of awareness-raising messages and promotion of life skills and resilience mechanisms, the fight against disinformation and hate speech. . strengthen the capacities of actors to promote women through the capacity building of three agricultural family schools with life skills; training sessions on ICT and entrepreneurship targeting 500 young people; the training of 300 artistic actors in cultural and creative entrepreneurship, copyright, neighbouring rights, intellectual property and digital dissemination; 100 women in crisis regions have been empowered technologically and vulnerable young people strengthened in 3D modeling and robotics. The response to the resilience of jobs threatened by Covid-19 has been organized according to a multisectoral approach allowing for the implementation of an interactive local IT system, to help hire young people, through 2 job stations installed within the partner Town Halls. Experimenting with job intensive approaches (HIMO) in urban sanitation works as a tool for job creation has mobilized 56 young people. In addition, a process of empowering women has been set up, including the training of 50 women active in the green economy, 20 of whom have benefited from Grants and successfully carried out their income-generating activities.
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | The project aims to contribute to the rapid recovery of vulnerable women and young people during the pandemic, and their post-COVID 19 resilience, and to contribute to the reduction of the negative socioeconomic effects of the COVID 19, through relevant actions. In total, the main findings on the effects of the pandemic on the labour market and informal economy workers have led the Government to seek a collaboration from the United Nations system to support the socio-economic response plan to deal with the negative consequences of the pandemic. A joint Socio-Economic Response Plan (SERP) for the United Nations system was developed and shared with the national side to contribute to national efforts to combat this health crisis.
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | The proposed interventions have contributed to reducing the economic and social vulnerability of women and youth through technical and financial support to combat job losses, reduce partial or total closures of micro and small businesses, but also empower them to be more innovative and resilient through sessionsto build the life skills of vulnerable women and youth. 134 young people were thus able to benefit from direct and indirect employment through activities promoting the creation of fast and sustainable jobs, particularly with activities of high labour intensity and women’s empowerment. While 304 young and female informal workers received training on occupational safety, health and hygiene. In addition, 2 terminals have been set up in the Councils of Douala 4 and Yaoundé II. The National Employment Fund (FNE) and the municipalities are actively preparing the operationality of the posts. 43 Small and medium-sized enterprises have been set up, including 21 in the green economy. In terms of building technical and professional skills to promote self-employment and socio-professional integration of vulnerable women and youth affected by the pandemic,109 persons of which 95 women in vulnerable situations benefited from technical and vocational self employment skills. 61 of them were able to set up income-generating activities. 3 Family and Technical Schools are equipped on media education programs. In terms of strengthening life skills, the project was able to contribute to the empowerment of the population, mainly women and young people, including people with disabilities, and local authorities through workshops and meetings. Thus, 6,329 women and young people from a total of 7,053 people benefited from know-how and human protection, while 6 Decentralised Local Authorities and 35 actors were able to promote among other things the conditions of women.
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | 1.1: The technical and financial capacities of women, vulnerable young people, micro-small informal enterprises are enhanced by improved access to the tools for labour-intensive jobs in pilot municipalities during and after COVID-19 51 women received empowerment training and 20 of them developed with the technical and financial assistance of the project, a Job and Income Generating Activity. 56 young people have strengthened their skills and capacities through job sites, 26 of whom are involved in a cooperative for the production of hide-noses. 1.2: Tools and means to facilitate access to innovative sustainable employment services (information, intermediation and placement) for vulnerable job seekers including women are being developed and applied in pilot municipalities 2 Jobs terminal have been set up in the pilot municipalities of Douala IV and Yaoundé II. 3 trainings were organized for the benefit of 71 executives of the FNE and the partner Town Halls and 2 others for the benefit of 20 young people in the experimental use of the jobs terminal. 2.1: Targeted tools and approaches to skills development for self-employment and professional integration are being applied for vulnerable women and youth at pilot sites 109 people including 95 women with self-employment skills and 3 EFAs trained and equipped in the field of work. 3.1: Women and youth's abilities are promoted in life skills for greater empowerment during and after COVID-19 7053 women and youth are seeing their life skills improved for greater empowerment during and after COVID19. 3.2: The capacity of decentralized institutions/actors to promote women is strengthened in terms of support for empowerment, social promotion and protection from violence and stigma during the pandemic The pedagogical and collaborative approach established contributes to strengthen the institutional capacities of the 6 Municipalities, the partners involved and 35 other actors in the action, thus helping them to master the processes for protecting the most disadvantaged and stigmatized layers in the face of Covid-19.
3.2 | Results: Gender | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | The project was implemented through a range of activities aimed at strengthening gender equality, empowering girls, and reducing gender discrimination and inequality. All activities benefit girls and boys alike. But the project targets are identified as a priority among the women and young people most affected by the health crisis and who are probably more easily affected by the decline in the volume of work, income and also by the cessation of activities. Some activities have mainly been dedicated to women, such as the empowerment of women in the communes of Douala IV and Yaoundé II. In addition, more than 80% of people who have benefited from life skills for greater empowerment during and after Covid-19 are women.
3.3 | Results: Direct Beneficiaries | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | (TOTAL 7435. Disagregated by population group and age range (Female: 6547 Male: 888 Children: XXX Youth 671 Elder: 320 People living with a disability: 01 Disaggregated by Location: Rural: 100 Urban: 3235 Any other location: XXX)
3.4 | Results: Indirect Beneficiaries | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | TOTAL: 300 + 400/day Estimated: 400/day and/or Verified: 300 At least 300 readers of the FNE newsletter produced in 300 copies, who are sensitized on the concept of terminal employment through a rather edifying article (Verified) 400 people per day who use the 10 out of 19 mechanical devices in operation and 1 electrical device built and installed in the Municipality of Yaoundé II (estimated) Institutional strengthening of 6 Decentralized Local Authorities (Douala IV, Yaoundé II, Bafoussam 3, Maroua, Ngaoundérée and Bertoua) and 3 Public Institutions (National Employment Fund -FNE, Green Jobs Promotion Programme in Cameroon - PPEVC and Integrated Support Programme for Informal Actors - PIAASI). Verified.
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words) | Project activities were implemented without exposing beneficiaries to additional risks and exacerbating inequalities and vulnerability because of the intervention. In view of the security situation and the crises in the North West and South West regions, the linguistic aspect was considered during the activities that included participants from these regions. In case there was competition, as was the case for access to Grants, the people not selected will be accompanied, despite everything, in the answer to their needs.
3.6 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | Unfortunately, the start of the MPTF II project took place very timidly, in a context strongly dominated by the health crisis, with measures to combat the spread of Coronavirus that were not compatible with a total deployment on the ground. Some Agencies have even had to deal with the management of some cases of contamination internally, which has forced to favour teleworking and often the holding of meetings in virtual mode even as the internet connection was not accessible everywhere. Moreover, the mobilization of institutional actors has been a source of incompatibility at the scheduling level in a COVID19 context. A request for extension will make it possible to make up for the delay. We can also note difficulties in measuring audiences following awareness radio sessions.
3.7 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words) | The implementation between several Agencies made it possible to highlight the individual qualities of each Agency and to put them at the service of the project. The identified convergence aspects amplified the outcomes and effects of the project. This coordination has enabled these Agencies to develop mechanisms which could possibly be exploited in the context of other actions. There is an enthusiasm, especially among young people, around the use of job kiosks as a tool for accessing employment. This tool thus reinforces the role of local authorities in the process of combating youth unemployment. The participation of the head of the Territorial Administration in the work of coordination of the production of the socio-economic recovery plans of the CTD (Decentralized local authorities), has undeniable added value, because thanks to him, have been incorporated in these plans, civil protection measures related to natural disasters and existing crises. • In capacity-building activities, it is imperative to maintain the momentum and put in place a monitoring mechanism through implementation partners to support beneficiaries in the training and use of distributed equipment, beyond the project period; • Advocate and train public partners to take action to consolidate the results and achievements of the MPTF II project; • Increase the share of communication activities with a view to popularizing business creation procedures so that all vulnerable young people can have access to accurate information and not fall into the trap of disinformation; • Where possible, obtain more funding for scaling up project activities.
3.8 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | The collaborative work between the different UN agencies has allowed for the mutual inspiration of working approaches and methodologies and the creation of synergies of action, planned as part of a weekly coordination meeting. UN HABITAT and the ILO have collaborated with the municipalities of Douala IV and Yaoundé II, enabling them to establish a communal development plan, the implementation of which is linked to the activities of the MPTF II project, thus giving them more impact and visibility. This is the case of the school project launched by the ILO, on the rehabilitation of water points identified by UNHABITAT and the City Hall of Yaoundé II and whose sustainability is included in the development plan of the Municipality of Yaoundé II. Innovative and practical means have been used by UNFPA to reach the maximum number of young people, notably through UNESCO’s community radio partners. Conversely, the players in these radios have been trained in comprehensive sexuality education, including life skills, SRG/FP, Covid-19 prevention and USRA orientation. Thanks to the partnership between the ILO and the FNE, the country’s first two Jobs Kiosks have been set up in Cameroon and in the municipalities of Yaoundé II and Douala IV, thus contributing to the territorial networking of the job offer and decentralizing access to employment. Some partners such as the World Bank are interested in the massive deployment of these job terminals on the national territory. Within the framework of the ArtResidence initiative and networks, innovative partnerships have been obtained by UNESCO, which have enabled not only to go beyond programmatic results by diversifying them, but also to mobilize additional funding.
3.9 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words). | No evaluation was conducted during the implementation of the project in 2021.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words). | Due to the Covid19 pandemic and to limit the dispersion of efforts, the Commune of Bafoussam III was ultimately not affected by ILO under MPTF II In addition, in terms of strategies, an acceleration plan for the implementation of the Project was put in place from the period July - October 2021 to catch up with the backlog of some implementing partners, At the same time, a 3-month extension without costs was requested. The implementation of this Acceleration Plan has made it possible to obtain satisfactory results that will be consolidated by obtaining the extension without costs of 3 months. Adjustments were also needed within UNESCO, which received some additional funding.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | The funds made available were managed according to the procedure manuals related to financial management in the various Agencies, and the “procurement” for purchases. Project managers have been recruited (ILO, UNESCO or UNFPA cases) or made available (UNHABITAT cases) to monitor the activities of the MPTF II project. Financial contributions from partners such as the German Cooperation have contributed to the capacity building of artists, their financial education and the establishment of financial inclusion mechanisms through credits in a financial institution to accompany the production of creative works. The Israeli embassy has mobilized and made available to trained artists US$10,000 for the production of video clips of their musical products. Mention should also be made of the financial contribution of UNESCO Headquarters for the financing of a series of Masterclasses with 105 participants in the artistic field in collaboration with TRACE TV and the mobile telephone operator MTN in the region in crisis. South-West Cameroon (Buea). ILO, for its part, benefited from the financial contribution of the RBSA COVID 19 project (Regular Budget Supplementary Account), which made it possible to take over a consultant to design, monitor and implement two job centres in Yaoundé II and Douala IV, and to strengthen the capacities of those involved in their use and handling, in order to facilitate the integration of young people and the workforce of the municipalities of Yaoundé2 and Douala4 in the context of the implementation of the ILO component, on strengthening the National Employment Fund.

## Project Indicators
Please include ALL indicators in the project document. Include the indicators and Baseline, Planned Target and Actuals for both OUTCOME and OUTPUT levels. "Actuals" refer to the total figures achieved for each indicator. Include separate actuals for 2021 and for 2022 (if applicable). Explain if targets were not achieved. Include means of verification. Use as many outputs cells as needed to present all project indicators.
| INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | DATA: ACTUALS 2022 (if applicable) | TOTAL actuals (agreggated 2021 and 2022 if applicable ) | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1
Indicator: | Number of vulnerable women/young, benefiting from socioeconomic recovery based on quick sustainable jobs and small grant
Baseline: | 0
Planned Target: | 300 (150 women, 150 young people) | 294 (163 women and 131 young people) | XXXXXX
Output 1.1 | [5 empty] | Daily Attendance Records/ Photographs/ Copies of Certificates of Participation
Indicator 1.1.1: | Number of rapid and sustained decent jobs created by High intensive Labour Approach in pilot communes
Baseline: | 0
Planned Target: | 150 (100 women, 50 young people) | 46 young people of which 21 are girls and women and 10 are municipal staff of which 5 are women. | XXXXXX
Indicator 1.1.2: | Number of beneficiaries of training on safety, health and hygiene at workplace; |  |  |  |  | Attendance forms. Terms of reference of the training of young people in school sites
Baseline: | 0
Planned Target: | 150 : 100 (informal young and female workers); 50 (women workers) | 294 young informal workers (163 women) and 10 community workers (5 women) | XXXXXX
Output 1.2 | [5 empty] | Financing contract; Photographs. Report of the consultant in charge of coaching women entrepreneurs. Newspaper articles.
Indicator 1.2.1: | Number of start ups and MSMEs led by women, particulary the most vulnerable, financed through micro grants.
Baseline: | 0
Planned Target: | 15 small business women particularly those operating in the green economy promotion | 21 micro-enterprises | XXXXXX
Indicator 1.2.2: | Number of pilot communes enhanced by the modern and digital employment services for vulnerable women and young job seekers |  |  |  | Due to the late start of the project due to COVID-19, the Commune of Bafoussam III, which had been identified, could not be affected by the action. | Photographs. Newspaper articles.
Baseline: | 0
Planned Target: | 3 | 2 | XXXXXX
Outcome 2
Indicator: | Number of women, particularly those in vulnerable situation, benefiting from technical and professionnal skills of self employment
Baseline: | 0
Planned Target: | 100 | 109 (95 women and 14 young people) | XXXXXX
Output 2.1 | [5 empty] | Photographs; Attendance records.
Indicator 2.1.1: | Number of women/young NEET empowered
Baseline: | 0
Planned Target: | 100 (50 women, 50 young people) | 109 (95 women and 14 young people) | XXXXXX
Indicator 2.1.2: | Number of TVET programmes and centers enhanced |  |  |  |  | Photographs; Attendance records. PV equipment receipt
Baseline: | 0
Planned Target: | 15 | 3 Agricultural family schools | XXXXXX
Outcome 3 | [5 empty] | Vidéo, reports, pictures
Indicator: | Number of women and young, particularly those stigmatized and in vulnerable situation, benefiting from lifeskills and human protection
Baseline: | 24697 (14 818 adolescents girls and 9 879 boys)
Planned Target: | 30 000 (75% adolescent girls, 25% boys) | 7053 ( 6329 girls and woman and 724 boys) | XXXXXX
Output 3.1 |  |  |  |  | Budgetary constraints. Difficulties in measuring audiences following awareness radio sessions. | Vidéo, reports, pictures.
Indicator 3.1.1: | Number of women and youth's benefiting from life skills for greater empowerment during and after COVID-19
Baseline: | 96862 (77 490 adolescents girls and 19 372 boys)
Planned Target: | 110 000 (75% adolescents girls, 25% boys) | 7053 ( 6329 girls and woman and 724 boys) | XXXXXX
Output 3.2 | [5 empty] | reports, pictures
Indicator 3.2.1: | Number of decentralized institutions/actors trained and become able to promote women conditions
Baseline: | 0 institutions/0 actor
Planned Target: | 3 institutions/20 actors | 6 decentralised institutions/2 actors*, 30 CSOs and 3 Agricultural Family Schools | XXXXXX
*National Employment Fund (FNE) and Green Employment Promotion Programme in Cameroon (PPEVC)

## Communication
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well as picture material please make sure you include all credits and share them in high resolution.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
Youth using the Employment Kiosk
A Beneficiary of the Women’s Empowerment Process
UNFPA Awareness Session
Beauty salon whose opening was supported by UNFPA
UNFPA Awareness Session
Mayor of Yaoundé II experimenting with an electronic hand washer installed in the Town Hall during the High labour intensity activities
MPTF II October 2021 Orientation Workshop
Training Workshop for 20 Community Radios on Covid-19 Resilience Mechanisms (UNESCO)
Meetings on ICT and Youth Entrepreneurship -Boostcamp (UNESCO)
Training and equipment for 300 women and youth from 3 Agricultural Family Schools (UNESCO)