## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | Immediate response to sustainable economic reintegration of young women in Chile | Overall Duration (months) | 18
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 01.01.2021
MPTF Office Project Reference Number: | MPTF_00209 | Original End Date (dd.mm.yyyy) | 30.06.2022
Country | Chile | In case of NCE Current End date(dd.mm.yyyy) | 30.06.2022
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UN Women, ECLAC, ILO and FAO. | National counterparts (government, private, NGOs & others) and other International Organizations | The Ministry of Labor and Social Security, the Ministry of Women and Gender Equity, the Ministry of Social Development and Family and their different services and programs (Chile Valora, Bolsa Nacional de Empleo, SENCE, Programa Mujeres Jefas de Hogar, Programa de 4 a 7, SERNAMEG, SENAMA), the Production Development Corporation (CORFO), the Ministry of Economy, the Export Promotion Bureau (ProChile), from the Ministry of Foreign Affairs and the Agriculture and the Livestock Development Institute (INDAP) from the Ministry of Agriculture. United Federation of Workers - CUT, the Confederation of Production and Trade - CPC. From the private sector, the WEPs Companies Network, the Global Compact Network, the Companies from the Gender Parity Initiative (IPG), and CPC. Local governments and the different services at a territorial level, in the Municipality of Renca in the Metropolitan Region and the Municipality of Padre Las Casas in the Araucanía Region. The Implementing partners are Innovacien and Fundación Emplea, Casa de la Mujer de Huamachuco, Programa de 4 a 7 San Pedro de Atacama, Fundación Datos Protegidos.
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | The Program was implemented successfully during the year, making progress in all the proposed indicators. One of the main achievements attained during the first year of the Program's implementation has been the establishment of many partnerships and collaboration networks, which have allowed to complete all the activities proposed at the beginning of the Program. The articulation of networks with different areas, actors, public and private sectors, employers and workers' organizations, civil society, communities, and other UN initiatives such as the MPTF project on Migrations, has led to the creation of better economic opportunities for women, especially for those that belong to the sectors most affected by the pandemic (heads of households, migrants, rural women, and caregivers). The MujeresEmplea.org virtual platform gathered employment opportunities, training programs, access to funding, and entrepreneurship and care services offerings (approximately 110 updated posts) with more than 33,000 visits during its implementation period. More than 700 women were trained on digital skills for employment or entrepreneurship, and approximately 300 women signed up for the labor insertion mentoring program. The women's job fair offered more than 22,000 job openings, and more than 10,000 women applied. Services supply and demand opportunities were provided for women entrepreneurs to implement projects with large companies through the ActivaEmpresarias.org platform that is soon to be launched, and that has the potential of expanding its services in the international sphere thanks to the support of ProChile and CORFO. The childcare services are available in two of the initially planned territories to facilitate the access of their caregivers to training programs and the labor market, with a daily capacity for 60 children. The certification process for women working in care services is already in place, and 200 women are currently part of it. The process of raising awareness and promoting care co-responsibilities has had a significant reach, both within the companies of the selected territories and in the general population, moving towards gender equality through communication strategies and workshops designed specifically for each target audience. The challenges faced during the implementation process have to do with the evolution of the pandemic in the territory, mainly due to mobility restrictions and social distancing imposed by health authorities that lead to delays in some of the Program's activities. Similarly, there have been delays in some activities due to the change of government authorities involved in the project at a local, national and institutional level. However, the activities were adapted to this situation to meet the Program's objectives. Many adjustments and learnings have taken place by articulating actors and initiatives that have allowed a faster implementation of the activities, especially in the selected territories. Also, a training, guidance, and care services provision strategy has been outlined, positively impacting women's insertion into the labor market. The information collected in the project will be used to promote the creation of public policies that address women's insertion in the workplace, decent labor, and care.
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | The project aims to promote greater women's and young women's economic empowerment. Its purpose is "For women and young women to improve their economic empowerment through greater participation in the labor market, especially in the technology and digital fields, and access care services under the framework of socio-economic recovery, immediate response and coordination for COVID-19."
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | Outcome 1 The MTPF project articulates a series of activities and the supply and demand to improve women's employability and their financial and labor opportunities. The MujeresEmplea.org platform, which has received more than 33,000 visits to date, includes work offers, training portals, information on subsidies, entrepreneurship incentive programs, care services, and free online courses updated on an ongoing basis. The 2021 Empleo Mujer Week job fair offered more than 22,000 job openings. Training programs were developed in the STEM and entrepreneurship fields, and these were articulated with the mentoring and workplace insertion program that provides labor opportunities and guidance to women. A network of public and private partners that work together to facilitate women's access to the labor market by connecting employment supply and demand was established. 9 cooperation/implementation agreements have been established with different institutions. It highlights the high commitment level of the Ministry of Labor and Social Security and the Ministry of Women and Gender Equity and their offices and other public institutions that is reflected in the active participation in the different initiatives of the Program. An Employers Network for Gender Equality was created to offer job openings for women to return to the workplace, either through internships, hiring, free training opportunities; implementing internal awareness-raising actions on care co-responsibility; and through their participation in the ActivaEmpresarias platform, a collaborative platform that seeks to connect the demands of the products and/or services of purchasing companies with the offer of supplier businesswomen. Collaborative work has taken place with the three selected local governments, Renca in the country's central area, San Pedro de Atacama in the north, and Padre Las Casas in the south, with which Collaboration Agreements were signed to implement the project at a territorial level. Outcome 2 Childcare services were implemented in two of the selected communes through partnerships with daycare institutions already in operation. A diagnosis on the supply and demand of care services was conducted for the commune of Renca, and the experiences on community care from Casa de la Mujer de Huamachuco in Renca were gathered to create recommendation guidelines to be used and implemented in other communes or sectors. We are currently working on creating a network of 300 certified female caregivers. This initiative lays the foundations to establish a national caregivers' network. Skills and care certifications allow women to access jobs with better labor conditions and show and acknowledge the vital role they play in our society.
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | Output 1.1 An integrated platform aimed at women's employability, connecting supply and demand. The MujeresEmplea.org platform was created and launched, and it already has 33,000 visits and 12,000 users that have logged in to obtain information on employment opportunities (16 job portals), training sessions (20 portals offering free training courses on STEM skills), caregiving services (four institutions), entrepreneurship programs (6 programs and 22 grants), subsidy programs for women (3), among other offerings that are updated every week. This platform is connected with the "Tu Oportunidad" program from UN Women that offers training sessions for women in several areas for their personal and economic development, and the "Originarias program" targeted at indigenous women in the country. It is interconnected with the largest job portal in Chile, Bolsa Nacional de Empleo. That platform hosted the "Semana de Empleo Mujer" job fair, offering more than 22,000 job openings for women, focusing on migrants. More than 10,000 women applied to the job openings. Workshops on socializing the platform took place to get to know women's experiences in two of the selected territories (San Pedro de Atacama y Padre Las Casas). A communication campaign was conducted to have all the institutions involved in the MPTF promote the platform, and it reached more than 170,000 people. In parallel, the ActivaEmpresarias.org platform was developed, connecting companies and entrepreneurs to close deals to purchase and sell products and services. The platform will be launched in March 2022. Output 1.2. Setting up a public and private partners network to promote sustainable employment plans for women, particularly for young women at a national and local level. The Program has established a network of public and private partners. Nine collaboration agreements and/or MoUs have been signed between the United Nations System and local governments such as the municipalities of Renca, Padre las Casas, and San Pedro de Atacama, and with the Production Development Corporation (CORFO) of the Ministry of Economy, and the Export Promotion Bureau (ProChile). The members of the ILO, the Ministry of Labor and Social Security, the United Federation of Workers (CUT), and the Confederation of Production and Trade (CPC) act as implementing partners of the project and participate actively in its activities. This has contributed to promoting social dialog for reinserting women into the workplace. Partnerships were established with ChileValora and SENCE, which provided funding to certify more than 300 female caregivers, collaborating with Universidad Federico Santa María and other higher education institutions such as INACAP. In addition, the community institution Casa de la Mujer de Huamachuco participates actively in the project by implementing the care services pilot program in the commune of Renca, and it acts as a strategic partner for the promotion of co-responsibility in care services at a local level. A collaborative partnership was established with the Ministry of Women and Gender Equity and the Ministry of Social Development and Family, which provide their support to all the Program's activities. Bilateral meetings are held on a periodical basis and diverse programs and services that depend on these organizations (Women Heads of the Household program, 4 to 7 program, SENAMA, among others) are included in the Program. The private institutions with which collaboration partnerships have been established are Microsoft, Claro, Cervecerías Chile, and Laborum. An articulated work is developed with IPG (Gender Parity Initiative) companies network and WEPs Companies within the framework of the Network of the Employers Network for Gender Equality. In this context, workshops have also been held to promote gender equality in companies. During this period, the funding for the basic digital basket was completed, and an assessment of the mechanisms that could be used for its implementation was conducted. This activity occurred within the agreements' framework of the Sixtieth Meeting of the Presiding Officers of the Regional Conference on Women, 2021. Within this context, the Ministry of Women and Gender Equity became interested in implementing the Basic Digital Basket proposal for women in the country. This activity has been escalated, as the Ministry invited the Undersecretariat of Telecommunications, and the Ministry of Social Development of Chile to become part of this initiative. Output 1.3. Training pilot program implemented in technology, entrepreneurship, labor, and women's rights issues to improve women's employment, particularly young women in the labor market. A training sessions plan on digital skills targeted at women, especially young women, was created. Up to date, five training cycles have taken place with the participation of 374 women gaining digital skills. Likewise, together with the European Southern Observatory (ESO), seven women were further trained in technical and labor skills to work in large astronomical observatories as coating operators in coordination with "Tu Oportunidad" program. In parallel, three trainers were trained in the Start and Improve Your Business (SIYB) program of the ILO in the selected communes, where 118 women entrepreneurs participated. Similarly, together with the company CLARO, 200 women have been trained under the framework of the digital skills program, and at least 200 more women will be trained during the first semester of 2022. The training process has been coordinated with the labor insertion, internships, and mentoring process, generating a workflow and a referral mechanism so that the women who complete their training programs can continue with their socio-economic integration process. During the job fair, women were offered access to mentorship programs. Out of all the women who signed up to the courses offered by the Mujeres Emplea program and registered at the job fair, 397 have been referred to the mentoring and guidance process, and 93 have started or have completed a social and labor diagnosis. 340 mentorships were provided for a total of 109 women. The labor insertion process has been the most difficult to implement stage due to the different interests of the women that were part of the Program, and the job offers from the companies. To date, 28 women have received guidance and financial incentives for their labor insertion, out of which 14 women have obtained a job, either through internships or job openings. Two supplementary training cycles for women in these areas were designed during this period, one on digital skills and another on digital security. Output 2.1 A strategy to coordinate existing public and private assistance services was created to facilitate the participation of women, specifically young women, in the labor market and business initiatives. Caregiving services institutions were identified to implement the Program in the three selected communes; collaboration and implementation agreements were stablished with two of them, and the third one is pending to offer childcare services for the women of the commune that are part of the Program. Currently, there is the capacity to provide childcare services daily to 60 children in Renca and San Pedro de Atacama. In parallel, the successful experience of community care of Casa de la Mujer de Huamachuco with more than 30 years of operation was systematized. A recommendations guide was drafted to replicate this project in other places. A road map was created with recommendations to implement childcare services for each commune involved in the project. This includes a supply and demand diagnosis for childcare services with the corresponding recommendations to design a successful policy. In parallel, awareness-raising and training workshops were designed for municipal teams integrating the main elements of the caregiving and gender equality policies and a training cycle for domestic workers. The collaborative work with Chile Valora has allowed coordinating certification cycles for women caregivers in the selected communes. A partnership with SENAMA (Senior Citizens National Service) was established to certify the women caregivers from that institution, to create a network of 300 women caregivers. Output 2.2 A greater level of awareness was developed to acknowledge and re-distribute unpaid housework and care work and promote co-responsibility between men and women, the State, the market, families, and the community. A communication campaign to promote co-responsibility in care has been launched in social media and the press. The campaign will be stronger during women's month, March 2022. For this, a quick gender diagnosis took place focusing on the need to have support in care work and unpaid housework focusing on a society of care. The target audience consisted of 2000 women participants of the programs implemented by UN Women in Chile. This initiative is developed with the purpose of highlighting the situation experienced by women in Chile. The information collected will be used as the main axes to create awareness on this topic. Up to date, there are 11 posts on social media with a reach of more than 26,000 users. In parallel, awareness-raising workshops were held on the co-responsibility of care with people from San Pedro de Atacama and Padre las Casas communities. In these instances, women engaged in participatory dialogs portraying their challenges and acknowledging the value of this work within the community. Municipal workers also participated in listening to the different realities of women in these issues. Technical assistance has been provided permanently for the Time Use National Survey pilot program of the National Institute of Statistics (INE) that will be implemented as a module on time use of the National Employment Survey conducted every quarter. The support provided consists of the collaborative work between ECLAC, ILO, and the National Institute of Statistics with ongoing meetings in which advice is provided to design questions, questionnaires, fieldwork, etc. Furthermore, technical assistance is being prepared for local governments in issues related to the project to create a work agenda at a community level for women's economic empowerment that considers topics as employability and co-responsibility of care services.
3.2 | Results: Gender | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | This project's outcomes are within the Gender Equality and Women's Economic Empowerment (GEEW) framework. The gender equality marker for this project is 3. This project aims to improve women's empowerment by participating in the workplace and increasing the offer of care services. The project has a significant component to create awareness and promote co-responsibility in care. The launch of advertising campaigns, gender awareness-raising workshops in the companies and the communities, and the workshops for municipal workers impact not only the women of each sector but in the communities where they are implemented and in the general population. SERP Indicators Regarding the global indicators of the United Nations System Plan for Economic Recovery in the Framework of the Pandemic (SERP Plan), the MPTF project contributes to the Third Pillar "Economic Response and Recovery," specifically in the promotion of decent, safe, and sustainable labor for women, in supporting sustainable small companies led by women, and promoting entrepreneurship in women of rural areas. 1. Indicator 3.1: Reinforcement of employment policies and a proper regulatory environment for economic recovery and decent labor, especially in sectors where women are more exposed to COVID. Although the project is focused on creating a rapid response to the impact of the crisis generating actions that contribute to the labor insertion of women, especially young women, migrants, residents of rural areas, and members of indigenous communities, it also generates evidence to create policies that promote decent labor. Through the training pilot program that aims at providing training and labor insertion opportunities for women of the target population in STEM areas, the objective is to generate evidence that can be used to design policies that promote decent labor in these sectors, also helping to close the digital gender gap. Moreover, the training and certification activities of women belonging to the caregivers' network move in line with improving work conditions and acknowledging the critical role they play in society. The development of training material on labor rights contributes to female workers knowing and exercising their rights in the workplace. In addition, considering that one of the most frequent barriers in the participation of women in the workforce is their unpaid care and housework responsibilities, the actions with the public sector to design a strategy to coordinate the existing services at a community level and provide a fast implementation solution, are initiatives that can be replicated in other sectors of the territory. The previously mentioned activities seek to promote decent labor with a gender perspective. 2. Indicator 3.2: Number of companies from the private sector and workers from the formal and informal sectors supported during and after the COVID-19 pandemic. This global indicator reflects the work with women entrepreneurs providing training opportunities in several areas. One of them is the incorporation of their businesses to promote their position as vendors for more demanding markets (large companies), fostering the growth of their businesses. And in a second stage, with the involvement of ProChile, reach international markets. Progress is being made by providing training to many women, giving them access to better work conditions and formal job opportunities in some cases.
3.3 | Results: Direct Beneficiaries | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | The total number of the Program's direct beneficiaries is 24,799. Details on the program’s direct beneficiaries Component Beneficiaries Platform 13,202 Training programs - Innovacien 374 Training programs - IMESUN 118 Training programs - Observatorio ESO 7 Training programs - CLARO 200 2021 Job Fair Users 10,781 Childcare Pilot Program - For Children of Renca 22 Care Services Pilot Program - For Women of Renca 17 Childcare Pilot Program - For Children of San Pedro 40 Care Services Pilot Program - For Women of San Pedro 38 Total 24,799 It was not possible to disaggregate all the information due to the mentioned variables. However, disaggregation by geographic area is conducted. - Central Zone Beneficiaries: 20,935 - Northern Zone Beneficiaries: 533 - Southern Zone Beneficiaries: 747 - Undetermined Zone Beneficiaries: 2,584 When disaggregated by age, four groups can be identified: - Beneficiaries of 14 years old or younger. 62 - Beneficiaries between 18 and 35 years old. 5,944 - Beneficiaries between 36 and 55 years old. 5,085 - Beneficiaries older than 55 years old. 243 - Beneficiaries of undetermined age. 13,465
3.4 | Results: Indirect Beneficiaries | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | The total number of indirect beneficiaries of the Program corresponds to the total population of the communes selected by the Program and the sum of the companies' workers that have attended the gender issues awareness-raising workshop. Estimated Total: 295,916 Estimated Population of San Pedro de Atacama: 10,434 Estimated Population of Renca: 160,847 Estimated Population of Padre las Casas: 82,110 Estimated Workers of Participating Companies: 42,525
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words) | As mentioned many times, the pandemic has disproportionately affected women because they have had to undertake care responsibilities. In many situations, they have had to leave the labor market. The intervention focuses on providing better conditions for women to improve their economic conditions. It has a particular focus on women that have been identified as the most affected, explicitly working with groups of rural, indigenous, and migrant women. The work has been conducted at a territorial level, considering the needs and particularities of the population and the communities involved. It has allowed creating a significant impact in the groups most affected by the pandemic and addressing their challenges accordingly.
3.6 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | The main challenges encountered have been the social distancing measures imposed due to the health crisis. This was identified in the risk management matrix, scheduling online activities. However, some in-person activities had to be adjusted to meet the regulations imposed, the venues to provide care services had to be larger, and the number of participants had to be reduced to meet the reduced capacity of the premises. The electoral process identified in the risk matrix has implied a delay in the coordination with the local governments renewed during 2021. Partners were identified within the territories to implement the project to mitigate the risk, thus accelerating its execution. During the development of the care services diagnosis at a commune level, an information gap was identified, thus leading to design a strategy for each municipality to survey their corresponding updated information. The lack of access to technological devices to take online courses was identified. Therefore, arrangements were made to provide public spaces with computers to increase women's access to the Program. In addition, computers were donated to the Municipality of San Pedro de Atacama, one of the communes with most connectivity issues; these were installed permanently and are available to the women of the Program.
3.7 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words) | The articulation and coordination between the different existing programs and the performance of activities that involve different public and private institutions allow providing women a broad range of possibilities to join training courses, access work opportunities, entrepreneurship funding, and care services. The design of a pilot program at a community level (training-internships/labor insertion-access to care services) is a holistic solution for economic reactivation in the communes with a gender perspective that addresses central elements that have restricted the economic participation of women, especially after the COVID-19 pandemic. At a territorial level, the articulation with local initiatives stands out since it has reduced preparation times for implementation. An example of this is the use of the installed capacity on the territories, such as areas with computers and internet access where women can attend training sessions and community areas that offer care services. A great and successful internal articulation was achieved, coordinating and executing initiatives with shared objectives, such as the collaboration with the Migration MPTF, the NODO SDG Project, other interagency projects of the United Nations System in Chile, and with the Second Chance Education and the Originarias Programs, both from UN Women in Chile, reaching more women in a more expeditious way. This has created synergies between different programs from the UN System and has become a best practice for the Delivery as ONE Program that can be replicated in other UNCTs. In parallel, work was conducted with the companies looking for women workers and with women looking for job opportunities, which allowed to develop initiatives based on actual needs. A series of adaptations were made to the training program to align them with the digital skills of women and the needs of the companies. The Program was strengthened with mentorships and guidance that promote women's autonomy in their labor insertion.
3.8 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | The project is implemented in association with the Ministry of Labor and Social Security, the Ministry of Women and Gender Equity, the Ministry of Social Development and Family and their different services and programs (Chile Valora, Bolsa Nacional de Empleo, SENCE, Programa Mujeres Jefas de Hogar, Programa de 4 a 7, SERNAMEG, SENAMA), the United Federation of Workers (CUT), and the Confederation of Production and Trade (CPC). The project also includes the participation of other public institutions according to the activities implemented, such as the Production Development Corporation (CORFO), the Ministry of Economy, the Export Promotion Bureau (ProChile), from the Ministry of Foreign Affairs and the Agriculture and the Livestock Development Institute (INDAP) from the Ministry of Agriculture. Collaborative work has taken place with local governments with which collaborative agreements have been signed in Renca, Padre Las Casas, and San Pedro de Atacama. These partnerships have allowed the Program to be implemented in the territories and achieve the proposed objectives. The work plans of CUT and CPC show their high level of commitment to the project. Those organizations have collaborated promoting women's labor rights, have brought closer the supply and demand of work for women, and collaborative work has promoted social dialog on these issues. Within the "Employers Network on gender equality framework," gender awareness-raising programs were implemented in the private companies part of the WEPs Companies network, the Global Compact Network, and the Gender Parity Initiative (IPG). The cooperative partnerships with CLARO and Microsoft supporting the training programs must be highlighted. The partnerships created with Casa de la Mujer de Huamachuco, a civil society institution led by women, with Universidad Federico Santa María and Instituto INACAP have viable the implementation of the different initiatives of the project in the territories.
3.9 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words).
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words). | During the conversations with women in the mentoring programs, it was observed that women were more interested in accessing job opportunities than internships in the companies. This alternative was included as one of the paths to follow, and an economic incentive was associated with the active job-seeking process. This incentive is targeted at women who are actively seeking employment opportunities or who get a job through the Program. It is intended to cover their initial costs such as transportation and meals. In parallel, autonomous job-seeking has been promoted and supported through mentors' ongoing guidance.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | The Program has mobilized many resources from both public and private institutions. The company CLARO Chile contributed with 400 digital skills training courses, including one computer for each woman participating in the Program, valued at USD 297,143. Similarly, they contributed with a Software Applications Developer course for 25 women, valued at USD 13,001. The total contribution adds up to USD 310,144. Microsoft committed to providing a digital skills training course for 400 women, which also includes the provision of an account that allows the participants to use all the applications of the Office suite (Word, Excel, Teams, PowerPoint, etc.), free of charge, and valued at USD 222,609. Three scholarships were provided for a train-the-trainer workshop in the framework of ILO's Start and Improve Your Business (SIYB) program, valued at USD 1,100 each, adding up to a total of USD 3,300. The public institution ChileValora (Commission of the National Certification System) will certify that the Program's caregivers network consists of 300 women. This service is valued at USD 93,168. In parallel, higher education institutions such as Universidad Santo Tomás and INACAP will lend their facilities to conduct these certifications, valued at USD 4,658. With a total contribution of USD 97,826. The Municipality of Renca has also made a financial contribution to implement care services at Casa de la Mujer de Huamachuco, valued at USD 4,484. At the date of this report, the total mobilized resources for the project are USD 638,363.

## Project Indicators
Please include ALL indicators in the project document. Include the indicators and Baseline, Planned Target and Actuals for both OUTCOME and OUTPUT levels. "Actuals" refer to the total figures achieved for each indicator. Include separate actuals for 2021 and for 2022 (if applicable). Explain if targets were not achieved. Include means of verification. Use as many outputs cells as needed to present all project indicators.
| INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | DATA: ACTUALS 2022 (if applicable) | TOTAL actuals (agreggated 2021 and 2022 if applicable ) | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | [5 empty] | National Employment Survey - INE Quarterly Report
Indicator: | Women's Labor Participation (National): Women in the Work Force (Working+Looking for a Job)/Female Population in working age (National) | 47.3%
Baseline: | 43.9%
Planned Target: | 48% | 48%
Indicator: | Women´s participation rate in Labor Market (Araucanía Region) | 40.2%
Baseline: | 35.7%
Planned Target: | 42.1% | 42.1%
Indicator: | Women´s participation rate in Labor Market (Antofagasta Region) | 50.7%
Baseline: | 44.6%
Planned Target: | 49.8% | 49.8%
Indicator: | Women´s participation rate in Labor Market (Metropolitana Region) | 52.9%
Baseline: | 44.9%
Planned Target: | 50.4% | 50.4%
Output 1.1 | [5 empty] | Information collected from Google Analytics MujeresEmplea.org
Indicator 1.1.1: | Number of users in the platform | 13202
Baseline: | 0
Planned Target: | 70000 | 70000
Output 1.2 |  | 9 |  |  |  | Partnership MoUs or agreements of implementation signed
Indicator 1.2.1: | Number of partnerships endorsed by RC and leading agency Reps.
Baseline: | 0
Planned Target: | 10 | 10
Output 1.3 | [5 empty] | Reports of the registration on trainings in digital skills, STEM and Enterpreunership
Indicator 1.3.1: | Number of young low income women trained in technological, labor and women`s right and entrepreneurship areas | 699
Baseline: | 0
Planned Target: | 2000 | 2000
[5 empty] | labor insertion is added to this indicator, due to the interest of women | Reports of the registration on mentoring and labor facilitation
Indicator 1.3.2: | Number of young low income women with internships completed or entering the labor market | 14
Baseline: | 0
Planned Target: | 400 | 400
Outcome 2
Indicator: | Number of care service demand and supply posts in the platform | 11 |  |  | The value of this indicator goes from 2,500 to 25, because in principle it corresponded to jobs in demand and offered on the platform. Now it corresponds to the number of care services included in the platform. It is closer to the reality of the services established in Chile. | Specific reports of care service cases posted in the platform
Baseline: | 0
Planned Target: | 25 | 25
Output 2.1 | [5 empty] | Copy of agreements uploaded to project M&E reports
Indicator 2.1.1: | Number of signed agreements between public and private care service initiatives and the project leading | 4
Baseline: | 0
Planned Target: | 5 | 5
Output 2.2 | [5 empty] | Verification and contrasting of project formulation components/parameters and Project M&E reports
Indicator 2.2.1: | Number of components of the strategy implemented, including parameters related to campaigns, workshops, polls, and technical assistance delivered at local governments (municipalities and regions) | 0.6
Baseline: | 0
Planned Target: | 1 | 1
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
Aylin Palma, from the commune of Padre Las Casas, participated in the digital skills training courses. She is an entrepreneur and now wants to work as an employee. Aylin joined the Program through an invitation sent by the Municipality. She remarks that the training courses have provided her updated information on how the digital world operates, which has been very important to become up to date with the new generations in new technologies, both for her business and the job she is seeking. She enjoyed the virtual modality of the Program because of the flexibility it provided, and she also appreciated the course's teaching methodology. She claims that the course has changed her and that her attitude towards life has improved. Now she feels like she can do more tasks independently and online to improve her work skills. https://drive.google.com/drive/folders/1wBAdxVtbKsVrfFYUnVUP4odDZuMDALcZ
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well as picture material please make sure you include all credits and share them in high resolution.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board