## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | Strengthening economic resilience and food security for women Home Based Workers and women farmers | Overall Duration (months) | 09 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 01.07.2021
MPTF Office Project Reference Number: | MPTF_00209: UN COVID-19 MPTF | Original End Date (dd.mm.yyyy) | 31.3.2022
Country | Pakistan | In case of NCE Current End date(dd.mm.yyyy) | 31.5.2022
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UN Women , UNFAO | National counterparts (government, private, NGOs & others) and other International Organizations | Pakistan Village Development Program (PVDP) NGO partner Balochistan Rural Support Program (BRSP) NGO patner
Report Cleared By
o Name: | Julien Harneis
o Title: | Resident/Humanitarian Coordinator
o Email address: | harneis@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Extension obtained in 2022

## Narrative
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | The overall objective of the project is to strengthen economic resilience and food security for women Home Based Workers and women farmers whose livelihoods have been affected by the Covid-19 pandemic, through existing government programs, cash grants, and skills training for initiating micro-enterprises. The project is being implemented in three districts each of Khyber Pakhtunkhwa (Peshawar, Kurram and Swabi) and Balochistan (Quetta, Pishin and Lasbela).Through the project framework the project is contributing to the interagency collaboration and partnership through alignment with the ‘One UN’ approach under the United Nations Sustainable Development Cooperation Framework UNSDCF 2018-2022” The project also promoted the ‘One UN’ approach, with UN agencies working to achieve results under the overall coordination of the Resident Coordinator’s office. Due to shorter duration i.e., nine months, the project followed an expedited plan from the inception to keep track with the workplan. The three months reporting period (Oct-Dec 2021) was mostly utilized by both the agencies for the ground level preparations to kick-start the work as planned. During the period, the major activities carried out were; staff hiring and orientation by both the agencies, onboarding field Responsible Parties (RPs) by UN Women (FAO does direct implementation), obtaining project NOCs from the government for operating in the target districts, union/village councils identification/selection, coordination among UN Women and FAO to ensure complementarity of interventions at the field level, community mobilization, formation of village/union council committees, baseline survey, awareness sessions with community on prevailing social safety nets, coordination meetings with stakeholders at union council level, radio programs for awareness around women rights, laws and Gender Based Violence (GBV) and monitoring visits to the field to validate progress, identify roadblocks, and ensure timely roll out of interventions. The project team has challenges while implementation including extreme delays in getting NOC for district Kurram, restrictions on physical interactions due to COIVD-19, cultural constraints meaning only women staff is able to access women beneficiaries, mobility issues etc., However, with proper planning, the teams were able to overcome these challenges and maintain a momentum for activities as planned.
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | The overall objective of the project is to strengthen economic resilience and food security for women Home Based Workers and women farmers whose livelihoods has been affected by the Covid-19 pandemic, through existing programs, cash grants,livelihood by distributing seed along with gaots and skills training for micro-enterprises. The theory of change is that when women are provided with livelihood opportunities and social protection, they can become economically empowered, can supplement the family’s income, increase their food security, and contribute to lifting their families out of poverty. The provision of more opportunities to women in the form of education, better health, possession of assets, provision of credit, employment opportunities and political empowerment starts a 'virtuous cycle' for their family and for the country. In times of increasing food insecurity, it is important to ensure that the purchasing power of households is not affected tremendously. Women headed households, women with disabilities and transgender persons are at a greater risk of food insecurity which were specifically identified and targeted within the categories of HBWs and women farmers. In addition to immediate goals, the project includes the gender transformative goal of sensitizing men towards increased responsibilities of women during lock downs and encouraging them to share the caregiving and domestic responsibilities through attitude and behavior change and encourage them to allow women control over their income.
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | The progress against project overall goal cannot be reported as in the reporting quarter, the project was in the inception stage.
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | The project couldn’t contribute considerably to the output level results as much of the efforts were put to commence the ground level work through establishing outreach to the target beneficiaries and building coordination with the service providers for the intended linkages of beneficiaries with the social safety nets. It is hoped that greater access to social safety nets and agri interventions like kitchen gardening, livestock and food processing will supplement family income and keep food purchasing power constant in times of economic stress. The identification process of women HBWs and women farmers initiated to be equipped with much needed skills on entrepreneurship and business development supplemented with the one-time cash grants to revitalize their micro-enterprises lost during COVID. This support is expected to increase economic participation which will raise household incomes and start a ‘virtuous cycle’ leading to economic empowerment of women. The project consistently adhered to the principle of leaving no one behind: It targeted women from the least developed and vulnerable communities, living at the lowest ebb of socio-economic indicators, who aspire to become economically active as well as women with disabilities.
3.2 | Results: Gender | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | GEWE is the principal objective of the project that focuses specifically on women HBWs and women farmers. The 100% direct beneficiaries are women whose livelihoods have been affected/disrupted by the COVID 19 pandemic and revitalization of the lost livelihoods will predominantly contribute towards COVID 19 response. The project includes the gender transformative goal of sensitizing men towards increased responsibilities of women during lockdowns and encouraging them to share the caregiving and domestic responsibilities through attitude and behavior change.
3.3 | Results: Direct Beneficiaries | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | Please refer to beneficiaries sheet
3.4 | Results: Indirect Beneficiaries | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | Please refer to beneficiaries sheet
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words) | The do no harm principle is adhered and the most vulnerable women are accessed. A selection criterion has been developed for identifying the beneficiaries. The selection prioritized high poverty rates, women headed households, areas with insufficient coverage of safety net programmes.
3.6 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | COIVD-19 Omicron Variant Wave prevented the field teams from visiting the field to roll out activities and monitor progress. The teams are vaccinated and following SOPs to keep themselves as well as community members safe. NOC for District Kurram (for UN Women) has still not been issued:. It is expected to be granted in Jan 2022. Cultural constraints: accessing women to conduct HBW identification survey, in the two target districts, especially Swabi and Pishin was challenging. The women Social Organizers have been on-board to fill out the HBW evaluation forms. In KP, because the men household members are part of the committee at Village Council and Union Council level, they are comfortable with women staff speaking to their women household members.
3.7 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words) | UN Women and FAO have been in close coordination throughout the implementation of the project. The provincial offices held multiple meetings at the onset of the project; the agencies coordinated on multiple levels, to plan for and conduct the baseline survey. The Islamabad offices of both FAO and UN Women met regularly to share progress and baseline related challenges. The two agencies plan to conduct baseline validation workshops jointly in Peshawar and Quetta to ensure cost efficiency. The agencies plan to continue this coordination by meeting regularly at provincial as well as Islamabad offices level.
3.8 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | Provincial teams have been liaising with relevant stakeholders i.e., government departments, civil society, local community groups etc., to develop a sense of ownership among these stakeholders which will ultimately add to the project’s sustainability.
3.9 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words). | A basline study has been conducted under the project both by FAO and UN Women
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words). | Nil
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | During the reporting period, the project utilized funds amounting to USD 148,034/- which is 15% of the total project budget. The key cost centres during the reporting period remained staffing, Responsible Parties advances and travel for field visits. Total Project Budget - $1,700,000/- Total Utilization (Jul 2021 - Dec 2021) - $253,883/- (15%) Utilization for the Quarter (Oct-Dec 2021) - $150,239/- (9%)

## Beneficiaries
Direct Beneficiaries
| Khyber Pakhtunkhwa | Balochistan | Total | Remarks | Age brackets | PWDs
Women | 10780 | 9320 | 20100 | Project support activities | 18-55 years | 500
Women | 3 million | 2 million | 5 million | Media campaign | 18-55 years
Men | 3 million | 2 million | 5 million | Media campaign | 18-55 years
Indirect beneficiaries (@ 6.5 per household size)
| Khyber Pakhtunkhwa | Balochistan | Total | Remarks | Age brackets | PWDs
Men and women | 70070 | 60580 | 130650 | 6.5 per household size | includes all age brackets | Included in total

## Project Indicators
Please include ALL indicat+A2:G10ors in the project document. Include the indicators and Baseline, Planned Target and Actuals for both OUTCOME and OUTPUT levels. "Actuals" refer to the total figures achieved for each indicator. Include separate actuals for 2021 and for 2022 (if applicable). Explain if targets were not achieved. Include means of verification. Use as many outputs cells as needed to present all project indicators.
| INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | DATA: ACTUALS 2022 (if applicable) | TOTAL actuals (aggregated 2021 and 2022 if applicable ) | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | Vulnerable women and HBWs, especially those affected by the COVID19 pandemic, have stronger economic resilience and food security. |  |  |  |  | Perception & skills survey/Household Resiliency Index survey
Indicator:1 | Percentage of women with improved economic resilience
Baseline: | 0
Planned Target: | 80%
Output 1.1 | Vulnerable women and HBWs have improved access to social safety nets.
Indicator 1.1.1: | Number of women and excluded groups linked with available social services and operational social safety nets
Baseline: | 0
Planned Target: | 10000 | 0 | NA | NA | The activity faced delay in the inception phase. Expedited plan has been adopted and the target will be achieved by May 31, 2022 | Government data, project records Monitoring reports from Project Delivery Units
Indicator 1.1.2: | Number of women to whom one-time cash transfers are provided
Baseline: | 0
Planned Target: | 4000 | 0 | NA | NA | Not planned for the reporting period | Records of the service provider Project records i.e. verification sheets, mobile sums , activity photographs, Monitoring reports from Project Delivery Units
Output 2.1 | Women farmers, HBWs and entrepreneurs have the skills and resources for increased economic participation.
Indicator 1.2.1: | Percentage of women beneficiaries employed in income-generating work. | N.A |  |  |  | Perception & skills survey
Baseline:
Planned Target:
Indicator 1.2.4: | Number of women owned micro/small enterprises supported through economic recovery solutions to mitigate impacts of COVID19.
Baseline: | 0
Planned Target: | 300 | 0 | NA | NA | Not planned for the reporting period | Beneficiary lists, attendance sheets, photographs, activity reports Monitoring reports from Project Delivery Units
Indicator 1.2.5: | Number of women trained on business development and entrepreneurial skills.
Baseline: | 0
Planned Target: | 200 | 0 | NA | NA | Not planned for the reporting period | Beneficiary lists, attendance sheets, photographs, activity reports Monitoring reports from Project Delivery Units
Indicator 1.2.6: | Number of women-owned businesses linked with private sector companies.
Baseline: | 0
Planned Target: | 100 | 0 | NA | NA | Not planned for the reporting period | Record of the companies with whom linkages have been developed, Project records i.e. beneficiary lists, documentary proof of the selection process Monitoring reports from Project Delivery Units
Indicator 1.2.7: | Number of men reached through media campaign on sharing domestic responsibilities
Baseline: | 0
Planned Target: | 5 million | Two radio programmes in KP | NA | NA |  | Radio programs recordings, Radio channels outreach /coverage area estimates Monitoring reports from Project Delivery Units
Indicator 1.2.8: | Number of women reached through messaging campaign health and nutritional awareness
Baseline: | 0
Planned Target: | 5 million | 0 | NA | NA | Not planned for the reporting period | Records of the service provider Monitoring reports from Project Delivery Units
Indicator 1.2.9: | Number of disabled women provided with menstrual hygiene kits.
Baseline: | 0
Planned Target: | 500 | 0 | 0 | 0 | Not planned for the reporting period | Beneficiary lists, activity reports and photographs Monitoring reports from Project Delivery Units
UNFAO Target and Actuals for 2021-2022
2.5 | Number of women assisted for small scale kitchen gardening, poultry, small ruminant livestock and food processing for value addition
Baseline: | 0 | 0
Planned Target: | 5000 | 0 | NA | NA | Not planned for the reporting period | Beneficiary selection criteria, beneficiary lost endorsed by Agriculture Extension department and Livestock department, inputs receiving list, Pre-distribution verification report by MEAL team, Post distribution monitoring report by MEAL team, photographs
2.6 | Number of women home-based workers and rural women trained in agro processing nursery raising, community vegetable gardens, honey bee keeping, establishing market linkages with small scale business
Baseline: | 0 | 0 | 0
Planned Target: | 500 | 0 | NA | NA | Not planned for the reporting period | Attendance sheet, photpgraphs, training report, training agenda
Outcoem level | Baseline Study for MPTF project | 1 | 0 | 1 |  | 1 Household baseline survey with food security indicators by UNFAO was conducted and triangulated with qualitative study with FGD and KII tools by UNWOMEN in six target districts of KP and Balochistan.
| Baseline validation workshop |  |  | 2 |  | 1 validation workshop organized in KP and 1 in Balochistan jointly by UNFAO and UNWOMEN MEAL team. Validation of findings of baseline and adaptive actions agreed with agriculture Extension, Livestock departments, Pakistan Baitul Mal, BISP,P&D department, PVDP NGO partner of UNWOMEN,BRSP partner NGO of UNWOMEN and project staff of six target districts of KP and Balochistan,
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well as picture material please make sure you include all credits and share them in high resolution.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board