## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | Mitigating the impacts of COVID-19 on women’s economic participation in the State of Palestine | Overall Duration (months) | 8 Months
Programme Number (if applicable) | NA, 00127923 is MPTF Office Project Reference Number | Start Date (dd.mm.yyyy) | 01 Aug, 2021
MPTF Office Project Reference Number: | 127923 | Original End Date (dd.mm.yyyy) | 01 April, 2022
Country | Occupied Palestinian Territory | In case of NCE Current End date(dd.mm.yyyy) | NA
Recipient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNDP, UN Women, FAO and WFP | National counterparts (government, private, NGOs & others) and other International Organizations | UNDP/PAPP Partners: Bethlehem Fair Trade Artisan (BFTA), Hebron Chamber of Commerce and Industry- Hebron Leather and Shoe Cluster (HLSC), The Union of Cooperative Associations for Saving and Credit (UCASC), MA'AN Development Center. WFP: Global Communities (GC) FAO: Business Women Forum (BWF) UN Women: Ministry of National Economy (MoNE) and Ministry of Finance (MoF)
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | During the reporting period, a total of 225 women-led MSMEs and cooperatives received technical support and accessed services by civil society organizations and national governmental partners. The targeted women were engaged in capacity assessments and consultations to identify their priorities and needs for technical and financial support services, to mitigate the impact of COVID-19 crisis on their businesses and enhance their economic opportunities, as follows: 68 of the targeted women had access to the services of the Ministry of National Economy (MoNE) including the formalization of their businesses, awareness and facilitation of export, registration, and procurement procedures. Most importantly, business registration for women-led businesses increased at the MoNE from 110 women-led businesses in 2020 to 255 registered women-led businesses in 2021, as a result of support of the Joint Programme (JP) that allowed for the wider reach of the MoNE to women during 2021. At the national level, the MoNE established national grants mechanism. A total of 115 women-led MSMEs from various sectors such as handicrafts, shoe sewing, and agri-food were provided with technical support to re-engineer their businesses and adopt innovative business models to respond to COVID-19 crisis. Accordingly, 94 women business owners and entrepreneurs were shortlisted to receive in-kind grants to enhance their businesses. Additionally, 42 women-led agribusinesses were selected, following a needs assessment, to benefit from the joint programme interventions. An accounting/financial software was developed and tailored to the needs of women-led businesses and cooperatives to improve MSMEs’ operations and financial management. Furthermore, 169 contracted shop owners were sensitized on the role of the MSMEs in the local market and how shops can support and promote the products of women led MSMEs. Two training needs assessments were completed, engaging 29 key staff members from the Ministry of Finance (MoF) and MoNE (18 women and 11 men) under the JP. The assessments aimed to support the development of a tailored training programme, to be implemented in Q1/2022 for MoF and MoNE staff and women business owners, that will include on-the-job training and coaching interventions to mainstream gender in budgeting, policy making, and fiscal stimulus packages and procedures. Furthermore, a draft national assessment on the gender responsiveness of the Palestinian Authority’s (PA) stimulus packages and services provided during COVID-19 crisis was finalized. To achieve the above, a technical committee was established by the JP, comprising of various partners of the project, which created a participatory platform for developing selection criteria, ensuring work synergies and sharing progress updates. During the reporting period, the JP technical committee met once to agree on the committee roles and responsibilities and beneficiaries’ selection criteria based on their vulnerabilities, which resulted in creating and testing new partnerships, working modalities and approaches for accelerating implementation by working with women-led grassroot organizations and national actors.
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | The project aims at mitigating the negative socio-economic impact of the COVID-19 crisis on women-led MSMEs including cooperatives and contributes to integrating and introducing measures and innovative solutions that enhances women’s access to equal economic opportunities and can mitigate and reduce the disproportionate burden of unpaid care on women during crisis.
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | Outcome 1: Improved and equitable access of women-led MSMEs impacted by COVID-19 to business support opportunities In total, 225 women-led MSMEs and cooperatives have had access to technical support opportunities and services in 2021. The targeted women were engaged in capacity assessments and consultations, to identify their priorities and needs for technical and financial support and services to mitigate the impact of COVID-19 crisis on their businesses and economic opportunities. Women business owners had access to MoNE services during the reporting period. Those services focused on the formalization of businesses including awareness and facilitation of export, registration, and procurement procedures.
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | Output 1.1 Women-led MSME’s capabilities, skills and business models improved to withstand current and future shocks 115 women-led MSMEs from various sectors such as handicrafts, shoe sewing, and agri-food were provided with technical support by the JP, through civil society partners, to re-engineer their businesses and adopt innovative business models. 42 women-led agribusinesses were selected, following a needs assessment and benefitted from the joint programme interventions. 80 women led MSMEs strengthened their quality and green production capacities through the technical assistance and training received on processing, packaging and branding. An accounting/financial software was developed and tailored to the needs of women-led businesses and cooperatives to improve MSMEs’ operations and financial management. 169 shop owners were sensitized on the role of the MSMEs in the local market and how shops can support and promote the women-led products. Six workshops were conducted in the Gaza governorates for this purpose. Output 1.2 Improved access of women-led MSMEs impacted by COVID-19 to emergency funding and resilience-based support 94 women business owners and entrepreneurs were shortlisted to receive in-kind grants to enhance their businesses. Business registration for women led businesses increased at the MoNE from 110 women businesses in 2020 to 255 registered women businesses in 2021. The MoNE established a national grants mechanism that serves as a national grant fund, which will target 90 women-led businesses in Q1 2022 directly by MoNE through in-kind grants, for purchasing production inputs. 68 women business owners, including in the informal sector, had access to the MoNE services, including access to information and facilitation of registration and procurement procedures. Output 2.2 Improved capacities of government and private sector entities for promoting care services that support women’s access to decent work opportunities A needs assessment was completed, engaging 29 key staff members from MoF and MoNE (18 women and 11 men). The assessment supports the development of a tailored training programme in Q1/2022 for MOF and MoNE staff to mainstream gender in budgeting, policy making, and fiscal stimulus packages and procedures.
3.2 | Results: Gender | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | The JPis marked as GEM3 since gender equality and women empowerment is the principal objective of the programme. The selection of the women owned MSMEs and cooperatives and the targeted sectors was based on vulnerability criteria, identified through a consultative workshop with different stakeholders and built on the results of previous assessments conducted on the impact of the COVID-19 crisis on MSMEs including those led by women. The JP was also inclusive in targeting MSMEs from the informal sector and MSMEs led by female heads of households. A special focus was put on MSMEs led by GBV survivors in Gaza. The grants mechanism established by MoNE with support of the JP is the first gender responsive service of its kind at MoNE. It was designed to serve women and women-led businesses, that were mostly affected by the pandemic. The grant mechanism targets women business owners in specific and was tailored to their needs and priorities. The mechanism will further enable MoNE to widen its database of registered formal women-led businesses, and their access to gender responsive services, in collaboration with a wide range of national stakeholders.
3.3 | Results: Direct Beneficiaries | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | Women-led businesses: TOTAL 225 women-led businesses. Disaggregated by population group and age range Female: 225 Male: 0 Disaggregated by Location: Rural: 93 Urban: 132 Shop-owners: TOTAL 169 shop owners Disaggregated by population group and age range Female: 4 Male: 165 Disaggregated by Location: Rural: 0 Urban: 169 WFP: 169 shop owners (4 females, 165 males), disaggregated by Location: Rural: 0 Urban: 169 UNDP: 115 women led MSMEs from the West Bank and Gaza (22 youth, 93 elder) (79 Urban, 36 Rural) FAO: 42 women led MSMEs from the West Bank and Gaza, (26 individuals and 16 cooperatives) (6 Urban, 36 Rural) UN Women: 68 women business owners (70% young women, 40% from the informal sector) (47 Urban, 21 Rural)
3.4 | Results: Indirect Beneficiaries | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | Total Estimated: 1,340 women and men, including female and male workers in the targeted women-led MSMEs as well as family members of the direct beneficiaries (calculated based on the national average number of household members = 5)
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words) | The JP avoided unintended harm and mitigated contextual challenges for women. Communication sensitivity in implementing the activities in Gaza for GBV survivors was ensured to avoid any potential harm for women. The partners like Bethlehem Fair Trade Artisan (BFTA), The Union of Cooperative Associations for Saving and Credit (UCASC) worked on improving women’s positions in the respective value chains without overburdening them, i.e., taking care of marketing, logistical issues and quality assurance while women focused on production with flexible working arrangements. A total of 43 employees of the MoNE (23 women, 20 men) were engaged in the development of the grant mechanism. This included in-depth analysis of women’s context in the entrepreneurial sector in Palestine. Also, a total of 36 women business owners were engaged in testing the grants application by MoNE to ensure its applicability to their priorities and its easy use.
3.6 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | Lack of digital literacy of beneficiaries: some beneficiaries couldn’t fill in the digital forms/needs assessment to benefit from the programme activities as they didn’t have the digital skills to do so. To tackle this challenge, implementing partners gave the option for written applications and enhanced the digital knowledge of the beneficiaries. Changing the attitude of women and their families on their formal and organized engagement in the economy was challenging; for example, organizing them in the leather and shoe value chain instead of working as subcontractors, and in registering their informal businesses. To mitigate this challenge, partners offered multiple awareness raising sessions and on-the-job training sessions. Procurement Challenges: implementing partners aggregated procurement requests for materials that women utilize in their businesses to tackle the challenge of the high materials prices. The short implementation duration: an extensive work plan has been developed to ensure timely implementation of all programme activities. Regular follow-up was carried out with all partners.
3.7 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words) | A blended and participatory approach for responding to crisis: it is of paramount importance to co-design interventions that follow a multifaceted approach in providing both financial and non-financial services to women-led MSMEs. The programme was built on a participatory approach through engaging women beneficiaries, while bringing together different stakeholders from civil society, public and private sectors at an early stage. This participatory approach has proved its effectiveness through the satisfaction expressed by women themselves. Importance of coordination and joint interventions: UN agencies worked together to avoid overlapping in interventions and building on the work of each other to maximize the impact on women. Importance of joint pre-set criteria for the selection of beneficiaries, based on their vulnerabilities: developing a joint list of criteria has supported the partners to adopt a fair evaluation and shortlisting system and giving all applicants a fair opportunity to apply and benefit from the programme especially since in-kind financial support is included in this joint programme. The grant mechanism has provided a national model that can be expanded, sustained, and replicated, due to its importance in enhancing nationally owned and gender responsive mechanisms in addressing the effects of COVID-19 on women’s economic participation. It has strengthened the government ability to reach out to women directly through financing opportunities, which promotes and protects women’s access to services during and beyond the crisis.
3.8 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | Testing new modalities: new partnerships were established and tested. A partnership with the Hebron Chamber of Commerce and Industry was done to initiate a women unit for sewing services as part of the leather and shoe cluster within the Chamber. This initiative aims to aggregate and organize the scattered women initiatives and enhance the economic representation of women in this industry. Another modality was tested through the blended financing approach in partnership with UCASC, by which loans to women-led MSMEs were complemented with UNDP contribution to support MSMEs’ recovery and ownership. Additionally, the MoNE has established new partnerships with four civil society organizations (BWF, PWWSD, Stars of Hope and Asala) and banking sector (PMA and Bank of Palestine), through the establishment of ongoing exchange as a vehicle for executing the MoNE gender action plan in underserved and remote communities across the West Bank. This approach has proved to be successful in enhancing the inclusivity and coordination of services provided to women and aligning their priorities and emerging needs during and beyond the COVID-19 Pandemic, especially in the underserved communities and geographic locations. A technical committee was established by the JP, comprising of various partners of the project, which created a participatory platform for developing selection criteria, ensuring work synergies and sharing progress updates. During the reporting period, the JP technical committee met once to agree on the committee roles and responsibilities and beneficiaries’ selection criteria based on their vulnerabilities, which ensured accelerating implementation by working with women-led grassroot organizations and national actors.
3.9 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words). | A national assessment on the gender responsiveness of the Palestinian Authority’s (PA) stimulus packages and services provided during COVID-19 crisis was finalized. The assessment was conducted in collaboration with the MoNE, Ministry of Finance (MoF), Palestine Palestinian Central Bureau of Statistics (PCBS). The assessment was implemented through a broad consultation with national actors from private and public institutions. Findings and policy recommendations of the assessment informed the JP’s planned support to MoNE and MoF on developing and implementing gender responsive stimulus packages, with a special focus on women-led businesses (Annex 1). Needs assessment for the women-led MSMEs across the targeted sectors in the West Bank and Gaza was also conducted in order to design and deliver the technical support packages: including training on marketing, digital marketing, business model canvas, risk management, etc.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words). | N/A
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | This programme was linked with The National Helpdesk Scheme-Monshati that was established by UNDP to streamline the MSMEs recovery and resilience packages through coordinated efforts by Palestinian Monetary Authority (PMA) along with the Palestinian Banking Institute, Federation of Palestinian Chambers of Commerce, Industry and Agriculture (FPCCIA) and MoNE. The beneficiaries of this programme were informed about the services of the National Helpdesk Scheme and will be given access to non-financial services. UN agencies applied a cost-effective approach in managing human resources under the JP, where salaries were co-funded by the JP and the different UN agencies. Additionally, the national assessment was produced and co-funded by the JP, UN Women, and the UN Women Regional Programme “Promoting productive employment and decent work for women”, funded by Sida. The 42 women-led agribusinesses and cooperatives who received training through the joint programme by FAO will be given the opportunity to apply for FAO investment support project based on FAO support modality.

## Project Indicators
Please include ALL indicators in the project document. Include the indicators and Baseline, Planned Target and Actuals for both OUTCOME and OUTPUT levels. "Actuals" refer to the total figures achieved for each indicator. Include separate actuals for 2021 and for 2022 (if applicable). Explain if targets were not achieved. Include means of verification. Use as many outputs cells as needed to present all project indicators.
| INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | DATA: ACTUALS 2022 (if applicable) | TOTAL actuals (agreggated 2021 and 2022 if applicable ) | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1 Improved and equitable access of women-led MSMEs impacted by COVID-19 to business support opportunities
Output 1.1 Women-led MSME’s capabilities, skills and business models improved to withstand current and future shocks
Indicator 1.1.1: | # of targeted women-led MSME obtaining tecnical and business development support |  |  |  | The participating UN agencies invested in various partnerships at the national and local level including grassroot organizations supporting women's economic empowerment in the State of Palestine. This approach improved the outreach and targeting of disadvantaged women-led MSMEs leading to target exceedance. | Training attendance sheets, field visits and programme reports
Baseline: | 0
Planned Target: | 80 | 225 | N/A for this reporting period
Indicator 1.1.2: | % of targeted women adopting digital tools and solutions to their business operations |  |  |  | Actual results will be provided in the final report given measurement of this indicator is scheduled in 2022 | Programme reports, field visits and survey results
Baseline: | 0
Planned Target: | 60% | 0 | N/A for this reporting period
Indicator 1.1.3: | # of market actors including CBT shops sensitized on promoting and seling the products of women-led MSMEs |  |  |  | More shops to be targeted in Q1/2022 | Training records, field visits and workshop reports
Baseline: | 0
Planned Target: | 200 | 169 | N/A for this reporting period
Output 1.2 Improved access of women -led MSMEs impacted by COVID-19 to emergency funding and resilience-based support
Indicator 1.2.1: | % of targeted women-led MSMEs reporting improved skills in business planning and management during and beyond crisis |  |  |  | Actual results will be provided in the final report given measurement of this indicator is scheduled in 2022 | Pre- and post self assessment survey
Baseline: | 0
Planned Target: | 70% | 0 | N/A for this reporting period
Indicator 1.2.2: | # of women-led MSMEs benefiting from in-kind grants delivered to restore their productivity |  |  |  | 94 women business owners and entrepreneurs were shortlisted to receive in-kind grants to enhance their businesses. Actual results will be provided in the final report. | Grants management system and reports
Baseline: | 0
Planned Target: | 50 | 0 | N/A for this reporting period
Indicator 1.2.3: | % of targeted women -led MSMEs reporting improved capabilities to pursue public and private procurement opportunities |  |  |  | Actual results will be provided in the final report given measurement of this indicator is scheduled in 2022 | Pre- and post self assessment survey
Baseline: | 0
Planned Target: | 60% | 0 | N/A for this reporting period
Outcome 2 Improved access of women impacted by COVID-19 to decent work opportunities
Output 2.1 Community awareness strengthened on the importance of promoting women’s access to decent work opportunities and the recognition of women’s work inside and outside the household is enhanced
Indicator 2.1.1: | # of awareness raising and advocacy campaigns/events conducted to promote decent work opportunities and care services |  |  |  | Actual results will be provided in the final report given measurement of this indicator is scheduled in 2022 | Programme reports and field visits
Baseline: | 2
Planned Target: | 1 | 0 | N/A for this reporting period
Output 2.2 Improved capacities of government and private sector entities for promoting care services that support women’s access to decent work opportunities
Indicator 2.2.1: | # of government, private and civil society organizations promoting care services that support women’s access to decent work opportunities. |  |  |  | Actual results will be provided in the final report given measurement of this indicator is scheduled in 2022 | Training attendance sheets, field visits and programme reports
Baseline: | 0
Planned Target: | 20 | 0 | N/A for this reporting period
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
To be shared in the final report
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well as picture material please make sure you include all credits and share them in high resolution.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board