## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | Building Forward Better: A Resilient Women and Youth Centred and Digitally Enhanced Value Chain Development in Vietnam | Overall Duration (months) | 15 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 01.02.2021
MPTF Office Project Reference Number: | MPTF_00209_00089 | Original End Date (dd.mm.yyyy) | 30.04.2022
Country | Vietnam | In case of NCE Current End date(dd.mm.yyyy) | 30.06.2022
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | IFAD and UNIDO | National counterparts (government, private, NGOs & others) and other International Organizations | - Ministry of Agriculture and Rural Development - Provincial People's Committees of Dong Thap province and Ben Tre province - Fruit enterprise associations - Farmers groups, Women’s Union, Youth Union, Farmers’ Union - Private sector - R&D and technological institutions
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | Receiving the COVID-19 MPTF Fund from February 2021, UNIDO and IFAD started their internal and the government approval process which was completed in June 2021. In parallel, both agencies kicked off the inception activities, including: 3 consultation workshops with the stakeholders, setting up 2 province PMUs and detailed workplan, review of other on-going projects to identify synergies, conducting 7 surveys and in-depth assessments along the 2 fruit value chains (mango and pomelo), selecting partners and service providers. The project fully implemented from July 2021 with the active involvement of the Dong Thap and Ben Tre provinces, the Ministry of Agriculutre and Rural Development (MARD) and the related partners including the Farmer’s Association, Women’s Union, Youth’s Union, digitalization/e-commerce platforms, Institute of Agriculture Engineering and Post Harvest Technology, Institute of Agriculture and Rural Development Policy and Strategy, Department of Agro Process and Market Development and the identified actors of mango & pomelo value chains. The project has placed the rural women and youth who have been exacerbated by the impact of Covid-19 at the center of attention, focusing on developing a digitally enhanced model for building the mango and pomelo value chain in the Mekong Delta. Six representative unions of women, youth and farmers of the two provinces have been strengthened to jointly facilitate the capacity-building activities on ICT and other technical skills to the producer groups, SMEs, wage labourers and entrepreneurs. 36 training courses to improve skills on production, business planning, financial management, e-commerce, etc. have been organized for more than 2,500 members, of which 70% are women and youth. The One Cooperative One Product (OCOP) digital platform developed by IFAD’s earlier project in order to utilize the ICT-based marketing application to promote and increase market access for mango and pomelo products was piloted. In addition, UNIDO also provided technical assistance to develop the digital supply chain ecosystem platform for the tropical fruits value chain. The platform enables all type of actors i.e., enterprises along the value chain, business services, and support institutions (technical and financial) to access the platform, and via the platform to connect to business partners and/or access necessary support services and inputs. The project also supported the development of COVID-19 related production standards, quality compliance and processing technologies, and developed policy engagement to promote the status of women and youth in leadership positions of the sector. 6 Standard Operation Procedures (SOPs) from farm to market for mango value chain were developed with 6 training modules. About 200 value chain actors have been trained on the SOPs. The SOPs is being also digitalized to develop e-learning courses to enable more learners/stakeholders to access. Added, 3 Production Unit Codes (PUC) and 2 Packing House codes (PHC) for export were developed for green-skinned pomelo products in the 3 pilot areas and 2 cooperatives. VietGAP certification were provided for 155 households growing green skin pomelo with an area of 84.36 ha, 11 households growing seasonal mango with an area of 4.58 ha. These interventions will lead directly to robust farm-enterprise contracts and significantly increase the chances for women and youth to obtain higher paid labour contracts and decent, safe working conditions. Farmer groups has been enabled to adopt climate smart fruit production technology and become more resilient to climate change effects and other externalities. As result, pilot intelligent pest and disease monitoring system (for 45 households) with integrated edge computing cameras, smart water quality monitoring system and smart water pumping system (for 15 households) in the area of 2 hectares have been piloted. Moreover, the project’s interventions have improved the enabling business environment for women and youth, enhanced the competitiveness and safety of women and youth led value chains, increase value addition, and their access to markets. Intensive technical assistance (technical and equipment support) were provided to 10 selected women/youth led enterprises and cooperatives to improve product packaging, apply proper post-harvest technology, increase quality and shelf-life of products, and reduce post-harvest loss. A manual and guideline on producing the value-added products for disseminating the good practices will be developed to scale up in the MRD provinces. 6 e-commerce platforms and 10 supermarkets/ shops chains have been investigated and facilitated to the interested cooperatives, enterprises for market linkage. An export promotion plan was developed with a model marketing plan which provide strategic recommendations to the targeted export markets. Ultimately, women and youth are expected to increase their income and self-esteem through higher skilled work and by becoming successful entrepreneurs. Together with advocacy and policy engagement, the social empowerment of women has gained concrete traction.
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | The goal is creating a model of a gender and youth-centred and innovative fruit value chain in the Mekong Delta of Viet Nam which can be scaled up for ‘recovering better together’ across the rural economy. The project would prioritize rural women and youth as the core target groups by (i) boosting their skills and capacities; (ii) offering COVID-19 safe working conditions and decent revenues and; (iii) most importantly, reducing barriers and opening a development pathway for women and youth to actively participate in modern and digitized economic activities. In addition, building forward better would result in (iv) greater safety of agricultural products for consumers. Demand for high quality and safe food is rising especially in urban areas as local markets receive more attention in Vietnam while export markets have contracted as a result of COVID-19. Opportunities for a COVID-19 safe value chain include (i) COVID sanitized and certified transport and tracing systems for agricultural produce and farm inputs; (ii) cold storage and packaging facilities to prevent goods from perishing; and (iii) digital extension and e-commerce (ICT) to mitigate the impact of physical distancing and to speed up trade.
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | Outcome 1: The project has strengthened women and youth centered business enabling environment. 2 women’s unions, 2 youth unions and 2 farmer’s unions of the Dong Thap and Ben Tre provinces were mobilized and strengthened their capacity to participate in implementing the project activities and to more effectively represent the interest of women and youth for partaking in digitised value chains in development planning sessions at Commune, District and Provincial levels. They jointly facilitated the capacity-building activities for their members on ICT and other technical skills. 36 training courses to improve skills on production, business planning, financial management, e-commerce, etc. have been organized for more than 2,500 members, of which 70% are women and youth. Enhanced capacity and accessibility of women and youth-focused support services to the developed digital OCOP platform and digital supply chain ecosystem platform. In addition, a policy and advocacy platform was established and facilitated for (a) promotion and scaling up of women and youth centered value chains; (b) promotion of women’s leadership roles in economic development; and (c) promotion of social norm change on gender roles in sharing the housework. Outcome 2: The project has supported to enhance the competitiveness, safety and sustainability of women and youth-led value chains. COVID-19 safe food standards, good practices and technologies was developed/promoted along the value chain. 6 Standard Operating Procedures (SOP) from farm to market covering a) disease management, b) cool chain, c) transportation d) traceability systems e) packhouse quality management f) field practices for quality management and preparing training were developed and applied in the demonstrated value chains. It aims to shorten national supply chains, ensure correct use of agro-chemicals, introduce more effective post-harvest handling and treatments to ensure shelf-life, upgrade quality control at all levels of the supply chain. The women and youth centered mango and pomelo value chain was upgraded through direct support for the application of good practices (SOPs, VietGaP/GlobalGab). In addition, two electronic supply chain management platforms were developed to establish a coordinated and digitally linked supply chain from farm to market. Outcome 3. The project has improved access to new markets for women and youth mango and pomelo producers through increased digital access to value addition, branding, promotion and e-commerce. Introduction of new value-added products (e.g. dried fruits, better packaging, processed products, etc.) in the selected 5 producer groups and SMEs. Six e-commerce platforms and 10 supermarkets/ shops chains have been facilitated to the interested cooperatives, enterprises for market linkage. Series of business matching meetings were facilitated to link producers to existing and new buyers and processors. An export promotion plan was developed with a model marketing plan which provided strategic recommendations to the targeted export markets.
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | Output 1.1 Women led farmer groups mobilized and strengthened through communication tools: 2 women’s unions, 2 youth unions and 2 farmer’s unions of Dong Thap province and Ben Tre province were guided by the professional institutions to lead the surveys and the organization of 36 training courses to improve skills on production, business planning, financial management, e-commerce, etc. for more than 2,500 members. The collaboration and coordination among these representative groups were strengthened. Output 1.2 Enhanced capacity and accessibility of women and youth-focused support services While IFAD linked the provinces with the One Cooperative One Product (OCOP) digital platform in order to utilize the ICT-based marketing application to promote and increase market access for mango and pomelo products, UNIDO provided technical assistance to develop the digital ecosystem platform for the tropical fruits value chain, piloted for Pomelo and Mango. The platform enables all type of actors i.e., enterprises along the value chain, business services, and support institutions (technical and financial) to access the platform, and via the platform to connect to business partners and/or access necessary support services and inputs. Output 1.3 Policy and advocacy platform established and maintained for (a) promotion and scaling up of women and youth centered value chains; (b) promotion of women’s leadership roles in economic development; and (c) promotion of social norm change on gender roles in sharing the housework. A plan for the policy and advocacy activities has been developed for each province. Output 2.1 COVID-19 safe food standards, good practices and technologies developed/promoted along the value chain. 6 Standard Operation Procedures (SOPs) from farm to market for mango value chain were developed with 6 training modules. About 200 value chain actors have been trained on the SOPs. The SOPs is being also digitalized to develop e-learning courses to enable more learners/stakeholders to access. In addition, training courses for 190 households on application of VietGap/GlobalGap were organized. 3 Production Unit Codes (PUC) and 2 Packing House codes (PHC) for export were developed for green-skinned pomelo products in the 3 pilot areas and 2 cooperatives. Output 2.2 Women and youth centered value chain established and upgraded. The application of SOPs was piloted and will be upscaled to increase compliance capacity along the mango and fruit value chain. In addition, technical support and VietGAP certification were provided for 155 households growing green skin pomelo with an area of 84.36 ha, 11 households growing seasonal mango with an area of 4.58 ha; support to implement the pilot application of 4.0 technology and smart equipment in green-skinned pomelo production, including intelligent pest and disease monitoring system (for 45 households) with integrated edge computing cameras, smart water quality monitoring system and smart water pumping system (for 15 households) in the area of 2 hectares. Output 3.1 Women and youth led innovation through value addition, branding, promotion and e-commerce. An in-depth assessment to identify the opportunities for value addition in the 10 selected women and youth led cooperatives and enterprises was conducted. Technical assistance (technical and equipment support) is being provided to improve product packaging, proper post-harvest handling, increase quality of products, increase shelf-life of product, and reduce post-harvest loss etc. A manual and guideline on producing the value-added products for disseminating the good practices will be developed to scale up in the MRD provinces through series of trainings. 6 e-commerce platforms and 10 supermarkets/ shops chains have been investigated and facilitated to the interested cooperatives, enterprises for market linkage. An export promotion plan was developed with a model marketing plan which provide strategic recommendations to the targeted export markets. Technical support was provided to the Ministry of Agriculture and Rural Development to develop a road map of activities aiming at providing information and training tools to agencies, companies, cooperatives and associations for development of branding strategy for tropical fruit industry. Output 3.2 Farm-enterprise, enterprise to enterprise contracts established. 5 buyer meeting events were organized to identify potential buyers, link producers to existing and new buyers and processors. The development of long-term farm to enterprise business relationships that are based in principles that support reciprocity and mutual benefits was faciliated.
3.2 | Results: Gender | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | The project has placed the rural women who have been exacerbated by the impact of Covid-19 at the center of attention. From support to establishment of norms and standards for COVID-19 safe and sustainable products, to building capacity of extension services, the project has ensured a thorough and gender-sensitive analysis (including assessment of digital skills levels and access to ICT improvement of which are central to the project) and interventions with the objective to specifically improve conditions of women in the fruits supply chain. The project pursued a gender-responsive approach in organizing any trainings, i.e. taking differential needs of women and men into account as to timing and safety considerations. The project engaged women and youth and promoted their role in the project not as mere beneficiaries but rather as leaders and partners of the project for delivery of results.
3.3 | Results: Direct Beneficiaries | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | Women and youth in Dong Thap and Ben Tre provinces working along the mango and pomelo value chains are the core target beneficiaries and intended change agents of the project. 450 rural households, 12 cooperatives, and 10 enterprises have been directly benefit from project activities, of which about 2,500 beneficiaries are women and youth.
3.4 | Results: Indirect Beneficiaries | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | Moreover, rural small and medium enterprises including wholesalers, transportation, storage and local input suppliers will also benefit from the outputs of the proposed project. 2000 rural households, 117 value chain operators (cooperatives, collectors, packing hourses, transporters, enterprises, input suppliers etc.) and institutions have been indirectly benefited from the project .
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words) | The project liaised with the Farmers’ Union and the Women and Youth Unions at District and Commune level to validate project approach and interventions and to strengthen its impact on gender equality and empowerment of women. The identification of women and youth growers – and the groups they are part of – was greatly facilitated by these unions. The project’s targeted intervention is to provide skills training for women and young farmers and entrepreneurs and to strengthen capacities of their organizations such as the Women’s Union and farmer groups/cooperatives. The individual and institutional strengthening provides the basis for sustainability of ICT and other capacity building support. The project is expected to serve as a model to ensure more equality during the economic recovery process from the COVID-19 pandemic for women and young farmers which are among the most vulnerable groups. The project uses gender-sensitive language; follows equal representation principles in any photographs/other depictions and pays attention to not reproducing any (gender) stereotypes.
3.6 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | Due to the Covid-19 pandemic situation, there has been restricted international and local travels, which delayed the mission of consultants and service providers. More virtual meetings and increased use of e-communications, virtual training etc have been taken.
3.7 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words) | The COVID-19 situation although affected the progress of the project implementation (the limited local travel and impossible presence of international experts), did strengthen the right direction of the project design. There has been a big congestion of agro-products at the border gates with China (major export market) for customs clearance which was slow because the two governments have to strictly implement measures to prevent and control Covid-19. In addition, exports to other countries have been limited. Domestic consumption in the short term could not be changed immediately to meet the large volume of surplus due to non-export. The country agricultural sector is in need to re-strategize to open new markets and to meet the increased requirements in terms of quality and compliance to ensure food safety and creating trust. Demand for high quality and safe food is rising especially in urban areas as local markets receive more attention in Vietnam while export markets have been contracted as a result of COVID-19. Opportunities for a COVID-19 safe value chain include (i) COVID sanitized and certified transport and tracing systems for agricultural produce and farm inputs; (ii) cold storage and packaging facilities to prevent goods from perishing; and (iii) digital extension and e-commerce (ICT) to mitigate the impact of physical distancing and to speed up trade. Even though digitalized agriculture sector and rural areas are of government's top priorities, the implementation is fragmented due to lack of coordination, resources and technical capability of the government institutions, business development service providers and the value chain actors. The application of digital technology along the value chain should aim to bring benefits to all the stakeholders (i.e. bringing more profit and business opportunities to the farmers and SMEs, supporting Government management and decision making, improving the transperancy and tracebility of the value chains/produce). The project is working to create such digitized value chain model for policy advocacy and replication.
3.8 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | Partnerships are envisaged during implementation with both national and international institutions such as: (i) National Coordination Office for NTP-NRD and OCOP; (ii) Central Committee for Ethnic Minorities (CEM) for integration with the NTP-EMD; (iii) the Mekong Delta Coordination Committee (MDCC) established by the Prime Minister Decision on 12 June 2020; (iv) the Ministry of Agriculture and Rural Development (MARD) and the development partners under the International Mekong Delta Working Group (MDWG) for implementation of the Mekong Delta Agriculture Transformation Programme; (v) the World Bank’s Mekong Delta Integrated Climate Resilience and Sustainable Livelihoods Project working in both Ben Tre and Dong Thap provinces; the project “Green Innovation Centres for the Agriculture and Food Sector” (GIZ), the project “Enhancing Global Competitiveness of Vietnam’s dragon fruit through Improving Quality Infrastructure in the Value chain” (IFC), the project “Improving smallholder farmer incomes through strategic market development in mango supply chains in southern Vietnam” (ACIAR), the project "Traceability development for export" (DFAT), and the project "Safe food for growth" (Canada). In addition, the project’s scope is catalytic and fully compatible with the other country programs of IFAD and UNIDO in Vietnam. The IFAD funded Adaptation in the Mekong Delta project (AMD) in Ben Tre and Tra Vinh provinces in the Mekong Delta has provided the basis and experience to develop and modernize the proposed value chain. IFAD through the AMD has promoted climate smart, pro-poor value chain development including value chain finance approaches. UNIDO has established a Center of Excellence for mango harvesting, packing operations, storage and transport in the Mekong River Delta. In addition, UNIDO is providing technical assistance to increase the quality and standards compliance of the mango value chain in the region through Global Quality and Standards Programme (GQSP). In response to the Covid-19 challenges – and in line with the government’s dual goals (response and recovery) – the Ministry of Agriculture and Rural Development (MARD) foresees a continued restructuring of agriculture, utilizing cutting edge technology, empowering its position in the supply chain, increasing the value-added and enhancing the competitiveness of Vietnamese agricultural products. A partnership model of 4 partners including the Ministry of Agriculture and Rural Development (MARD), the Women's Union, the Farmers' Union, and the Youth Union was established to facilitate agriculture products consumption. This has been a successful model to connect demand and supply in the context of the complicated development of the COVID-19 epidemic. The project could use this model and foster the partnership better.
3.9 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words). | The PMUs have conducted a review of experience and lessons learnt from completed and on-going projects/programs in Ben Tre and Dong Thap provinces. A umber of surveys and in-depth assessments on mango and pomelo value chains, including market assessment, have been conducted. In addition, the Project Completion Report (PCR) of the IFAD-supported Climate Change Adaptation in Mekong Delta (AMD) is a resourceful assessment of the on-going initiatives for the women and youth development.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words). | N/a
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | The Government and IFAD have approved a continued IFAD investment to the Mekong Delta, the Climate Smart Agriculture Transformation in Ben Tre and Tra Vinh provinces (CSAT), which will be implemented in 2022 and maximize impacts of the MPTF support. The MPTF project activities will be integrated with the CSAT programme which has mobilized partnership with DFCD, SNV and IDH. In additon, UNIDO is developing the 2nd phase of the Global Quality Infrastructure and Standard programme which continues to focus on increasing the compliance capacity of tropical fruit value chain in the Mekong River Delta.

## Project indicators
| Achieved Indicator Targets (2021-Feb. 2022) | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1 Women and youth centred digitally enhanced business enabling environment |  |  | Project reports, PMU reports
Indicator: District agencies pursue and support women and youth centred business in at least one fruit value chain
Baseline:
Planned Target: Twelve Districts report concerted efforts by agencies in at least one fruit value chain | 15
Output 1.1 Women led farmer groups mobilized and strengthened through digital communication tools |  |  | Project reports, PMU reports
Indicator 1.1.1: Number of organised women and youth partaking in the programme
Baseline:
Planned Target: 2,000 female and/or young fruit producers participate in the model value chain support programme by the end of 2021 | 1500
Output 1.2 Enhanced capacity and digital accessibility of women and youth-focused support services (ICT, finance, extension, business advisory, skills development, etc.) |  |  | Project reports, PMU reports
Indicator 1.2.1: Frequency of using digital platforms to establish, maintain or use value chain relations
Baseline:
Planned Target: 80% of groups report using the digital platforms at least weekly | 70%
Output 1.3 Policy and advocacy platform for (a) the promotion and scaling up of women and youth centred value chains; (b) promotion of women’s leadership roles in economic development; and (c) the promotion of social norm change on gender roles in sharing housework |  |  | Project reports, PMU reports
Indicator 1.3.1: # of significant Provincial Resolutions promoting women and youth centred value chains
Baseline: |  |  | Project reports, PMU reports
Planned Target: One Provincial Resolution (per Province) articulating steps for promoting women and youth centred value chains | 2
Outcome 2 Enhanced competitiveness, safety and sustainability of women and youth-led value chains
Indicator: $ of sales, % increase is sales volume and value |  |  | Project reports, PMU reports
Baseline:
Planned Target: Target increase in $ of sales to be determined 30% increase in sales volume/value | not available yet
Output 2.1
Indicator 2.1.1: COVID-19 safe food standards, good practices and technologies developed/ digitally promoted along the value chain |  |  | Project reports, PMU reports
Baseline:
Planned Target: # of good practices, pre-and post-harvest technologies applied by the value chain operators | 8
Output 2.2 Women and youth centred digitally enhanced value chain upgraded
Indicator 2.2.1: # of value chains upgraded/created to explicitly benefiting women and youth producers |  |  | Project reports, PMU reports
Baseline:
Planned target: 1 model fruit value chain established | 2
Outcome 3 Improved digital access to new markets for women and youth
Indicator: # of beneficiaries using digital access technologies |  |  | Project reports, PMU reports
Baseline:
Planned Target: 5 enterprises | 5
Output 3.1 Women and youth led innovation through increased digital access to value addition, branding, promotion and e-commerce
Indicator 3.1.1: # of diversified primary products / product market combinations |  |  | Project reports, PMU reports
Baseline:
Planned Target: 2 innovated primary products accessed to the markets | 4
Output 3.2 Farm-enterprise, enterprise to enterprise contracts digitally facilitated and established
Indicator 3.2.1: # of producer – enterprise business relationships per producer group established digitally |  |  | Project reports, PMU reports
Baseline:
Planned target: 3 digitally facilitated business relationships with growth potential per producer group | 6
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
Ms. Phan Thi Thuy, Director of Westernfarm Co., Ltd. was on the ground to witness how Covid-19 has impacted her business and everyone around her so severely. Thuy is the director of Westernfarm Co., Ltd, which was established in June 2020 at An Dinh hamlet, An Binh commune, Cao Lanh district, Dong Thap province. Westernfarm exports local tropical fruits such as mango, durian, jackfruit, longan, guava, dragon fruit, passion fruit... to markets like Japan, Russia, and the EU. "In the context of the COVID-19 pandemic, my company had been severely affected. Sometimes, we had to arrange for employees to temporarily work, eat, rest and sleep on-site ("four-on-the-spot" model) to continue operations amid the waves of Covid-19. The company met huge challenges in terms of operation. Transportation costs surged to increase 15 times at times. Air and sea freight were limited and extremely difficult to book,” – said Thuy. This was truly a crisis for goods with short shelf life like fresh fruits. Moreover, employees following the "four-on-the-spot" model for too long started having mental health issues. With the company's expenses increasing dramatically, Thuy almost suffered a hefty loss. Then her company was selected to participate in the post-COVID recovery support project "Building Forward Better: A Resilient Women and Youth Centred and Digitally Enhanced Value Chain Development in Vietnam", funded by MPTF Covid-19 and co-implemented by IFAD and UNIDO in collaboration with the Dong Thap province Department of Agriculture and Rural Development. "As a female business leader, I decided to participate in this project because I feel that the project is significant and makes an important contribution to bringing more resilience to our business and employees," - said Thuy. To better help the company recover from the pandemic, an in-depth assessment has been carried out with Westernfarm to identify the opportunities for support. Thuy's company is stepping into the next phase of implementation. Westernfarm will soon receive technical and equipment support to increase compliance capacity along the mango and fruit value chain. This include advices on the application of SOPs in their factory design and cool chain management to increase quality of products and reduce post-harvest loss. As a women-led enterprise, Westernfarm will also be piloted for better digital access to value additions, branding, promotion and e-commerce. Soon, Westernfarm will join a digital supply chain ecosystem platform for the tropical fruits value chain, piloted for pomelo and mango. The platform enables value chain actors, including exporters like Thuy's company, to connect to business partners and access necessary support services and inputs. With all the above supports, the company wishes to develop sustainably in the direction of both exporting fresh fruits and frozen or dried goods for those which do not meet fresh fruit export standards. Thuy shared, "We aim to build standard planting areas and stay closer to farmers. Especially now when the company is very trusted by farmers and local authorities, we feel more confident to move forwards and recover from the pandemic."
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
The project has been covered in newpaper articles from both provincal and national level news agencies. All of the them clearly stated the objectives and expected outcomes of the project, with an emphasis on women and youth. The provincal news agencies helped the project reach more audience at the project provinces. The Signing Ceremony of the Joint Delaration on the project was also covered by newspapers that specialize in agriculture and policy-making.
Press clipping
Bao Dong khoi (Dong Khoi Newspaper - Ben Tre Province) Triển khai Dự án MPTF Bến Tre https://baodongkhoi.vn/trien-khai-du-an-mptf-ben-tre-21022022-a97096.html Bao Dong Thap (Dong Thap Newspaper) https://www.baodongthap.vn/kinh-te/unido-va-ifad-ho-tro-xay-dung-du-an-phat-trien-chuoi-gia-tri-trai-cay-tai-dong-thap-103188.aspx UN Vietnam UNIDO và IFAD hợp tác khởi động dự án mới để phát triển chuỗi giá trị trái cây tại vùng Đồng bằng sông Cửu Long https://vietnam.un.org/en/129977-unido-va-ifad-hop-tac-khoi-dong-du-moi-de-phat-trien-chuoi-gia-tri-trai-cay-tai-vung-dong https://vietnam.un.org/en/129976-unido-and-ifad-join-hands-launch-new-project-develop-fruit-value-chain-mekong-river-delta Đài phát tranh và truyền thình Đồng Tháp Một ngàn hộ dân sẽ được hưởng lợi từ dự án IFAD và UNIDO triển khai tại Đồng Tháp http://thdt.vn/mot-ngan-ho-dan-se-duoc-huong-loi-tu-du-an-ifad-va-unido-trien-khai-tai-dong-thap.html Tin tức miền Tây (The West News) UNIDO và IFAD hỗ trợ xây dựng dự án phát triển chuỗi giá trị trái cây tại Đồng Tháp https://tintucmientay.baoangiang.com.vn/unido-va-ifad-ho-tro-xay-dung-du-an-phat-trien-chuoi-gia-tri-trai-cay-tai-dong-thap-a323743.html Tạp chí Tài chính (Finance Magazine) Đẩy mạnh xúc tiến đầu tư vào lĩnh vực nông nghiệp, nông thôn https://tapchitaichinh.vn/tai-chinh-kinh-doanh/day-manh-xuc-tien-dau-tu-vao-linh-vuc-nong-nghiep-nong-thon-343511.html Sở Nông nghiệp An Giang (An Giang Agriculture) Hội thảo nâng cao năng lực đối với xoài xuất khẩu https://sonongnghiep.angiang.gov.vn/wps/portal/Home/2018/home/tin-chi-tiet/!ut/p/z0/fYyxDoIwGISfhpH0b4GWjiYkirgYEwNdTCUN_EJakGJ8fKuLcXG6u-8uRxSpibL6gZ326KweQ24Uv0hZlFCl9JCXnMIxLdLz9lTBrmBkT9T_QXjA2zyrDVGts948PakXZ53tbNejmeIRrxH8kAW9CUjHHq1f22Ud0NgP-I78PdjQ9xHkUgJQyliSZBnnQuSBvFUIANAUKANGpkE1L10R3_4!/#gsc.tab=0 Nông nghiệp Việt Nam (Viet Nam Agriculture) Nâng cao năng lực tuân thủ các quy định đối với xoài xuất khẩu https://nongnghiep.vn/nang-cao-nang-luc-tuan-thu-cac-quy-dinh-doi-voi-xoai-xuat-khau-d288237.html Pháp luât Việt Nam (Viet Nam Law) Thị trường xuất khẩu xoài của Việt Nam còn rất lớn https://baophapluat.vn/tieu-dung-va-du-luan/thi-truong-xuat-khau-xoai-cua-viet-nam-con-rat-lon-583490.html
To share the video as well as picture material please make sure you include all credits and share them in high resolution.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Link to HD photographs to be added later
Capacity building trainings for group leaders on management skills, production planning, gender issues at the pomelo Giong Trom cooperative in Ben Tre province.
Director of Giong Trom green-skinned pomelo cooperative is checking
the pest monitoring system (Ben Tre province)
Cooperative members are monitoring the density of pests in the garden and the water monitoring results are reported on the smartphones. (Ben Tre province)
Preliminary processing and packing area of green-skin pomelo (Ben Tre province)
Ms. Phan Thi Thuy