## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | Leveraging digital solutions to improve the Recovery to resilience (R2R) of vulnerable populations in Benin | Overall Duration (months) | 18 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | February 2021
MPTF Office Project Reference Number: | _00209_00301 | Original End Date (dd.mm.yyyy) | January 2022
Country | Benin | Current End date(dd.mm.yyyy) | June 2022
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNDP, Joint SDG fund contribution & UNCDF | National counterparts (government, private, NGOs & others) and other International Organizations | TIC Agro Bisiness Center - ALIDé Microfinance - FECECAM Bénin - Consortium Numérica Center / SIF Group - T- Ventures
Report Cleared By
o Name: | Cossoba Nanako
o Title: | Program Officer
o Email address: | cossoba.nanako@uncdf.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | The main programme is divided in 2 outcomes and each outcome is divided into 2 main results 1- Increased responsiveness of the fund to the socio-economic impact of the COVID-19 pandemic on countries 1.1 An increasing number of digital and financial literate population (women, youth, micro-entrepreneurs and agri-cooperatives) capable to adopt and/or elaborate innovative solutions to their own needs is available. 1.2 Greater and easier access to market for micro-entrepreneurs, agri-cooperatives, women and youth are achieved to foster their economic inclusion. 2. Increased access to immediate health and socio-economic support to respond to the health and social impact of the COVID-19 pandemic 2.1 Access to finance is increased for affected micro-entrepreneurs and agri-cooperatives to accelerate SDGs. 2.2 Resilience and Recovery initiatives are duly monitored and lessons learnt shared.
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | Direct impact on 10,000 persons including: at least 60% women in the 10 municipalities; 6,000 micro and small entrepreneurs (MSME); 4,000 smallholder farmers mobilized through agri-cooperative cooperatives and women's savings groups, to adress the adverse impact of the COVID-19 pandemic to their livelihoods.
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | The project trained 12,761 persons directly among which 6,629 women ; allocated 15 egrants to SME owned by young and women ; supported 2 financial services providers' digital transformation ; trained 202 beneficiaries in agri-processing and other innovative technics accross the 10 target municipalities (Nikki, Kalalé, Boukombe, Glazoué, Avrankou, Aplahoué, Grand Popo, Zagnanado, Bassila and Ketou) by building their capacities in : digital literacy, financial education & entrepreneurship and allowing the beneficiaries to increase their income. These results have been reached through partnership through performance based grants to implementing partners selected on a competitive process. Involving both local autorithies and deconcentrated state services have also played a key role. By doing this, the project has built a pilot ecosystemic approach to vulnerable populations' resilience which can be upscaled by relevant national entities and other partners in implementing the nationwide digital transformation promoted by the government.
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | In 104 villages in the targeted 10 municipalities, 6,316 beneficiaries, among which 3,105 women, are now using platforms (AGRICeF & AGRIYARA) designed by implementing partner and adapted by the R2R project support) to learn and/or upskill themselves in basic management and financial operations and to access market. 601 among the project benefiaries used e-commerce platforms. In addition, 2 digital hubs are installed to facilitate access to those basic digital services and also to be used as mobile phones charging facilities. By supporting to 2 financial service providers, R2R make possible access to digital saving, loans and payments to 10,762 (7,083 women) smallholder farmers (304 cooperatives mostly women associations). 15 SME benefited from egrant (+/-8000 USD each) to recover and build resilience.
3.2 | Results: Gender | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | On capacity building, the targeted women is 6,000 while actual beneficiaries number is 6,629 (completion rate of 110,48%) ; regarding using digital solutions, the planned number was 3,000 women while the actual achievement is 3,105 (103,50%). The trend is similar regarding access to digital financial services where women represent 66.18% of the beneficiaries. As far as egrants are concerned, all SME are owned by young people (<35) and/or women.
3.3 | Results: Direct Beneficiaries | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | The project impacted directly in rural and remote areas 12,761 persons among which 6,629 women (upskilling in digital literacy, financial education & entrepreneurship). Geographically, 104 most vulnerable villages accross the 10 munipalilities. 6,316 beneficiaries among which 3,105 womens are now using applications (basic technical and financial operations). 601 use e-commerce platforms. 10,762 people have access to digital financial services (payments, savings, loans).
3.4 | Results: Indirect Beneficiaries | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | Some pupils/students who are not yet carrying out any productive activity attended capacity building activities. AGRICeF app benefit for 316 non targeted beneficiaries
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words) | N/A
3.6 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | It took us longer than originally planned to finalize implementing partners selection. 6 months no cost extension has been requested in order to implement and report properly on activities and results achieved.
3.7 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words) | Efficient collaboration with and the involvement of the local authorities and sectorial ministries entities made it possible to target the most vulnerables villages and real beneficiaries. Such ecosystemic approach linked public and private (policy makers, regulators, capacity builders, financial services providers, fintech) stakeholders on common interests/objectives which is critical to innovation, long lasting partnerships and sustainable services providing.
3.8 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | Partnership between UNO (UNDP and UNCDF) has helped to better target, benefiaries and national entities and ongoing projects to be involved for better and complementary impact regarding responses to COVID 19. Also, partnering with private implementing partners through performance based grants conciliate market and sustainibilty approaches.
3.9 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words).
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words). | Capacity building activities have initially been planned for some national structures. Following up on the project steering committee recommendations, it has been decided to focus on financial services providers' digital transformation that directly aimed to improve digital financial services providing to vulnerables populations over the 10 targeted districts.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | No additional resources mobilized

## Project Indicators
Please include ALL indicators in the project document. Include the indicators and Baseline, Planned Target and Actuals for both OUTCOME and OUTPUT levels. "Actuals" refer to the total figures achieved for each indicator. Include separate actuals for 2021 and for 2022 (if applicable). Explain if targets were not achieved. Include means of verification. Use as many outputs cells as needed to present all project indicators.
| INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | DATA: ACTUALS 2022 (if applicable) | TOTAL actuals (agreggated 2021 and 2022 if applicable ) | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | Increased responsiveness of the Fund to the socio-economic impact of the covid-19 pandemic on countries
Indicator: | XXXXXX | example 15 | example 47 | total would be 62
Baseline: | XXXXXX
Planned Target: | XXXXXX | XXXXXX | XXXXXX
Output 1.1 | A growing volume of digital and financial literate population (women, youth, micro-entrepreneurs and agri-cooperatives) capable to adopt and/or elaborate innovative solutions to their own needs is available |  |  |  | beneficiaries' interest and implementing partners' approach to capacitty building | Data Base of the partners TIC Agro Business on the SharePoint
Indicator 1.1.1: | Number of beneficiaries trained on financial education, digital literacy and entrepreneurship (gender disaggregated)
Baseline: | 0
Planned Target: | 10000 | 0 | 12761 | 12761
Indicator 1.1.2: | Number of beneficiaries using digital literacy tools with entrepreneurship skills (gender disaggregated) |  |  |  | beneficiaries' interest and implementing partners' approach to capacitty building | More details on the SharePoint
Baseline: | 0 |  |  | 0
Planned Target: | 5000 | 0 | 6629 | 6629
Indicator 1.1.3: | Number of beneficiaries reinforced in Agri-processing and innovative technics
Baseline | 0 | 0 | 0 | 0
Target | 180 | 0 | 220 | 220
Output 1.2 | Greater and easier access to market for micro-entrepreneurs, agri-cooperatives, women and youth are achieved to foster their economic inclusion |  |  |  | Greater interest to digital due to the initial capacity building activities completed as starting point | TIC ABC (implementing partner) reports + data base
Indicator 1.2.1: | Number of new beneficiaries accessing market (disaggregated per women, micro and small entrepreneurs and smallholder farmers)
Baseline: | 0 |  |  | 0
Planned Target: | 5000 | 0 | 5745 | 5745
Indicator 1.2.2: | Number of beneficiaries transacting on e-commerce platforms (disaggregated per women, micro and small entrepreneurs and smallholder farmers) |  |  |  | Greater interest to digital driven by capacity building activities initially completed as starting point | Numerica Center (implementing partner) reports+data base
Baseline: | 0 |  |  | 0
Planned Target: | 500 | 0 | 601 | 601
Outcome 2 | Increased access to immediate health and socio-economic support to respond to the health and social impact of the COVID-19 pandemic
Output 2.1 | Access to finance is increased for micro-entrepreneurs and agri-cooperatives to accelerate SDGs. |  |  |  | Due to government's previous support to SMEs, the allocation's treshold has been raised from 3000 USD to 8000 USD in ordrer to target other beneficiaries segment | UNCDF Dual Key system platform
Indicator 2.1.1: | Number of e-grant beneficiaries (disaggregation per women, smallholder farmers, MSME)
Baseline: | 0 |  | 0 | 0
Planned Target: | 50 | 0 | 15 | 15
Indicator 2.1.2: | Number of FSPs supported in its digital transformation |  |  |  | Existing fund were not enough to support more than 2 financial service providers (FSP) in their digital transformation ; in order not to sprinkle, the 10 districts have been grouped into two zones, one for each FSP | Data Base on implementing partners FSP ALIDé & FECECAM available on the SharePoint
Baseline: | 0 |  |  | 0
Planned Target: | 5 | 0 | 2 | 2
Indicator 2.1.3: | Number of beneficiaries accessing digital solutions (digital savings and digital payments) availed by FSPs
Baseline
Target | 300 groups/cooperatives | 0 | 304 | 304 |  | FSP (ALIDé & FECECAM) final evaluation reports
Output 2.2 | Resilience and Recovery initiatives are duly monitored, and lessons learnt shared |  |  |  |  | BTOR on the SharePoint
Indicator 2.2.1: | At least 4 monitoring visits are organized
Baseline: | 0 |  |  | 0
Planned Target: | 4 | 1 | 3 | 4
Indicator 2.2.2: | At least 1 evaluation is conducted |  |  | 0 | Misunderstanding regarding the closing date didn't allow time do complete final evaluation
Baseline: | 0 |  |  | 0
Planned Target: | 1 | 0 | 0 | 0
Indicator 2.2.3: | At least 4 Knowledge management Tools shared with the beneficiaries
Baseline: | 0 | 0 | 0 | 0
Planned Target: | 4 | 0 | 4 | 4 |  | A flyer printed (500 copies) shared with diverse public including benefiaries groups, 2 articles published on the UNDP website and 9 messages on Twitter
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
1 Prospectus of 500 copies are produced and shared
https://eur03.safelinks.protection.outlook.com/?url=https%3A%2F%2Fwww.bj.undp.org%2Fcontent%2Fbenin%2Ffr%2Fhome%2Flibrary%2Fcrisis_prevention_and_recovery21%2Fdepliant-de-presentation-du-projet-r2r-au-benin.html&data=04%7C01%7Cmadinatou.ahounou%40uncdf.org%7C66028f26d1e549423fcf08da1b93b23a%7Cb3e5db5e2944483799f57488ace54319%7C0%7C0%7C637852618399348165%7CUnknown%7CTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7C3000&sdata=FlQEdOhFhMQECKP5pG864xn%2FvwwdoVbA7JEu00gGjvw%3D&reserved=0
2 Articles was wrote and shared on UNDP Website
https://eur03.safelinks.protection.outlook.com/?url=https%3A%2F%2Fpnudbenin.medium.com%2Frel%25C3%25A8vement-post-covid-19-au-b%25C3%25A9nin-linclusion-num%25C3%25A9rique-pour-stimuler-l-%25C3%25A9conomie-locale-52c129d903be&data=04%7C01%7Cmadinatou.ahounou%40uncdf.org%7C66028f26d1e549423fcf08da1b93b23a%7Cb3e5db5e2944483799f57488ace54319%7C0%7C0%7C637852618399348165%7CUnknown%7CTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7C3000&sdata=Cbm7t1RJ15uY1XLwAxArG4UUVd9xg4IwGbVTvcQ8U0s%3D&reserved=0
https://eur03.safelinks.protection.outlook.com/?url=https%3A%2F%2Fwww.bj.undp.org%2Fcontent%2Fbenin%2Ffr%2Fhome%2Fpresscenter%2Farticles%2Fameliorer-le-relevement-post--covid-des-populations-vulnerables-.html&data=04%7C01%7Cmadinatou.ahounou%40uncdf.org%7C66028f26d1e549423fcf08da1b93b23a%7Cb3e5db5e2944483799f57488ace54319%7C0%7C0%7C637852618399348165%7CUnknown%7CTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7C3000&sdata=guyHR0Ifrzv4od%2BUZ6tW0NCMh1pXDUW%2FL9KpVdBq0Jw%3D&reserved=0
9 messages had put on Twitter
https://eur03.safelinks.protection.outlook.com/?url=https%3A%2F%2Ftwitter.com%2FPNUDBenin%2Fstatus%2F1498960740526530564%3Fs%3D20%26t%3D_zzUmT4h1fpJeMnLqF9xKg&data=04%7C01%7Cmadinatou.ahounou%40uncdf.org%7C66028f26d1e549423fcf08da1b93b23a%7Cb3e5db5e2944483799f57488ace54319%7C0%7C0%7C637852618399348165%7CUnknown%7CTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7C3000&sdata=SsE10fWH5NCxTOXGucUfI5L4J3b0DMXpG6qr290r%2Bkw%3D&reserved=0
https://eur03.safelinks.protection.outlook.com/?url=https%3A%2F%2Ftwitter.com%2FPNUDBenin%2Fstatus%2F1498958051906310148%3Fs%3D20%26t%3D_zzUmT4h1fpJeMnLqF9xKg&data=04%7C01%7Cmadinatou.ahounou%40uncdf.org%7C66028f26d1e549423fcf08da1b93b23a%7Cb3e5db5e2944483799f57488ace54319%7C0%7C0%7C637852618399348165%7CUnknown%7CTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7C3000&sdata=e7E7%2BIQeJ8oAOLWp8ABKo1vnOnsl1FhRHLbMJYEL%2F9o%3D&reserved=0
https://eur03.safelinks.protection.outlook.com/?url=https%3A%2F%2Ftwitter.com%2FPNUDBenin%2Fstatus%2F1498217048735985664%3Fs%3D20%26t%3D_zzUmT4h1fpJeMnLqF9xKg&data=04%7C01%7Cmadinatou.ahounou%40uncdf.org%7C66028f26d1e549423fcf08da1b93b23a%7Cb3e5db5e2944483799f57488ace54319%7C0%7C0%7C637852618399348165%7CUnknown%7CTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7C3000&sdata=pVLJJpZDylZjGX7gPcSYGz72w9xuxrSmFxHYDlLhmlI%3D&reserved=0
https://eur03.safelinks.protection.outlook.com/?url=https%3A%2F%2Ftwitter.com%2FPNUDBenin%2Fstatus%2F1496358530026287104%3Fs%3D20%26t%3D_zzUmT4h1fpJeMnLqF9xKg&data=04%7C01%7Cmadinatou.ahounou%40uncdf.org%7C66028f26d1e549423fcf08da1b93b23a%7Cb3e5db5e2944483799f57488ace54319%7C0%7C0%7C637852618399348165%7CUnknown%7CTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7C3000&sdata=9qCrvvqqJjR7aP2kD8yGCDowIOJWgY6eFK11uI%2F6vZc%3D&reserved=0
https://eur03.safelinks.protection.outlook.com/?url=https%3A%2F%2Ftwitter.com%2FPNUDBenin%2Fstatus%2F1496214006700331008%3Fs%3D20%26t%3D_zzUmT4h1fpJeMnLqF9xKg&data=04%7C01%7Cmadinatou.ahounou%40uncdf.org%7C66028f26d1e549423fcf08da1b93b23a%7Cb3e5db5e2944483799f57488ace54319%7C0%7C0%7C637852618399348165%7CUnknown%7CTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7C3000&sdata=7iOMJtsGp6dhyWd8lfXRfqpr1am%2BnJePdDSgU0eKWzU%3D&reserved=0
https://eur03.safelinks.protection.outlook.com/?url=https%3A%2F%2Ftwitter.com%2FPNUDBenin%2Fstatus%2F1496216284287148033%3Fs%3D20%26t%3D_zzUmT4h1fpJeMnLqF9xKg&data=04%7C01%7Cmadinatou.ahounou%40uncdf.org%7C66028f26d1e549423fcf08da1b93b23a%7Cb3e5db5e2944483799f57488ace54319%7C0%7C0%7C637852618399348165%7CUnknown%7CTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7C3000&sdata=HPVc9FL8T8aOz9hmq5%2F%2BLqAsCLS4mGoRIKeuPEzQTyw%3D&reserved=0
https://eur03.safelinks.protection.outlook.com/?url=https%3A%2F%2Ftwitter.com%2Ftchaoudonald%2Fstatus%2F1468779169496584195%3Fs%3D20%26t%3D_zzUmT4h1fpJeMnLqF9xKg&data=04%7C01%7Cmadinatou.ahounou%40uncdf.org%7C66028f26d1e549423fcf08da1b93b23a%7Cb3e5db5e2944483799f57488ace54319%7C0%7C0%7C637852618399348165%7CUnknown%7CTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7C3000&sdata=PG%2Flt7Sv9E4apPxbna%2Bke2TkExsiuFn1h4iFvzadAhU%3D&reserved=0
https://eur03.safelinks.protection.outlook.com/?url=https%3A%2F%2Ftwitter.com%2FPNUDBenin%2Fstatus%2F1488456382663770113%3Fs%3D20%26t%3D_zzUmT4h1fpJeMnLqF9xKg&data=04%7C01%7Cmadinatou.ahounou%40uncdf.org%7C66028f26d1e549423fcf08da1b93b23a%7Cb3e5db5e2944483799f57488ace54319%7C0%7C0%7C637852618399348165%7CUnknown%7CTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7C3000&sdata=tZORC0Hrd0bgFhEEm2GyiLL0%2BMoZRdcl8cA7fpzrUJE%3D&reserved=0
https://eur03.safelinks.protection.outlook.com/?url=https%3A%2F%2Ftwitter.com%2FPNUDBenin%2Fstatus%2F1488104204354965506%3Fs%3D20%26t%3D_zzUmT4h1fpJeMnLqF9xKg&data=04%7C01%7Cmadinatou.ahounou%40uncdf.org%7C66028f26d1e549423fcf08da1b93b23a%7Cb3e5db5e2944483799f57488ace54319%7C0%7C0%7C637852618399348165%7CUnknown%7CTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7C3000&sdata=tQP8HImDbx6E%2F6KT9MUDj9r6DUbWk%2FvMXgjwfrqu2Ow%3D&reserved=0
Some pictures abd videos are produced ()
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well as picture material please make sure you include all credits and share them in high resolution.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board