## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | Concerted action with forcibly displaced women, girls and host communities against consequences of the COVID-19 crisis | Overall Duration (months) | 12
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-11-01
MPTF Office Project Reference Number: | 12472 | Original End Date (dd.mm.yyyy) | 2021-11-01
Country | Democratic Republic of Congo | In case of NCE Current End date(dd.mm.yyyy) | 2022-02-01
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNFPA, UNWOMEN and UNHCR | National counterparts (government, private, NGOs & others) and other International Organizations | Government counterparts: ANR (intelligence), PNC (police), civil affairs offices, social affairs office and territorial administration, Tribunal de paix Implementing partners: Hope In Action, Intersos (INGO), AHCOPDI (NGO), Caritas (INGO), AIDPROFEN (NGO) Local women's organisations: Forum Des Femmes, SOFEM, CAFPEDI, Wamama Simameni and ALW Other International organisations: Humanitarian partners participating in the protection cluster benefit from protection monitoring data. IP:Government counterparts; DPS, PNSR, PNSM, DIVISION DU GENRE et des affaires sociales Implementing partners: Hope in Action, Other International organisations; Members of GBV Sub Cluster UN System : Monusco, OHCHR, OCHA
Report Cleared By
o Name: | Dr Eugene KONGNYUY
o Title: | Resident Representative
o Email address: | kongnyuy@unfpa.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | During the month of January 2022 the project worked on the training of health personnel on Emergency Obstetric and Neonatal Care, maternal death surveillance and response, prevention and control of Infection in an obstetrical environment and clinical management of rape including infection prevention and control and COVID-19 detection, response and referral/case management including Mental Health and Psychosocial Support to IDPs/host families. GBV/EAS referral pathways and entry points for COVID were strengthened and promoted. Community engagement and social mobilization were promoted at local level to manage rumors, build trust between health facilities, health providers and community members, they now have reinforced awareness and understanding of the COVID-19 pandemic, and how to address the risks of gender-based violence. Mental health and psychosocial support was provided to improve health services response to gender-based violence. Protection monitoring through the reporting and analysis of protection incidents against IDPs and host communities, particularly incidents of SGBV continued. Referral of incident survivors to medical and legal structures and psychosocial supportcontinued.
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | North Kivu is the DRC's second most affected province by Covid-19, with disproportionate effects on women and girls. The situation aggravates already strained state and society relations in a province that is deeply marked by pockets of fragility, forced displacement, weak public service delivery, wide-spread poverty and harmful gender norms and practices. The project implemented with MPTF support shows that implementing agencies can continue achieving the Sustainable Development Goals despite the COVID-19 pandemic, especially SDG3 (Good health and well-being), SDG5 (gender equality), SDG 10 (reduced inequalities), SDG 16 (peace, justice and strong institutions) and SDG17 (Partnership for achieving goals).In line with humanitarian's and développement intervention approach, leaving no one behind, with attention to "do no harm", holistic and community-based protection approach, agencies worked with different layers of the targeted populations (host communities, displaced), in collaboration with local authorities ensuring that the protection plans reflect the priorities of those different groups, and community leaders, to achieve the results listed in this document. The efforts made in consortium have made it possible to achieve the expected objectives, in particular to strengthen the socio-economic resiliency of displaced women and residents in the health zones of Karisimbi, Mweso and Birambizo as well as to strengthen the prevention and protection measures against gender-based violence and reduce the risks of the spread of COVID-19 in North Kivu.
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | With the support of MPTF, the joint programme was able to work towards crossed and complementary interventions approaches: (1) More than 4,002 Women and girls IDPs and refugees and women from host communities receive urgent support for improved health services to cope with and prevent the spread of COVID-19, (2) Livelihoods and socio-economic resilience of 900 displaced women and host communities vulnerable and at risk of SGBV, were strengthened through the development of community initiatives; (3) Prevention, monitoring and accountability measures in North Kivu through the mitigation, and protection of human rights violations as negative effects of COVID-19, were strengthened.
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | In ordre to provide an appropriate response to the Covid 19 pandemic, UNFPA, UNHCR and UNWOMEN achieved the following annual results in 2022: (1) 6 community organizations were supported (2) 425 women and girls participated in psychosocial activities, including survivors (3) 6547 women and girls participated in psychosocial activities, including survivors who benefited from age-appropriate and disability sensitive case management;(4) 72 survivors were supported with mental health and psychosocial support (5) Capacity-building (training and financial support) was provided to 5community structures involved in protection monitoring; (6) 6 local authorities (administrative and traditional) had capacities strengthened on the key concepts of GBV, human rights, the legal framework, and their involvement, responsibilities and role in the prevention and protection of women and girls, displaced/returnees and very vulnerable/marginalized people, including the referral pathways, in GBV and COVID 19; (7) 3168 cases were registered in the monitoring of protection identification and registration of protection and SGBV incidents and victims of SGBV and other human rights violations,
3.2 | Results: Gender | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | This project, undertaken by UNFPA, UNHCR and UN Women, had a particular focus on forcibly displaced women and girls. These three organizations are very involved in protection, especially in the fight against SGBV and worked in a synergic way in terms of coordination, prevention and protection, including the holistic assistance to SGBV survivors. The Gender Age Marker (GAM) of this project is 3, as the joint project targets women or men, girls or boys that suffers discrimination or disadvantage, creating a more level playing field and includes activities on building gender-related services or more equal relations between women and men.
3.3 | Results: Direct Beneficiaries | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | TOTAL: 7,417 persons (Female: 7, 090 and Male: 327).
3.4 | Results: Indirect Beneficiaries | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | TOTAL: 35,677 - Estimated value. Only directed beneficiaries of the implemented activities were counted.
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words) | The principles of "Do No Harm" was applied. Mechanism of beneficiaries’ identification was clear and explain to all, and local leaders were consulted through focus groups. All project activities were implemented respecting protection standards and do no harm approaches. Non-discriminatory ethics was applied and beneficiaries had equal access to services according to their needs, including the most vulnerable (people living with disabilities, HIV, the elderly and marginalized people).
5 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | Several parts of the province, including Masisi Territory, remain the theatre of longstanding violence and armed conflict, accompanied by human rights violations, breaches of International Humanitarian Law and massive forced displacement. The permanent presence of the local staff of the implementing partners in the targeted health zones could help to circumvent this challenge of insecurity. The President of the Republic declared a state of siege in North Kivu in May 2021 in an effort to address the deteriorating security situation. The civilian authorities, territorial administrators and Governors have been replaced by military/ police officers, and the level of military operations have increased, with accompanying impacts on the protection of civilians including IDPs. The state of siege hindered the effective rule of law as civilian cases needed to be introduced before military courts in Goma. Often with delays due to the lack of magistrates and bringing additional costs to the victims such as transport and accommodation. The state of siege also impacted on the renewal of the moratorium leading to a delay in the implementation of the statelessness activities. Finally, in a context of continued violence and human rights violations, protection needs, and root causes remain unresolved, limiting the potential for solutions. Large influxes of population movements continue to overwhelm host communities who share the little that they have. While host families have welcomed IDP families in their community, they keep being exposed to vulnerabilities and have limited access to services and livelihoods.
6 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words) | The success of the holistic approach to SGBV and close collaboration between consortium members, Implementation Partners, monitoring actors, Health care providers in health zones, community-based psychosocial assistance and professional legal and judicial assistance, supported by socio-economic interventions, was a programmatic lesson and confirmed the efficiency of this kind of approach. After a further external evaluation of the project in February, through field visits, discussions with key actors (authorities, etc.), focus groups and individual discussions with beneficiaries in Masisi and Mweso, UNHCR hopes to continue and expand this model in more secure IDP-hosting areas of North Kivu, ensuring access for beneficiaries from less secure areas through the cash-for-protection program.
7 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | Carrying out joint missions with the Provincial Divisions of Health and Gender, the members of BCZ (Bureau Central de la Zone de Santé) management teams have enabled us to improve the services of the APS (Assistants Psycho-Sociaux) in the counseling centers and to strengthen their technical capacity. JP implementing agencies attended meetings of the humanitarian territorial sub-coordination at the Masisi territorial level and of the GBV sub-cluster (in Goma) which facilitated the coordination of stakeholders in GBV protection and ensure complementarity with all actors in the field This has facilitated complementarity and facilitated the transfer of good practices, lessons learned from one project to another, the harmonization of interventions and joint planning between projects. The partnerships and synergies with the state party were developed during project implementation.
8 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words). | During project implementation, supervision missions and several evaluations and participatory field visits were carried out separately by UNFPA, UNWOMEN and UNHCR for monitoring, evaluation and learning with implementation parteners in different zones of project.
9 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words). | The state of siege that was put in place in North Kivu, had a negative impact on legal action for any civilian cases, as the civilian courts were replaced by military ones. This meant that civilian cases - including cases of GBV needed to be introduced before courts in Goma. The number of military magistrates was too limited to be deployed in rural areas - outside Goma. Furthermore, state of siege also hampered the achievement of objectives, such as the renewal of the moratorium on statelessness activities. Since 2017 a moratorium was in place that allows the temporary suspension of the payment of legal fees linked to registration at the civilian office. This suspension allows families to register the birth of their children after the legal period of 90 days has passed - without any additional fees.
10 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | UNFPA: To facilitate the achievement of the project's results, UNFPA proceeded with the international purchase of kits (medical equipment and drugs), then deployed them in the various health facilities, for free offer of services. Some of these kits include: condoms, Clean Delivery (Individual and Birth attendants), Rape Treatment kit, Oral and Injectable Contraception kit, Sexually Transmitted Infections (STI) kit, Clinical Delivery Assistance kit (Reusable Equipment & Drugs and Disposable Equipment), Referral Level (Drugs and Disposable Equipment & Drugs and Disposable Equipment). About human resources, UNFPA had mobilized an expert in GBV and SEA to coordinate project activities, in collaboration with reproductive health analysts. UNWOMEN: In term of human resources, the project received new focal points one in April 2021 and another in August. The recruitment and handover to the new staff created a delay in terms of project implementation but activities were accelerated to meet the required period and outcomes.

## Project Indicators
Please include ALL indicators in the project document. Include the indicators and Baseline, Planned Target and Actuals for both OUTCOME and OUTPUT levels. "Actuals" refer to the total figures achieved for each indicator. Include separate actuals for 2021 and for 2022 (if applicable). Explain if targets were not achieved. Include means of verification. Use as many outputs cells as needed to present all project indicators.
| INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | DATA: ACTUALS 2022 (if applicable) | TOTAL actuals (agreggated 2021 and 2022 if applicable ) | Reasons for Variance with Planned Target (if any) | Source of Verification
UNFPA
Outcome 1 | Women and girls IDPs and refugees and women from host communities receive urgent support for improved health services to cope with and prevent the spread of COVID-19. |  |  |  | None planned in 2022 target already achieved | Table for monitoring indicators, activity reports.
Indicator: | Number of women and girls who received urgent support during Covid-19. | example 15 | example 47 | total would be 62
Baseline: | 0
Planned Target: | 1000 | 1314 | 0 | 1314
Output 1.1 | Strengthen the institutional capacities of health facilities and service providers with 08 IPC and 04 WGSS(Infection Prevention and Control) kits, personal protective equipment and other materials for COVID-19 prevention 400 dignity kits adapted to the cultural realities of the needs of women and girls in targeted health zones, provision of emergency SR kits (1A, 1B, 2A, 3, 4, 5, 6A, 6B, 11A and 11B) and other essential RH commodities at all service delivery points are provided in target areas |  |  |  | None planned in 2022 target already achieve
Indicator 1.1.1: | Number of health centres provided with COVID-19 protection material |  |  |  |  | Distribution plan, material and equipment receipt form signed by the MCZs
Baseline: | 0
Planned Target: | 8 | 8 | 0 | 8
Indicator 1.1.2: | Number of IPC (Infection Prevention and Control) kits, personal protective equipment, essential RH commodities and other materials for COVID-19 during the COVID-19 outbreak |  |  |  | None planned in 2022 target already achieved | Distribution plan, material and equipment receipt form signed by the MCZs
Baseline: | 0
Planned Target: | 12 | 12 | 0 | 12
Indicator 1.1.3: | Number of women and girls including IDPs, refugees and host communities who received dignity kits, stay-at-home kits and other support material |  |  |  | None planned in 2022 target already achieved | Training report and participant list
Baseline: | 0
Planned Target: | 400 | 400 | 0 | 400
Output 1.2 | Training of health personnel on Emergency Obstetric and Neonatal Care, maternal death surveillance and response, prevention and control of Infection in an obstetrical environment and clinical management of rape including infection prevention and control and COVID-19 detection, response and referral/case management including Mental Health and Psychosocial Support to IDPs/host families.
Indicator 1.2.1: | Midwives, nurse supervisors of health zones and community health workers trained on relevant topics |  |  |  | Target moderatly overachieved in Health professional training | Activity Report
Baseline: | 0
Planned Target: | 40 | 0 | 57 | 57
Output 1.3
indicator 1.3.1: | Number of community organizations, women's rights advocates and groups supported |  |  |  | In 2022, 37 people from 6 community organisations were trained. This was an additional traning as 8 had already been trained.
baseline: | 0 |  |  |  |  | Activity Report
planned target: | 8 | 8 | 6 | 8
Output 1.4 | GBV/EAS referral pathways and entry points for COVID strengthened and promoted
Indicator 1.4.1: | Number of persons informed on referral pathways |  |  |  | None planned in 2022 target already achieved | Activity Report
Baseline: | 0
Planned Target: | 4000 | 4002 | 0 | 4002
Indicator 1.4.2: | Number of GBV cases that received legal/judicial support |  |  |  | None planned in 2022 target already achieved | Partner report
Baseline: | 3
Planned Target: | 30 | 78 | 0 | 78
Indicator 1.4.3: | % of survivors of sexual violence who received medical care at service delivery points by trained staff within 72 hours of the rape incident, disaggregated by age and sex |  |  |  | Percentage reflects overall statistics | Activity Report and GBV Dashboard
Baseline: | 0
Planned Target: | 100 | 93% | 0% | 93%
Indicator 1.4.4: | Number of survivors of sexual violence who received medical care disaggregated by age/gender/disability |  |  |  | Change of situation in the area led to a larger than anticipated number of survivors target overachieved | Activity Report and GBV Dashboard
Baseline: | 0
Planned Target: | 108 | 234 | 66 | 300
Indicator 1.4.5: | Number of women and girls who participated in psychosocial activities, including survivors who benefited from age-disaggregated/disability case management |  |  |  | Change of situation in the area led to a larger than anticipated number of survivors target overachieved | Activity Report and GBV Dashboard Appui psychosocial UNHCR 2022: 425 cas dont 302 femmes, 26 Hommes, 92 filles et 5 garçons
Baseline: | 0
Planned Target: | 1800 | 1892 | 425 | 2317
Output 1.5 | Community engagement and social mobilization promoted at local level to manage rumors, build trust between health facilities, health providers and community members, and reinforce awareness and understanding of the COVID-19 pandemic at the community level, and address the risks of gender-based violenceCommunity engagement and social mobilization promoted at local level to manage rumors, build trust between health facilities, health providers and community members, and reinforce awareness and understanding of the COVID-19 pandemic at the community level, and address the risks of gender-based violence
Indicator 1.5.1: | Number of individuals reached with awareness-raising |  |  |  | In addition to 4,000 people informed directly, 15,445 others were informed through messages relayed with megaphones in various targeted health zones. | Activity Report and GBV Dashboard
Baseline: | 0 |  |  |  | 171 community sensitisation sessions took place on the prevention of GBV for 6547 people (2893women, 965 men , 1785 girls , 904 boys).
Planned Target: | 4000 | 4002 | 6547 | 10549
Output 1.6 | Mental health and psychosocial support provided to improve health services response to gender-based violence
Indicator 1.6.1: | Number of service provider strengthened on mental and psychosocial response including the GBV case management |  |  |  | 6 women were trained in a 3 day training in kinshasa adding to the orgiginal total | Training report and participant list
Baseline: | 0
Planned Target: | 40 | 40 | 6 | 46
Indicator 1.6.2: | Number of Cases of GBV that received psychosocial support |  |  |  | 210 cases refered in UNHCR safe spaces for 72 psychosocial, 66 medical and 72 legal assitance ; | On-site monitoring to be conducted in 2021, desk-review of reporting by partner, activity report and GBV dashboard
Baseline: | 77
Planned Target: | 1085 | 1977 | 72 | 2049
Outcome 2 : Livelihoods and socio-economic resilience of displaced women and host communities vulnerable and at risk of SGBV strengthened through the development of community initiatives
Output 2.1 | Conduct a rapid gender assessment in the four targeted health zones and identify opportunities for Women's Economic Empowerment |  |  |  |  | Desk review of reporting by partner , assessment report
Indicator 2.1: | Report on gender and economic opportunities in targeted areas published |  |  |  | Report Completed | Desk review of reporting by partner , assessment report
Baseline: | 0
Planned Target: | 1 |  | 1 | 1
Output 2.2 | Provide cash-transfers to women at high-risk or victims of SGBV to contribute to their socio-economic resilience with post-distribution monitoring and technical support |  |  |  | None planned in 2022 target already achieved | Beneficiary lists and receipt lists
Indicator 2.2.1 | Number of beneficiaries having received cash transfers/Provide cash-transfers to women at high-risk or victims of SGBV
Baseline: | 0
Planned Target: | 660 | 660 | 0 | 660
Output 2.3 | Strengthen the livelihood of vulnerable women-led households including SGBV survivors through the distribution of "resilience kits" followed by post distribution monitoring and technical support |  |  |  |  | Beneficiary lists and receipt lists
Indicator 2.3: | Number of beneficiaries having received resilience kits |  |  |  | None planned in 2022 target already achieved | Beneficiary lists and receipt lists
Baseline: | 0
Planned Target: | 600 | 600 | 0 | 600
Output 2.4 | Support villages savings and credit associations (VSLAs) and Mutuals Solidarity (MUSO) in target areas |  |  |  | None planned in 2022 target already achieved | Activity Report
Indicator 2.4 : | Number of beneficiaries in VSLA activities
Baseline: | 0 | 0 | 0
Planned Target: | 180 | 180 | 0 | 180
Output 2.5 | Trained beneficiaries selected on the basis of the rapid gender assessment on rapid income-generating activities, savings, life skills and leadership |  |  |  | None planned in 2022 target already achieved | Activity report
Indicator 2.5 : | Number of beneficiaries trained in Rapid Income Generating Activities
Baseline: | 0
Planned Target: | 150 | 150 | 0 | 150
Outcome 3 | Strengthened prevention, monitoring and accountability measures in North Kivu through the mitigation, and protection of human rights violations as negative effects of COVID-19
Outcome 3.1: | Support the Ministry of Gender and its Provincial, territorial and local Gender Thematic Groups for the implementation of the National Strategy against SGBV |  |  |  | None planned in 2022 target already achieved | Activity report
Indicator 3.1.1: | Number of structures (Provincial, territorial and local Gender Thematic Groups and their sub-groups and the 1325-coordination committee) supported through technical and institutional assistance.
Baseline: | 4
Planned Target: | 6 | 11 | 0 | 11
Output 3.2 : Provide training on international and national law on the fight against statelesness, provide dotations to civil state's offices, provide material support to offices; Conduct information sessions, focus group discussions and radio broadcasts in partnership with community structures on the possibilities and the importance of birth registration and Provide direct support, legal support and financial assistance to specific families through implementing partners and state officers
Indicator 3.2.1 : Support civil state offices in the registration of births | Support civil state offices in the registration of births |  |  |  | The non-renewal of the moratorium, especially because of the implementation of the state of siege in May 2021, and the long administrative procedures impeded the smooth running of the activities | Partner report
Baseline: 1 | 1
Planned Target: 4 | 4 | 1 | 0 | 1
Indicator 3.2.2 | Number of persone reached with information campaigns o registration moratorium |  |  |  | This is a tentative number based on interim report however 4 campaigns were held . Further campaigns were were impossible due to state of siege and non renewal of moratorium. | Direct implementation
Baseline | 0
Planned Target | 4000 | 2121 | 0 | 2121
Indicator 3.2.3 | Support to children to obtain birth certificates |  |  |  | The non-renewal of the moratorium, especially because of the implementation of the state of siege in May 2021, and the long administrative procedures impeded the smooth running of the registration activities | Partner report
Baseline | 255
Planned Target | 1200 | 0 | 0 | 0
Output 3.3 | Provide material and technical support to the Child and Family Protection Unit of the Congolese National Police to implement its Action Plan against GBV and strengthen the capacities of 200 members of EPEPVS, prison officers, police etc. on the prevention of violence, particularly GBV due to COVID -19 |  |  |  | An armed administration was decrated in May 10th, 2021 in North Kivu and Ituri. Military governor installed in favor of the state of siege. It was then difficult for then to mobilise several officers for a trainings. Instead 150 women activist from Mwesso and Birambizo were trained. | Mission reports
Indicator 3.3: | Number of police officers in decentralized territorial entities trained on prevention of violence, particularly SGBV
Baseline: | 0 | 0 | 0 | 0
Planned Target: | 200 | 70 | 150 | 220
Output 3.4 | Support the establishment of 4 “Girl Shine” spaces that aim to strengthen girls' social assets so that they have someone to turn to when experiencing or threatened by |  |  |  | None planned in 2022 target already achieved
Indicator 3.4.1: | Number of "Girl Shine" safe spaces establishes( WGSS) |  |  |  |  | Activity report Activity report
Baseline: | 0
Planned Target: | 4 | 4 | 0 | 4
Indicator 3.4.2: | Number of girls who benefitted from support in safe spaces |  |  |  | None planned in 2022 target already achieved | Activity report and attendance register
Baseline: | 0
Planned Target: | 2888 | 2890 | 0 | 2890
Output 3.5 | Provide direct support, both financial and technical, to local women's organizations, traditional leaders and organizations of people with disabilities, to conduct awareness-raising campaigns on gender-based violence.
Indicator 3.5.1 | Provide direct technical and financial support to women's organisations and organisations for persons with disabilities |  |  |  | None planned in 2022 target already achieved | Partner report
Baseline | 5
Planned Target | 5 | 5 |  | 5
None planned in 2022 target already achieved
Indicator 3.5.3: | Number of persons reached through awareness-raising campaigns |  |  |  |  | Activity report
Baseline: | 0 | 0
Planned Target: | 13000 | 13000 | 0 | 13000
Output 3.6 | Conduct protection monitoring through the reporting and analysis of protection incidents against IDPs and host communities, particularly incidents of SGBV; Referral of incident survivors to medical and legal structures and psychosocial support
Indicator 3.6.1 | Capacity-building (training and financial support) to community structures involved into the protection monitoring |  |  |  | 5 structures had been identified and trained as well as provided with support. | Partner report
Baseline | 0
Planned Target | 2 | 5 | 5 | 5
Indicator 3.6.2 | Strengthen the capacities of local authorities (administrative and traditional) on the key concepts of GBV, human rights, the legal framework, and their involvement, responsibilities and role in the prevention and protection of women and girls, displaced/returnees and very vulnerable/marginalized people, including the referral circuit, in GBV and COVID 19 |  |  |  | 18 participants (12 Men and 6 women) from DIVAS and those from service genre, famille et enfant from Butembo and Beni were tranined. | Partner report
Baseline | 5
Planned Target | 5 | 5 | 6 | 5
Indicator 3.6.3 | Monitoring of protection identification and registration of protection and SGBV incidents and victims of SGBV and other human rights violations |  |  |  | The number of supported people had been more important than planned, especially due to the increasing insecurity and the displacements they led to. For 2022, numbers are as follows: Masisi: 841 Mweso: 723 Kibirizi: 484 Kibua: 282 Others: 24 | Partner report
Baseline | 68 in November/December 2020
Planned Target | 250 | 381 | 3168 | 381
Indicator 3.6.4: | Percentage of survivors of SGBV referred to medical and legal structures and psychosocial support structures |  |  |  | Percentage reflects overall statistics | Referral notes and activity report and GBV Dashboard
Baseline: | 0
Planned Target: | 80% | 97% | 0 | 97%
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.
Note on C37: Martin BIAYI: 217 / 234
Note on C104: Martin BIAYI: 2521+369

## Communication
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
8 health centres was provided with COVID-19 protection material by UNFPA, and this allowed to treat IDPs and host communities free of charge, thus improving health of approximately 4,002 people in targeted health zones. This meets the SDG3 (Good health and well-being).
Collaboration between police authorities and UNFPA: Following the rapid assessment of the needs and risks of GBV and SEA in the 09 collective centers of IDPs in Masisi, UNFPA and the police authorities worked together to distribute dignity kits to women, girls and vulnerables who had fled conflict and military operations against armed groups.
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well as picture material please make sure you include all credits and share them in high resolution.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
UNHCR
Project tweet: https://twitter.com/UNHCR_DRC/status/1502257299200565248
UNFPA
sensitization of women's organizations, including people living with disabilities.