## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | Implementation of a gender-sensitive Social Household Registry in Guatemala. | Overall Duration (months) | 17 months
Programme Number (if applicable) | 124304 | Start Date (dd.mm.yyyy) | 2020-10-31
MPTF Office Project Reference Number: | 124304 | Original End Date (dd.mm.yyyy) | 2021-12-31
Country | Guatemala | In case of NCE Current End date(dd.mm.yyyy) | 2022-03-01
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNDP, UNFPA, UNICEF and UNHCHR. | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Social Development, National Institute of Statistics, Presidential Secretariat for Women, and Vicepresidency of the Republic.
Report Cleared By
o Name: | Miguel Barreto
o Title: | Resident Coordinator
o Email address: | miguel.barreto@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | At the end of 2021 gathering of information was finished in three of six municipalities originally prioritized - according to ProDoc – by the Gender-Sensitive Social Registry of Households (RSH). These were: San Gaspar Ixchil, Santa Cruz La Laguna, and San Bartolomé Jocotenango that represented a total of 5,213 homes for 2021. Field activities resumed during the first quarter of 2022 among United Nations System (UNS) agencies and the Ministry of Social Development (MIDES) to continue with the information gathering process in the four remaining municipalities. Implementation of good practices and learning generated was prioritized. In February 2022, local governance and territorial management meetings were held with mayors and governors, and information gathering began in March in the municipalities of Santa Lucía La Reforma; Totonicapán, and Santa Apolonia, Chimaltenango, which enabled reaching a running total of 11,515 homes. Due to circumstances beyond the project control and in agreement with MIDES, it was decided not to address the municipality of Santa María Chiquimula, Totonicapán, because of risk situations of social conflict, violence, and forest fires. In order to achieve goals of the RSH pilot project, MIDES agreed, along with UNS agencies, on taking the census of another two municipalities in the department of Huehuetenango, analyzing poverty, inequality, and high vulnerability criteria to replace the municipality of Santa María Chiquimula. In the second quarter of 2022, municipalities of Santiago Chimaltenango and Colotenango, located both in Huehuetenango, were selected for a total of 19,639 homes identified as preliminary result from which 46% are men and 54% women. The initial analysis of the information gathered between 2021 and 2022, reflected high rates of underregistration in every municipality, especially regarding children who lack personal id documents. Therefore, and as direct result of the RSH pilot project, the Main Government in collaboration with MIDES, National Demographic Registry (Registro Nacional de las Personas, RENAP), and municipal governments implemented shifts to issue Personal ID Documents (DPI, for its initials in Spanish) and/or birth certificates, free of charge, in order to eradicate the underregistration. Even though this support finished in the first 3 municipalities registered, requirements to extend this support to the other 4 ones of the RSH pilot project have already been submitted. The Personal ID Document represents the entrance to any social program, and benefits mainly women and children. Lastly, it is worth mentioning that the last 2 registered municipalities did not have an updated cartography; therefore, coordination and exchange of information with the National Statistics Institute (INE) was necessary.
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | Guatemala is a country lacking statistics and a sole registry. This weakness was evidenced during the COVID-19 pandemic, since there were no homes registration to make money transfers to the ones affected by the pandemic. So, it was necessary to conduct focused information gathering which created delays in the time of response. The Gender-Sensitive Social Housing Registry (SRH) is classified as a tool to strengthen the social protection system in the country. Therefore, the pilot project enabled identifying and determining peoples in poverty condition, prioritizing women, indigenous women, women with disability, and women heads of the household, in vulnerable condition in 7 municipalities prioritized by MIDES. To this aim a tool was developed and validated in the field to identify women in a multidimensional poverty situation. Throughout the life of the program enquiries were conducted with groups of women in order to guarantee their full participation in the design and implementation of the information gathering tool. The pilot exercise covered 7 municipalities and provides information to create social protection program proposals that will contribute to women leadership and empowerment. The Program planned to reach 20,000 registrations of homes during the pilot phase. A total of 19,639 homes in 7 municipalities were registered in the RSH when registration of the last municipality was finished. The project is linked to SERP indicators, especially to the Indicator 2.5 Number of Beneficiaries in the Social Protection Scheme and Services Related to COVID-19.
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | The preliminary count registered in the Social Housing Registry was 19,639 homes, with the last municipality registered. Strengthening of MIDES capacities regarding the use of digital cartography and a more organized and technical criteria based planning has been evidenced. Information gathered demonstrates needs of homes and municipalities' situation which has enabled placing the project in the strategic agenda of the Central Government, essential to reach the institutionalization and scalability of the pilot project. To July 2022, actions such as the interinstitutional coordination, and registration and issue of personal id documents days have been developed in the project, in addition to submitting results to the Presidency along with its ministries cabinet to identify other initiatives to be implemented in the territories. UNS Agencies will continue supporting MIDES to finish the job in pilot municipalities after finishing PC execution in July 2022 when all municipalities will be covered.
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | (i) MIDES has a digital Socioeconomic Assessment Card (FECS, for its initials in Spanish) to determine the socioeconomic situation of homes with a multidimensional approach sensitive to women's rights that is being evaluated to be officially used in regular MIDES programs; (ii) Finished community enquires supporting technical criteria set to design the information gathering tool; (iii) 19,639 registered homes; (iv) appropriation of MIDES technical teams for the use of digital tools, from digital cartography to data collection tools; (v) appropriation of MIDES technical teams to plan and implement planning meetings at the field and strengthening community governance processes.
3.2 | Results: Gender | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | Results of information gathered on the field allow recognizing needs of and gaps for women, as well as identifying poverty conditions and privations faced in their surroundings. Information gathered allows showing main needs and opportunities to design projects and programs for a specific response to their surroundings. It is worth mentioning that accompaniment for community leader women and guide mothers has also allowed strengthening information gathering processes from an inclusive participation approach, which is the starting point for community consultations in which women group opinions are reflected on the Socioeconomic Assessment Card (FECS) structure. At the closing of the Project, and as result of the information gathered, MIDES and UNS teams hold meetings to set actions to be taken and analyze opportunities for new social programs aimed at handling gaps identified by the Social Registry of Households. A clear example of this is the Program "Pisos Dignos" announced on early August 2022 by the President as result of the RSH (concrete floors in the 7 municipalities).
3.3 | Results: Direct Beneficiaries | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | TOTAL 19,639 homes (94,319 persons). Disaggregated by population group and age range (Female: 54% Male: 46% Early childhood:20% Children:16% Youth: 25% Adults:25% Elder: 7%
3.4 | Results: Indirect Beneficiaries | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | There is still no calculation of indirect beneficiaries
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words) | Each registered municipality had a planning strategy, which approach is based on respect to communities and their men and women leaders. Before entering each municipality or populated area, territorial coordination is conducted to have required accompaniment for MIDES and UNS field teams. A close communication and comprehensive planning have been kept with government authorities, at both central and municipal level, taking actions that consider conflicts at some municipalities.
3.6 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | Municipality of Santa María Chiquimula, Totonicapán, was one of the prioritized municipalities in the Project initial planning which, in addition, had the greatest number of structures/homes. It was cancelled due to circumstances beyond the Project control since there was a high risk and vulnerability environment for field teams. Facing this, a technical analysis was conducted with MIDES to identify other municipalities meeting prioritization criteria and, due to analysis outcome, municipalities of Santiago Chimaltenango and Colotenango were selected to comply with the objectives determined in the initial planning document. Likewise, important progress has been made placing the Project in the Government's strategic agenda, even though there are still challenges to set the institutionalization road map and the Project coordination unit (in MIDES). Currently, scenario and proposal analysis are being conducted along with UNDP, UNICEF, UNFPA, and OHCHR for the pilot project scalability. Even though MIDES institutional response capacity was slow in most phases, mainly due to high staff turnover in key positions linked to RSH, agencies reduced this situation by modifying the budget and timelines, in addition to adapting processes responding to MIDES institutional capacities. Lack of MIDES personnel experience using cartography and information systems was one of the expected risks; however, trainings and permanent accompaniment was favorable for the adoption of field tools.
3.7 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words) | The working model from the Social Registry of Households pilot project has created important learnings for interinstitutional collaboration, considering that processes require coordination from central government, and both municipal and community authorities. This enabled having support and accompaniment at the most distant communities. In addition to demonstrating the underregistration situation of people in the most distant communities, interinstitutional coordination supported by the central government allowed beginning with registration days of individuals in the first registered municipalities, which favored more than 20,000 persons. Lastly, the beginning of the collaboration from RSH and the National Statistics Institute (INE) is mentioned as an important outcome for the exchange of information and joint work opportunities analysis in the following phase that would mean the scalability at national level prioritizing municipalities with a greater poverty and extreme poverty situation. To strengthen Guatemala’s social protection system, quality information and versatile interinstitutional coordination mechanisms are necessary. These are two of the main lessons generated by the COVID-19 pandemic. RSH serves as a collaboration model to reach the most vulnerable population and in a greater poverty situation.
3.8 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | Social Registry of Households (RSH) has become a political, strategic, and institutional priority for the current government. A clear example of this is how it has generated important interinstitutional collaborations, such as: Coordination between the National Demographic Registry (RENAP) and MIDES to address a strategy to reduce the level of underregistration of the most vulnerable population. To this aim, the Executive Branch and the Board of Directors at RENAP approved the exoneration of any charge regarding the issuance, replacement, or registration in order to obtain the Personal ID Document (DPI) at the RSH municipalities, besides the coordination between MIDES and the National Statistics Institute (INE) for the cartographic information exchange. It should be mentioned the collaboration among MIDES and municipalities where mayors have allocated resources for food and lodging for field operating staff. Also, the President of the Republic has submitted RSH outcomes to the Ministers Cabinet indicating to direct initiatives, projects, and programs at registered RSH municipalities. Likewise, given the Project outcomes, the Inter-American Development Bank has initiated talks with MIDES for the design of a loan transaction aimed at supporting Guatemala’s Government for the process scalability and program outcomes.
3.9 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words). | Teams from different UNS agencies have fostered dialogue and analysis spaces to assess regional learnings in the Social Housing Registry implementation, taking into consideration models from countries such as: Brazil, Colombia, Chile, Costa Rica. In the first quarter of 2022 an exchange was developed along with regional experts from UNDP, UNICEF, UNFPA, and CEPAL to be aware of challenges and opportunities, in addition to identifying the route map for scalability.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words). | One of the most important methodological challenges and adjustments in the RSH approach strategy is the cancellation of the municipality of Santa María Chiquimula. This was because such municipality had already an updated cartography as part of the pilot project and, in order to address other municipalities, coordination was conducted with the National Statistics Institute (INE) to use databases of the cartography corresponding to the 2018 Population and Housing Census. To this effect, methodological adjustments were made to the information system, as well as changes to the planning and field approach process, and a link of the outdated and practical cartography. This has created leanings to guide a scale model that enables validating how it works with updated cartography and with outdated one.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | UN agencies have supported the program implementation through: (i) specialized technical assistance; (ii) workshops, (iii) field visits, and (iv) technological tools. WFP has become part of the project as technical advisor and has also financed the project systematization. Mayors, through municipalities, have provided support for food, translation into local languages, and lodging for MIDES field teams. An interinstitutional progress that can be seen regarding resources management is that MIDES has also provided travel allowances to pollsters who travel outside their own department. In the first quarter of 2022, the Inter-American Development Bank (IADB) approved US$300 million for social protection measures to benefit most vulnerable populations in Guatemala, among which is the Social Housing Registry that is still in the design phase with the Guatemalan Government.

## Project Indicators
Please include ALL indicators in the project document. Include the indicators and Baseline, Planned Target and Actuals for both OUTCOME and OUTPUT levels. "Actuals" refer to the total figures achieved for each indicator. Include separate actuals for 2021 and for 2022 (if applicable). Explain if targets were not achieved. Include means of verification. Use as many outputs cells as needed to present all project indicators.
| INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | DATA: ACTUALS 2022 (if applicable) | TOTAL actuals (agreggated 2021 and 2022 if applicable ) | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] |  |  |  |  | Information gathering was finished in 7 priority municipalities. | Each municipality database disaggregated by gender variables
Indicator: | A Gender-sensitive Social Registry of Households pilot plan implemented in seven prioritized municipalities with higher incidences of poverty and extreme poverty and vulnerable populations, including women, indigenous women, women with disabilities, and female heads of household.
Baseline: | 0
Planned Target: | 1 | 0 | 1 | 1
Output 1.1 | A tool to characterize the socioeconomic conditions of households is implemented with a multidimensional approach that is sensitive to women's rights. |  |  |  | Socioeconomic assessment tool validated and approved by MIDES. Internal meetings at MIDES have been addressed to analyze the possibility to include beneficiaries through the use of the RSH tool in the future. | Tool validation document and Ministerial Resolution that allow the use of RSH FECS to include users for the Social Bonus.
Indicator 1.1.1: | Form designed and institutionalized for regular use in ministry.
Baseline: | no
Planned Target: | yes | yes | yes | yes
Indicator 1.1.2: | Population identified in the Household Registry, according to the characterization tool (households) |  |  |  | Largest municipality from initial proposal modified due to governance issues. In addition, homes with high permanent and work migration rates were identified in most municipalities. | Database with number of households identified as inhabitable and of temporary use.
Baseline: | 0
Planned Target: | 20000 | 5213 | 14426 | 19639
Output 1.2 | Consultation processes are carried out with women, indigenous women, women with disabilities, and women heads of household at all stages of the process to ensure their full involvement in the implementation of the SRH. |  |  |  | No disaggregated goal set for consultation purposes. The purpose of the project determines community consultations and territorial management to be conducted, mainly to build the tool and to know local needs before gathering information. | (i) Reports on community consultations for each municipality; (ii) Suggestions for changes to FECS; (iii) Meetings and focus groups with women and local organizations
Indicator 1.2.1: | Number of women, indigenous women, women with disabilities and women heads of households consulted, in all stages of Social Household Registry development.
Baseline: | 0
Planned Target: | TBD | 40 | 16 | 56
Indicator 1.2.2: | Number of consultations with women, indigenous women, women with disabilities, and women heads of households, in all stages of Social Household Registry development. |  |  |  | More consultations than those originally planned were conducted. | (i) Reports on community consultations for each municipality; (ii) Suggestions for changes to FECS; (iii) Meetings and focus groups with women and local organizations
Baseline: | 0
Planned Target: | 3 | 5 | 0 | 5
Output 1.3 onwards
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
Video 1:
https://drive.google.com/file/d/1tBumMkpRNV4QHLem0wL2AP97BEnEL4v7/view?usp=sharing
Video 2:
https://drive.google.com/file/d/1uEbjWGYzvBqaVsN0KP9FpNp2jYyvVlTG/view?usp=sharing
Life story 1:
https://drive.google.com/file/d/1R29GgXRmgICvIi2g3cp_zFJ6PuzjbgXE/view?usp=sharing
Photographs (credits: UNDP)
https://drive.google.com/drive/folders/1GPPmCX4DiKKZjsLxzsY8dNZtLH6m-Eqx?usp=sharing
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well as picture material please make sure you include all credits and share them in high resolution.
Links about the Joint Program:
https://www.undp.org/es/guatemala/blog/registro-social-de-hogares-en-guatemala-como-mecanismo-para-contribuir-la-reduccion-de-la-pobreza
https://www.mides.gob.gt/informan-avances-del-registro-social-de-hogares/
https://guatemala.gob.gt/inicio-ultimo-levantamiento-para-piloto-del-registro-social-de-hogares/
https://guatemala.gob.gt/registro-social-de-hogares-inicia-levantamiento-de-informacion-en-campo/
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board