## OVERALL REPORTING INSTRUCTIONS (hidden)
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | Revitalización de la Actividad Económica en Panamá a través de un Enfoque en los Sectores Productivos | Overall Duration (months) | 6
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2022-01-01
MPTF Office Project Reference Number: | MPTF_00209: UN COVID-19 MPTF | Original End Date (dd.mm.yyyy) | 30/06/2022
Country | Panamá | In case of NCE Current End date(dd.mm.yyyy)
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | FIDA, FAO, OIT, PNUD | National counterparts (government, private, NGOs & others) and other International Organizations | MIDA MInisterio de Desarrollo Agropecuario. MITRADEL, MInisterio de Trabajo y Desarrollo Laboral AMPYME Autoridad de la Micro Pequeña y Mediana Empresa MINSA Ministerio de Salud MEDUCA, Ministerio de Educación MiAmbiente Ministerio de Ambiente INADEH Instituto Nacional de Formación Profesional y Capacitación para el Desarrollo Humano IPACOOP - Instituto Panameño Autónomo Cooperativo CONADAF - Comite Nacional de Diálogo de la Agricultura Familiar
Report Cleared By
o Name: | Cristian Munduate
o Title: | Coordinadora Residente
o Email address: | amaya.perez@un.org (Team Leader) cristian.munduategarcia@un.org (RC up to August 31)
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Responses
1 | Executive Summary | During the COVID-19 pandemic crisis, Panama faced great challenges in economic matters, widening the inequality gap mainly in rural areas and the group of people with limited resources for agricultural activities and MSMEs. The measures implemented in the country did not immediately reach this sector of the population. The focus was on building the capacities of the country's most vulnerable indigenous and peasant population, providing techniques to support family agriculture with a particular focus on the needs of the area, respecting cultural aspects, and including aspects that facilitate marketing opportunities. The Socioeconomic Response Plan for COVID-19 showed that among the most affected groups were young people and women in the different areas of the country, but with greater impact in rural areas. As a contingency measure, through the tripartite dialogue table for the economy and labor development, some guidelines were defined so that the country's active forces would support the economic recovery processes. Outcome 3.1 sought to assist to improve productivity and promote women's leadership for entrepreneurship, enabling them to insert themselves into the productive and economic chain of their region and the country. It also became evident that micro, small and medium-sized enterprises (MSMEs) had been hard hit by the multidimensional crisis due to the collateral impacts. Opportunities to improve food security and promote participation in productive processes were strengthened through training in family garden techniques in the poorest regions of the country (Comarca Ngäbe Buglé, Emberá Wounaan, Naso Teribe), working directly with 750 families and indirectly impacting 5,000 people. To facilitate the financial inclusion and participation in productive processes of families engaged in family agriculture (FA), the joint program provided technical support to MIDA for the creation of the Special Fund for Family Agriculture (FONDAF) as a unique instrument in the country that will allow FAs to access financing to support agrifood systems. FONDAF has an initial capitalization of US$1,000,000.00, allocated from the General State Budget for the fiscal year 2022. In addition to technical assistance for the operationalization of FonDAF, technical and operational capacities (rural finance, fund management, public procurement, and digitalization of family farming) were also strengthened with MIDA, MEDUCA, IPACOOP, CONADAF, and family farming producers. As part of the support for the digitalization of agriculture, a Prospective Study on the Analysis of the Supply and Demand of Innovative Technology Solutions Applied to Finance and Agriculture was prepared, through which 13 StartUps related to FinTech and Agritech with potential for the Family Farming sector were identified, 3 of which shared their solutions and experiences. Important tools were developed that will enable better development of family farming activities, namely: Gender and Youth Diagnosis and Gender Mainstreaming Strategy. In support of school feeding programs, a guide was designed to guide public procurement processes with healthy and nutritious food using local family farming products, and an exchange trip was made to Guatemala and Costa Rica to share experiences and lessons learned. Another result of the project was the creation of business diagnostics and employment studies for four regions in the provinces of Chiriquí (Renacimiento, Boquete, tierras altas), Coclé (Penonomé), Azuero (Tonosí) and Panamá Oeste (La Chorrera). All these places correspond to Plan Colmena districts. These programs were developed in the areas of business administration, financing, gender equality, and MYPE. Seventy-nine business plans were designed and prepared. The capacities of the business sector were strengthened through training and self-diagnosis to measure labor performance, through the digital platform of the National Council of Private Enterprise. This training also included a guide on occupational health and safety training for agricultural employers. The training program included piloting in 6 companies in the agricultural sector, including Agriculture, Livestock, Aquaculture, Fishing, and Forestry. On the other hand, with the government and worker sectors, various training programs were developed to strengthen capacities in occupational safety and health. Interinstitutional committees were reorganized, and a qualitative study was conducted on the implementation of the registry of mixed committees and biosafety plans with an emphasis on agribusiness, which will enable better performance in the development of economic activity.
2 | Purpose | Given the structure of multidimensional poverty in Panama and the drivers of economic growth, this proposal focuses on two fundamental pillars for sustainable and inclusive economic reactivation: rural production and MSMEs. The proposal focused on three outcomes, with specific outputs in each of them, in line with SERP activity 3.1, which focuses on the sustainable reactivation of the economy, with special attention to rural production and MSMEs.
3 | Results: Outcome Level | The intervention had a dual purpose since many families during the pandemic suffered from a lack of access to income and food due to a lack of knowledge of techniques for the creation and cultivation of home gardens. It also facilitated the entry of 3,286 farmers into the SGAB so that they would have opportunities to be included in the public policies developed by the Ministry of Agricultural Development. One of the most significant contributions of the Joint Program has been the creation and operationalization of the Special Fund for Family Farming (a financial instrument contemplated in Law 127/2020 on Family Farming), which will allocate 50% of the resources to women. In support of the insertion of economic reactivation processes, the "business diagnosis" was implemented to identify the needs of 122 MYPES in the territories with the greatest needs, and technical capacities were strengthened to access better income-generating opportunities that can guarantee economic rights and good quality of life. To ensure the dynamization of businesses, a georeferencing process was created through which, using informative public murals in the districts, QR codes are provided to guide visitors so that they can learn about the different businesses offered by the region and determine their location in the district. In support of the different actors in the economic reactivation processes, employers' organizations were trained in occupational health and safety tools through the OSH training guide for agricultural employers, which was developed through the OSH portal of the National Council of Private Enterprise and a pilot program was implemented with 6 companies in the agricultural sector (agriculture, livestock, aquaculture, fishing, and forestry). In the government sector, the reorganization of the inter-institutional committees for occupational safety and health was achieved, as well as the implementation of the registry of the Mixed Committees and the Biosafety Plans. Eighty-seven percent of the direct beneficiaries of the Program are women and 94% of the interventions are in rural areas.
4 | Results: Output Level | Agricultural production and family farming benefit from the creation and operation of the Special Fund for the Development of Family Farming (FonDAF), a unique instrument in the country, which seeks to support access to financing for family farming activities. This fund starts with a seed capital of US$1 million. In addition, support was provided for the formulation of business plans and direct investment for 136 family farming producers. Opportunities for access to credit were generated, the capacities of 750 families in family farming processes were improved and 3,286 farmers were registered on the SIGAB platform; likewise, business and employment diagnoses were developed, benefiting 88 MYPIMES. The production and marketing chains were strengthened through the development of capacities in business management and markets, public procurement and its link with family farming, the promotion of strategic alliances with new partners, and the preparation of 79 business plans, with a gender focus and targeting young people. The economic recovery capacity of the partners was strengthened through the training of employers' and workers' organizations in occupational health and safety, with a focus on agribusiness activities, the reorganization of the Interinstitutional Committee on Occupational Health and Safety, and the Biosafety Plans. The company also strengthened its capacity to manage finance for MYPES led by women.
5 | Results: Gender | he participation of women was taken as a priority in the processes for strengthening family agriculture, being referents in the techniques of orchards and agricultural management. Actions focused on women heads of households, prioritizing interventions in women's organizations in the Naso Teribe, Ngäbe Buglé, and Emberá Wounaan indigenous communities, directly benefiting more than 200 women. These actions were achieved through key partners such as the Women's Institute and INADHE. In support of the productive chain, business diagnostics were conducted for MYPES led by 88 women and for the development of business plans through training, with the predominant participation of women. In Chorrera, 100% of the participants were women; in Tonosí, 90%; and in Penonomé, 50%. In the Chiriqui regions, female participation was also outstanding, with 71.4% in Renacimiento, 56% in Tierras Altas, and 50% in Boquete. Having strengthened their productive capacities and provided them with the tools to promote them as small and medium-sized entrepreneurs, 50% of the estimated funds of the Family Agriculture Development Fund for women have been made available, as well as direct investment support for the transformation and acceleration of businesses in which 75% of the beneficiaries of this direct support are women. The project completed the activities with a Gender Marker 2.
6 | Results: Direct Beneficiaries
7 | Results: Indirect Beneficiaries | Estimated indirect beneficiary:23,159
8 | Do not Harm | During the whole process of project implementation, the Principles of Free Prior, and informed consent were taken into account. The work plan and actions were developed in conjunction with the communities and key partners, respecting family work plans and incorporating the project's actions within the agricultural calendar, the targeting of interventions in MYPES, economic activities according to the size of the enterprises, and territorialization. The above contributes to the construction of public policies focused on family farming, self-entrepreneurship, and the generation of decent work.
9 | Results: Challenges/Difficulties Encountered and Measures Taken | In the process of capacity building, there were limitations of movement and health risks associated with COVID19 for the convening of consultation workshops in the field. Similarly, the lack of access to the territories due to natural phenomena affected the roadmap and forced us to reschedule interventions. In other cases, virtual sessions had to be set up for those who could not attend the training sessions in person. In terms of accompaniment, MSEs were identified that did not have basic resources for marketing their services or products, so the 79 beneficiaries were provided with marketing materials based on the needs of each MSE. The lack of prioritization by state institutions delayed the processes related to the creation of the Family Agriculture Fund and the implementation of parametric insurance. Approval at the executive decree level is still pending.
10 | Results: Qualitative Assessment and Learning
A notable contribution that has taken place during the implementation of the joint program has been the appropriation by local authorities of the expected results and objectives, generating not only spaces for co-creation and advocacy, but also the active participation of multiple stakeholders in rural and indigenous regions where opportunities for capacity building in family agriculture and business self-management, with a special focus on women and youth and taking as a priority the specific needs of the area, were not regularly provided. The dynamism shown by institutions that were incorporated during the implementation process, such as the National Women's Institute (INAMU) and the National Institute of Vocational Training and Training for Human Development (INADEH), has allowed the capacity-building dynamics imparted in the Joint Program to be incorporated into the general scheme of both institutions, generating a contribution to the management of inter-institutional synergies in remote regions of the country. The Joint Program facilitated an equitable design to reduce the inequality of opportunity gap, granting 50% of the fund's resources to be allocated to women.
11 | Results: Partnerships | In terms of the partnership, the SNU achieved active participation of government institutions in the regions and local governments, as well as the empowerment and leadership of central authorities in agricultural, labor, and microenterprise issues, and the private sector through the National Council of Private Enterprises, who not only adopted the results as their own but also opened spaces for association with emerging partners (INAMU-INADEH) to whom guidance was provided to facilitate inter-institutional exchange and strengthening in the areas of the indigenous comarcas.
Through the implementation of the joint program, important spaces for dialogue and technical analysis were developed between the main labor partners, where reflection between workers and employers led to important findings for the improvement of processes in the technical health committees and the facilitation of inspection and improvement processes in agribusinesses. This exercise was the first post-pandemic experience, since the country had not been able to bring the parties together to address these issues. In the context of financial instruments, the Joint Program succeeded in creating and launching the Family Agriculture Development Fund, which enabled coordination with other initiatives of international financial organizations and entities: the Alliance for Development in Democracy, the Rural Youth Strategy approved by SICA, the IDB's Sustainable and Inclusive Agricultural Innovation Program, the Panamanian Cooperative Institute, and the Agricultural Insurance Institute. Start-Ups were identified in FinTech and AgTech with operations in Panama and technologies applicable to family agriculture, which may be included in the National Financial Education Strategy, led by the Superintendency of Banks of Panama, including the participation of German Sparkassenstiftung and the Innovatec Project. The coordination with FAO to carry out actions with family farming organizations and organize a joint IFAD/FAO event on coffee and cocoa exports with the participation of FAs made it possible to coordinate efforts to achieve greater results. The experience-sharing tour to Costa Rica and Guatemala on public procurement models for family farming, in which officials from MIDA, MEDUCA, and IPACOOP participated, made it possible to identify concrete opportunities for strengthening the implementation of the Study Without Hunger Program.
12 | Other Assessments or Evaluations (if applicable) | With reference to instruments and assessments generated from the Joint Program, the following instruments were generated, - A gender and youth diagnosis was carried out, as well as the gender mainstreaming strategy in the projects that will allow visualizing the gender and youth situation in two districts of the region. - Prospective Study on the Analysis of the Demand for Innovative Solutions for Technologies Applied to Finance and Agriculture. - Report on the Exchange of Experiences between Panama, Costa Rica and Guatemala on linking Family Agriculture with the Public Procurement System and School Feeding Programs. - Draft of the FONDAF Operating Manual. Compilation, Review and Systematization of the Experience of the Ministry of Labor and Labor Development on the - Labor and Labor Development, on the Adoption of Occupational Health and Safety Measures during the COVID-19 pandemic".
13 | Programmatic Revisions (if applicable) | Two budget adjustments were made that did not result in adjustments to the strategy, objectives, outputs, and results. In the first case, resources were mobilized from the following budget lines: (i) Personnel and others, Supplies, (ii) Commodities and materials Equipment, and (iii) Vehicles and Furniture. Budgetary mobility was of the order of US$35,903.39 and was carried out by the ILO. In the case of IFAD and based on the adjustment in the planning of activities due to delays in the signing of the Executive Decree creating FONDAF, IFAD made a budget modification, allocating US$5,000 to the Equipment item to provide direct investment support to family farmers, with emphasis on associations with female leadership. In both cases, the adjustments were less than US$50,000.00.
14 | Resources (Optional)

## Project Indicators
| INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | DATA: ACTUALS 2022 (if applicable) | TOTAL actuals (agreggated 2021 and 2022 if applicable ) | Reasons for Variance with Planned Target (if any) | Source of Verification | Other Comments
Outcome 1[1] | Outcome 1. Agricultural production and family farming improved through technical assistance. |  |  |  | The process of signing the Executive Decree creating FonDAF was delayed at the Ministry of Agricultural Development and the Ministry of the Presidency. Due to the delay in the approval of the legal instruments for the effective creation of FonDAF, FONDAF's field consultation activities were rescheduled and included support for capacity building and direct investments in family producer organizations (5 organizations, 4 of which are women-led). | _ Executive Decree creating FonDAF - FONDAF Operating Manual and associated management manuals. - Photographic and documentary material (agenda, list of participants, etc.) of training sessions, workshops and events. | Technical and legal design of the Special Fund for the Development of Family Agriculture (FonDAF) through the Executive Decree and draft Cabinet Resolution creating the Trust Fund for its implementation. - Design of the FonDAF Operating Manual, establishing that at least 50% of the funds will be earmarked for women, and 50% in support of agri-food systems. - Mobilization of resources to capitalize FonDAF (US$1,000,000 from the General State Budget for the fiscal year 2022). - Technical assistance and training sessions on access to financing, management of FONDAF, and preparation of business plans for the National Rural Development Directorate of MIDA (the governing body in charge of FONDAF) and family farmers' organizations. Communication launching of FONDAF: - Public event for the signing of the Executive Decree creating FONDAF by the Minister of Agricultural Development, Mr. Augusto Valderrama, before the press. - Workshop to present the launch of FONDAF to the National Committee for Dialogue on Family Farming (CONADAF). | IFAD
Output 1.1 | Output 1.1 Special Fund for the Development of Family Farming launched, and rural microfinance promoted
Indicator 1.1.1: | Numbers of activities to develop and promote the Special Fund for Family Farming. |  | 4 | 4
Baseline:
Planned Target: | 4 (The design of the Special Fund for the Development of Family Farming ensures that at least 50% of the loans are granted to women. •The design of the Special Fund for the Development of Family Farming ensures that at least 50% of the requested credits are for investment projects in agri-food systems. •Technical support for development of the Government’s; Communication Strategy on the launch of the Special Fund for the Development of Family Farming |  | 4 | 4
Output 1.2 | Digitalization of agriculture and MSMEs enhanced .
Indicator 1.2.1: | Number of technical assitance and technology transfer to enhance digitalization of agricultural production and family farming. |  | 4 | 4 | Some challenges were identified that impacted the scope of the results. There is a need to further encourage young people as promoters of digitalization and new agricultural practices, to deepen the work with women in the organizations and their leadership, and to take advantage of the approaches in the private sector. Due to capacity limitations (technical and infrastructure), the platform design had to be reformulated in terms of digitization as well as several FinTech and AgTec needs MIDA institutional processes (registration, certifications, etc.), service delivery (extension, access to finance, traceability, etc.), connectivity limitations and use of mobile devices in rural areas. The Prospective Study will be very useful to define the next steps in terms of digitalization and connection of FinTech and AgTecn startups with Family Farming organizations. | Preliminary Study on the Analysis of the Supply and Demand of Innovative Technologies for Finance and Agriculture. Photographic and documentary material of the workshop on Capacity Building for Rural Finance (Simulator), virtual workshop to Raise Awareness of Family Farming Producers on Innovative Technologies for the Digitalization of Agriculture and presentation workshop of the study with the participation of Startup FinTech and AgTech. | 4 (3 trainings, 1 study) Preparation of the Prospective Study on the Analysis of Supply and Demand for Innovative Technology Solutions Applied to Finance and Agriculture. Workshop to present the results of the study on the analysis of the demand for innovative technology solutions applied to finance and agriculture, through which 13 StartUps related to FinTech and Agritech with potential for the AF sector were identified, 3 of which shared their solutions and experiences. Virtual workshop to raise awareness and train Family Farming Producers on digitalization and access to innovative technologies (FinTech and AgTech). 24 participants, 58% of whom were women. Face-to-face training workshop on digitization and analysis of the demand for innovative solutions with family farming organizations and officials of the National Directorate of Rural Development of MIDA: through which the needs of family farmers in terms of technology were identified. There were a total of 36 participants and 50% were women.
Baseline: |  |  | 0
Planned Target: | 4 (2 trainings, 1 platform, 1 study) - 2 Training in digitalization of agricultural developed and conducted. 50% women. - 1 platforms designed and implemented. - 1 Prospective study of the agricultural sector developed. |  | 4 | 4
Output 1.3 | MSMEs strengthened through technical assistance | [6 empty] | UNDP
Indicator 1.3.1 | Number of initiatives implemented to improve productivity and working conditions in MSMEs led by women. |  |  |  | The intervention was expanded and four participatory business diagnostics and employment studies were carried out for the four regions of Chiriquí (renacimiento, boquete, tierras altas), Coclé (penonomé), Azuero (Tonosí), and Panamá Oeste (La Chorrera). Training program in the areas of business administration, financing, preparation of 79 business plans, technology consulting, and workshops on gender equality and MSEs. | Business diagnostic instrument and employment studies for the four regions of Chiriquí (renacimiento, boquete, tierras altas), Coclé (penonomé), Azuero (Tonosí), Panamá Oeste (La Chorrera). Training program in the areas of business administration, financing, preparation of 79 business plans, technology consulting, and workshops on gender equality and MSEs. | 4 diagnostics 1 Training Program with 79 companies.
Baseline: |  |  | 0
Planned Target: | • 2 participatory diagnosis and employment studies with proposals. • 1 training program for 50 MSMEs implemented |  | 3 | 4
Output 1.4 | Agricultural production improved through technical assistance and support. | [5 empty] | 750 families have been trained directly, benefiting more than 5,000 indirectly. 3,286 farmers in the SIGAB platform (90% of the goal). A diagnosis was carried out to identify the barriers for women and young people to joining the economic life of the region. More than 40 technicians from the different ministries were trained in public procurement issues and a document was prepared on linking family farming to public procurement processes. | FAO
Indicator 1.4.1 | Number of technical assistance provided and knowledge products produced to improve agricultural production. |  | 4 | 4
Baseline: | 0
Planned Target: | • 12,500 rural and indigenous family farmers will have improved productivity, sustainability and resilience of their agri-food systems; • At least 30% of family farmers have registered with SIGAP. • Analysis of the situation of socioeconomic exclusion of 3 items with commercial value in the communities served. • 15 members of the local technical staff implement the plan to strengthen agri-food systems. |  | 4 | 4 (partially achieved) | Difficulties of access to the area forced us to reduce the number of families per community we had planned to reach. In the 30 communities identified, a priority training plan was established with the community according to the needs identified. Although the scope of what was planned was less, the training plan that was developed was more complete and in accordance with the requirements. | List of participants of the 2 days of exchange of experiences of PAE programs in the LAC. List of participants of the Field Schools (ECAs)SIGAP report of registered farmers. Diagnosis of the barriers to the economic exclusion of indigenous women and youth. Diagrammed document on linking PA to public procurement processes.
Outcome 2. Production chains, marketing and productive social inclusion strengthened.
Output 2.1 | Food markets from Family Farming and MSMEs strengthened
Indicator 2.1.1. | Proportion of the intersectoral and interinstitutional work agenda implemented in selected Colmena townships. |  | 30%
Baseline: |  | 0
Planned Target: | • 30% implementation of intersectoral and interinstitutional work agenda. • Management model defined and approved by COLMENA townships. • 30% of EAP suppliers are small-scale producers or family farmers. • At least 70% of the suppliers are small-scale producers or family farmers. • At least 30% of the actors identified within the COLMENA townships have been trained. • 70% of family farmers, small producers and MSMEs participate in the training sessions. • At least 30% of the identified actors within the COLMENA townships have been trained. |  | 30% | 30% | Four farmers' organizations were strengthened in the areas of business management and markets, benefiting 160 members directly and more than 1,120 indirectly. | Diagnóstico y caracterización de los dos distritos Colmena, planes de capacitación a 30 comunidades. Plan de capacitación para la gestión comercial en apoyo a las organizaciones. Documento para el acompañamiento técnico y fortalecimiento de capacidades a los productores | 100% beehive districts. 90% (3,286) of registered family farmers who could be potential suppliers . 4 organizations of mixed farmers and women were strengthened through 3 workshops on business management and markets, benefiting 160 associates directly and more than 1,120 indirectly. The goal was met 100% are Family Farmers and were trained in Field Schools in productive and organizational aspects. | FAO
Output 2.2 Rural Youth and Women doing development enjoy improved skills, employment prospects and access to finance. PNUD | [7 empty] | UNDP
Indicator 2.2.1. | Number of nitiatives are implemented for capacity building and strengthening access to microcredit focused on youth and women. |  |  |  | Strategic alliances with local governments of the 4 regions Chiriquí (renacimiento, boquete, tierras altas), Coclé (penonomé), Azuero (Tonosí), Panamá Oeste (La Chorrera), acadamias (Universidad de Panamá), AMPYME and INADEH. | Calls and attendance list for training workshops in conjunction with the local governments of the four regions of Chiriquí (renacimiento, boquete, tierras altas), Coclé (penonomé), Azuero (Tonosí), Panamá Oeste (La Chorrera), acadamias (Universidad de Panamá), AMPYME and INADEH. | Of the business plans developed between the ages of 18 to 29 years, a total of 20 beneficiaries, representing 25.31% of the total number of beneficiaries, broken down as follows: Chorrera (Panama Oeste) 19 in total, of which will have an impact between the ages of 20-35 years (M:2). Coclé (Penonomé) 10 in total, ages 20-35 years (M:2- H:2); Azuero (Tonosí) 10 in total, ages 20-35 years (M:3- H:1); Chiriqui (Renacimiento) 21 total, ages 20-35 years (M:7- H:0); Chiriqui (Boquete) 10 total, ages 20-35 years (M:7- H:0) Chiriqui(Boquete) 10 total, ages 20-35 years (M:0- H:3); Indigenous groups: Rregion Chiriqui and La Chorrera 3 indigenous people of which 2 were women and 1 man, group originating from Guna Yala. Business diagnosis was applied to MYPES led by 88 women. The total number of MSEs led by women in each region was 100% in Chorrera, 90% in Tonosí and 50% in Penonomé. In the Chiriqui regions, female participation was also predominant, with 71.4% in Renacimiento, 56% in Tierras Altas and 50% in Boquete.
Baseline: |  | 0
Planned Target: | •At least 25% of the loans granted are requested by young people (between 18 and 29 years old); • At least 5 indigenous rural youth enterprises are operating; •The private sector hires rural youth within the framework of characterizing the labor demand; •At least 30% of the boards of directors of women's organizations renewed and with their legal status updated.
Outuput 3.1 Training and information packages for companies, social partners and relevant organizations and institutions (municipalities and the Authority of Micro, Small and Medium-sized companies [AMPYME]) developed and rolled out. | [7 empty] | ILO
Indicator 3.1.1. | Training and information packages developed. |  | 3 |  | Se completaron 12 procesos de capacitación para el fortalecimiento de capacidades de las partes interesadas. | Platform: OSH self-diagnosis tool for employers (https://sst.conep.org.pa/inicio/); Training module on occupational health and safety and control of Covid-19, with emphasis on agribusiness, for the Labor Inspection in Panama; PPT's prepared for the training process + Training reports + photographic records + press releases. Training PPTs for union delegates + Press releases. | 230 union representatives trained 115 trained CONATO delegates 115 trained CONUSI delegates
Baseline: |  | 0
Planned Target: | •Study on the institutional structure on Occupational Safety and Health (OSH), its legislation and determining the role of the trade unions at national, sectoral and enterprise level providing recommendations for tripartite and bipartite trade union action. •40 representatives of trade unions trained as trainers with a special focus on (i) the agricultural sector; (ii) OSH management and strengthening internal structures on OSH Committees participation at sectorial and enterprise levels; and (iii) OSH policy-making at national and sectorial levels in accordance with International Labour Standards. •500 delegates from trade unions CONATO and CONUSI trained at national level |  | 3 | 3
Indicator 3.1.2 | Implementation of two work packages on the Supplier Development Program: "Starting with your business", "Growing with your business" and in "Marcha Digital" |  | 2 |  | A process was developed for a methodology to accompany the implementation of the EN MARCHA Program with the National Institute of Vocational Training and Training for Human Development (INADEH) and thus create a link between INADEH, as a strategic ally, and the En Marcha - ODS Value Chains program. This process is expected to be implemented in the four regions where the Economic Revitalization project was developed, where participating MSMEs in the agricultural and handicraft sector will be able to benefit from INADEH's training and education programs in economic activities". | Accompanying methodology document for the implementation of the EN MARCHA Program with the National Institute of Vocational Training and Training for Human Development (INADEH). Training program in the areas of business administration, financing, business plan development, technology consulting, workshops on gender equality and MSEs. | Design and implementation of 1 training program in the areas of business administration, financing, preparation of 79 business plans, technology consulting, gender equality workshops, and MSEs. | UNPD
Baseline: |  | 0 |  |  |  |  | Design of accompaniment methodology for the implementation of the EN MARCHA Program with the National Institute of Vocational Training and Training for Human Development (INADEH) with the En Marcha - ODS Value Chains program.
Planned Target: | At least 2,500 companies led by women, a 30% of the efforts will focus on sectors where entrepreneurship is predominantly female |  | 2 | 2
Output 3.2 Training and information packages for companies, social partners and relevant organizations and institutions (municipalities and the Authority of Micro, Small and Medium-sized companies [AMPYME]) developed and rolled out. | [7 empty] | ILO
Indicator 3.2.1. | Number of initiatives to strengthen MITRADEL's occupational health and safety committees |  | 3 |  | There was no variation. | A document that compiles, reviews, and systematizes the Experience of the Ministry of Labor and Labor Development, on the Adoption of Measures on Health and Safety at Work, during the pandemic of COVID-19" in Panama | Three initiatives to strengthen MITRADEL's occupational health and safety committees
Baseline: |  | 0
Planned Target: | Three initiatives to strengthen MITRADEL's occupational health and safety committees |  | 3 | 3

## Communication (hidden)
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well as picture material please make sure you include all credits and share them in high resolution.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board