## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | Promoting Innovative Service Provision Models to Support the COVID-19 Health System Response | Overall Duration (months) | 16
Programme Number (if applicable) | N/A | Start Date (dd.mm.yyyy) | 12.02.2021
MPTF Office Project Reference Number: | 125919 | Original End Date (dd.mm.yyyy) | 01.12.2021
Country | Turkey | In case of NCE Current End date(dd.mm.yyyy) | 2022-06-30
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNFPA WHO | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Health (DG of Public Health, DG of Health Information Systems, District Health Directorates in Ankara, Konya and Samsun) WHO UNHCR
Report Cleared By
o Name: | Alvaro Rodriguez
o Title: | Resident Coordinator
o Email address: | alvaro.rodriguez@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | The project effectively began as of February 12th, 2021 with the release of funds. Under Result 1; UNFPA Turkey CO immediately started to complete necessary procedures for recruitment of the project team as well as procuring necessary equipment and materials. Such processes consisted of drafting ToRs, vacancy announcements (for a programme manager, project associate, field associates, nurses, and translators), interviews, pre-service trainings (orientation), preparing ToRs for medical equipment, personal and protective equipment, acquiring no objection letters from Ministry of Health of Turkey and WHO as well as taking necessary steps to ensure that communication and visibility materials were ready before project activities started.With the finalization of such processes, six MHUs (three units for each province) started to effectively work in Ankara and Konya as of May 27th, 2021. As the need arises in the field and upon the request of the Ministry of Health, the project team has mobilized 4 more units to the field (2 for Ankara and 2 for Konya) in September. All units provided uninterrupted access to essential health services in the field of COVID-19 pandemic as well as sexual and reproductive health and gender-based violence counselling (where needed). As a result, MHUs have provided service to 61165 people by the end of June 2022 (See Annex for the breakdown). Within the framework of service provision, 12888 people have been vaccinated by our units against COVID-19 . Within the framework of Result 2; Meetings were held with the Ministry of Health, the General Directorate of Public Health, and the General Directorate of Health Information Systems. By enabling these two different general directorates to work together, the technical infrastructure of the Tele-health system was prepared together with WHO CO Turkiye, and related Ministry units. Research was carried out regarding a practice that did not exist in Turkey before, other country samples, implementations, and regulations on telehealth were researched and consultants were determined. Agreements were prepared, a draft legal regulation document was prepared at the meetings held in cooperation with the Ministry of Health, Consultants and WHO CO. The final report on the necessary legislations was shared with the Ministry of Health. The contents of the technical videos for patients, healthcare professionals, and physicians to use the system were completed in collaboration with healthcare information systems, consultant companies, and WHO CO. Training videos on diseases to be served in the telehealth system were developed by the different departments of the Ministry, and their contents were developed in the most understandable, and simple. For Result 3; Standard Operation Procedure (SOP) was developed in an inclusive approach through which all team’s (including field associates and MHU staff) views and opinions were reflected on the document. The document which was sent to the Ministry for approval covers several critical issues such as the provision of preventive health services that are integrated to filiation; identification of risk groups and improvement of their access to healthcare; and promoting public health literacy. Field associates and MHU staff were trained on the SOPs during August 2021. MHUs are regularly raising awareness on Covid-19 related prevention measures as well as sexual and reproductive health during their service provision through brochures and short informational sessions. Field associates are holding regular meetings with local governmental organizations in Ankara and Konya to ensure efficient provision of MHU services as well as risk communication. They are also in touch with certain NGOs including the Turkish Red Crescent, which are specifically providing services to refugees, to develop specific cooperation modalities to use MHUs in local refugee contexts. Last but not least, two videos have been produced in late December. Whereas one video on a macro level promotes the project's outcomes so far, the other is about a human interest story which was published on UNFPA's website. As of late March, the project is extended with an additional funding of $110000 until the end of June 2022.
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | The purpose of the project is to promote innovative service provision models that would facilitate uninterrupted access to essential health services among vulnerable groups while supporting the health system response to Covid-19 in Turkey. These innovative models are (i) deploying mobile health units in the field and (ii) piloting telemedicine in primary health facilities as well as (iii) enhanced risk communication. In this sense, the project aims at improving access to healthcare services delivery related to Covid-19 and also other essential needs, such as routine maternal and child health services like vaccination and antenatal/postnatal care; prevention and treatment of non-communicable diseases (NCDs). This was achieved through promotion of innovative service provision models which are scaling mobile health units up for Covid-19 response and piloting telemedicine in primary health facilities, along with improving risk communication in the field for the most vulnerable groups.
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | With service provision by 10 MHUs in two provinces under Result 1, there is a significant increase in access to immediate health and socio-economic support to respond to the health and social impact of the COVID-19 pandemic (See Annex-1). Thanks to the project team's adaptation efforts, the project target group did not only have access to COVID filiation services but also to vaccination and SRH/GBV-related services including family planning. Under Result 2, the first legal document on the provision of telehealth services has been published. The telehealth appointment system is planned to be opened all over Turkey. An application that will facilitate and increase access to health services. In Result 3, on the other hand, 23514 people have been reached out in terms of improving the risk communication related to COVID-19 pandemic among project target group.
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | Result 1 1- Project team (Programme Manager, Project Associate, and 2 Field Associates) was recruited (ToR drafting, vacancy announcement, interviews). 2- MHU staff (10 nurses, 10 translators, 10 drivers) was recruited (vacancy announcement, interviews) and 10 vehicles were procured. 3- Medical Equipment and PPEs were procured (ToR drafting, announcement, no objection letters by Ministry of Health and WHO). 4- Communication, visibility and accountability materials were developed, and procured. 5- Preparations regarding logistics, distribution, and storage of relevant equipment and materials were completed. 6- Coordination meetings with the Ministry of Health and District Health Directorates were held to integrate MHUs into the existing system. 7- Orientation and pre-service trainings for MHUs were organized between May 24th and 25th, 2021. 8- MHUs have become operational on May 21th, 2021 for Ankara and on May 27th, 2021 for Konya. 9- 5 in-service trainings were organised. Firstly, a project orientation training of 2 days was organised for the nurses, interpreters, and drivers. Later on, trainings on Prevention of Sexual Exploitation and Abuse (PSEA) and Gender-based Violence Awareness (GBV), COVID-19 Pandemic's effect on women and reproductive health services, COVID-19 Vaccination on public and reproductive health perspectives, Standard Operating Procedures (SOP) and Reproductive Health Awareness Training have conducted for MHU staff. Moreover, 6 nurses of MHUS participated in face-to-face reproductive health counseling trainings. 10- MHUs provided service to 61165 people by the end of the project. Within the framework of service provision, 12888 people have been vaccinated against COVID-19 by our units (See Annex-1 for further details). 11- 8 out of 10 MHUs have been mobilized to specifically follow-up pregnant women to raise their awareness on preventive and protective measures against COVID-19 (including vaccination) as well as on SRH and GBV related issues (including family planning, reproductive health, safe motherhood, etc.) 12- In this respect, MHUs have made over 11312 phone interviews and paid 4327 house visits and thereby reached out to 8279 pregnant women and peuperants. 1164 of them were vaccinated against COVID-19 by the units. 13- MHU nurses have provided 439 trainings to 2654 pregnant women and puerperants on safe motherhood, family planning, ante and post natal care along with GBV related issues. 14-A training was delivered by Prof. Dr. Zeynep Şimşek about outraching activities for MHU teams. MHU team members attended to the training on 23 May 2022 via online channels. 15-MHU teams supported the outreach activities of Migrant health Centers in Ankara for the Syrian groups who were under the threat of COVID-19 by May 2022. Konya MHU teams supported agricultural migrant workers since May 2022. 16-A closing ceremony was organized in Afyonkarahisar province on 16 June 2022 with the participation of 80 people from Provincial Directorates of Health in Ankara and Konya, MoH, governmental organisations like TÜİK, PDMM, CSOs from Ankara and Konya, WHO, UNHCR and UNFPA members and members of MHU teams in Ankara and Konya. The agenda of the Closing was composed of opening speeches, veido screening, presentation of project's outcomes by UNFPA and WHO, presentation of SOP, outcomes presented by Ankara and Konya Provincial health Directorates and presentations from MHUs. The need for the continuation of COVID-19 MHUs in the future periods were declared by the official of MoH and Provincial Directorates of Ankara and Konya in several times. Result 2 1- Draft legal regulations regarding the usage of telemedicine, and informational documents were prepared. 2- Draft patient consent forms were prepared. 3-Preliminary work has begun for the necessary software and to the integration of this software into the information systems of the Ministry of Health 4- The contents and properties of the video and training materials on the usage of telemedicine were identified. (For doctors, nurses/midwives working at the Family Health Centres, Healthy Life Centres, Refugee Health Centres and Beneficiary Population). 5- Two consultants were recruited on legal regulations. 6- Procurement processes for the preparation of training videos to be prepared for patients, doctors, and healthcare professionals have been completed. Result 3 1- SOP was developed and sent to the Ministry for approval. SOP training for MHUs and field associates was conducted during August 2021. 2- Field Associates held regular meetings with certain NGOs (working with refugee populations) to discuss possible cooperation opportunities to be seized in local refugee contexts. 3- Awareness-raising materials such as brochures on different themes (COVID-19 protection, COVID-19 and pregnancy hand washing, etc) were distributed to 32500 people within the framework of mobile service provision. 4- 31893 people have been reached out in terms of risk communication by the end of project. 5- One project video and one human interest story video have been produced. Both videos were published in UNFPA's website and distrubuted through social media channels of UNFPA and UNHCR. The Closing of the Project News were published in UNFPA website. 6- With the assistance of UNHCR, the target group (particularly migrants and refugees) has been regularly informed through online platforms (Twitter and Whatsapp trees) regarding the location of mobile vaccination clinics. In this sense, 25 links (messages) have been shared to different groups and the number of the total clicks is 8,8,27. 7-On UNHCR Help website, COVID-19 vaccine page received 302,110 page views and the COVID-19 general information page received 697,123 page views. 8- On UNHCR Turkey Information Board Facebook page, above 25 posts related to COVID-19 pandemic were published in Arabic and Farsi. 9- 10.000 brochures, 1200 posters and, 150.000 consent forms (50.000 in Arabic, 50.000 in English and 50.000 in Turkish) related to COVID-19 vaccination have been drafted, produced, and distributed. Moreover, 5000 brochures on COVID-19 and pregnancy were produced, printed and distributed.
3.2 | Results: Gender | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | Under Result 1, 16989 females (%53,57) and 14727 males (%46,43) have received mobile health services from units. Women received 38040 services by the end of 2021 and among them, 39 percent is COVID filiation, 22 percent is COVID and other vaccinations and 11 percent are SRH counselling services. Among 16989 women, 6028 of them received SRH services which means that more than one-third of all women who were reached out have received SRH services in addition to COVID-related services. This has been particularly due to the adaptation efforts performed by the project staff which led to the mobilization of MHUs from COVID Filiation to pregnant women and new mother monitoring (see Output Level Results, Result 1 - Bullet 12). Men, on the other hand, received 27768 services from our units. The distribution of services is 28 percent is COVID filiation, 11 percent is COVID and other vaccinations and 1,5 percent are SRH counselling services. Under Result 2, approximately 80% of the health workers who have attended the trainings so far are women. After the trainings are completed, the exact numbers and rates will be given. Especially female healthcare professionals stated that they would feel safer with Tele-health service delivery instead of physical contact with the patient.
3.3 | Results: Direct Beneficiaries | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | Under Result 1; # of Total Beneficiaries: 61165 # of Female Beneficiaries: 34753 # of Male Beneficiaries: 26412 # of Beneficiaries Below 15 Years Old: 6391 # of Beneficiaries Betwen 15-49 Age Group: 42336 # of Beneficiaries Betwen 50-65 Age Group: 5105 # of Beneficiaries Betwen Above 65: 7333 # of Beneficiaries Living with a Disability: 4333 # of Beneficiaries in Ankara: 23699 # of Beneficiaries in Konya: 37466 # of Beneficiaries Living in Rural: 2614 # of Beneficiaries Living in Urban: 58551 Under Result 2; N/A
3.4 | Results: Indirect Beneficiaries | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | Estimated Total Under Result 1: 112146 Assumptions: 1. A person who received a filiation service would protect the entire household. (Average number of houselholds for Local Communities in Ankara: 3.02) 3.02*15920= 48078 (Average number of houselholds for Local Communities in Konya: 3.38) 3,38*19340=65369 (Average number of houselholds for Refugees and Migrants: 6) 6*25905=155430 Ref: TURKSTAT and Turkey Population and Health Survey 2018 2. Based on the r coefficient in Turkey, a person who is vaccinated would protect 1,56 people. 12888*1,56=20105 Ref: Ministry of Health in Turkey 3. Any kind of service which is provided to every pregnant women would also protect their unborn babies. 8279*2=16558 Under Result 2; N/A
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words) | The SOP produced under Result 1 extensively covers Do No Harm principles and as other principles in the document, it must be followed by all MHUs. During the SOP training held in August 2021, all project staff was particularly informed by the specifics of Do No Harm approach. Furthermore, MHUs also received several trainings (Prevention of Sexual Exploitation and Abuse (PSEA) and Gender-based Violence Awareness (GBV), COVID-19 Pandemic's effect on women and reproductive health services, COVID-19 Vaccination on public and reproductive health perspectives) , principles of outreaching during COVID-19 prevention and protection works in the field, all of which to certain extent address the Do No Harm principles. On the other hand, for accountability purposes, all units distributes pamphlets which indicate communication channels to file complaints regarding any kind of MHU services in case any kind of issue arises to this end.
3.6 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | Under Result 1, several challenges have been faced and addressed accordingly. One of them was about staff turnover. In Konya province, one of the nurses quit, and the one who was hired instead also left after a couple of days. Following this experience, the team was extra careful during the recruitment process and took additional measures to ensure that nothing similar was to happen. As a result, the newly hired nurse has been providing service in the field for a month without any problem. A second challenge was about some minor difficulties experienced by MHU staff in terms of providing health services in addition to the ones that are related to COVID-19 (where needed) in the presence of COVID positive individuals. Nonetheless, as the SOP was finalized and the relevant training programme was conducted, this problem was solved in a smooth manner. Furthermore, district health directorates requested additional MHUs to be mobilized under the project due to the emerging need in the field and therefore the project team recruited 4 new units and mobilized them in the field as of October 2021. Last but not least, the constantly changing nature of the pandemic has presented a very profound challenge for the team. As each surge needed different approaches, the project team adapted the service provision types and methods to better address the needs of project target groups. Details are explained in the "Programmatic Revisions" section. For Result 2, family physicians generally have a resistance to new projects developed by the Ministry of Health. It was estimated as a risk they might think this project would increase their workload. It has been emphasized in the training videos, and trainings prepared according to reduce these worries and explained this telehealth services will facilitate the service delivery of health personnel. Good feedback was received in the trainings at the end. It was foreseen that without a legal infrastructure, family physicians would not want to use the telehealth service. For this reason, a couple of meeting was held with the Ministry of Health for the official publication of the legislation on the provision of Tele-health services. The process accelerated and the circular was published on February 10, 2022.
3.7 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words) | An important challenge that might be considered as an operational lesson and significant finding was about different modus operandi of MHUs that is embraced by the different district health directorates. To ensure convergence among different service provision modalities used by MHUs, the field associates were in close communication with the authorities to ensure uniformity among MHUs service provision models. The modus operandi for all MHUs is currently, to a large extent, the same. In addition, during the service provision process, the project team as well as MHU staff have concluded that having a medical doctor in each MHU would be highly beneficial, especially in terms of efficiency. The project team, field associates particularly, has been in close contact with district health directorates to this end. In a nutshell, as different districts might have different priorities and requirements, the project team strongly believes that ensuring uniformity among MHU services is critical. To achieve that the team (particularly field associates) has been following up on the situation in the field by maintaining close communication both with MHUs and district directors and proposing corrective actions where necessary.
3.8 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | The project is being executed in close partnership with the Ministry of Health, district health directorates, WHO, and UNHCR. It is safe to say that the communication and cooperation capacity with the Ministry of Health, DG of Public Health, DG of Health Information Systems, and district directorates are improving. The Ministry and district directorates are particularly pleased with the contribution of MHUs to pandemic-related health services (including Covid- 19 prevention, surveillance, detection, filiation, and referral) and therefore asked for additional MHUs to be mobilized. In addition, draft legal documents were prepared for the telehealth infrastructure to be established within the Ministry. These documents are of vital importance for such services, which are planned to be extended to all provinces in the future. With the partnership built under the project, all stakeholders witness the convenience of the services provided to people with chronic diseases and vulnerable groups. For instance, it will help to reach the goals of the 3 billion people targeted by the World Health Organization at the global level. (One billion more people are benefiting from universal health coverage, One billion more people are better protected from health emergencies, one billion more people are enjoying better health and well-being) The project also facilitated cooperation among UNFPA, WHO, and UNHCR by providing all sides the opportunity to closely examine and (where available) contribute to the work done by others. Agencies gather every month to discuss project's progress and coordination-related issues along with how to benefit from others' efforts or effectively execute joint activities. One concrete example to that end would be UNHCR's assistance to UNFPA in terms of extending UNFPA's risk communication endeavors (not only about COVID-19 pandemic but also sexual and reproductive health) to the refugee population in Turkey by using UNHCR's existing mechanisms and channels.
3.9 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words). | Tele-health services, which have not been provided in public health institutions in Turkey so far, will begin to be implemented in public institutions on February 10, 2022, with the "REGULATION ON THE PROVISION OF REMOTE HEALTH SERVICES". This is a very important step to start telehealth services in Turkey. In the pilot implementation of our project, it will start to be implemented in 3 provinces. Many Turkish citizens and Syrian immigrants who cannot access health services due to physical reasons will be provided with easy access to health services.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words). | Under Result 1, though mobile units originally started to provide COVID-19 filiation services to a large extent, the strategy and targets have been changed several times to adapt to the developing situations in the field. For instance, in the fourth month of implementation when vaccination became available, units have been mobilized for that purpose in mobile clinics and tents. Whereas in the next few months, they were re-assigned to screening and tracking due to new variants. As of late 2021 however, as pregnant women were recognized as a high-risk group for COVID-19, units have been mostly re-mobilized to follow-up pregnant women not only in terms of vaccination, and awareness-raising for COVID-19 filiation, but also for SRH-related issues. Under Result 2, due to the high interest and demand of the Ministry of Health in Telehealth services, more detailed training and information videos were prepared for physicians, health workers and citizens. Negotiations with the Ministry of Health continue to expand the project to the whole country after the pilot implementation is over. The Ministry of Health looks very warmly towards the dissemination of the project throughout Turkey.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | N/A

## Project Indicators
Please include ALL indicators in the project document. Include the indicators and Baseline, Planned Target and Actuals for both OUTCOME and OUTPUT levels. "Actuals" refer to the total figures achieved for each indicator. Include separate actuals for 2021 and for 2022 (if applicable). Explain if targets were not achieved. Include means of verification. Use as many outputs cells as needed to present all project indicators.
| INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | DATA: ACTUALS 2022 (if applicable) | TOTAL actuals (agreggated 2021 and 2022 if applicable ) | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 2 | Increased access to immediate health and socio-economic support to respond to the health and social impact of the COVID-19 pandemic
Output 2.1 | Mobile health service provision for enhanced outreach to vulnerable populations
Indicator 2.1.1: | 6 MHUs are operational |  |  |  | Ministry's request for additional units based on the need arose in the field. The depreciation of Turkish Lira also made possible mobilizing four additional units to the field. | UNFPA Turkey CO -Vehicle Daily Logsheets for the 10 vehicles -Timesheets of the MHU staff -Regular field visits to Ankara and Konya by UNFPA project staff
Baseline: | 0
Planned Target: | 6 | 10 | 10 | 10
Indicator 2.1.2: | 18 personnel in the MHUs and 2 Field Associates trained |  |  |  | Additional four units resulted in 12 new staff. | UNFPA Turkey CO -Recording of the orientation -Training and attendence sheet
Baseline: | 0
Planned Target: | 20 | 32 | 32 | 32
Indicator 2.1.3: | # of beneficiaries receiving services from 6 MHUs (10). |  |  |  | Additional 4 units as well as overperformance of the project staff. | UNFPA Turkey CO Online Database
Baseline: | 0
Planned Target: | 11000 | 31716 | 29449 | 61165
Output 2.2 | Telemedicine for increased access and coverage of services in primary health care
Indicator 2.2.1: | 18 modules of Telemedicine guidelines, algorithms, and patient information materials developed |  |  |  |  | A total of 39 videos and information guides were prepared for patients and physicians. It was published in the link of the Ministry of Health in a way that all citizens and physicians can access. Please kindly find the link: https://hsgm.saglik.gov.tr/tr/uzaktan-saglik-hizmeti-sunumu
Baseline: | 0
Planned Target: | 18 | 39 | 39 | 39
Indicator 2.2.2: | Draft Regulation on telemedicine and personal data protection is developed |  |  |  |  | On February 10, 2022, "REGULATION ON THE PROVISION OF REMOTE HEALTH SERVICES" circular published. https://www.resmigazete.gov.tr/eskiler/2022/02/20220210-2.htm#:~:text=MADDE%2014%20%E2%80%93%20(1)%20Uzaktan,alanda%20uzaktan%20sa%C4%9Fl%C4%B1k%20hizmeti%20sunamaz.
Baseline: | No
Planned Target: | Yes | Yes | Yes | Yes
Indicator 2.2.3: | 10 HLC and 3RHC equipped with hardware for technology based patient consultation |  |  |  | The purchasing process completed. | WHO CO Türkiye
Baseline: | 0
Planned Target: | 13 | 0 |  | 13
Indicator 2.2.4: | 222 FHC center employees trained on telemedicine |  |  |  | The training completed at the end of March. | WHO CO Türkiye
Baseline: | 0
Planned Target: | 222 | 0 | 36 | 234
Indicator 2.2.5: | 80 HLC center employees trained on telemedicine |  |  |  | The training will be completed at the end of March. | WHO CO Türkiye
Baseline: | 0
Planned Target: | 80 | 0 | 32 | 78
Indicator 2.2.6: | # of beneficiaries reached through telemedicine |  |  |  | Implementation of the project at the field began after the approval of General Directorate of Information Systems of MoH Turkey. And the certain numbers will be provide by MoH. | WHO CO Türkiye
Baseline: | 0
Planned Target: | 204175 | 0 |  | 0
Indicator 2.2.7: | 40 RHC center employees trained on telemedicine |  |  |  | The training completed at the end of March 2022. | WHO CO Türkiye
Baseline: | 0
Planned Target: | 40 | 22 |  | 41
Indicator 2.2.8: | 3 press conferences to promote telemedicine are conducted |  |  |  | Press briefings and news were made. Information and evaluation meetings were held with family physicians and provincial health directorate and ministry managers. | WHO CO Türkiye
Baseline: | 0
Planned Target: | 3 | 0 |  | 3
Output 2.3 | Risk communication on Covid-19, essential health services and social protection services through multiple channels
Indicator 2.3.1: | # of beneficiaries reached through risk communication
Baseline: | 0 |  |  |  |  | UNFPA Turkey CO UNHCR Turkey CO
Planned Target: | 30000 | 31893 |  | 31893
Indicator 2.3.2: | Information Platform on service delivery regularly updated
Baseline: | No |  |  |  |  | UNFPA Turkey CO UNHCR Turkey CO
Planned Target: | Yes | Yes | Yes | Yes
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
The visual materials and stories can be reached via the links in the attached document (COVID-19 Project Engagements of Visibility Activities).
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well as picture material please make sure you include all credits and share them in high resolution.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board
PICTURES FROM THE CLOSING MEETING (16 JUNE 2022)
Note on A1: @atilganozgenc@unfpa.org -Deniz Gole

## Annex-1 MHU Services Breakdown
MHU Service Provision (May 2021-June 2022)
MHU Service Distribution by Service Type (May 2021-June 2022) |  |  | Column1 | May | June | July | August | September | October | November | December | January | February | March | April | 2022-05-01 | 2022-06-01
Service Type | # of Service | # of people | # of people | 54 | 2287 | 2288 | 2621 | 5545 | 5173 | 6090 | 7658 | 7739 | 7680 | 6847 | 3774 | 1934 | 1475
COVID-19 Screening and Tracking | 23869 | # of services | # of services | 137 | 5341 | 4881 | 5805 | 10123 | 9310 | 11112 | 19099 | 28460 | 25005 | 18838 | 10498 | 5089 | 2654
COVID-19 Counselling (information provision and Hygiene-health awareness) | 36971
COVID-19 Medication | 5923
COVID-19 Sampling | 2312
COVID-19 Vaccination | 12888
SRH and GBV Counselling | 10530
Other Vaccination | 12285
Referral | 9461
Other | 42113
TOTAL | 156352
# of Beneficiaries by Age, Gender and Nationality (May 2021-June 2022)
|  |  | Column1 | Female | Male | Total
|  |  | Below 15 | 3232 | 3159 | 6391
|  |  | 15 to 49 | 25704 | 16632 | 42336
|  |  | 49 to 65 | 2557 | 2548 | 5105
|  |  | 65 and above | 3260 | 4073 | 7333
|  |  | TOTAL | 34753 | 26412 | 61165
|  |  | Column1 | Female | Male | Total
|  |  | Turkish | 19426 | 15834 | 35260
|  |  | Syrian | 11410 | 6322 | 17732
|  |  | Other | 3917 | 4256 | 8173
|  |  | TOTAL | 34753 | 26412 | 61165

## Annex2 WHO Tables,Pictures,News
Branch Distribution Table of Healthcare Professionals Attending Training | [10 empty] | Working place Distribution of Healthcare Professionals Attending Training
| Branch | Ankara |  | Konya |  | Samsun |  | Total |  |  | Province / | Ankara |  | Konya |  | Samsun |  | Total
1 | Family Health Center Worker | 68 | 34,3% | 32 | 26,7% | 8 | 22,9% | 108 | 30,6% |  | Center
2 | Child Development | 1 | 0,5% | 3 | 2,5% | 0 | 0,0% | 4 | 1,1% |  | FHC / PHD | 144 | 72,7 % | 70 | 58,4 % | 20 | 57,1 % | 244 | 66,3 %
3 | nutritionist | 8 | 4,0% | 9 | 7,5% | 1 | 2,9% | 18 | 5,1% |  | RHC | 22 | 11,1 % | 15 | 12,5 % | 4 | 11,4 % | 41 | 11,6 %
4 | Midwife / Nurse | 20 | 10,1% | 20 | 16,7% | 8 | 22,9% | 48 | 13,6% |  | HLC | 32 | 16,2 % | 35 | 29,2 % | 11 | 31,4 | 78 | 22,1 %
5 | Physiotherapist | 3 | 1,5% | 4 | 3,3% | 1 | 2,9% | 8 | 2,3% |  |  | 198 |  | 120 |  | 35 |  | 353 | 100%
6 | Physician | 82 | 41,4% | 33 | 27,5% | 10 | 28,6% | 125 | 35,4%
7 | Psychologist | 6 | 3,0% | 7 | 5,8% | 2 | 5,7% | 15 | 4,2%
8 | Social Worker | 2 | 1,0% | 4 | 3,3% | 1 | 2,9% | 7 | 2,0% |  | Working place Distribution of Healthcare Professionals Attending Training
9 | Administrative Staff | 8 | 4,0% | 8 | 6,7% | 4 | 11,4% | 20 | 5,7% |  | Province / | Ankara |  | Konya |  | Samsun |  | Total
Total |  | 198 | 100 | 120 | 100 | 35 | 100 | 353 | 100 |  | Center
[11 empty] | FHC / PHD | 144 | 72,7 % | 70 | 58,4 % | 20 | 57,1 % | 244 | 66,3 %
[11 empty] | RHC | 22 | 11,1 % | 15 | 12,5 % | 4 | 11,4 % | 41 | 11,6 %
[11 empty] | HLC | 32 | 16,2 % | 35 | 29,2 % | 11 | 31,4 | 78 | 22,1 %
[12 empty] | 198 |  | 120 |  | 35 |  | 353 | 100%
Some Press News Samples About Telehealth
https://www.trthaber.com/haber/gundem/uzaktan-saglik-hizmeti-basliyor-ayrintilar-belli-oldu-653781.html
https://www.ntv.com.tr/saglik/bakan-koca-uzaktan-saglik-hizmeti-basliyor,gQfWZRkQDkCpDGjG8q7blA
https://www.hurriyet.com.tr/gundem/son-dakika-saglik-bakani-koca-duyurdu-uzaktan-saglik-hizmeti-basliyor-42001308