## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2022
4 | ALL projects that received funds in 2021 must complete annual report, HOWEVER if you have your project ending on 31st December 2021 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 30 April 2022
7 | ALL projects that received funds in 2021 must complete annual report, HOWEVER if you have your project ending on 31st December 2021 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Empowering women through safe, resilient, gender responsive food markets and systems in response to covid 19 in Zimbabwe | Overall Duration (months) | 18 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | October, 2019
MPTF Office Project Reference Number:[2] |  | Original End Date (dd.mm.yyyy) | April, 2022
Country | Zimbabwe | Current End date(dd.mm.yyyy) | 2022-09-30
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UN Women, UNDP, and ILO | National counterparts (government, private, NGOs & others) and other International Organizations | Oxfam, NSSA, Helpline- Zimbabwe, Community Water Alliance, Knowledge Transfer Africa, DEGI
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The project was aimed at enhancing the role and participation of women as key actors in the establishment and operationalization of resilient last mile distribution markets and systems that are safe, responsive to their needs and fully functional during the Covid-19 outbreak and beyond. Key activities were implemented in the project duration contributed significantly to the tangible results as set in the project document. Achievements under Pillar 1 Health first Seven (7) OSH trainings were conducted to improve safety and adherence to Covid-19 and prevention of other infectious diseases at the marketplaces. Two ablution blocks (toilets) in Mbare and Highfields markets and three hand washing stations were built in Mbare, fully equipped with solar lighting, bin area, drainage system and a perimeter wall. An ablution facility (toilet) was refurbished to accommodate the vendors, including an extension to cater for children in Hatcliffe. A Covid-19 vaccination programme was rolled out in three locations and PPEs procured, benefitting 1285 vendors (730 females and 555 males) in Mbare, Hatcliffe and Highfields. The vaccination program benefited the marketers by increasing productivity at the market place and their immunity against Covid-19 and contributed to the National program of increasing herd immunity. Three solar powered boreholes were installed, fitted with 5000-litre tanks and 3 (1000litre) at the three markets ( Mbare, Highfields and Hatcliffe) to help alleviate water challenges experienced by women vendors at the markets. 30 trainer of trainers (19 females and 11 males) were trained on First Aid, 26 trainer of trainers (18 females and 8 males) trained as Safety, Health and Environmental (SHE) Champions. These futher cascaded trainings to others. These were equipped with necessary information on safety and health so that they can create a safe working environment and help promote an occupational safety and health preventive culture in the marketplace. Five clean up campaigns to remove Solid Waste Dumped on Illegal sites were conducted in all three project sites (Mbare, Highfields and Hatcliffe) as part of raising awareness on COVID-19 regulations and the need to keep the markets and communities clean as preventative measures to reduce the spread of COVID 19 and other diseases. Achievements under Pillar 2 Protecting people: Social protection and basic services •Six (6) Community-based gender responsive mechanisms were established. Awareness on SGBV prevention and response was also integrated in clean up campaigns to increase awareness on SGBV which had increased due to lockdowns and other COVID-19 regulations. One National Knowledge Centre, and Provincial and District Knowledge Centres and website established to enable women to access information on food markets and women discussion fora via e solutions such as social media, voice calls, bulk messages, website, etc. •Six trainings on Prevention of Sexual Exploitation and Abuse (PSEA) and prevention and response to Sexual Gender Based Violence (SGBV) conducted. Achievements under Pillar 3 on Economic Response and Recovery • 120 market stalls refurbished at the Mbare wholesale market. 72 F and 48M marketers are now working from the established safe and gender responsive market, receiving an average 5000 customers daily. •The Project facilitated disbursement of a total of USD 5500 cash loans from USD50-$500. These were granted by Zimbabwe Women Microfinance Bank benefitting in: Mbare (70 beneficiaries- 20M, 50 F) Highfields, 30 (10M, 20F) and, Hatcliffe, 48 (15 M, 33F) •An online platform established to generate, process and share market-oriented information with women vendors and small holder farmers with 70% female of communal farmers. •285 women vendors trained in Occupational Safety and Health (OSH), 1800 women trained through intergrated trainings on business management, financial literacy and transformative leadership. They voiced their concerns on the market committee male dominated composition and advocated for 50-50 representation in the next committee elections. •One Occupational Safety and Health National Strategy drafted and one Occupational Safety and Health Management System developed to address informal traders issues towards market regulation and adherence to OSH standards. • 10 participatory by-laws and one Standard Operating Procedure (SOPs on regulation and monitoring of local food supply systems drafted. One gender responsive policy framework for safe and gender responsive urban food markets developed and operationalised. A handbook on participatory by- law and policy making was also developed. This is to strengthen institutions working on Local Economic Development (LED) and will guide Zimbabwean Councils establish and operate safe and gender-sensitive urban food markets. Four (4) ISALS groups were established that will allow for sustainability of the project.
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The programme specifically targeted and reached out to vulnerable women and girls who are survivors of sexual gender based violence, women with disabilities and young women who are survivors of harmful practices such as child marriages, sex workers, older persons, and the youth as per the project document. Secondary group of beneficiaries consisting of national and local level institutions were also reached through trainings to develop guidelines and regulations to support safe markets and local economic development. Number of direct and indirect beneficiaries: Direct A total of 3149 (2290 females, and 859 males) from the age range of 18-55 were reached by the project directly and the project targeted vulnerable groups such as survivors of sexual gender based violence, sex workers, persons with disabilities, women living with HIV, women, men and youth COVID-19 Vaccines benefitted 1285 vendors (730 females and 555 males) in Mbare, Highfields and Hatcliffe markets to curb the spread of COVID-19 in the targeted markets i.Refurbished Mbare mass market is benefitting 120 (72 females, 48 males directly, and 228 females and 152 males indirectly, (with ages ranging from 18-45 years). The market has an estimated flow of 5,000 customers per day directly benefitting from a safe and gender responsive and Covid-compliant trading environment and improved market linkages. ii. The ablution facility, borehole and 5000 litre tank at the Hatcliffe market are benefitting 304 vendors, 120 direct project beneficiaries (comprised of 19 female youth (35 years and below), 9 male youth (35 years and below), 11 males (36 years and above), 81 females (36 years and above). iii. 94 market vendors (68 females, 26 males) stationed at the Highfields market were reached through trainings on COVID-19, OSH and GBV prevention and response. iv. COVID- 19 and SGBV prevention and response awareness campaigns held in partnership with Zimbabwe Republic Police Victim friendly Unit reached a total of 7509 people (1430 female youths, 1044 male youths, 3145 female adults, and 1890 male adults). 1800 participants were trained on intergrated trainings on business management, transfrmative leadershiop, financial literacy, including e- commerce and entrepreneurship drawn from the markets, Community Health Clubs and youth groups. 10 community health volunteers (5 females & 5 males) were reached. Trained community health volunteers working with the Environmental Health Technician, established 13 Community Health Clubs and supported them with Participatory Health and Hygiene Education tools. CHCs managed to reach out to 228 community members comprised of 88 female youths, 73 female adults, 16 male youths and 51 male adults. 30 (14 females, 16 males) secondary group of beneficiaries consisting of national and local level institutions were trained on SOPs and a Gender responsive policy framework that was developed to support safe markets and local economic development. Indirect Reach An estimated 50 200 residents in Mbare, Highfields and Hatcliffe were reached through clean up campaigns, road shows, TV shows, youth events and community door to door awareness on COVID-19 and sexual gender-based violence held in 3 project locations. An estimated 10969 people were reached through the radio talk shows, SMSs, and road shows and sensitization by Cash for work beneficiaries.
3.1 | Results: Outcome Level | Please include outcome level results achieved | Outcome 1 Improved livelihoods of women marketers & vulnerable groups through safe, gender responsive market infrastructure and systems The project successfully refurbished and completed the Mbare wholesale market, comprising 120 market stalls. Three completed ablution facilities (toilets) were constructed and renovated in Mbare, Highfields and Hatclifee markets. 120 marketers (72 F and 48 M) are now working from the established safe market in Mbare, and these were identified from the following categories: persons with disabilities, women, and girls’ survivors of SGBV, sex workers, older persons, and the youth. An estimated average of between 3000-5000 customers are benefitting from the infrastructures (two markets sheds, ablution facilities, 3 (1000) litre hand washing stations and three solar powered boreholes fitted with 5000 litre tanks installed to enhance sanitation, hygiene, and provision of adequate water supply. 300 vendors access the market on a daily basis as they come to sell their wares to those operating from the newly constructed safe market. The completed market infrastructures are sensitive to women’s needs and complies with OSH and COVID-19 regulations as the market stalls are partitioned to allow 1,5 metre distancing between market users. The project supported the maintenance of hygiene at the market by constructing a separate bin area for waste management purposes. The completed market created an enabling environment for women who are no longer exposed to the harsh weather conditions and due to the lighting of the market, incidencies of robberies and attacks to women have been reduced. The refurbishment of the Mbare mass market to respond to the needs of women whose lives has been impacted negatively by the COVID-19 pandemic has been hailed by the local authority and Government ministries as an important step which saw the market being changed from a violence prone public place to a safe operating environment for women. The rehabilitated market has provided a model for the City of Harare to replicate in other other markets outside Mbare. As a result of the project, the City of Harare has embraced devolved markets in line with the devolution agenda of the Government. The Ministry of Women Affairs has started rolling out and replicating the safe markets model in other areas, a positive indicator of the multiplier effect of the project in Zimbabwe. The construction of the market was a result of the project’s strategic engagements with key Government stakeholders such as the Ministry of Local Government, Ministry of Agriculture and the Ministry of Women Affairs, Community, Small and Medium Enterprise at the various stages of the project implementation. These institutions' capacities and skills were strengthened through capacity development initiatives on the various strategies, policies, SOPs and plans developed during the course of project implementation. To ensure that the refurbished market is in compliance with occupational health and safety regulations, the project carried out inspections during the renovation work at the market which allowed adjustments to be made in view of the identified gaps. It further delivered OSH trainings at all the three markets, including the provision of PPEs to help avert the adverse impact of COVID-19 pandemic on the markets. Information, education and communication material (IEC) covering the following:- COVID protocols and regulations, hazard information and control, manual lifting, housekeeping, waste management and general hygiene at the market developed and disseminated to the market vendors have enhanced awareness, knowledge and skills on the above covered topics. What was more innovative about the project was the ability to recognize the evolving nature of the COVID-19 pandemic, and how people are impacted differently, especially those at the markets. The project conducted a gender gap assessment of the impact of COVID-19 and the findings informed the interventions to adapt and respond to new needs. Through NSSA, the vaccination programme was launched. The vaccination exercise for all sites benefited 749 informal economy workers being 500 females and 249 males in Hatcliffe, Highfields and Mbare. The project was able to respond to the needs and concerns of the women marketers who had raised challenges in accessing vaccines and ensured the vaccination was delivered at the market doorstep to the benefit of the beneficiaries. Vaccinating informal economy workers at their worksites ensured that they did not lose productive time searching and queuing for vaccinations. The noble initiative ensured that informal economy workers maximised their productive time to improve their businesses and promote their safety and that of customers. Increased vaccination awareness was realised and the fears and myths around the effects of vaccines which were expressed by the beneficiaries during the gender gap assessment were demystified as the project responded and intensified trainings and community awareness campaigns. Not only did the project beneficiaries benefit from the campaigns, but the communities at large as mobile campaigns and clinics were pitched to give the communities information on COVID- 19 protocols and regulations and information on vaccines One Occupational Safety and Health National Strategy drafted and one Occupational Safety and Health Management System developed to address informal traders issues towards market regulation and adherence to OSH standards. The project through NSSA used the Zimbabwe television to raise awareness on OSH in the informal economy. The project through the baseline survey realised that informal economy workers and stakeholders such as local authorities have little or no knowledge about OSH in the informal sector. The three TV programmes were done in English, Shona and Ndebele in order to have a national coverage and benefit beyond the project sites. The improved awareness of OSH in the informal economy will contribute towards changing attitudes and perceptions about the informal sector. The sector is viewed as disorganised with no systems despite the fact that they are workers who deserve protection. Following a HIRA and needs assessment conducted by NSSA at the project markets, a hazard Identification and Risk Assessment checklist and OSH assessment tools were developed in the reporting period. These tools were useful as they were used to assess occupational hazards being faced by vendors at the three markets. The outcomes of the assessments guided the training and response services delivered in the course of the project. The response promoted decent work by market vendors and contributed to productivity and safety at their workspaces. The trainings on hazard identification and control, first aid, accident prevention and control, COVID-19, waste management and material handling enhanced the women vendors and other vulnerable groups’ knowledge and skills to identify and to be alert to hazards and risks at the food markets, and how to prevent and control them, especially in the context of COVID-19. City Council stakeholders improved knowledge on Standards Operating Procedures on COVID-19 mitigation measures. The SOPS produced through the project are helping the local authorities in establishing mitigation measures within markets covered by the project and those beyond the project target, which is a positive impact of the project paving way for replication and sustainability. In addition, the establishment of the Mbare mass market was also accompanied by the establishment of six gender responsive mechanisms to prevent and address SGBV and harassment in public spaces. The mechanisms provided women and young girls who are survivors of SGBV and other vulnerable groups with first-hand information on the reporting channels, how to report and, where to report and where to access other services such as the clinics, courts, psycho-social support, among others. The trainings on SGBV prevention and response were timely considering that COVID-19 exacerbated cases of gender-based violence against women and young girls. Equipped with information, survivors of GBV were able to seek and access GBV and SRHR related services. The project also managed to build and strengthen close working relationships with key stakeholders within the referral pathway at community level in all project locations such as the Police victim friendly unit, local clinics, courts, and the department of social development. The stakeholders were sensitised on the impact of COVID-19 on women and young girls in the informal sector (markets), and their roles in supporting women in the informal sector to get protection against SGBV. 30 (22 females, 8 males) stakeholders were trained on the nexus between gender and SGBV, harmful practises and SRHR and how their roles and responsibilities connect and intersect as outlined in the multi sectoral protocol on the prevention of sexual violence and abuse against women and girls. The stakeholders were equipped with knowledge and skills on how to ensure survivors of SGBV receive timely and quality services considering the impact of violence on women and young girls, especially in the context of COVID-19. As a result of the engagements and training targeting these stakeholders within the community referral pathway, women survivors of SGBV in the communities have reported receiving timely and quality services from all the service providers. The project beneficiaries have confessed that since the project inception, the working environment safety has improved and there has been a significant reduction in incidences of SGBV and sexual harassment at all the three markets. Equipped with skills and knowledge on COVID prevention protocols and SGBV prevention and response, including the referral pathway, market committees are leading in driving behaviour change for market users. A working relationship between markets committees and the Zimbabwe Republic Police (ZRP) has been established. ZRP is working with established markets committees to enforce COVID-19. The project also engaged male marketers as partners and gender champions in fighting GBV; and created 3 committees specifically for addressing GBV issues in all the three markets. 30 male gender champions and 20 females are part of the committees. The continued community engagements and awareness raising on COVID-19 and GBV by the UN volunteers contributed to a safe, inclusive and violence free operating environment and improved livelihoods of women marketers. The Project facilitated disbursement of a total of USD 5500 cash loans from USD50-$500. These were granted by Zimbabwe Women Microfinance bank benefitting in: Mbare (70 beneficiaries- 20M, 50 F) Highfields, 30 (10M, 20F) and, Hatcliffe, 48 (15 M, 33F). The financial support was timely and welcome considering how the women’s incomes have been eroded by the impact of COVID-19. Before the project intervention, it was difficult for women to access credit facilities as the banks required collateral which the majority of women did not have. The project was able to negotiate with the banks on the issue of collateral and inroads were made resulting in women and other vulnerable groups accessing cash loans. This was a breakthrough in women’s lives, as for the first time, the women were able to get credit, which boosted their operating capital, improved their economic base and financial security. As the project focused on supporting the economic empowerment of women and other vulnerable groups, 285 women vendors trained in Occupational Safety and Health (OSH), 1800 benefitted through intergrated trainings on business management, financial literacy, including e- commerce and transformative leadership. As a result, the vendors’ capacities, skills, and abilities to run and manage their business in a sustainable way as well as the utilisation of digital financial services were enhanced. The ILO business concept of ‘Start and Know your Business’ was utilized considering its positive impact on other urban resilience food markets projects implemented by the joint UN partners in other locations. Knowledge Transfer Africa Private Limited was contracted by the project to ‘develop capacities of key AGRITEX institutions responsible for crop and livestock production and marketing through e-Extension with a specific focus on Extension Officer and Farmer capacity building as well as provision of ICT tools and e-commerce applications’. This intervention was meant to facilitate access to safe markets under COVID-19 pandemic period through monitoring of local food supply systems for safety. A comprehensive Operational Manual/Guide for Agritex Knowledge Centre e-Solutions Applications was developed and this will be used during trainings of Agriculture Extension Officers and Knowledge Administrators at National, Provincial and District Offices. The manuals were reviewed to ensure gender lens and gender mainstreaming in training processes and subsequent use of the platform/gathering data for it. An online platform was established that generate, process and share market-oriented information with women vendors and small holder farmers with 70% female of communal farmers. A website was also established, accessed as www.agritextraining.co.zw which hosts modes of communication for women to access information such as a virtual centre for voice calls, WhatsApp system for messaging; sms system for messaging, access to Facebook; twitter; LinkedIn, live chats and a discussion fora. It is a platform for agricultural extension officers to access relevant information that they will share with women they work with on a daily basis or as part of their extension services to women. 225 extension officers and 30 district knowledge centre administrators have been trained in 15 districts The following tools were developed for collecting data along the supply chain using mobile phone based Kobo Collect application. Below is a list of developed tools: Production Area and Farmer Profiling. Markets and Buyer Profiling. Farmers’ and Traders’ Commodity Stocks & Sales Tracking. Collected data will be analysed and interpreted for purposes of: Organizing and coordinating commodity market supplies. Sharing with supply chain actors (farmers, traders, processors, vendors etc.) to timely and accurately inform their business planning and decision making. Reviewing and developing agro-related policies and key supply chain support institutions’ strategic programming Outcome 2: Enabling a gender responsive policy framework and institutions responsible for administration, regulation and monitoring of food supply systems The development of a gender responsive policy framework which outlines policy areas requiring local authorities' attention in developing and managing safe and gender-sensitive urban food markets, coupled with generic standard operating procedures for food markets were major achievements of the project. To facilitate institutionalisation of the gender responsive policy framework and SOPs, the project further capacitated national and local level institutions on the policy documents and their implementation to strengthen them on local Economic Development (LED). As a result of the trainings, national and local level institutions' capacities were enhanced to implement SOPs and gender responsive policy frameworks. In terms of strengthening women's voice and agency, the project resulted in improved women's participation in market leadership structures as efforts were put towards ensuring women participate and influence decisions in market leadership structures. Capacity building initiatives on transformative leadership did not only target women leadership but incorporated male leadership as agents of change. . The result was increased leadership capacities, increased voice and agency, knowledge and skills among the market committees and positive attitude and support from men towards women leadership. Testimonials from the women' leadership attested to significant change in men's attitude towards women, improved respect, and support to women's leadership. Women were able to influence the inclusion of a clause on 50-50 representation in market Constitutions that were developed for the various clubs established under the project such as the community health clubs. Women were also able to voice their concerns on the composition of the market committees, which are male dominated and advocated for 50-50 representation in the next elections. The project further supported women to engage with key decision makers, particularly the local authority, Ministry of Women Affairs, Local Government during meetings to discuss the development of market plans, construction of ablution facilities, selection of market beneficiaries and impact of COVID-19 impact assessments, development of SOPs and policies, establishment of gender responsive mechanisms, establishment of market committees. The engagements resulted in increased voice of women and their influence resulted in the construction of gender responsive market in Mbare and other infrastructures, gender responsive governance of food supply chain management, development of gender responsive action plans, SOPs, and establishment of SGBV response mechanisms and gender responsive market committees and ISALS.
3.2 | Results: Output Level | Please include output level results achieved | Output 1: Safe markets – infrastructure and systems that are sensitive to women’s needs, complies with occupational health and safety regulations, and accompanied by mechanisms and structures to prevent and address gender-based violence and harassment. The project successfully refurbished and established the Mbare wholesale safe market, with a provision to cater for an estimated 300 traders who sell their produce on a daily basis. 120 marketers, 72 women and 48 men are now working from the established safe market, and these were identified from the following categories: persons with disabilities, women, and girls’ survivors of SGBV, sex workers, older persons, and the youth. The market is sensitive to women’s needs and complies with COVID-19 regulations such as the maintenance of 1,5 metres distances between stalls, equipped with 3 (1000litre) hand washing stations and a solar powered borehole installed resulting in improved hygiene and water, a positive response to avert COVID-19. Three ablution block/ toilets were refurbished/ constructed and three solar powered boreholes and 3 (5000 litre water tanks) installed at the 3 markets, which are not only benefitting the women vendors, but an estimated 3000-5000 customers who visit the markets to buy food. To promote OSH, the project developed an Informal sector OSH Policy amd Management System. Once adopted, the documents will give the Government an obligation to address the challenges faced by informal traders and help in market regulation and adherence to OSH standards. Workers in the informal economy have not been part of Government support and cushioning to promote their work hence vulnerability to hazards and lack of support during times of pandemics like COVID-19. Tools for OSH assessments are a key result that the project used to identify hazards being faced by SMEs in the informal economy. Seven (7) OSH trainings were conducted to improve adherence to Covid-19 and prevention of other infectious diseases at the 3 markets reaching 379 vendors ( 221 females, 158 males). The trainings covered areas such as hazard identification and control, accident prevention and control, COVID-19, waste management and manual handling. 30 market leaders (19 females, 11 males) were identified and trained as First Aiders, and equipped with knowledge, skills and capacities to handle any emergencies in the marketplace. The training improved emergency preparedness since every workplace should have competent people to deal with hazards and accidents. The ability to deal with hazards and accidents at work places is a critical pathway to attaining decent work. 26 vendors (15 females, 8 males) were trained on basic safety and health, and were equipped with necessary information on safety and health so that they become SHE Champions at the markets creating a safe working environment. In addition, ten (10) Standard Operating Procedures (SOPs) for markets in line with COVID-19 mitigation measures were updated and adopted by the City of Harare. The project engaged 2815 youths, (1144 male youths and 1671 female youths) on COVID-19 mitigation measures. 20 young volunteers were hired on decontamination of marketplaces. 372 women and youth directly benefited through one of the following: Cash-for-Work volunteering on decontamination, establishment of community health clubs and ISAL groups, community volunteer trainings on OSH, health, hygiene and gender aspects. An estimated 50, 200 residents in all three project locations were reached through mobile road shows, clean up campaigns, youth events and door-to-door awareness raising on COVID-19, health education and prevention and response to GBV. These initiatives increased communities’ awareness and knowledge on COVID-19 protocols and helped them to respond and adhere to the preventative measures, resulting in reduced cases of COVID-19 and outbreak of diseases such as cholera and diarrhoea. The project established a community movement on hygiene promotion and implementation of COVID-19 Prevention Protocols. The movement is shown through established community health clubs and youth volunteers who have been working with City of Harare Environment Health Technician in entrenching community-based disease surveillance mechanisms. The built community movement has been engaging in door-to-door awareness, producing WASH detergents, and selling to local residents. Markets committees have been successfully engaged in occupational health and safety (OSH) and their capacity has been enhanced such that they have started implementing safety measures like inspections that guarantee decent work for informal traders. To address, SGBV in the marketplace, six (6) Community based reporting and response mechanisms were developed with the participation of project beneficiaries, the local authority, local police, social welfare, clinics, and other key stakeholders. Women marketers, including survivors of SGBV are now equipped with knowledge and skills on SGBV prevention and response, and aware of where to access SGBV and SRHR services in cases of violation of their rights. In total 223 (183 females, 40 males) project beneficiaries received training on SGBV, prevention and response and available referral pathways within their communities. 30 (24 females, 6 males) stakeholders within the multi sectoral referral pathway were also trained on the nexus between gender and SGBV and their roles and responsibilities towards the protection of women and other vulnerable groups against gender-based violence. In additiohn, to promote access to information and services on SGBV and sexual harassment, six mobile door to door awareness campaigns were conducted in 3 project sites, reaching an estimated 50200 people. Output 1.2 Improved economic base and financial security for women marketers. The programme engaged with financial institutions such as the Women's Bank, Empower Bank and Commercial Bank of Zimbabwe to facilitate linkages of women beneficiaries financial packages such as credit facilities, insurance, and other facilities to protect against economic shocks. As a result of the engagements, disbursement of a total of USD 5500 cash loans from USD50-$500 were granted by Zimbabwe Women Microfinance bank benefitting in: Mbare (70 beneficiaries- 20M, 50 F) Highfields, 30 (10M, 20F) and, Hatcliffe, 48 (15 M, 33F). 1800 women vendors were trained and their capacities increased in business management, financial literacy, entrepreneurship, including e- commerce. Output 1.3 Inclusive E-solutions for safe markets established to promote more effective food market access by consumers Through partnership with Knowledge Transfer Africa and AGRITEX, the project established an e-based National Knowledge Centre that will facilitate women vendors and rural small holder farmers in 15 districts to access information on markets, food markets value chains, transport tracking and chatbot tools). The main purpose of the centre is to generate, process and share market oriented information with small holder farmers, mainly women who constitute more than 70% of communal farmers. A website is now complete, accessed as www.agritextraining.co.zw which hosts modes of communication for women to access information such as a virtual centre for voice calls, WhatsApp system for messaging; SMSs system for messaging, access to Facebook; twitter; LinkedIn, live chats, discussion fora. It is also a platform for agricultural extension officers to access relevant information that they will share with women they work with on a daily basis or as part of their extension services to women. 1800 women vendors, 27 extension officers and 30 district knowledge centre administrators were trained on the use of the online platform. Data profiling of farmers was also conducted and data base created. Output 2.1: Capacity of local institutions to review, develop and implement regulations and by laws that ensure OSH compliance and gender sensitive food marketplaces are strengthened. The project provided institutional support to local authorities that resulted in the review of council by - laws, policies, and other regulatory frameworks for the food markets from a gendered lens/ dimension. The review resulted in the development of a gender responsive policy and guiding framework for safe markets and its operationalisation by the Government. The project also facilatated the development of a Consolidated SOPs handbook, Manual/Guide on the participatory By-Law Development Model; and capacity development of local authorities, government departments and market leaders on participatory By-law Development Model & Standard Operating Procedures for Safe Markets. Output 2.2: Increased voice and agency of women markets in community and market-oriented leadership structures. The baseline conducted in all project locations before the project kick off revealed a gender gap in the composition of the leadership structures in market committees, with more than 80% men occupying leadership positions. The greatest proportion of respondents, 87% both females and males, believed women should not be included in leadership structures as their place was in the home. To address the gender inequalities in market leadership, the project initiated conversations targeting market committees directed towards shifting norms and attitudes towards women leadership, and creating spaces for women’s leadership and participation. Three training sessions on gender transformative leadership were conducted in Mbare, Highfields and Hatcliffe, reaching to a total of 261 vendors (151 females, 65 males). The training targeted men as agents of social change and to discourage negative social norms, attitudes, and belief systems towards women’s leadership. As a result of the training and dialogues, women have been actively participating in market meetings. Ten (10) action plans were developed and implemented by women trained in transformative leadership to increase their influence in decision making structures within markets and relevant institutions. Participation and active involvement of women in market leadership structures has improved since the project directed efforts that ensured women occupy leadership positions within the market committee structures in all three project locations.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved PRODoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The COVID-19 pandemic had an impact on the delivery of the project considering the lockdown conditions that were introduced by the Government in 2021. Steps taken to prevent and contain the pandemic such as restricted movement affected the full implementation of the project. Although virtual means of communication were adopted, some interventions required on-site visits, for instance the assessment of the satellite markets could not be done in the first quarter of the year due to restrictions on movement. The introduction of the vaccination programme by the Government to some extent eased some of the challenges associated with the implementation of the project as the Government earmarked those in the informal sector for targeted vaccination. The project frequently assessed the situation and made necessary adjustments in planned interventions to ensure inclusivity, timeliness and effectiveness of measures on the ground. The project was able to adjust and adapt to the evolving COVID-19 trends and employed a hybrid approach to programme implementation as both in person and virtual modalities were used to ensure the project implementation was not halted. The finalisation and the identification of the satellite markets and selection of implementing partners took longer than anticipated due to protocols and finalisation of engagements with the local authority and the required approvals. The approval of the memorandum of agreement with the city of Harare, UN Women and Helpline- Zimbabwe was delayed and this derailed the start of the construction of the Hatcliffe market in the fourth quarter in 2021 and first quarter in 2022. The approval of the MOU required full Council resolution and due to COVID-19 restrictions, the physical seating of the full Council was not possible. The bureaucratic government systems and lengthy processes to get approvals from the local authority to start construction of markets was a major challenge which the project has no control and delayed the construction of the Hatcliffe market until the project duration ended in April 2022. A No Cost extension of two months was granted by the MPTF Secretariat to allow for the commencement and completion of construction of the Hatcliffe market to be completed by 30 June 2022. However, the Implementing Partner Helpline-Zimbabwe could not complete the construction of the market during the period of the No Cost extension as they faced challenges with delays by the Construction Company. The other planned activities at the Hatclifee market such as the renovation and extension of the toilet, drilling and installation of a borehole, installation of a 5000 litre water tank and procurement of children's play centre materials were completed within the reporting period. The major challenge the project faced is the fact that the Hatcliffe market construction remain incomplete (IP and Contractor are having challenges in accounting for some resources at the Hatcliffe market. In addition, politicisation of markets, especially at the Mbare Mass market and the excessive power and control over markets by market barons had an impact on the construction of the toilet for council staff in Mbare. The construction of the toilet could not materialise as a result of the politicisation of the market and the power and influence bestowed on market barons and despite engagements and negotiations with stakeholders, including the market barons, the outcome of the negotiations was not positive. Since the construction of the toilet was stalled, the project team deliberated on Plan B and resolved to shift and support the construction of the ablution facility in Highfields satellite market.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | Considering the challenges encountered during the implementation of the project, the following are the lessons learnt that will inform future interventions;- i.Stakeholder management- the need for extensive engagements with key stakeholders such as the local authority, Ministry of Local Government, Ministry of Ministry of Transport and Infrastructural Development and others prior to the start of the project to ensure proposed sites designated for markets are regulated, all the necessary legal papers and clearances are already approved and in place. This will not delay the construction of the markets and reduce the back and forth between the authorities and the project implementers as experienced during the implementation of this project. ii. Operational management- In future projects of a constructional nature, it is important for UN agencies to do direct implementation rather than contracting CSOs to implement such projects as they might not have the requisite technical skills to manage infrastructural projects and the risks associated with construction. In addition, the UN should ensure private engineers are hired to oversee and manage the project, instead of relying on engineers from the local authority. In addition, an extensive risk analysis is required and a risk management plan developed which are strickly implemented and monitored to reduce the risks associated with projects of a constructional nature. iii. Involvement of key stakeholders is critical at all stages of the project cycle, particularly during the planning stages. Market places in Zimbabwe are 'very sensitive and political spaces' which require project implementers to employ diplomatic tact, maintain neutrality and ensure close collaboration with all key stakeholders as the political actors can easily manipulate and divert the project to lure support and gain mileage from the voters. Stakeholder participation is important so that they get to understand the project in detail as well as their contributions to the project, their roles and responsibilities. iv. Building upon existing initiatives and partnerships is also critical for learning and experience exchange as this was reflected during the implementation of the programme where a partner in other similar projects such as Katswe Sistahood was involved in the project team retreat and shared their experiences which were beneficial during project implementation. v. Harnessing stakeholder strengths and joint delivery of project activities help deliver results at scale due to complimentary expertise and capacities drawn from different stakeholders. During project implementation, UN-Women helped with capacity building on gender and referral systems for SGBV, NSSA officials helped with capacity building on occupational health and safety; Ministry of Women Affairs helped with capacity building on requirements for transformation of ISALs into SACOs and City of Harare Department of Works provided the market technical oversight. The combined efforts resulted in smooth project implementation and delivery of results at scale. Understanding of the concepts of gender and gender mainstreaming is still low among communities and some stakeholders as they associate any discussions on gender to refer to ' women' and nothing to do with men. Constant and continued education on gender and gender mainstreaming concepts is critical to demystify misconceptions to ensure the advancement of gender equality and women empowerment. The need to engender and make participatory the law and policy making process at local level is important to ensure the needs of women, men, boys and girls are captured and addressed as the local authorities develop legislation and policies for the communities. This was revealed during the baseline study consultative process with communities, where the citizens expressed ignorance and limited participation during the policy making processes by the local authority. Mainstreaming gender in male dominated contexts to demystify misconceptions and to promote women participation in legal and policy making process at local level. Advocacy on gender responsive budgeting within local authorities should be prioritised for sustainability considering that post project implementaion, infastractures such as markets will need regular maintanance and repairs. Developmental use of Municipal budgets e.g. ring-fencing portions of revenue from food markets for market improvements becomes critical for sustainability. vi.Bureaucratic government systems and processes and lengthy processes to get approvals from the local authority to start construction of markets remain a concern which the project has no control. It is important to overcome politicization of targeted contexts (Mbare Mass market) and seek a balance to avoid excessive power on specific groups (market barons) influencing project implementation activities. The project implementers to employ diplomatic tact, maintain neutrality and ensure close collaboration with all key stakeholders and political actors. vii. It is critical to ensure that the selection and registration of market beneficiaries is carried out and finalised before the construction or renovation of the markets. A data base with all the project beneficiaries is finalized and updated and the selected beneficiaries are involved from the planning, designing of the market, construction and implementation. The identification and registration of the project beneficiaries in the initial stages help limit the politicisation of the project and disagreements on the exact project beneficiaries viii. The country does not have an Occupational Safety and Health Management System which has led to the vulnerability of informal economy workers. The system is only available for the private sector and its development during the project will be valuable towards promoting decent work in the informal economy. An Informal Sector National OSH Policy is being developed to safeguard informal economy workers especially in times of pandemics such as Covid-19.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The programme aims to build upon existing initiatives and partnerships to ensure timely and adequate response, at the same time new partnerships are being built, with continued mobilisation of resources for a scaled up and thorough inclusive response with nation-wide geographical coverage that would ensure stronger impact. Collaborative and transformative partnerships were strengthened with financial institutions and the private sector. The project worked closely with a private sector player Knowledge Transfer Africa (and/or other similar private sector stakeholders operating through online market platforms) which facilitated coordination of farm produce supply chains and support the livelihoods and ICT access of vulnerable women in food supply chain that were disrupted through COVID-19 induced lockdown measures. Oxfam has been re-engaged, while Helpline- Zimbabwe and NSSA were engaged as new partners ( Responsible Parties) who led the implementation of the programme with the support of the UN agencies. The project partners conducted routine monitoring of project activities, and liaised with relevant government ministries and departments, providing technical expertise and playing the role of coordination and integrating of the various stakeholders for the achievement of key project activities. The new partnership with NSSA brought in an innovative approach which complemented the government national level response plan through the rolling out of COVID-19 vaccination which was administered to project beneficiaries at all 3 project sites. A total of 749 (500 females, 249 males) in Hatcliffe, Highfields and Mbare who volunteered to be vaccinated were delighted and appreciated the project for bringing the vaccination programme at their doorstep (at the market places) and the intervention was a first of its kind positive response. The project also engaged with financial institutions such as the Women's bank, Commercial Bank of Zimbabwe and Empower Bank and VIRL- a micro finance institution. The project facilitated access to cash loans from the banks at reasonable lending rates from the Women's bank resulting in Mbare (50 beneficiaries- 10 M, 40 F) Highfields, 30 (10M, 20F) and, Hatcliffe, 48 (15 M, 33F) The cash loans helped boosted the beneficiaries' start up capital and in the long term improved their income and livelihoods. The financial institutions voluntarily provided training as part of their corporate social responsibility and the trained vulnerable groups' knowledge and skills in business management and financial literacy increased as a result of the trainings. Due to acute need of similar approach in other locations not currently covered by MPTF funds, the programme leveraged technical expertise of three RUNOs and conducted a workshop to mainstream safe markets guidelines (with focus on gender, OSH, regulatory environment and climate proofing) to other partner CSOs and Local authorities that are working on safe markets in location other than Harare. In addition, a partnership with the Environmental Management Agency was forged which resulted in the clearance of illegal solid waste dumpsites in Mbare. The EMA volunteered and availed trucks needed for the transportation of waste to designated dumpsites. It further provided an opportunity for interactions on alternative waste management models besides the collect, transport and throw away approach. This partnership was established through engagements between Community Health Clubs and City of Harare waste management division. Another strategic partnership with Spar Zimbabwe was established which triggered conversations, interests and knowledge sharing among private players on waste management. Spar Zimbabwe also donated rubbish bins that helped contain the illegal dumping of rubbish in Mbare and reduced the spread of diseases. Partnership with the Zimbabwe Republic Police Victim Friendly Unit (ZRP-VFU, local clinics, Department of Social development, ward councillors and local CSOs, community gender champions as partners in the GBV referral pathways was also established. The partnership assisted in strengthening the GBV referral systems for GBV survivors at local level, promoted knowledge on SGBV, the referral pathway and promoted access to survivor friendly justice/ services for women and girls and other vulnerable groups in the project areas. Joint programs such as campaigns were held with the above stakeholders increasing awareness on SGBV and COVID-19 protocols and regulations. The strategic partnerships with the media increased the visibility of the project and accelerated efforts to advance gender equality and women empowerment and raised awareness of COVID regulations and prevention and response to SGBV in communities, even beyond the project focus areas. The partnerships also increased the new partners' knowledge and skills on gender and gender mainstreaming as their capacities were built as they interacted with the project and also benefited through the targeted capacity building initiatives implemented within the project. The project successfully managed to utilise a holistic and multi- sectoral approach bringing together all key stakeholders/ partners such as local authorities, community leadership, CSOs, the private sector, media, and communities (women, men and youth) from the onset and during project implementation. This resulted in project ownership paving way to sustainability. The project fully complemented the Government's National Development Strategy (NDS1)devolution agenda through supporting the local authorities' district level plans on constructing satellite decongesting the major market such as the Mbare Mass market.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken. | Baseline assessment, end of project evaluation and other assessments were conducted for the project. Key findings from the baseline and assessments gave pointers to the situation on the ground and these informed the project intereventions and adjustments that were done. for example the baseline revealed high prevalence of sexual gender based violence in market places; inadequate reporting mechanisms and education to prevent and respond to SGBV; the markets are not sensitive to the needs of women, and lack compliance with occupational health and safety regulations, etc. The project was able to respond and address the identified gaps during project implementation and spearheaded interventions that are sensitive to women's needs and complies with occupational health and safety regulations. The OSH assessments informed the project response and promoted safety and productivity by SMEs in the selected markets. The project undertook a risk assessment of the current workplace and identified good local practices to reduce vulnerability to hazards and COVID-19. The project was able to recognize that the pandemic was/ is still evolving, and was able to undertake an assessment of the gendered dynamics around COVID-19, which unearthed issues such as the lack of information on vaccines and the myths surrounding vaccinations to women and men. The study helped understand the project beneficiaries' fears around vaccinations and was able to focus the interventions to adapt and respond to new needs. The project brought in partners such as the local health workers who came in to support with vaccination awareness and the project also responded by delivering vaccination at the Hatcliffe market following the requests by the project beneficiaries. In addition to this, UNDP's Accelerator Lab conducted research to understand network theory in relation to urban food markets and players in the urban food system. This helped identify how market network nodes have been impacted by COVID for potential market reorganization. By exploring how market players interacted pre-COVID and post-COVID, the research sought to identify which nodes in the supply chain emerged as either strong or weak and why that was the case. The Project also procured expert services that gathered and analysed data on the state of urban food markets, including conducting a review of policies, regulations, legal frameworks, by-laws with a gender lens. The secondary and primary data provided insights on the emerging changes in urban food supply chains in terms of sources, actors, and the infrastructure available at/around urban food markets. A gender responsive policy framework and generic SOPs were developed and local authorities were capacitated on their use.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | The project was ear marketed to support the refurbishment/ construction of the Mbare mass market and three other satellite markets that feed into the Mbare mass market. However as the project kicked off, it was realised that due to the unstable macro economic environment and the continued escalating costs of goods and services, the project budget was not sufficient to support the refurbishment / construction of all three targeted markets. The costs of goods and services continue to escalate in the country, compelling the project to adjust its target to focus only on the Mbare mass market, Hatcliffe and Highfields- Lusaka satellite markets. The other major adjustment was the construction of staff toilet at the Mbare Mass Market (due to complexity of market environment and tensions between various actors, construction of staff toilet at designated area posed substantial sustainability risk. Therefore, upon discussion with technical team and stakeholders, the solution was to relocate construction to Highfields where NSSA was already supporting with some of the WASH infrastructure. A toilet was successfully constructed in Highfields.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | The programme was able to engage with partners already implementing similar projects such as Katswe Sistahood and NSSA which were able to share experiences and best practise around safe markets. The programme was able to draw learning and best practise on how Katswe and NSSA have implemented safe markets in other districts. Additional resources from the French Embassy were mobilized to support Gendered Agribusiness for Resilient Markets. Borehole for solarized irrigation with drip irrigation, was installed. The borehole facilitated farming throughout the year as opposed to seasonal rain-fed farming that had dominated agriculture in the communal area. Small holder farmers in Buhera who are doing agribusiness under the Fostering Agribusiness for Resilient Markets (FOGARM) were linked to the market in Mbare. The Fostering Gendered Agribusiness for Resilient Markets (FOGARM) project that seeks to leverage rural women’s entrepreneurship drive to initiate a solar powered agribusiness program that places gender transformative approach & inclusivity at the centre of climate resilience, adaptation initiatives, discourse and programming ahead of possible COVID-19 recovery phase. The project does this through placing gender issues, especially women empowerment and positive masculinity, at the forefront of climate adaptation initiatives. The good partnership with the City of Harare has resulted in the local authority volunteering/ seconding some of its manpower such as architects, engineers, technicians, communications and M and E to support with technical expertise during project implementation.

## RBM-Annual
Indicator | Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Indicator:Number of resilient food and vegetable markets and systems that are safe, responsive to women's needs and fully functional during the Covid-19 outbreak and beyond | 3 | The Hatcliffe market is yet to be completed due to challenges with the contractor and Implementing Partner. However an Ablution facility was built, solar powered borehole and 5000 Litre tank installed | Minutes of meetings, field reports
Baseline:0
Planned Target: 4
Output 1.1 | 3 | An Ablution facility was built, solar powered borehole and 5000 Litre tank installed The Hatcliffe market is yet to be completed due to challenges with the contractor and Implementing Partner. | Minutes of meetings, project reports
Indicator 1.1.1:Number of markets adhering to public and occupational health and safety requirements (including COVID-19) and standards for gender sensitive infrastructure and including green energy solutions
Baseline:1
Planned Target:4
Indicator 1.1.2:Number of gender responsive mechanisms established to prevent and address GBV and harassment in public spaces | 8 | A GBV directory was produced and distributed. 2 trained Gender champions per market to assist in identifying and reporting cases. 3 trained community health clubs are assisting in identifying cases and assisting survivors to access the referral system for services | Field reports, Distribution list
Baseline:1
Planned Target: 8
Indicator 1.1.2: Number of women working in established safe makets | 400+ | More than 3000 women vendors and farmers access the renovated Mbare Mass Market and benefit from other infastructures constructed such as ablution facilities. Many women are directly working from the established market per day since the refurbished market sheds are accessed by women on a daily basis who come to sell their produce and make use of the market stalls in Mbare that were constructed.The market sheds are accessed by different women every day since the market is open to everyone. The markets are also occupied by men who were already occupying the market before the project commencement | Project reports & Council documents
Baseline: 200
Planned Target: 400
Output 1.2 | 148 | The bank ( Women MicroFinance Bank failed to cope with the demand for credit facilities nationwide. To address this challenge, the project then supported the women to establish ISALS as a means of saving and supporting each other with capital. | Field reports, attendance registers
Indicator 1.2.1:Number of women supported to access financial credit facilities
Baseline: 0
Planned Target: 280
Indicator 1.2.2:Number of women with increased capacity in business management including e- commerce |  | No variance | Field reports, attendance registers
Baseline: 0 | 1800
Planned Target: 1800
Indicator 1.2.3:Percentage increase in growth of women businesses |  | No variance
Baseline: 0 |  |  | Field reports
Planned Target: 5%
Output 1.3 | 1 | No variance | platform is in place: http://agritextraining.co.zw/
Indicator 1.3.1: A platform that ensure regular supply of quality produce to women marketers and facilitate electronic sales to a broad range of consumers established
Baseline:0
Planned Target:1
Indicator 1.3.2: Number of women trained on utilisation of the E-platform | 1800 | Women were sensitised on the use of the platform | Training reports and attendance registers
Baseline:0
Planned Target: 1800
Indicator 1.2.3: Proportion of women reporting increased market sales through use of multiple marketing avenues |  |  | Reports
Baseline: 0
Planned Target: 45% (810)
Indicator:Number of gender responsive laws, policies and strategies effectively implemented to facilitate last mile food supply management system in compliance with OSH standards, and address gender differential needs. | 2 | A Gender responsive policy and guiding framework for safe markets and Standard Operating Procedure were developed | Policy document, reports
Baseline:0
Planned Target: 2
Existence of gender responsive policy and guiding framework for safe markets in place | 1 | A Gender responsive policy and guiding framework for safe markets and SoPs were developed and operationalised. A handbook on participatory by- law and policy making was also developed | Reports, Policy document
Baseline: 0
Planned Target: 1
Number of institutions supported to develop and/or review policies, regulations, legal frameworks, by-laws with a gender lens. | 10 | Ministry of Local Government, Ministry of Women Affairs, Ministry of Justice, Harare City Council, Epworth Local Board, Ministry of Agriculture, Ministry of Home affairs, NSSA, Women's bank and KTA | Reports
Baseline: 0
Planned Target: 10
Number of action plans implemented by women trained in transformative leadership to increase their influence in decision making structures within markets and relevant instituions | 10+ | The target was surpassed as the projects facilitated many engagements to support women's participation in decision making processes | Reports
Baseline: 0
Planned Target:4
Number of women’s engagements with key decision makers | 30+ | Since the project was implemented during COVID-19, a lot of engagements were organised by various stakeholders in which women were involved | Field reports
Baseline: 0
Planned Target: 24
Improved women's participation in market leadership structures | 20 | The project supported the creation of committes such as the water point committee, health committee, First Aid and ensured that women were fully represented | Field reports
Baseline: 0
Planned Target: 20

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
Project Documentary Link: https://drive.google.com/file/d/1Eu1WcREy4pXanS6diWb6HwEj1qrM13fm/view
"Taking COVID-19 Vaccination to The Market, a boost for Traders Lucia Kainga getting vaccinated at Hatcliffe Dust Market As COVID-19 spread became more evident in the urban set up of Harare and many other cities, high density communities and dust markets like Hatcliffe would not be spared. For 54-year-old Lucia Kainga staying at home was not an option as trading at the market was her only source of income and staying at home would mean failing to feed her household. For most traders like her, getting vaccinated was only but a distant possibility, as she struggled to access the free vaccine rolled out by the Government at the same time discouraged by the hesitancy around getting vaccinated. “I did not want to get vaccinated because I was told if you get the vaccine you will die, but because of the education and training I received through the Joint Multi-Partner Trust Fund Safe Markets programme being implemented by Helpline- Zimbabwe here in Hatcliffe, I was able to see how important the vaccine is to my health and wellbeing.” said Lucia Kainga. Due to different misconceptions of the vaccine and the disinformation campaign on social media many market traders like Lucia were slow to embrace the vaccine regardless of how dangerously exposed they were while working at the Market. Through support from NSSA an implementing partner of the project, a mobile vaccination center was set up at Hatcliffe dust market to enable unvaccinated marketers to access the vaccine for free. “As a Market trader, I was pleased to be able to get this opportunity to get vaccinated with an understanding of what it meant and how it benefits me, I can now see my family and business surviving this difficult time.” said Lucia An understanding of how the vaccine works and how it benefits the health and wellbeing of the trader’s community in the long term was important in getting traders like Lucia to embrace the vaccine. “I did not know when it was going to be possible for me to get the vaccine, I thank this project and Helpline- Zimbabwe for assisting us, now I can work freely knowing I am protected from getting seriously ill in the event that I contract the COVID-19 virus.” she said "
Clean-Up Campaign to Remove Solid Waste Dumped on Illegal Sites Upon completion of the lessons on PHHE tools, 3 community health clubs namely Good Hope with Long Life, Hutsanana Hupenyu and Jekesa Pfungwa/Noble Ideas came together and planned to clear an illegal dumpsite at Tsiga market as part of the practical session of their lessons. CWA helped the health clubs to acquire a police clearance and to engage other stakeholders to be part of the clean-up campaign. Different stakeholders who include UN-Volunteers, Oxfam, Environmental Management Agency (EMA), Spar Zimbabwe, City of Harare Health department and waste management, Helpline, Zimbabwe Republic Police (ZRP) and Combined Harare Residents Association (CHRA) participated on the event. The facilitators from other community health clubs were also invited to participate taking some notes from clean-up campaign. The exercise could not manage to clear all the garbage at Tsiga market due to unavailability of enough trucks (tippers).
Tinokunda Community Health Club Tinokunda Community Health Club is based in Mashawasha Flats has already started implementing what they are learning through clearing illegal dumpsite in their area. They managed to put all the garbage in one place, and they have approached City of Harare local district offices to provide refuse collection trucks and front loader to clear the garbage to ensure the environment is clean. In addition to illegal dumpsite clearance, Tinokunda Health Club cleaned toilets at Mashawasha flats. The toilets are serving 540 people who reside at Mashawasha flats. Tinokunda Health Club also managed to include Blessing Manditsera a person with physical impairment as one of the club volunteers which is a great step towards inclusiveness.
Good Hope with Long Life There are some outputs already realized from capacity building of Community Health Clubs. Good Hope with Long Life has embarked on a program to improve home hygiene after learning about model homes. All members are contributing $2 every Friday to buy kitchen utensils for members as a way of showing commitment to lead by example. They buy their items and distribute to one member of the group every Monday until they are all covered.
Cleaning kitchen sinks in Mbare flats as part of home hygiene. Mbare flats have often been a centre of disease outbreaks such as cholera and typhoid which are largely caused by poor hygiene conditions. Through the Empowering Women Through Safe, Resilient, Gender Responsive Food Markets and systems in response to covid 19 in Zimbabwe project funded by MPTF, a cleaning kitchen sinks in Mbare flats initiative was done by Maoresa community health club members leading to a transformation in the outlook and hygiene standards of the Kitchens which had been neglected for a long time and becoming a health hazard for citizens. The kitchen sinks are used by approximately 700 people from 7 blocks of Mbare flats. Improvements on hygiene ensures families are protected from possible hygiene related diseases.
Community Based Diseases Surveillance Mechanism saves lives : Communities normally suffer in silence, experiences diseases and sickness that is not reported until it is too late when victims begin to die. Repeatedly such was the case in Mbare. Through the Empowering Women Through Safe, Resilient, Gender Responsive Food Markets and systems in response to covid 19 in Zimbabwe project funded by MPTF, implementing partners mobilised and trained Community Health Clubs in Shawasha. After trainings the Health Clubs were able to detect a number of cases including a diarrhoea case in November 2021. The Health Clubs were quick to alert Community Water Alliance, Oxfam and City of Harare Environmental Health Technician. Patients were quickly attended at a nearby clinic. A rapid needs assessment was carried out on 26 November 2021 and emergency interventions were implemented. After the trainings, There is now a well-co-ordinated disease surveillance mechanism in Mbare where community health clubs work with the district Environmental Health Technician. Outside referring people to relevant duty bearers, community health clubs in Mbare embark on community awareness and sensitization programs in response to emergencies. Door to door sensitization on hygiene promotion were carried out twice as well as sensitization on prevention of sexual and gender-based violence which was done in partnership with Zimbabwe Republic Police Victim Friendly Unit.
WASH detergent production for improved livelihoods and hygiene promotion: As part of the Empowering women through safe, resilient, gender responsive food markets and systems in response to covid 19 in Zimbabwe project Oxfam and CWA trained 168 members picked from 13 community health clubs on WASH detergents production. They were trained on how to produce dishwasher, toilet dip and petroleum jelly (PJ) to earn a living. Mbare citizens are set to improve their livelihoods through production of WASH detergents as a mitigation measure to recover from Covid-19 related shocks. Each community health club managed to produce 20 litres of toilet dip, 20 litres of dishwasher and 20 litres of petroleum jelly during the training. They were given the produced detergents for them to sell generating income as the starting point. After realizing the proceeds from the sales, they purchased more ingredients and start production on their own.
Hygiene Promotion through Public Toilet Rehab and Extension : Limited access to a clean and hygienic toilet facility has always been a big challenge at the Highfield market. In many cases the toilet is overwhelmed and non-factional. Through the Empowering Women Through Safe, Resilient, Gender Responsive Food Markets and systems in response to covid 19 in Zimbabwe project funded by MPTF Under Output 1” Strengthened market food chain supply and decentralisation to other markets in suburbs through rehabilitation of one marketplace” Oxfam in partnership with City of Harare rehabilitated and constructed an extension of Highfield market toilet. Department of Works City Architect division and Oxfam led the technical works and came up with the BOQs and monitored all works which the private contracts were undertaking. A total of 194 market vendors, 68 females, 26 males at the Highfields- Lusaka market were reached through the rehabilitation and construction of the market toilet. The vendors now have access to hygienic toilets which are equipped with shoers for bathing, accessible to people on wheelchairs, equipped with mirrors and connected to alternative source of water. The toilet is manned by city of Harare official and market committee members. Access into the toilet is at a small amount of 100 Zimbabwe Dollars. This amount is for purchasing chemicals for cleaning and assisting in terms of repairs if anything breaks down.
Construction in progress, borehole Drilling a success at the construction site of #Hatcliffe #safemarket. Installation of tank, solar panel and tap complete today. Un interupted supply of water will ensure improved hygene condition for vendors and the local community.
Community Health Clubs Taking a Lead Role on Clean Environment and Home Hygiene: Through the Empowering Women Through Safe, Resilient, Gender Responsive Food Markets and systems in response to covid 19 in Zimbabwe project funded by MPTF , Oxfam and Community Water Alliance working in partnership with City of Harare Environmental Health Technician, trained 10 Community Health Club Facilitators on WASH and health care issues, door to door hygiene promotion, the human right to health, gender, community mapping, social problems in Mbare hygiene (personal, home, and general hygiene) and community-based disease surveillance mechanisms. Participants were trained on various topics which included Participatory Health and Hygiene Education (PHHE) concept for health club formation within Mbare working together with the EHT complementing government efforts in preventing Covid-19 and other diseases such as Cholera, Typhoid, T.B, Malaria, HIV, STIs, Diabetics, Hypertension, Cancer, Bilharzia and Impairment. After Training the community health volunteers working with the Environmental Health Technician, established 13 Community Health Clubs with a combined membership of 250 people (CHC) and supported them with Participatory Health and Hygiene Education tools. After the establishment and training the Community Health Clubs where able to achieve the following: 1) Clean-Up Campaign to Remove Solid Waste Dumped on Illegal Sites Upon completion of the lessons on PHHE tools, 3 community health clubs namely Good Hope with Long Life, Hutsanana Hupenyu and Jekesa Pfungwa/Noble Ideas came together and planned to clear an illegal dumpsite at Tsiga market and other public places as part of the practical session of their lessons. CWA helped the health clubs to acquire a police clearance and to engage other stakeholders to be part of the clean-up campaign. Different stakeholders who include UN-Volunteers, Oxfam, Environmental Management Agency (EMA), Spar Zimbabwe, City of Harare Health department and waste management, Helpline, Zimbabwe Republic Police (ZRP) and Combined Harare Residents Association (CHRA) participated on the event. The facilitators from other community health clubs were also invited to participate taking some notes from clean-up campaign. The exercise could not manage to clear all the garbage at Tsiga market due to unavailability of enough trucks (tippers) from City of Harare. Several dumpsites were however had dumped waste cleared.
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
News Links: https://dailynews.co.zw/decentralise-vending-points-to-fight-covid-19/ https://www.kwayedza.co.zw/vechidiki-vodzidziswa-nezvecovid-19/ https://www.kwayedza.co.zw/vorwisa-huchapa-munharaunda/ https://www.kwayedza.co.zw/vodzidziswa-nezvecovid/ https://www.facebook.com/corahfm/videos/1002737477177501/?app=fbl https://www.facebook.com/corahfm/videos/833483577237806/?app=fbl https://www.facebook.com/corahfm/videos/159100376374754/?app=fbl https://www.facebook.com/2179437298962520/posts/2961577374081838/?app=fbl https://www.kwayedza.co.zw/kutora-zvinodhaka-covid-nevechidiki/ https://www.facebook.com/CommunityWaterAlliance/posts/a-2-day-mptf-safe-markets-program-planning-and-accelerated-delivery-session-is-c/4383934478392042/ https://www.zw.undp.org/content/zimbabwe/en/home/stories/harnessing-digital-solutions-for-the-resilience-of-urban-food-su.html :https://twitter.com/helplinezim/status/1526529635852464129/photo/1
Vendor's life through Covid-19 in Harare https://youtu.be/7GVj_8fIAR8
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number |  | Programme Duration
Programme Title: | Empowering women through safe, resilient, gender responsive food markets and systems in response to covid 19 in Zimbabwe | Overall Duration (months) | 18 Months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | October, 2019
MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy) | 2022-04-30
Country | Zimbabwe | Current End date(dd.mm.yyyy) | 2022-09-30
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UN Women, UNDP, and ILO | National counterparts (government, private, NGOs & others) and other International Organizations | NSSA, Helpline- Zimbabwe, Oxfam, Community Water Alliance, Knowledge Transfer Africa, DEGI
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
_ftn1
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
_ftnref1

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board