## IOM format (hidden)
Budget Consumption Report by Project Structure
Project ID | IB.0315
Project Name | Cross-border cooperation Gambia Senegal
From | 001 2000
To | 005 2022
Budget From | 001 2000
To | 012 2045
Currency | USD
Date | Date & Time:13.06.2022-14.28.29
Time | User Name:ETOKGOZ
Project Structure: Description |  | Description | Currency | Budget | Revenue | Expense | Pre-Commitment | Commitment | Available Balance | Project Balance | % Budget Consumption | % Available Balance | % Exp | % Exp & Comm & Pre-C | Proj. Start | Proj. End
IB.0315 |  | Cross-border cooperation Gambia Senegal | USD | 1400000.04 | 0 | 41879.53 | 64256.34 | 503.94 | 1357616.57 | 1293360.23 | 3% | 97% | 3% | 8% | 14.12.2021 | 14.12.2023 |  | Budget | Expenditure | Burn Rate
IB.0315.GM10.10.01.001 |  | Chief of Mission | USD | 31920 | 0 | 691.13 | 0 | 0 | 31228.87 | 31228.87 | 2% | 98% | 2% | 2% | 14.12.2021 | 14.12.2023 | Additional personnel costs | 31920 | 691.13 | 2.165%
IB.0315.GM10.10.02.001 |  | Programme Coordinator | USD | 140400 | 0 | 23436.44 | 0 | 0 | 116963.56 | 116963.56 | 17% | 83% | 17% | 17% | 14.12.2021 | 14.12.2023 | Additional personnel costs | 140400 | 23436.44 | 16.69%
IB.0315.GM10.10.04.001 |  | Resource Management Officer | USD | 29040 | 0 | 3698.94 | 0 | 0 | 25341.06 | 25341.06 | 13% | 87% | 13% | 13% | 14.12.2021 | 14.12.2023 | Additional personnel costs | 29040 | 3698.94 | 12.74%
IB.0315.GM10.11.02.001 |  | National Programme Officer | USD | 36000 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Additional personnel costs | 36000 | 0 | 0%
IB.0315.GM10.11.02.002 |  | MIDAS Senior Project Assistant | USD | 11400 | 0 | 538.89 | 0 | 0 | 10861.11 | 10861.11 | 5% | 95% | 5% | 5% | 14.12.2021 | 14.12.2023 | Additional personnel costs | 11400 | 538.89 | 4.727%
IB.0315.GM10.11.02.003 |  | Project Assistant -IBM | USD | 8160 | 0 | 321.61 | 0 | 0 | 7838.39 | 7838.39 | 4% | 96% | 4% | 4% | 14.12.2021 | 14.12.2023 | Additional personnel costs | 8160 | 321.61 | 3.941%
IB.0315.GM10.11.02.004 |  | M&E Senior Project Assistant | USD | 13800 | 0 | 0 | 0 | 0 | 13800 | 13800 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Additional personnel costs | 13800 | 0 | 0%
IB.0315.GM10.11.02.005 |  | Senior Project Assistant -Livelihoods | USD | 16800 | 0 | 0 | 0 | 0 | 16800 | 16800 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Additional personnel costs | 16800 | 0 | 0%
IB.0315.GM10.11.02.006 |  | Project Administrative Assistant -IBM | USD | 16800 | 0 | 255.02 | 0 | 0 | 16544.98 | 16544.98 | 2% | 98% | 2% | 2% | 14.12.2021 | 14.12.2023 | Additional personnel costs | 16800 | 255.02 | 1.518%
IB.0315.GM10.11.04.001 |  | Resource Management L | USD | 21600 | 0 | 425.56 | 0 | 0 | 21174.44 | 21174.44 | 2% | 98% | 2% | 2% | 14.12.2021 | 14.12.2023 | Additional personnel costs | 21600 | 425.56 | 1.97%
IB.0315.GM10.12.01.001 |  | Building Office Premises | USD | 17280 | 0 | 252.89 | 0 | 0 | 17027.11 | 17027.11 | 1% | 99% | 1% | 1% | 14.12.2021 | 14.12.2023 | Additional Operational Costs | 17280 | 252.89 | 1.463%
IB.0315.GM10.12.02.001 |  | Travel Sub Rep ( local & International) | USD | 12000 | 0 | 237.56 | 0 | 0 | 11762.44 | 11762.44 | 2% | 98% | 2% | 2% | 14.12.2021 | 14.12.2023 | Additional Operational Costs | 12000 | 237.56 | 1.98%
IB.0315.GM10.12.03.001 |  | Communications O | USD | 14400 | 0 | 778.02 | 0 | 0 | 13621.98 | 13621.98 | 5% | 95% | 5% | 5% | 14.12.2021 | 14.12.2023 | Additional Operational Costs | 14400 | 778.02 | 5.403%
IB.0315.GM10.12.04.001 |  | Vehicle cost fuel and maintanance | USD | 7200 | 0 | 9.42 | 0 | 0 | 7190.58 | 7190.58 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Additional Operational Costs | 7200 | 9.42 | 0.1308%
IB.0315.GM10.12.06.001 |  | Office Furniture and Equipment | USD | 12000 | 0 | 5925.02 | 0 | 282.59 | 5792.39 | 5792.39 | 52% | 48% | 49% | 52% | 14.12.2021 | 14.12.2023 | Additional Operational Costs | 12000 | 5925.02 | 49.38%
IB.0315.GM10.12.08.001 |  | Supplies Materials O | USD | 4800 | 0 | 86.91 | 0 | 188.39 | 4524.7 | 4524.7 | 6% | 94% | 2% | 6% | 14.12.2021 | 14.12.2023 | Additional Operational Costs | 4800 | 86.91 | 1.811%
IB.0315.GM10.12.09.001 |  | Security Moss Morss O | USD | 14400 | 0 | 567.19 | 0 | 0 | 13832.81 | 13832.81 | 4% | 96% | 4% | 4% | 14.12.2021 | 14.12.2023 | Additional Operational Costs | 14400 | 567.19 | 3.939%
IB.0315.GM10.12.10.001 |  | Others (bank charges, miscellaneous expe | USD | 12000 | 0 | 26.5 | 0 | 0 | 11973.5 | 11973.5 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Additional Operational Costs | 12000 | 26.5 | 0.2208%
IB.0315.GM10.D3.12.001 |  | Support grants for youth and women led g | USD | 89000 | 0 | 0 | 0 | 0 | 89000 | 89000 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Activity 3.1.2 | 89000 | 0 | 0%
IB.0315.GM10.D3.12.002 |  | Support for cross-border community livel | USD | 60000 | 0 | 0 | 0 | 0 | 60000 | 60000 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Activity 3.1.3 | 60000 | 0 | 0%
IB.0315.GM10.D3.13.001 |  | Construct & equip one new immigrtaion p | USD | 155000 | 0 | 0 | 0 | 0 | 155000 | 155000 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Activity 1.2.1 | 155000 | 0 | 0%
IB.0315.GM10.D3.13.002 |  | Equip border facilities with furniture, | USD | 25000 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Activity 1.2.2 | 25000 | 0 | 0%
IB.0315.GM10.D4.01.001 |  | Develop community engagement plans to ad | USD | 20000 | 0 | 0 | 0 | 0 | 20000 | 20000 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Activity 1.3.2 | 20000 | 0 | 0%
IB.0315.GM10.D4.01.002 |  | Social mobilization and awareness traini | USD | 25000 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Activity 1.4.1 | 25000 | 0 | 0%
IB.0315.GM10.D4.01.003 |  | Cross-border social mobilization and awa | USD | 25000 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Activity 1.4.2 | 25000 | 0 | 0%
IB.0315.GM10.D4.02.001 |  | Sensitization & trainings on the ECOWAS | USD | 25000 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Activity 1.1.1: | 25000 | 0 | 0%
IB.0315.GM10.D4.02.002 |  | Trainings on mediation, conflict resolut | USD | 15000 | 0 | 0 | 0 | 0 | 15000 | 15000 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Activity 1.1.2: | 15000 | 0 | 0%
IB.0315.GM10.D4.03.001 |  | Joint training of border communities wit | USD | 30000 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Activity 1.1.3: | 30000 | 0 | 0%
IB.0315.GM10.N1.01.001 |  | Support inter-agency border coordination | USD | 15000 | 0 | 0 | 0 | 0 | 15000 | 15000 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Activity 1.5.1 | 15000 | 0 | 0%
IB.0315.GM10.N1.01.002 |  | Support cross-border inter-agency coordi | USD | 25000 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Activity 1.5.2 | 25000 | 0 | 0%
IB.0315.GM10.N1.03.001 |  | Joint cross-border training of border au | USD | 25000 | 0 | 0 | 0 | 0 | 25000 | 25000 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Activity 1.1.4 | 25000 | 0 | 0%
IB.0315.GM10.N1.03.002 |  | Training of border officials on organize | USD | 15000 | 0 | 1277.32 | 52.66 | 0 | 13722.68 | 13670.02 | 9% | 91% | 9% | 9% | 14.12.2021 | 14.12.2023 | Activity 1.2.3 | 15000 | 1277.32 | 8.515%
IB.0315.GM10.N1.03.003 |  | Advanced and Basic MIDAS training for bo | USD | 20000 | 0 | 0 | 0 | 0 | 20000 | 20000 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Activity 1.6.2 | 20000 | 0 | 0%
IB.0315.GM10.N1.04.001 |  | Joint cross- border trainings for border | USD | 15000 | 0 | 0 | 0 | 0 | 15000 | 15000 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Activity 1.2.4 | 15000 | 0 | 0%
IB.0315.GM10.N1.12.001 |  | Assessment & Installation of MIDAS at Da | USD | 95000 | 0 | 65.05 | 0 | 0 | 94934.95 | 94934.95 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Activity 1.6.1 | 95000 | 65.05 | 0.06847%
IB.0315.GM10.OH |  | Overhead | USD | 91588.83 | 0 | 2739.8 | 4203.68 | 32.96 | 88816.07 | 84612.39 | 3% | 97% | 3% | 8% | 14.12.2021 | 14.12.2023 |  | 91588.83 | 2739.8 | 2.991%
IB.0315.GM10.Q1.01.001 |  | Psychosocial baseline assessments at tar | USD | 15000 | 0 | 0 | 0 | 0 | 15000 | 15000 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Activity 1.3.1 | 15000 | 0 | 0%
IB.0315.GM10.Q1.01.002 |  | Assessment for alternative green livelih | USD | 14411 | 0 | 0 | 0 | 0 | 14411 | 14411 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Activity 3.1.1 | 14411 | 0 | 0%
IB.0315.GM10.Q1.03.001 |  | Project Monitoring | USD | 80000.21 | 0 | 546.26 | 60000 | 0 | 79453.95 | 19453.95 | 1% | 99% | 1% | 76% | 14.12.2021 | 14.12.2023 | Monitoring budget | 80000.21 | 546.26 | 0.6828%
IB.0315.GM10.Q1.05.001 |  | Evaluation | USD | 80000 | 0 | 0 | 0 | 0 | 80000 | 80000 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Budget for independent final evaluation | 80000 | 0 | 0%
IB.0315.GM10.Q2.03.001 |  | Visibility | USD | 20000 | 0 | 0 | 0 | 0 | 20000 | 20000 | 0% | 100% | 0% | 0% | 14.12.2021 | 14.12.2023 | Monitoring budget | 20000 | 0 | 0%
[18 empty] | 1400000.04 | 41879.53 | 2.991%

## Report
Annex D - PBF Project Budget
Table 1 - PBF project budget by outcome, output and activity
Outcome/ Output number | Description (Text) | Recipient Organization 1 | Recipient Organization 2 Budget | Recipient Organization 3 Budget | Recipient Organization 4 Budget | Total Expenditure | Total Budget | Burn Rate
|  | IOM The Gambia | IOM SENEGAL | FAO The Gambia | FAO Senegal
OUTCOME 1: | Enhanced engagement between communities and border management authorities for improved border management.
Output 1.1: | Strengthening communication and capacity building of border officials in communicating border procedures, mediating, building trust, conflict resolution, developing effective approaches to addressing community concerns, and conveying the public’s concerns to law enforcement management.
Activity 1.1.1: | Sensitization & trainings on the ECOWAS Free Movement Protocol & border procedures | 0 |  |  |  | 0 | 45000 | 0%
Activity 1.1.2: | Trainings on mediation, conflict resolution and trust building targeting border officials at 4 border posts ( Senegal & The Gambia) Target : 4 trainings in Senegal & 4 trainings in The Gambia targeting the border | 0 |  |  |  | 0 | 25000 | 0%
Activity 1.1.3: | Joint training of border communities with a focus on enhancing capacity to engage with border authorities to report concerns and crime ( Senegal & The Gambia) Target: 2 joint trainings per year | 0 |  |  |  | 0 | 55000 | 0%
Activity 1.1.4 | Joint cross-border training of border authorities on mediation, conflict resolution and trust building ( Senegal & The Gambia) Target: 2 joint trainings per year | 0 |  |  |  | 0 | 45000 | 0%
| Output Total | 0 | 0 | 0 | 0 | 0 | 170000 | 0%
Output 1.2: | Enhance border operational capacities through improved infrastructure, equipment and trainings of border officials on organized cross-border crime, document security, and protection of vulnerable migrants to improve effectiveness of service delivery and community safety
Activity 1.2.1 | Construct & equip one new immigrtaion post in CRR, The Gambia | 2214.27 |  |  |  | 2214.27 | 155000 | 1.429%
Activity 1.2.2 | Equip border facilities with furniture, equipment & border security tools ( 8 border posts provide with furniture, equipment & border security tools) | 0 |  |  |  | 0 | 122000 | 0%
Activity 1.2.3 | Training of border officials on organized crime & document security & protection of vulnerable migrants targeting 8 border posts ( 2 trainings per year x 2yrs = 4 trainings in each country) =target officials trained =100 | 6474.36 | 0 |  |  | 6474.36 | 25000 | 25.9%
Activity 1.2.4 | Joint cross- border trainings for border officials on organized crime, document security & protection of vulnerable migrants ( 1 joint training per year x2 = 2 joint cross-border trainings ) The Gambia & Senegal | 0 |  |  |  | 0 | 25000 | 0%
| Output Total | 8688.63 | 0 | 0 | 0 | 8688.63 | 327000
Output 1.3: | Enhance community cross-border partnerships through rebuilding trust between the law enforcement and the community and encouraging communities to work collaboratively with border authorities in setting priorities and developing and implementing local anti-cross-border crime strategies/plans
Activity 1.3.1 | Psychosocial baseline assessments at targeted border communities aimed at providing analytical insights into the perception of communities on safety and security ( done for 4 border communities ) | 0 |  |  |  | 0 | 35000 | 0%
Activity 1.3.2 | Develop community engagement plans to address cross-border crimes ( engagement plans available for 4 communities) | 0 |  |  |  | 0 | 40000 | 0%
| Output Total | 0 | 0 | 0 | 0 | 0 | 75000 | 0%
Output 1.4: | Community engagement and mobilization events to promote a collaborative relationship between communities and law enforcement agencies to improve social cohesion and peaceful coexistence in cross-border communities
Activity 1.4.1 | Social mobilization and awareness trainings, focus is trust building and promoting dialogue for peacebuilding ( Target 4 border communities in each country, x 2 events per year = 8 events ) | 351.74 |  |  |  | 351.74 | 50000 | 0.7035%
Activity 1.4.2 | Cross-border social mobilization and awareness trainings, focus is trust building and promoting dialogue for peacebuilding & social cohesion ( Target 4 cross- border communities, X 1 cross-border event in each community = 4 cross border events) | 0 |  |  |  | 0 | 45000 | 0%
| Output Total | 351.74 | 0 | 0 | 0 | 351.74 | 95000 | 0.3703%
Output 1.5: | Strengthen inter-agency and cross-border cooperation and exchanges among border authorities in both countries national and local levels for improved border coordination mechanisms to address cross border crime.
Activity 1.5.1 | Support inter-agency border coordination committees meetings ( 4 meetings per year X 4 borders= 16 meetings ) in each country | 12616.2 |  |  |  | 12616.2 | 30000 | 42.05%
Activity 1.5.2 | Support cross-border inter-agency coordination committee meeting ( 2 meetings per year x 4 = 8 cross- border meetings ) The Gambia & Senegal | 0 |  |  |  | 0 | 45000 | 0%
| Output Total | 12616.2 | 0 | 0 | 0 | 12616.2 | 75000 | 16.82%
Output 1.6: | Install Migration Information and Data Analysis System (MIDAS) in The Gambia (Senegal already has a border management system) this will allow for data collection & intelligence exchange for risk analysis of travelers to avert cross-border crime
Activity 1.6.1 | Assessment & Installation of MIDAS at Darsilami border posts ( Target = 3 work stations + 1Solar installation + Furniture + LANs ) | 86196.9 |  |  |  | 86196.9 | 95000 | 90.73%
Activity 1.6.2 | Advanced and Basic MIDAS training for border officials ( 2 trainings per year x3 = 6 trainings ) | 730.95 |  |  |  | 730.95 | 20000 | 3.655%
| Output Total | 86927.85 | 0 | 0 | 0 | 86927.85 | 115000 | 75.59%
OUTCOME 2:
Outcome 2.1 | Joint border comunities' solutions to address continued deforestation and forest degradation developed and implemented
Activity 2.1.1 | Identification and mapping of transboundary forest fire hot spots |  |  |  | 10113.492 | 10113.492 | 33713.18 | 30%
Activity 2.1.2 | Cross-border consultation and dialogue meetings before project implementation |  |  | 13464.17 | 15170.238 | 28634.408 | 63440.62 | 45.14%
Activity 2.1.3 | Sensitization of border commuities on transboundary forest fire protection and management |  |  |  |  | 0 | 18000 | 0%
Activity 2.1.4 | Development of natural resources managment plans (including fire management plans) |  |  |  |  | 0 | 30000 | 0%
Activity 2.1.5 | Formation of cross-border fire management Committees |  |  |  |  | 0 | 24000 | 0%
Activity 2.1.6 | Train villagers on good environmental governance including community charters and other participatory approaches that support sustainable cross border forest management |  |  |  |  | 0 | 35000 | 0%
Activity 2.1.7 | Povide firefighting materials/equipment to border fire management Committees |  |  |  | 8075.47 | 8075.47 | 65000 | 12.42%
Activity 2.1.8 | Conduct controlled early burning along transboundary fire hots spots |  |  |  |  | 0 | 20000 | 0%
Activity 2.1.9 | Provision of seedlings and organize tree planting exercises on degraded landscapes along the border |  |  | 34475.94 | 7993.19 | 42469.13 | 65000 | 65.34%
Activity 2.1.10 | Organize exchange visits among border communities to share best practices on matters related to natural resources management |  |  |  |  | 0 | 40000 | 0% | 71719.65
| Output Total | 0 | 0 | 47940.11 | 41352.39 | 89292.5 | 394153.8 | 22.65%
Output 2.2
Activity 2.2.1 | Sensitize and train law enforcement authorities at boders posts on the forest legislative frameworks of The Gambia and Senegal |  |  |  |  | 0 | 20923.64 | 0%
Activity 2.2.2 | Sensitize timber and forest products dealers and their affiliated associations on the forest legislative frameworks of The Gambia and Senegal |  |  |  | 5900 | 5900 | 20000 | 29.5%
Activity 2.2.3 | Implement 50 agrpastoral field school to streghtenen technical capacities |  |  |  | 4621.24 | 4621.24 | 20000 | 23.11%
Activity 2.2.4 | Sensitize border communities on the forest legislative frameworks of The Gambia and Senegal |  |  | 3154.32 |  | 3154.32 | 25000 | 12.62%
Activity 2.2.5 | Develop and disseminate awareness-raising messages (forum and community radio, use of traditional communicators) |  |  |  |  | 0 | 27573.64 | 0%
Activity 2.2.6 | Sesitize border communities on participatory forest management approaches including community forestry, Joint Forest Park Management and range management |  |  |  | 4425 | 4425 | 20000 | 22.12%
Activity 2.2.7 | implement 30 Dimitra Clubs for inclusive communication at community level |  |  |  | 3248.54 | 3248.54 | 30000 | 10.83%
Activity 2.2.8 | Develop a joint border tracking compliance mechanism/database at border posts taken into consideration, a forest produce delaration form, timber and charcoal production permit/license, movement permit etc. |  |  | 10000 |  | 10000 | 25000 | 40%
Activity 2.2.9 | Provide needed equipment (laptops) and train national and regional actors to maintain the compliance mechanism/system |  |  | 3546 |  | 3546 | 20000 | 17.73%
| Output Total | 0 | 0 | 16700.32 | 18194.78 | 34895.1 | 208497.28 | 16.74%
Output 2.3 | Technical capacity of staff of the Department of Livestock Services (DLS) on transboundary livestock disease surveillance and IPM enhanced
Activity 2.3.1 | Sensitize and train PPS and Livestock staff on plant and animal pest surveillance cross-border regulatory frameworks |  |  |  |  | 0 | 20000 | 0%
Activity 2.3.2 | Support PPS and DLS with equipment and other necessary materials to facilitate cross-border plant and animal pest and disease sruveillance and reporting |  |  |  |  | 0 | 20000 | 0%
| Output Total | 0 | 0 | 0 | 0 | 0 | 40000 | 0%
Output 2.4 | Livestock monitoring and management systems to mitigate theft and cattle rustling by both the authorities and local border communities strengthened/introduced
Activity 2.4.1 | Scale-up the livestock identification system in place to all the project sites (tagging) |  |  |  |  | 0 | 15000 | 0%
Activity 2.4.2 | Establish livestock watering points at strategic locations along the identified border areas |  |  | 99.37 |  | 99.37 | 139888.92 | 0.07103%
Activity 2.4.3 | Estalishment of local conventions on sustainable grazing and natural resources management through border community participation |  |  |  |  | 0 | 55000 | 0%
Activity 2.4.4 | Train border communities and herders/transhumance on rangeland mangement |  |  |  |  | 0 | 9000 | 0%
Activity 2.4.5 | Re-dermarcation/marking of livestock tracks and grazinging areas |  |  | 1147.71 |  | 1147.71 | 80450 | 1.427%
Activity 2.4.6 | Mapping of transhumance corridors |  |  |  |  | 0 | 29992.62 | 0%
| Output Total | 0 | 0 | 1247.08 | 0 | 1247.08 | 329331.54 | 0.3787%
OUTCOME 3: | Improved community resilience through the promotion of inclusive dialogue processes and support for alternative green livelihoods
Output 3.1 | Support for alternative green livelihoods for border communities for their adaptation and increased social cohesion targeting women and youth.
Activity 3.1.1 | Assessment for alternative green livelihoods in 4 border communities | 244.45 |  | 244.45 |  | 488.9 | 29345.58 | 1.666%
Activity 3.1.2 | Support grants for youth and women led green livelihoods initiatives -on technical skills & ( Target 20 youths in each border community x 6 = 90 ) | 0 |  | 0 |  | 0 | 178000 | 0%
Activity 3.1.3 | Support for cross-border community livelihoods as a peace devident ( 1 cross- border community based livelihood activity identified & supported X 3 = 3 cross-border community based livelihoods supported ) | 0 |  | 0 |  | 0 | 120000 | 0%
| Output Total | 244.45 | 0 | 244.45 | 0 | 488.9 | 327345.58 | 0.1494%
Output 3.2: | Integrated climate resilient strategies for diversified livelihoods strengthened/introduced and sources of income improved for vulnerable border comunities
Activity 3.2.1 | Establisment of community gardens with durable fences and reliable water supply (boreholes with solar operating pumps) |  |  | 6322.03 |  | 6322.03 | 255436.82 | 2.475%
Activity 3.2.2 | Training of 200 young people to develop skills (Productive capacity building and skills development for youth employability and entrepreneurship). |  |  |  | 4425 | 4425 | 70000 | 6.321%
Activity 3.2.3 | Support vulnerable farmers with vegetable seeds on refund mechanism |  |  |  |  | 0 | 5000 | 0%
Activity 3.2.4 | Train women and youth stakeholders on agro-sylvo-pastoral and honey value chains and entrepreneurship (processing, value addition, marketing etc.) |  |  |  |  | 0 | 28000 | 0%
Activity 3.2.5 | Organize two exposure visits outside project zones to expose value chain stakeholders to entrepreneurial practices |  |  |  |  | 0 | 10000 | 0%
Activity 3.2.6 | Training border women and youth groups on modern beekeeping |  |  |  |  | 0 | 6000 | 0%
Activity 3.2.7 | Train women and youth farmers on construction of prototypes of low-cost improved stoves, Kenyan Top Bar beehives and disseminate across the project area |  |  |  |  | 0 | 41000 | 0%
Activity 3.2.8 | Provision of beehives (Kenyan Top Bar -KTB) |  |  |  |  | 0 | 34000 | 0%
Activity 3.2.9 | Provision of beekeeping and agro-sylvo-pastoral processing equipment for women and youth groups in the project areas |  |  |  | 7747.48 | 7747.48 | 65636.64 | 11.8%
| Output Total | 0 | 0 | 6322.03 | 12172.48 | 18494.51 | 515073.46 | 3.591%
Output 3.3
Activity 3.3.1 | Support women and youth group involved in processing of agro-sylvo-pastoral with small processing equipment |  |  |  |  | 0 | 10000 | 0%
| Output Total | 0 | 0 | 0 | 0 | 0 | 10000 | 0%
Additional personnel costs | Project personnel costs if not included in activities above | 105663.01 |  |  |  | 105663.01 | 486520 | 21.72%
Additional Operational Costs | Project operational costs if not included in activities above | 37595.6 |  |  |  | 37595.6 | 138480 | 27.15%
Monitoring budget | Project M&E budget : Baseline assessment, Project coordination meetimgs, monitoring, and visibility | 25708.57 |  |  |  | 25708.57 | 165000.2149 | 15.58%
Budget for independent final evaluation | Final Evaluation | 0 |  |  |  | 0 | 80000 | 0%
| Total Additional Costs | 168967.18 | 0 | 0 | 0 | 168967.18 | 870000.2149 | 19.42%
Total Expenditures
|  | Recipient Organization 1 | Recipient Organization 2 | Recipient Organization 3 | Recipient Organization 4
|  | IOM The Gambia | IOM SENEGAL | FAO The Gambia | FAO Senegal | Total Expenditure
| Sub-Total | 277796.05 | 0 | 72453.99 | 71719.65 | 421969.69
| Indirect support costs (7%): | 19445.7235 | 0 | 5071.7793 | 5020.3755 | 29537.8783
| Total | 297241.7735 | 46049 | 77525.7693 | 76740.0255 | 497556.5683
Total Budget
|  | Recipient Organization 1 | Recipient Organization 2 | Recipient Organization 3 | Recipient Organization 4 | Total
|  | IOM The Gambia | IOM SENEGAL | FAO The Gambia | FAO Senegal
| Sub-Total Project Budget | 1308411.2149 | 700934.58 | 934579.44 | 607476.64 | 3551401.8749
| Indirect support costs (7%): | 91588.785 | 49065.4206 | 65420.5608 | 42523.3648 | 248598.1312
| Total | 1399999.9999 | 750000.0006 | 1000000.0008 | 650000.0048 | 3800000.0061
Total Burn Rates
|  | Recipient Organization 1 | Recipient Organization 2 | Recipient Organization 3 | Recipient Organization 4 | Total
|  | IOM The Gambia | IOM SENEGAL | FAO The Gambia | FAO Senegal
| Sub-Total Project Budget | 21.23% | 0% | 7.753% | 11.81% | 11.88%
| Indirect support costs (7%): | 21.23% | 0% | 7.753% | 11.81% | 11.88%
| Total | 21.23% | 6.14% | 7.753% | 11.81% | 13.09%

## FAOGM (hidden)
Annex D - PBF Project Budget
Instructions:
1. Only fill in white cells. Grey cells are locked and/or contain spreadsheet formulas. 2. Complete both Sheet 1 and Sheet 2. a) First, prepare a budget organized by activity/output/outcome in Sheet 1. (Activity amounts can be indicative estimates.) b) Then, divide each output budget along UN Budget Categories in Sheet 2. 3. Be sure to include % towards Gender Equality and Women's Empowerment 3. Do not use Sheet 4 or 5, which are for MPTF and PBF use. 4. Leave blank any Organizations/Outcomes/Outputs/Activities that aren't needed. DO NOT delete cells. 5. Do not adjust tranche amounts without consulting PBSO.
Table 1 - PBF project budget by outcome, output and activity
Outcome/ Output number | Description (Text) | Recipient Organization 1 Budget | Recipient Organization 2 Budget | Recipient Organization 3 Budget | Recipient Organization 4 Budget | Recipient Organization 5 Budget | Recipient Organization 6 Budget | Total | % of budget per activity allocated to Gender Equality and Women's Empowerment (GEWE) (if any): | Current level of expenditure/ commitment (To be completed at time of project progress reporting) | Any remarks (e.g. on types of inputs provided or budget justification, esp. for TA or travel costs)
OUTCOME 1:
Output 1.1:
Activity 1.1.1: | [7 empty] | 0
Activity 1.1.2: | [7 empty] | 0
Activity 1.1.3: | [7 empty] | 0
Activity 1.1.4 | [7 empty] | 0
Activity 1.1.5 | [7 empty] | 0
Activity 1.1.6 | [7 empty] | 0
Activity 1.1.7 | [7 empty] | 0
Activity 1.1.8 | [7 empty] | 0
| Output Total | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Output 1.2:
Activity 1.2.1 | [7 empty] | 0
Activity 1.2.2 | [7 empty] | 0
Activity 1.2.3 | [7 empty] | 0
Activity 1.2.4 | [7 empty] | 0
Activity 1.2.5 | [7 empty] | 0
Activity 1.2.6 | [7 empty] | 0
Activity 1.2.7 | [7 empty] | 0
Activity 1.2.8 | [7 empty] | 0
| Output Total | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Output 1.3:
Activity 1.3.1 | [7 empty] | 0
Activity 1.3.2 | [7 empty] | 0
Activity 1.3.3 | [7 empty] | 0
Activity 1.3.4 | [7 empty] | 0
Activity 1.3.5 | [7 empty] | 0
Activity 1.3.6 | [7 empty] | 0
Activity 1.3.7 | [7 empty] | 0
Activity 1.3.8 | [7 empty] | 0
| Output Total | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Output 1.4:
Activity 1.4.1 | [7 empty] | 0
Activity 1.4.2 | [7 empty] | 0
Activity 1.4.3 | [7 empty] | 0
Activity 1.4.4 | [7 empty] | 0
Activity 1.4.5 | [7 empty] | 0
Activity 1.4.6 | [7 empty] | 0
Activity 1.4.7 | [7 empty] | 0
Activity 1.4.8 | [7 empty] | 0
| Output Total | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
OUTCOME 2: | Enhanced cross-border natural resource management through a community-based participatory approach
Output 2.1 | Joint border comunities' solutions to address continued deforestation and forest degradation developed and implemented
Activity 2.1.1 | Identification and mapping of transboundary forest fire hot spots | 10000 | [5 empty] | 10000
Activity 2.1.2 | Sensitization of border commuities on transboundary forest fire protection and management | 9000 | [5 empty] | 9000
Activity 2.1.3 | Formation of cross-border fire management Committees | 6000 | [5 empty] | 6000
Activity 2.1.4 | Develop cross-border fire management plans with the border communities | 6000 | [5 empty] | 6000
Activity 2.1.5 | Povide firefighting materials/equipment to border fire management Committees | 40000 | [5 empty] | 40000
Activity 2.1.6 | Conduct controlled early burning along transboundary fire hots spots | 10000 | [5 empty] | 10000
Activity 2.1.7 | Provision of seedlings and organize tree planting exercises on degraded landscapes along the border | 40000 | [5 empty] | 40000
Activity 2.1.8 | Organize exchange visits among border communities to share best practices on matters related to natural resources management | 30000 | [5 empty] | 30000
| Output Total | 151000 | 0 | 0 |  |  |  | 151000 | 0 | 0
Output 2.2 | Increased awareness and capacity of law enforcement agents including forestry officers at border posts, and other actors (border communities and timber and forest products associations/dealers) on the Forest Policy, Forest Act and Regulations of The Gambia and Senegal to improve compliance mechanism to address illegal logging and charcoal production and trade across the border
Activity 2.2.1 | Sensitize and train law enforcement authorities at boders posts on the forest legislative frameworks of The Gambia and Senegal | 8000 | [5 empty] | 8000
Activity 2.2.2 | Sensitize timber and forest products dealers and their affiliated associations on the forest legislative frameworks of The Gambia and Senegal | 10000 | [5 empty] | 10000
Activity 2.2.3 | Sensitize border communities on the forest legislative frameworks of The Gambia and Senegal | 10000 | [5 empty] | 10000
Activity 2.2.4 | Sesitize border communities on participatory forest management approaches including community forestry, Joint Forest Park Management and range management | 10000 | [5 empty] | 10000
Activity 2.2.5 | Develop a joint border tracking compliance mechanism/database at border posts taken into consideration, a forest produce delaration form, timber and charcoal production permit/license, movement permit etc. | 10000 | [5 empty] | 10000
Activity 2.2.6 | Provide needed equipment (laptops) and train national and regional actors to maintain the compliance mechanism/system | 10000 | [5 empty] | 10000
Activity 2.2.7 | [7 empty] | 0
Activity 2.2.8 | [7 empty] | 0
| Output Total | 58000 | 0 | 0 |  |  |  | 58000 | 0 | 0
Output 2.3 | Technical capacity of staff of the Department of Livestock Services (DLS) on transboundary livestock disease surveillance and IPM enhanced
Activity 2.3.1 | Sensitize and train PPS and Livestock staff on plant and animal pest surveillance cross-border regulatory frameworks | 10000 | [5 empty] | 10000
Activity 2.3.2 | Support PPS and DLS with equipment and other necessary materials to facilitate cross-border plant and animal pest and disease sruveillance and reporting | 22000 | [5 empty] | 22000
Activity 2.3.3 | [7 empty] | 0
Activity 2.3.4 | [7 empty] | 0
Activity 2.3.5 | [7 empty] | 0
Activity 2.3.6 | [7 empty] | 0
Activity 2.3.7 | [7 empty] | 0
Activity 2.3.8 | [7 empty] | 0
| Output Total | 32000 | 0 | 0 |  |  |  | 32000 | 0 | 0
Output 2.4 | Livestock monitoring and management systems to mitigate theft and cattle rustling by both the authorities and local border communities strengthened/introduced
Activity 2.4.1 | Scale-up the livestock identification system in place to all the project sites (tagging) | 20000 | [5 empty] | 20000
Activity 2.4.2 | Establish livestock watering points at strategic locations along the identified border areas | 250000 | [5 empty] | 250000
Activity 2.4.3 | Estalishment of local conventions on sustainable grazing and natural resources management through border community participation | 10000 | [5 empty] | 10000
Activity 2.4.4 | Train border communities and herders/transhumance on rangeland mangement | 9000 | [5 empty] | 9000
Activity 2.4.5 | Re-dermarcation/Marking of livestock tracks and grazinging areas and mapping of transhumance corridors | 10000 | [5 empty] | 10000
Activity 2.4.6 | Reseeding and reclaimation of degraded grazing lands (deffered grazing areas) | 10000 | [5 empty] | 10000
Activity 2.4.7 | Provision of Milk processing Facilities and Compost Penning | 20000 | [5 empty] | 20000
Activity 2.4.8 | Supply and distribution of pasture seeds, Establishement of Intensive Feed Garden (with fencing materials and watering facilities) and Provision of Forage Choppers to livestock farmers | 15000 | [5 empty] | 15000
| Output Total | 344000 | 0 | 0 |  |  |  | 344000 | 0 | 0
OUTCOME 3: | Improved community resilience through the promotion of inclusive dialogue processes and support for alternative green livelihoods
Output 3.1 | Integrated climate resilient strategies for diversified livelihoods strenthened/introduced and sources of income imrpoved for vulnerable border communities
Activity 3.1.1 | Establisment of community gardens with durable fences and reliable water supply (boreholes with solar operating pumps) | 240000 | [5 empty] | 240000
Activity 3.1.2 | Support vulnerable farmers with vegetable seeds on refund mechanism | 5000 | [5 empty] | 5000
Activity 3.1.3 | Training of producers on agro-processing, packaging and marketing | 8000 | [5 empty] | 8000
Activity 3.1.4 | Training border communities on modern beekeeping | 6000 | [5 empty] | 6000
Activity 3.1.5 | Provision of beehives (Kenyan Top Bar -KTB) | 34000 | [5 empty] | 34000
Activity 3.1.6 | Provision of beekeeping equipment to identified border communities | 40000 | [5 empty] | 40000
Activity 3.1.7 | Train beekeepers on beehive construction and maintenance and apiary management | 6000 | [5 empty] | 6000
Activity 3.1.8 | Train beekeepers on value addition on honey products | 10000 | [5 empty] | 10000
| Output Total | 349000 | 0 | 0 |  |  |  | 349000 | 0 | 0
Output 3.2:
Activity 3.2.1 | [7 empty] | 0
Activity 3.2.2 | [7 empty] | 0
Activity 3.2.3 | [7 empty] | 0
Activity 3.2.4 | [7 empty] | 0
Activity 3.2.5 | [7 empty] | 0
Activity 3.2.6 | [7 empty] | 0
Activity 3.2.7 | [7 empty] | 0
Activity 3.2.8 | [7 empty] | 0
| Output Total | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Output 3.3
Activity 3.3.1 | [7 empty] | 0
Activity 3.3.2 | [7 empty] | 0
Activity 3.3.3 | [7 empty] | 0
Activity 3.3.4 | [7 empty] | 0
Activity 3.3.5 | [7 empty] | 0
Activity 3.3.6 | [7 empty] | 0
Activity 3.3.7 | [7 empty] | 0
Activity 3.3.8 | [7 empty] | 0
| Output Total | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Output 3.4
Activity 3.4.1 | [7 empty] | 0
Activity 3.4.2 | [7 empty] | 0
Activity 3.4.3 | [7 empty] | 0
Activity 3.4.4 | [7 empty] | 0
Activity 3.4.5 | [7 empty] | 0
Activity 3.4.6 | [7 empty] | 0
Activity 3.4.7 | [7 empty] | 0
Activity 3.4.8 | [7 empty] | 0
| Output Total | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
OUTCOME 4:
Output 4.1
Activity 4.1.1 | [7 empty] | 0
Activity 4.1.2 | [7 empty] | 0
Activity 4.1.3 | [7 empty] | 0
Activity 4.1.4 | [7 empty] | 0
Activity 4.1.5 | [7 empty] | 0
Activity 4.1.6 | [7 empty] | 0
Activity 4.1.7 | [7 empty] | 0
Activity 4.1.8 | [7 empty] | 0
| Output Total | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Output 4.2
Activity 4.2.1 | [7 empty] | 0
Activity 4.2.2 | [7 empty] | 0
Activity 4.2.3 | [7 empty] | 0
Activity 4.2.4 | [7 empty] | 0
Activity 4.2.5 | [7 empty] | 0
Activity 4.2.6 | [7 empty] | 0
Activity 4.2.7 | [7 empty] | 0
Activity 4.2.8 | [7 empty] | 0
| Output Total | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Output 4.3
Activity 4.3.1 | [7 empty] | 0
Activity 4.3.2 | [7 empty] | 0
Activity 4.3.3 | [7 empty] | 0
Activity 4.3.4 | [7 empty] | 0
Activity 4.3.5 | [7 empty] | 0
Activity 4.3.6 | [7 empty] | 0
Activity 4.3.7 | [7 empty] | 0
Activity 4.3.8 | [7 empty] | 0
| Output Total | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Output 4.4
Activity 4.4.1 | [7 empty] | 0
Activity 4.4.2 | [7 empty] | 0
Activity 4.4.3 | [7 empty] | 0
Activity 4.4.4 | [7 empty] | 0
Activity 4.4.5 | [7 empty] | 0
Activity 4.4.6 | [7 empty] | 0
Activity 4.4.7 | [7 empty] | 0
Activity 4.4.8 | [7 empty] | 0
| Output Total | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Additional personnel costs | [7 empty] | 0
Additional Operational Costs | [7 empty] | 0
Monitoring budget | [7 empty] | 0
Budget for independent final evaluation | [7 empty] | 0
| Total Additional Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals
|  | Recipient Organization 1 | Recipient Organization 2 | Recipient Organization 3 | Recipient Organization 4 | Recipient Organization 5 | Recipient Organization 6 | Total
|  | 0 | 0 | 0
| Sub-Total Project Budget | 934000 | 0 | 0 |  |  |  | 934000
| Indirect support costs (7%): | 65380 | 0 | 0 |  |  |  | 65380
| Total | 999380 | 0 | 0 |  |  |  | 999380
Performance-Based Tranche Breakdown
|  | Recipient Organization 1 | Recipient Organization 2 | Recipient Organization 3 | Recipient Organization 4 | Recipient Organization 5 | Recipient Organization 6 | Total | Tranche %
|  | 0 | 0 | 0
| First Tranche: | 699566 | 0 | 0 | 0 | 0 | 0 | 699566 | 70%
| Second Tranche: | 299814 | 0 | 0 | 0 | 0 | 0 | 299814 | 30%
| Third Tranche | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Total: | 999380 | 0 | 0 | 0 | 0 | 0 | 999380 | 100%
| $ Towards GEWE (includes indirect costs) | 300000 | [6 empty] | Total Expenditure | 0
| % Towards GEWE | 30.02% | [6 empty] | Delivery Rate: | 0%
| $ Towards M&E (includes indirect costs) | 50000
| % Towards M&E | 5.003%
Note: PBF does not accept projects with less than 5% towards M&E and less than 15% towards GEWE. These figures will show as red if this minimum threshold is not met.

## FAOSN (hidden)
Annex D - PBF Project Budget
Instructions:
1. Only fill in white cells. Grey cells are locked and/or contain spreadsheet formulas. 2. Complete both Sheet 1 and Sheet 2. a) First, prepare a budget organized by activity/output/outcome in Sheet 1. (Activity amounts can be indicative estimates.) b) Then, divide each output budget along UN Budget Categories in Sheet 2. 3. Be sure to include % towards Gender Equality and Women's Empowerment 3. Do not use Sheet 4 or 5, which are for MPTF and PBF use. 4. Leave blank any Organizations/Outcomes/Outputs/Activities that aren't needed. DO NOT delete cells. 5. Do not adjust tranche amounts without consulting PBSO.
Table 1 - PBF project budget by outcome, output and activity
Outcome/ Output number | Description (Text) | Recipient Organization 1 Budget | Recipient Organization 2 Budget | Recipient Organization 3 Budget | Recipient Organization 4 Budget | Recipient Organization 5 Budget | Recipient Organization 6 Budget | Total | % of budget per activity allocated to Gender Equality and Women's Empowerment (GEWE) (if any): | Current level of expenditure/ commitment (To be completed at time of project progress reporting) | Any remarks (e.g. on types of inputs provided or budget justification, esp. for TA or travel costs)
FAO-SN
OUTCOME 1: | Improved border management and engagement between communities and border authorities
Output 1.1: | a) Enhance border officials’ operational and technical capacities to strengthen surveillance and facilitate safe and orderly movement of people and goods and to address transnational organized crimes.
Activity 1.1.1: | set up tools for cross-border consultation in order to engage a dialogue for planning of activities before the project implementation | 25000 | [5 empty] | 25000
Activity 1.1.2: | [7 empty] | 0
Activity 1.1.3: | [7 empty] | 0
Activity 1.1.4 | [7 empty] | 0
Activity 1.1.5 | [7 empty] | 0
Activity 1.1.6 | [7 empty] | 0
Activity 1.1.7 | [7 empty] | 0
Activity 1.1.8 | [7 empty] | 0
| Output Total | 25000 | 0 | 0 |  |  |  | 25000 | 0 | 0
Output 1.2: | c) Expand the Migration Information and Data Analysis System in The Gambia at select borders
Activity 1.2.1 | installation of local 4 offices for reception and referral to returning migrants | 21500 | [5 empty] | 21500
Activity 1.2.2 | development of migration information system in line with regional and global objectives | 15000 | [5 empty] | 15000
Activity 1.2.3 | [7 empty] | 0
Activity 1.2.4 | [7 empty] | 0
Activity 1.2.5 | [7 empty] | 0
Activity 1.2.6 | [7 empty] | 0
Activity 1.2.7 | [7 empty] | 0
Activity 1.2.8 | [7 empty] | 0
| Output Total | 36500 | 0 | 0 |  |  |  | 36500 | 0 | 0
Output 1.3: | e) Support the implementation of community engagement plans to build a collaborative relationship between the community and the authorities
Activity 1.3.1 | Organize meetings at village and communes level | 2000 | [5 empty] | 2000
Activity 1.3.2 | develop capacities to prepare local developent plans | 3000 | [5 empty] | 3000
Activity 1.3.3 | [7 empty] | 0
Activity 1.3.4 | [7 empty] | 0
Activity 1.3.5 | [7 empty] | 0
Activity 1.3.6 | [7 empty] | 0
Activity 1.3.7 | [7 empty] | 0
Activity 1.3.8 | [7 empty] | 0
| Output Total | 5000 | 0 | 0 |  |  |  | 5000 | 0 | 0
Output 1.4: | f) Facilitate social mobilization and raise awareness of border communities and local and border authorities to promote trust-building
Activity 1.4.1 | Develop and disseminate awareness-raising messages (forum and community radio, use of traditional communicators) | 20000 | [5 empty] | 20000
Activity 1.4.2 | implement 100 Dimitra Clubs for inclusive communication at community level | 23097 | [5 empty] | 23097
Activity 1.4.3 | [7 empty] | 0
Activity 1.4.4 | [7 empty] | 0
Activity 1.4.5 | [7 empty] | 0
Activity 1.4.6 | [7 empty] | 0
Activity 1.4.7 | [7 empty] | 0
Activity 1.4.8 | [7 empty] | 0
| Output Total | 43097 | 0 | 0 |  |  |  | 43097 | 0 | 0
OUTCOME 2:
Outcome 2.1 | Support border communities in Gambia and Senegal to plan joint and viable border community solutions to address the continued deforestation and forest degradation
Activity 2.1.1 | participtive analyse of good practices | 25840 | [5 empty] | 25840
Activity 2.1.2 | Développement et proposition de stratégies management | 15000 | [5 empty] | 15000
Activity 2.1.3 | [7 empty] | 0
Activity 2.1.4 | [7 empty] | 0
Activity 2.1.5 | [7 empty] | 0
Activity 2.1.6 | [7 empty] | 0
Activity 2.1.7 | [7 empty] | 0
Activity 2.1.8 | [7 empty] | 0
| Output Total | 40840 | 0 | 0 |  |  |  | 40840 | 0 | 0
Output 2.2 | Strengthen integrated management practices through cross-border regulatory frameworks on pest and disease surveillance, livestock grazing and trans-human transhumant migration
Activity 2.2.1 | developp agropastoral field school modules | 5000 | [5 empty] | 5000
Activity 2.2.2 | Implement 50 agrpastoral field school ti streghtenen technical capacities | 25000 | [5 empty] | 25000
Activity 2.2.3 | [7 empty] | 0
Activity 2.2.4 | [7 empty] | 0
Activity 2.2.5 | [7 empty] | 0
Activity 2.2.6 | [7 empty] | 0
Activity 2.2.7 | [7 empty] | 0
Activity 2.2.8 | [7 empty] | 0
| Output Total | 30000 | 0 | 0 |  |  |  | 30000 | 0 | 0
Output 2.3
Activity 2.3.1 | [7 empty] | 0
Activity 2.3.2 | [7 empty] | 0
Activity 2.3.3 | [7 empty] | 0
Activity 2.3.4 | [7 empty] | 0
Activity 2.3.5 | [7 empty] | 0
Activity 2.3.6 | [7 empty] | 0
Activity 2.3.7 | [7 empty] | 0
Activity 2.3.8 | [7 empty] | 0
| Output Total | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Output 2.4
Activity 2.4.1 | [7 empty] | 0
Activity 2.4.2 | [7 empty] | 0
Activity 2.4.3 | [7 empty] | 0
Activity 2.4.4 | [7 empty] | 0
Activity 2.4.5 | [7 empty] | 0
Activity 2.4.6 | [7 empty] | 0
Activity 2.4.7 | [7 empty] | 0
Activity 2.4.8 | [7 empty] | 0
| Output Total | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
OUTCOME 3: | Improved community resilience through the promotion of inclusive dialogue processes and support for alternative green livelihoods
Output 3.1 | a) Enhance women and youth participation in community decision making by supporting alternative green livelihoods for the border communities through direct livelihoods assistance
Activity 3.1.1 | Taining of 200 young people to develop skills (Productive capacity building and skills development for youth employability and entrepreneurship). | 20000 | [5 empty] | 20000
Activity 3.1.2 | [7 empty] | 0
Activity 3.1.3 | [7 empty] | 0
Activity 3.1.4 | [7 empty] | 0
Activity 3.1.5 | [7 empty] | 0
Activity 3.1.6 | [7 empty] | 0
Activity 3.1.7 | [7 empty] | 0
Activity 3.1.8 | [7 empty] | 0
| Output Total | 20000 | 0 | 0 |  |  |  | 20000 | 0 | 0
Output 3.2: | b) Empower cross-border host communities and their socio-economic well-being and promote social cohesion through prioritized rehabilitation of basic community infrastructure to improve access to essential services, e.g., water and sanitation
Activity 3.2.1 | construction of 30 cisterns for water havesting | 43743 | [5 empty] | 43743
Activity 3.2.2 | installation of 20 agroecological farm 1ha | 37194 | [5 empty] | 37194
Activity 3.2.3 | [7 empty] | 0
Activity 3.2.4 | [7 empty] | 0
Activity 3.2.5 | [7 empty] | 0
Activity 3.2.6 | [7 empty] | 0
Activity 3.2.7 | [7 empty] | 0
Activity 3.2.8 | [7 empty] | 0
| Output Total | 80937 | 0 | 0 |  |  |  | 80937 | 0 | 0
Output 3.3 | d) Enhance capacities of border communities on value addition techniques on agriculture and Non-Timber Forest Products (NTFPs.).
Activity 3.3.1 | equipement transformation of PFNL | 34744 | [5 empty] | 34744
Activity 3.3.2 | [7 empty] | 0
Activity 3.3.3 | [7 empty] | 0
Activity 3.3.4 | [7 empty] | 0
Activity 3.3.5 | [7 empty] | 0
Activity 3.3.6 | [7 empty] | 0
Activity 3.3.7 | [7 empty] | 0
Activity 3.3.8 | [7 empty] | 0
| Output Total | 34744 | 0 | 0 |  |  |  | 34744 | 0 | 0
Output 3.4
Activity 3.4.1 | [7 empty] | 0
Activity 3.4.2 | [7 empty] | 0
Activity 3.4.3 | [7 empty] | 0
Activity 3.4.4 | [7 empty] | 0
Activity 3.4.5 | [7 empty] | 0
Activity 3.4.6 | [7 empty] | 0
Activity 3.4.7 | [7 empty] | 0
Activity 3.4.8 | [7 empty] | 0
| Output Total | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
OUTCOME 4:
Output 4.1
Activity 4.1.1 | [7 empty] | 0
Activity 4.1.2 | [7 empty] | 0
Activity 4.1.3 | [7 empty] | 0
Activity 4.1.4 | [7 empty] | 0
Activity 4.1.5 | [7 empty] | 0
Activity 4.1.6 | [7 empty] | 0
Activity 4.1.7 | [7 empty] | 0
Activity 4.1.8 | [7 empty] | 0
| Output Total | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Output 4.2
Activity 4.2.1 | [7 empty] | 0
Activity 4.2.2 | [7 empty] | 0
Activity 4.2.3 | [7 empty] | 0
Activity 4.2.4 | [7 empty] | 0
Activity 4.2.5 | [7 empty] | 0
Activity 4.2.6 | [7 empty] | 0
Activity 4.2.7 | [7 empty] | 0
Activity 4.2.8 | [7 empty] | 0
| Output Total | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Output 4.3
Activity 4.3.1 | [7 empty] | 0
Activity 4.3.2 | [7 empty] | 0
Activity 4.3.3 | [7 empty] | 0
Activity 4.3.4 | [7 empty] | 0
Activity 4.3.5 | [7 empty] | 0
Activity 4.3.6 | [7 empty] | 0
Activity 4.3.7 | [7 empty] | 0
Activity 4.3.8 | [7 empty] | 0
| Output Total | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Output 4.4
Activity 4.4.1 | [7 empty] | 0
Activity 4.4.2 | [7 empty] | 0
Activity 4.4.3 | [7 empty] | 0
Activity 4.4.4 | [7 empty] | 0
Activity 4.4.5 | [7 empty] | 0
Activity 4.4.6 | [7 empty] | 0
Activity 4.4.7 | [7 empty] | 0
Activity 4.4.8 | [7 empty] | 0
| Output Total | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Additional personnel costs | [7 empty] | 0
Additional Operational Costs | [7 empty] | 0
Monitoring budget | [7 empty] | 0
Budget for independent final evaluation | [7 empty] | 0
| Total Additional Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals
|  | Recipient Organization 1 | Recipient Organization 2 | Recipient Organization 3 | Recipient Organization 4 | Recipient Organization 5 | Recipient Organization 6 | Total
|  | FAO-SN | 0 | 0
| Sub-Total Project Budget | 316118 | 0 | 0 |  |  |  | 316118
| Indirect support costs (7%): | 22128.26 | 0 | 0 |  |  |  | 22128.26
| Total | 338246.26 | 0 | 0 |  |  |  | 338246.26
Performance-Based Tranche Breakdown
|  | Recipient Organization 1 | Recipient Organization 2 | Recipient Organization 3 | Recipient Organization 4 | Recipient Organization 5 | Recipient Organization 6 | Total | Tranche %
|  | FAO-SN | 0 | 0
| First Tranche: | 236772.382 | 0 | 0 | 0 | 0 | 0 | 236772.382 | 70%
| Second Tranche: | 101473.878 | 0 | 0 | 0 | 0 | 0 | 101473.878 | 30%
| Third Tranche | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
| Total: | 338246.26 | 0 | 0 | 0 | 0 | 0 | 338246.26 | 100%
| $ Towards GEWE (includes indirect costs) | 0 | [6 empty] | Total Expenditure | 0
| % Towards GEWE | 0% | [6 empty] | Delivery Rate: | 0%
| $ Towards M&E (includes indirect costs) | 0
| % Towards M&E | 0%
Note: PBF does not accept projects with less than 5% towards M&E and less than 15% towards GEWE. These figures will show as red if this minimum threshold is not met.

## Dropdowns (hidden)
0%
20%
40%
60%
80%
100%

## Sheet2 (hidden)
Other peacebuilding objectives not related to specific SDG target | Other
1.1 By 2030, eradicate extreme poverty for all people everywhere, currently measured as people living on less than $1.25 a day | 1.1
1.2 By 2030, reduce at least by half the proportion of men, women and children of all ages living in poverty in all its dimensions according to national definitions | 1.2
1.3 Implement nationally appropriate social protection systems and measures for all, including floors, and by 2030 achieve substantial coverage of the poor and the vulnerable | 1.3
1.4 By 2030, ensure that all men and women, in particular the poor and the vulnerable, have equal rights to economic resources, as well as access to basic services, ownership and control over land and other forms of property, inheritance, natural resources, appropriate new technology and financial services, including microfinance | 1.4
1.5 By 2030, build the resilience of the poor and those in vulnerable situations and reduce their exposure and vulnerability to climate-related extreme events and other economic, social and environmental shocks and disasters | 1.5
1.a Ensure significant mobilization of resources from a variety of sources, including through enhanced development cooperation, in order to provide adequate and predictable means for developing countries, in particular least developed countries, to implement programmes and policies to end poverty in all its dimensions | 1.a
1.b Create sound policy frameworks at the national, regional and international levels, based on pro-poor and gender-sensitive development strategies, to support accelerated investment in poverty eradication actions | 1.b
2.1 By 2030, end hunger and ensure access by all people, in particular the poor and people in vulnerable situations, including infants, to safe, nutritious and sufficient food all year round | 2.1
2.2 By 2030, end all forms of malnutrition, including achieving, by 2025, the internationally agreed targets on stunting and wasting in children under 5 years of age, and address the nutritional needs of adolescent girls, pregnant and lactating women and older persons | 2.2
2.3 By 2030, double the agricultural productivity and incomes of small-scale food producers, in particular women, indigenous peoples, family farmers, pastoralists and fishers, including through secure and equal access to land, other productive resources and inputs, knowledge, financial services, markets and opportunities for value addition and non-farm employment | 2.3
2.4 By 2030, ensure sustainable food production systems and implement resilient agricultural practices that increase productivity and production, that help maintain ecosystems, that strengthen capacity for adaptation to climate change, extreme weather, drought, flooding and other disasters and that progressively improve land and soil quality | 2.4
2.5 By 2020, maintain the genetic diversity of seeds, cultivated plants and farmed and domesticated animals and their related wild species, including through soundly managed and diversified seed and plant banks at the national, regional and international levels, and promote access to and fair and equitable sharing of benefits arising from the utilization of genetic resources and associated traditional knowledge, as internationally agreed | 2.5
2.a Increase investment, including through enhanced international cooperation, in rural infrastructure, agricultural research and extension services, technology development and plant and livestock gene banks in order to enhance agricultural productive capacity in developing countries, in particular least developed countries | 2.a
2.b Correct and prevent trade restrictions and distortions in world agricultural markets, including through the parallel elimination of all forms of agricultural export subsidies and all export measures with equivalent effect, in accordance with the mandate of the Doha Development Round | 2.b
2.c Adopt measures to ensure the proper functioning of food commodity markets and their derivatives and facilitate timely access to market information, including on food reserves, in order to help limit extreme food price volatility | 2.c
3.1 By 2030, reduce the global maternal mortality ratio to less than 70 per 100,000 live births | 3.1
3.2 By 2030, end preventable deaths of newborns and children under 5 years of age, with all countries aiming to reduce neonatal mortality to at least as low as 12 per 1,000 live births and under-5 mortality to at least as low as 25 per 1,000 live births | 3.2
3.3 By 2030, end the epidemics of AIDS, tuberculosis, malaria and neglected tropical diseases and combat hepatitis, water-borne diseases and other communicable diseases | 3.3
3.4 By 2030, reduce by one third premature mortality from non-communicable diseases through prevention and treatment and promote mental health and well-being | 3.4
3.5 Strengthen the prevention and treatment of substance abuse, including narcotic drug abuse and harmful use of alcohol | 3.5
3.6 By 2020, halve the number of global deaths and injuries from road traffic accidents | 3.6
3.7 By 2030, ensure universal access to sexual and reproductive health-care services, including for family planning, information and education, and the integration of reproductive health into national strategies and programmes | 3.7
3.8 Achieve universal health coverage, including financial risk protection, access to quality essential health-care services and access to safe, effective, quality and affordable essential medicines and vaccines for all | 3.8
3.9 By 2030, substantially reduce the number of deaths and illnesses from hazardous chemicals and air, water and soil pollution and contamination | 3.9
3.a Strengthen the implementation of the World Health Organization Framework Convention on Tobacco Control in all countries, as appropriate | 3.a
3.b Support the research and development of vaccines and medicines for the communicable and non‑communicable diseases that primarily affect developing countries, provide access to affordable essential medicines and vaccines, in accordance with the Doha Declaration on the TRIPS Agreement and Public Health, which affirms the right of developing countries to use to the full the provisions in the Agreement on Trade-Related Aspects of Intellectual Property Rights regarding flexibilities to protect public health, and, in particular, provide access to medicines for all | 3.b
3.c Substantially increase health financing and the recruitment, development, training and retention of the health workforce in developing countries, especially in least developed countries and small island developing States | 3.c
3.d Strengthen the capacity of all countries, in particular developing countries, for early warning, risk reduction and management of national and global health risks | 3.d
4.1 By 2030, ensure that all girls and boys complete free, equitable and quality primary and secondary education leading to relevant and effective learning outcomes | 4.1
4.2 By 2030, ensure that all girls and boys have access to quality early childhood development, care and pre-primary education so that they are ready for primary education | 4.2
4.3 By 2030, ensure equal access for all women and men to affordable and quality technical, vocational and tertiary education, including university | 4.3
4.4 By 2030, substantially increase the number of youth and adults who have relevant skills, including technical and vocational skills, for employment, decent jobs and entrepreneurship | 4.4
4.5 By 2030, eliminate gender disparities in education and ensure equal access to all levels of education and vocational training for the vulnerable, including persons with disabilities, indigenous peoples and children in vulnerable situations | 4.5
4.6 By 2030, ensure that all youth and a substantial proportion of adults, both men and women, achieve literacy and numeracy | 4.6
4.7 By 2030, ensure that all learners acquire the knowledge and skills needed to promote sustainable development, including, among others, through education for sustainable development and sustainable lifestyles, human rights, gender equality, promotion of a culture of peace and non-violence, global citizenship and appreciation of cultural diversity and of culture’s contribution to sustainable development | 4.7
4.a Build and upgrade education facilities that are child, disability and gender sensitive and provide safe, non-violent, inclusive and effective learning environments for all | 4.a
4.b By 2020, substantially expand globally the number of scholarships available to developing countries, in particular least developed countries, small island developing States and African countries, for enrolment in higher education, including vocational training and information and communications technology, technical, engineering and scientific programmes, in developed countries and other developing countries | 4.b
4.c By 2030, substantially increase the supply of qualified teachers, including through international cooperation for teacher training in developing countries, especially least developed countries and small island developing States | 4.c
5.1 End all forms of discrimination against all women and girls everywhere | 5.1
5.2 Eliminate all forms of violence against all women and girls in the public and private spheres, including trafficking and sexual and other types of exploitation | 5.2
5.3 Eliminate all harmful practices, such as child, early and forced marriage and female genital mutilation | 5.3
5.4 Recognize and value unpaid care and domestic work through the provision of public services, infrastructure and social protection policies and the promotion of shared responsibility within the household and the family as nationally appropriate | 5.4
5.5 Ensure women’s full and effective participation and equal opportunities for leadership at all levels of decision-making in political, economic and public life | 5.5
5.6 Ensure universal access to sexual and reproductive health and reproductive rights as agreed in accordance with the Programme of Action of the International Conference on Population and Development and the Beijing Platform for Action and the outcome documents of their review conferences | 5.6
5.a Undertake reforms to give women equal rights to economic resources, as well as access to ownership and control over land and other forms of property, financial services, inheritance and natural resources, in accordance with national laws | 5.a
5.b Enhance the use of enabling technology, in particular information and communications technology, to promote the empowerment of women | 5.b
5.c Adopt and strengthen sound policies and enforceable legislation for the promotion of gender equality and the empowerment of all women and girls at all levels | 5.c
6.1 By 2030, achieve universal and equitable access to safe and affordable drinking water for all | 6.1
6.2 By 2030, achieve access to adequate and equitable sanitation and hygiene for all and end open defecation, paying special attention to the needs of women and girls and those in vulnerable situations | 6.2
6.3 By 2030, improve water quality by reducing pollution, eliminating dumping and minimizing release of hazardous chemicals and materials, halving the proportion of untreated wastewater and substantially increasing recycling and safe reuse globally | 6.3
6.4 By 2030, substantially increase water-use efficiency across all sectors and ensure sustainable withdrawals and supply of freshwater to address water scarcity and substantially reduce the number of people suffering from water scarcity | 6.4
6.5 By 2030, implement integrated water resources management at all levels, including through transboundary cooperation as appropriate | 6.5
6.6 By 2020, protect and restore water-related ecosystems, including mountains, forests, wetlands, rivers, aquifers and lakes | 6.6
6.a By 2030, expand international cooperation and capacity-building support to developing countries in water- and sanitation-related activities and programmes, including water harvesting, desalination, water efficiency, wastewater treatment, recycling and reuse technologies | 6.a
6.b Support and strengthen the participation of local communities in improving water and sanitation management | 6.b
7.1 By 2030, ensure universal access to affordable, reliable and modern energy services | 7.1
7.2 By 2030, increase substantially the share of renewable energy in the global energy mix | 7.2
7.3 By 2030, double the global rate of improvement in energy efficiency | 7.3
7.a By 2030, enhance international cooperation to facilitate access to clean energy research and technology, including renewable energy, energy efficiency and advanced and cleaner fossil-fuel technology, and promote investment in energy infrastructure and clean energy technology | 7.a
7.b By 2030, expand infrastructure and upgrade technology for supplying modern and sustainable energy services for all in developing countries, in particular least developed countries, small island developing States and landlocked developing countries, in accordance with their respective programmes of support | 7.b
8.1 Sustain per capita economic growth in accordance with national circumstances and, in particular, at least 7 per cent gross domestic product growth per annum in the least developed countries | 8.1
8.2 Achieve higher levels of economic productivity through diversification, technological upgrading and innovation, including through a focus on high-value added and labour-intensive sectors | 8.2
8.3 Promote development-oriented policies that support productive activities, decent job creation, entrepreneurship, creativity and innovation, and encourage the formalization and growth of micro-, small- and medium-sized enterprises, including through access to financial services | 8.3
8.4 Improve progressively, through 2030, global resource efficiency in consumption and production and endeavour to decouple economic growth from environmental degradation, in accordance with the 10‑Year Framework of Programmes on Sustainable Consumption and Production, with developed countries taking the lead | 8.4
8.5 By 2030, achieve full and productive employment and decent work for all women and men, including for young people and persons with disabilities, and equal pay for work of equal value | 8.5
8.6 By 2020, substantially reduce the proportion of youth not in employment, education or training | 8.6
8.7 Take immediate and effective measures to eradicate forced labour, end modern slavery and human trafficking and secure the prohibition and elimination of the worst forms of child labour, including recruitment and use of child soldiers, and by 2025 end child labour in all its forms | 8.7
8.8 Protect labour rights and promote safe and secure working environments for all workers, including migrant workers, in particular women migrants, and those in precarious employment | 8.8
8.9 By 2030, devise and implement policies to promote sustainable tourism that creates jobs and promotes local culture and products | 8.9
8.10 Strengthen the capacity of domestic financial institutions to encourage and expand access to banking, insurance and financial services for all | 8.10
8.a Increase Aid for Trade support for developing countries, in particular least developed countries, including through the Enhanced Integrated Framework for Trade-related Technical Assistance to Least Developed Countries | 8.a
8.b By 2020, develop and operationalize a global strategy for youth employment and implement the Global Jobs Pact of the International Labour Organization | 8.b
9.1 Develop quality, reliable, sustainable and resilient infrastructure, including regional and trans-border infrastructure, to support economic development and human well-being, with a focus on affordable and equitable access for all | 9.1
9.2 Promote inclusive and sustainable industrialization and, by 2030, significantly raise industry’s share of employment and gross domestic product, in line with national circumstances, and double its share in least developed countries | 9.2
9.3 Increase the access of small-scale industrial and other enterprises, in particular in developing countries, to financial services, including affordable credit, and their integration into value chains and markets | 9.3
9.4 By 2030, upgrade infrastructure and retrofit industries to make them sustainable, with increased resource-use efficiency and greater adoption of clean and environmentally sound technologies and industrial processes, with all countries taking action in accordance with their respective capabilities | 9.4
9.5 Enhance scientific research, upgrade the technological capabilities of industrial sectors in all countries, in particular developing countries, including, by 2030, encouraging innovation and substantially increasing the number of research and development workers per 1 million people and public and private research and development spending | 9.5
9.a Facilitate sustainable and resilient infrastructure development in developing countries through enhanced financial, technological and technical support to African countries, least developed countries, landlocked developing countries and small island developing States | 9.a
9.b Support domestic technology development, research and innovation in developing countries, including by ensuring a conducive policy environment for, inter alia, industrial diversification and value addition to commodities | 9.b
9.c Significantly increase access to information and communications technology and strive to provide universal and affordable access to the Internet in least developed countries by 2020 | 9.c
10.1 By 2030, progressively achieve and sustain income growth of the bottom 40 per cent of the population at a rate higher than the national average | 10.1
10.2 By 2030, empower and promote the social, economic and political inclusion of all, irrespective of age, sex, disability, race, ethnicity, origin, religion or economic or other status | 10.2
10.3 Ensure equal opportunity and reduce inequalities of outcome, including by eliminating discriminatory laws, policies and practices and promoting appropriate legislation, policies and action in this regard | 10.3
10.4 Adopt policies, especially fiscal, wage and social protection policies, and progressively achieve greater equality | 10.4
10.5 Improve the regulation and monitoring of global financial markets and institutions and strengthen the implementation of such regulations | 10.5
10.6 Ensure enhanced representation and voice for developing countries in decision-making in global international economic and financial institutions in order to deliver more effective, credible, accountable and legitimate institutions | 10.6
10.7 Facilitate orderly, safe, regular and responsible migration and mobility of people, including through the implementation of planned and well-managed migration policies | 10.7
10.a Implement the principle of special and differential treatment for developing countries, in particular least developed countries, in accordance with World Trade Organization agreements | 10.a
10.b Encourage official development assistance and financial flows, including foreign direct investment, to States where the need is greatest, in particular least developed countries, African countries, small island developing States and landlocked developing countries, in accordance with their national plans and programmes | 10.b
10.c By 2030, reduce to less than 3 per cent the transaction costs of migrant remittances and eliminate remittance corridors with costs higher than 5 per cent | 10.c
11.1 By 2030, ensure access for all to adequate, safe and affordable housing and basic services and upgrade slums | 11.1
11.2 By 2030, provide access to safe, affordable, accessible and sustainable transport systems for all, improving road safety, notably by expanding public transport, with special attention to the needs of those in vulnerable situations, women, children, persons with disabilities and older persons | 11.2
11.3 By 2030, enhance inclusive and sustainable urbanization and capacity for participatory, integrated and sustainable human settlement planning and management in all countries | 11.3
11.4 Strengthen efforts to protect and safeguard the world’s cultural and natural heritage | 11.4
11.5 By 2030, significantly reduce the number of deaths and the number of people affected and substantially decrease the direct economic losses relative to global gross domestic product caused by disasters, including water-related disasters, with a focus on protecting the poor and people in vulnerable situations | 11.5
11.6 By 2030, reduce the adverse per capita environmental impact of cities, including by paying special attention to air quality and municipal and other waste management | 11.6
11.7 By 2030, provide universal access to safe, inclusive and accessible, green and public spaces, in particular for women and children, older persons and persons with disabilities | 11.7
11.a Support positive economic, social and environmental links between urban, peri-urban and rural areas by strengthening national and regional development planning | 11.a
11.b By 2020, substantially increase the number of cities and human settlements adopting and implementing integrated policies and plans towards inclusion, resource efficiency, mitigation and adaptation to climate change, resilience to disasters, and develop and implement, in line with the Sendai Framework for Disaster Risk Reduction 2015-2030, holistic disaster risk management at all levels | 11.b
11.c Support least developed countries, including through financial and technical assistance, in building sustainable and resilient buildings utilizing local materials | 11.c
12.1 Implement the 10-Year Framework of Programmes on Sustainable Consumption and Production Patterns, all countries taking action, with developed countries taking the lead, taking into account the development and capabilities of developing countries | 12.1
12.2 By 2030, achieve the sustainable management and efficient use of natural resources | 12.2
12.3 By 2030, halve per capita global food waste at the retail and consumer levels and reduce food losses along production and supply chains, including post-harvest losses | 12.3
12.4 By 2020, achieve the environmentally sound management of chemicals and all wastes throughout their life cycle, in accordance with agreed international frameworks, and significantly reduce their release to air, water and soil in order to minimize their adverse impacts on human health and the environment | 12.4
12.5 By 2030, substantially reduce waste generation through prevention, reduction, recycling and reuse | 12.5
12.6 Encourage companies, especially large and transnational companies, to adopt sustainable practices and to integrate sustainability information into their reporting cycle | 12.6
12.7 Promote public procurement practices that are sustainable, in accordance with national policies and priorities | 12.7
12.8 By 2030, ensure that people everywhere have the relevant information and awareness for sustainable development and lifestyles in harmony with nature | 12.8
12.a Support developing countries to strengthen their scientific and technological capacity to move towards more sustainable patterns of consumption and production | 12.a
12.b Develop and implement tools to monitor sustainable development impacts for sustainable tourism that creates jobs and promotes local culture and products | 12.b
12.c Rationalize inefficient fossil-fuel subsidies that encourage wasteful consumption by removing market distortions, in accordance with national circumstances, including by restructuring taxation and phasing out those harmful subsidies, where they exist, to reflect their environmental impacts, taking fully into account the specific needs and conditions of developing countries and minimizing the possible adverse impacts on their development in a manner that protects the poor and the affected communities | 12.c
13.1 Strengthen resilience and adaptive capacity to climate-related hazards and natural disasters in all countries | 13.1
13.2 Integrate climate change measures into national policies, strategies and planning | 13.2
13.3 Improve education, awareness-raising and human and institutional capacity on climate change mitigation, adaptation, impact reduction and early warning | 13.3
13.a Implement the commitment undertaken by developed-country parties to the United Nations Framework Convention on Climate Change to a goal of mobilizing jointly $100 billion annually by 2020 from all sources to address the needs of developing countries in the context of meaningful mitigation actions and transparency on implementation and fully operationalize the Green Climate Fund through its capitalization as soon as possible | 13.a
13.b Promote mechanisms for raising capacity for effective climate change-related planning and management in least developed countries and small island developing States, including focusing on women, youth and local and marginalized communities | 13.b
14.1 By 2025, prevent and significantly reduce marine pollution of all kinds, in particular from land-based activities, including marine debris and nutrient pollution | 14.1
14.2 By 2020, sustainably manage and protect marine and coastal ecosystems to avoid significant adverse impacts, including by strengthening their resilience, and take action for their restoration in order to achieve healthy and productive oceans | 14.2
14.3 Minimize and address the impacts of ocean acidification, including through enhanced scientific cooperation at all levels | 14.3
14.4 By 2020, effectively regulate harvesting and end overfishing, illegal, unreported and unregulated fishing and destructive fishing practices and implement science-based management plans, in order to restore fish stocks in the shortest time feasible, at least to levels that can produce maximum sustainable yield as determined by their biological characteristics | 14.4
14.5 By 2020, conserve at least 10 per cent of coastal and marine areas, consistent with national and international law and based on the best available scientific information | 14.5
14.6 By 2020, prohibit certain forms of fisheries subsidies which contribute to overcapacity and overfishing, eliminate subsidies that contribute to illegal, unreported and unregulated fishing and refrain from introducing new such subsidies, recognizing that appropriate and effective special and differential treatment for developing and least developed countries should be an integral part of the World Trade Organization fisheries subsidies negotiation[c] | 14.6
14.7 By 2030, increase the economic benefits to small island developing States and least developed countries from the sustainable use of marine resources, including through sustainable management of fisheries, aquaculture and tourism | 14.7
14.a Increase scientific knowledge, develop research capacity and transfer marine technology, taking into account the Intergovernmental Oceanographic Commission Criteria and Guidelines on the Transfer of Marine Technology, in order to improve ocean health and to enhance the contribution of marine biodiversity to the development of developing countries, in particular small island developing States and least developed countries | 14.a
14.b Provide access for small-scale artisanal fishers to marine resources and markets | 14.b
14.c Enhance the conservation and sustainable use of oceans and their resources by implementing international law as reflected in the United Nations Convention on the Law of the Sea, which provides the legal framework for the conservation and sustainable use of oceans and their resources, as recalled in paragraph 158 of “The future we want” | 14.c
15.1 By 2020, ensure the conservation, restoration and sustainable use of terrestrial and inland freshwater ecosystems and their services, in particular forests, wetlands, mountains and drylands, in line with obligations under international agreements | 15.1
15.2 By 2020, promote the implementation of sustainable management of all types of forests, halt deforestation, restore degraded forests and substantially increase afforestation and reforestation globally | 15.2
15.3 By 2030, combat desertification, restore degraded land and soil, including land affected by desertification, drought and floods, and strive to achieve a land degradation-neutral world | 15.3
15.4 By 2030, ensure the conservation of mountain ecosystems, including their biodiversity, in order to enhance their capacity to provide benefits that are essential for sustainable development | 15.4
15.5 Take urgent and significant action to reduce the degradation of natural habitats, halt the loss of biodiversity and, by 2020, protect and prevent the extinction of threatened species | 15.5
15.6 Promote fair and equitable sharing of the benefits arising from the utilization of genetic resources and promote appropriate access to such resources, as internationally agreed | 15.6
15.7 Take urgent action to end poaching and trafficking of protected species of flora and fauna and address both demand and supply of illegal wildlife products | 15.7
15.8 By 2020, introduce measures to prevent the introduction and significantly reduce the impact of invasive alien species on land and water ecosystems and control or eradicate the priority species | 15.8
15.9 By 2020, integrate ecosystem and biodiversity values into national and local planning, development processes, poverty reduction strategies and accounts | 15.9
15.a Mobilize and significantly increase financial resources from all sources to conserve and sustainably use biodiversity and ecosystems | 15.a
15.b Mobilize significant resources from all sources and at all levels to finance sustainable forest management and provide adequate incentives to developing countries to advance such management, including for conservation and reforestation | 15.b
15.c Enhance global support for efforts to combat poaching and trafficking of protected species, including by increasing the capacity of local communities to pursue sustainable livelihood opportunities | 15.c
16.1 Significantly reduce all forms of violence and related death rates everywhere | 16.1
16.2 End abuse, exploitation, trafficking and all forms of violence against and torture of children | 16.2
16.3 Promote the rule of law at the national and international levels and ensure equal access to justice for all | 16.3
16.4 By 2030, significantly reduce illicit financial and arms flows, strengthen the recovery and return of stolen assets and combat all forms of organized crime | 16.4
16.5 Substantially reduce corruption and bribery in all their forms | 16.5
16.6 Develop effective, accountable and transparent institutions at all levels | 16.6
16.7 Ensure responsive, inclusive, participatory and representative decision-making at all levels | 16.7
16.8 Broaden and strengthen the participation of developing countries in the institutions of global governance | 16.8
16.9 By 2030, provide legal identity for all, including birth registration | 16.9
16.10 Ensure public access to information and protect fundamental freedoms, in accordance with national legislation and international agreements | 16.10
16.a Strengthen relevant national institutions, including through international cooperation, for building capacity at all levels, in particular in developing countries, to prevent violence and combat terrorism and crime | 16.a
16.b Promote and enforce non-discriminatory laws and policies for sustainable development | 16.b
17.1 Strengthen domestic resource mobilization, including through international support to developing countries, to improve domestic capacity for tax and other revenue collection | 17.1
17.2 Developed countries to implement fully their official development assistance commitments, including the commitment by many developed countries to achieve the target of 0.7 per cent of gross national income for official development assistance (ODA/GNI) to developing countries and 0.15 to 0.20 per cent of ODA/GNI to least developed countries; ODA providers are encouraged to consider setting a target to provide at least 0.20 per cent of ODA/GNI to least developed countries | 17.2
17.3 Mobilize additional financial resources for developing countries from multiple sources | 17.3
17.4 Assist developing countries in attaining long-term debt sustainability through coordinated policies aimed at fostering debt financing, debt relief and debt restructuring, as appropriate, and address the external debt of highly indebted poor countries to reduce debt distress | 17.4
17.5 Adopt and implement investment promotion regimes for least developed countries | 17.5
17.6 Enhance North-South, South-South and triangular regional and international cooperation on and access to science, technology and innovation and enhance knowledge-sharing on mutually agreed terms, including through improved coordination among existing mechanisms, in particular at the United Nations level, and through a global technology facilitation mechanism | 17.6
17.7 Promote the development, transfer, dissemination and diffusion of environmentally sound technologies to developing countries on favourable terms, including on concessional and preferential terms, as mutually agreed | 17.7
17.8 Fully operationalize the technology bank and science, technology and innovation capacity-building mechanism for least developed countries by 2017 and enhance the use of enabling technology, in particular information and communications technology | 17.8
17.9 Enhance international support for implementing effective and targeted capacity-building in developing countries to support national plans to implement all the Sustainable Development Goals, including through North-South, South-South and triangular cooperation | 17.9
17.10 Promote a universal, rules-based, open, non‑discriminatory and equitable multilateral trading system under the World Trade Organization, including through the conclusion of negotiations under its Doha Development Agenda | 17.10
17.11 Significantly increase the exports of developing countries, in particular with a view to doubling the least developed countries’ share of global exports by 2020 | 17.11
17.12 Realize timely implementation of duty-free and quota-free market access on a lasting basis for all least developed countries, consistent with World Trade Organization decisions, including by ensuring that preferential rules of origin applicable to imports from least developed countries are transparent and simple, and contribute to facilitating market access | 17.12
17.13 Enhance global macroeconomic stability, including through policy coordination and policy coherence | 17.13
17.14 Enhance policy coherence for sustainable development | 17.14
17.15 Respect each country’s policy space and leadership to establish and implement policies for poverty eradication and sustainable development | 17.15
17.16 Enhance the Global Partnership for Sustainable Development, complemented by multi-stakeholder partnerships that mobilize and share knowledge, expertise, technology and financial resources, to support the achievement of the Sustainable Development Goals in all countries, in particular developing countries | 17.16
17.17 Encourage and promote effective public, public-private and civil society partnerships, building on the experience and resourcing strategies of partnerships | 17.17
17.18 By 2020, enhance capacity-building support to developing countries, including for least developed countries and small island developing States, to increase significantly the availability of high-quality, timely and reliable data disaggregated by income, gender, age, race, ethnicity, migratory status, disability, geographic location and other characteristics relevant in national contexts | 17.18
17.19 By 2030, build on existing initiatives to develop measurements of progress on sustainable development that complement gross domestic product, and support statistical capacity-building in developing countries | 17.19