## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | Building back a resilient health system responsive to the needs of women, children, and adolescents | Overall Duration (months) | 13.5 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2021-03-12
MPTF Office Project Reference Number: |  | Original End Date (dd.mm.yyyy) | 2022-04-30
Country | Liberia | In case of NCE Current End date(dd.mm.yyyy) | 2022-04-30
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | IOM, UNFPA, UNICEF and WHO | National counterparts (government, private, NGOs & others) and other International Organizations | Ministry of Health, Ministry of Education and Ministry of Gender, County Health Teams
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | During the reporting period(12 March 2021 to 31 March 2022) the following key activities were jointly planned, implemented and results achieved. Project detailed implementation plan with log frame, organogram developed. The project was jointly launched by UN, Government and partners in the three counties (Grand Bassa, Gbarpolu, and Grand Kru). A rapid assessment to support implementation and monitoring of results. Implemented and delivered essential RMNCAH and nutrition services in 35 facilities across the 3 counties. Competency based trainings and supportive supervision were conducted for EmONC, IPC, IMNCI, Quality of Care and laboratory services covering the 35 facilities. Procurement, delivery and last mile distribution of life saving RMNCAH and N medicines and other supplies. Installed 35 Foot-pedal Hand Washing Stations and distributed visual aids/risk communication materials to 35 healthcare facilities. Joint annual operational planning, quarterly review to take stock of achievements, bottlenecks and recommendations and county emergency preparedness and response planning, implementation and coordination conducted in line with preparedness and responding to COVID 19 pandemic in Liberia while ensuring continuity of essential health services. Produced and utilized the WHO Safe Birth checklist to strengthen referral pathway. The following key results were achieved; Skilled Birth Attendant deliveries increased from 55% in 2020 to 97.2% by March 2022, deliveries in facilities increased from 61% to 97.3% by March 2022, Ceaserian Section rate increased from 4% in 2020 to 6.7% by March 2022. Postpartum care coverage increased from 65% in 2020 to 91.5% by March 2022. Couple Years of protection increased from 8420 in 2020 to 13,934 by March 2022. DPT3/Penta 3 coverage increased from 32% in 2020 to 78% by March 2022. In 2021, a total of 129,412 children under 5 years received health care services using the IMNCI protocol for common childhood illnesses in the three counties. The proportion of children under 5years treated for malaria increased from 41% in 2020 to 61% by March 2022 . WASH in facilities increased from 13% in 2020 to 60% by March 2022, HMIS reporting increased from 85% to 97%. MPDSR increased from 8.8% in 2020 to 14% by March 2022 while IDSR was sustained at 100% during the project. The following areas (in maternal and child health) saw decline; notably ANC 4+ visits declined from 68% in 2020 to 31% by March 2022, malaria IPTp declined from 55% in 2020 to 45% by March 2022, proportion children treated for diarrhea decreased from 55% in 2020 to 36% by March 2022, while the proportion of children treated for pneumonia/ARI declined from 78% in 2020 to 68% by March 2022. The decline may be attributed to the disruption in health service delivery, access to and utilization during the COVID 19 pandemic, availability of human resources and supply chain issues. On the latter, availability was increased to from 42% to about 70% during the project. Restoring confidence in the health systems took time as community dwellers did not feel comfortable visiting health facilities.
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | The main objective of the project was to accelerate the delivery, access and utilization of key essential health services, especially for children, adolescent girls and women and contribute to building resilient health systems in three counties (Grand Bassa, Gran Kru and Barpolu) with worst health outcomes. This project was linked to and in line with addressing the effects and impacts of COVID 19 on the population health, health service delivery and health systems. The project specifically contributed to the following pillars of the COVID 19 preparedness and response plan for Liberia. These pillars included; case management, delivery of essential health services with more focus on RMNCAH and nutrition services, surveillance, vaccination, infection prevention and control. The project directly linked and contributed to the primary pillar one of the COVID 19 SERP i.e. health first. The project contributed to the post COVID 19 trasition and recovery plan, pillar one of the PAPD and outcome one of the UNSDCF.
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | The project contributed to improved access to and utilization of key essential health services, especially for children, adolescent girls and women and contribute to building local health systems that resulted in the following outcomes: (a). a total of 46,899 unintended pregnancies were averted as a result of the family planning services provided to women and girls, ages 10 – 49 years. (b). A total of 16,042 unsafe abortions were averted. Since abortions contribute to 10% of maternal deaths in Liberia; this contributed to the prevention of unintended pregnancies that often lead to women and girls to resort to back street abortion which is often fatal. (c). A total of 196 maternal deaths and 16,528 child’s deaths were averted through the project interventions.
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | Skilled Birth Attendant deliveries increased from 55% in 2020 to 97.2% by March 2022, deliveries in facilities increased from 61% to 97.3% by March 2022, Ceaserian Section rate increased from 4% in 2020 to 6.7% by March 2022. Postpartum care coverage increased from 65% in 2020 to 91.5% by March 2022. Couple Years of protection increased from 8420 in 2020 to 13,934 by March 2022. DPT3/Penta 3 coverage increased from 32% in 2020 to 78% by March 2022. In 2021, a total of 129,412 children under 5 years received health care services using the IMNCI protocol.for common childhood illnesses . The proportion of children under 5years treated for malaria increased from 41% in 2020 to 61% by March 2022 . The following areas (in maternal and child health) saw decline; notably ANC 4+ visits declined from 68% in 2020 to 31% by March 2022, malaria IPTp declined from 55% in 2020 to 45% by March 2022, proportion children treated for diarrhea decreased from 55% in 2020 to 36% by March 2022, while the proportion of children treated for pneumonia/ARI declined from 78% in 2020 to 68% by March 2022.
3.2 | Results: Gender | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | With a gender marker of three (3), the project's interventions were directed targeted at women, adolescents, children . The main population reached included: children 704,819 ( 51% males, 49% females); Adolescents 108, 909 ( 80% females and 20% males), Pregnant women and girls 190,716 (28% were adolescent girls ages10-19 years; 55% young people ages 10-24 years; 45% above age 25 years).
3.3 | Results: Direct Beneficiaries | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | TOTAL:475,488 Estimated: female 237,565 Male238,023 urban 245,451 and rural 230,137 chidrren under 5 years 80,850 adolescents 108909 preganant women 21,877 and women of reproductive gae group 109,385
3.4 | Results: Indirect Beneficiaries | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | TOTAL:4,145,996 Estimated: female 2,071,437 Male 2074559 urban 2,160,064 and rural 1,985,932 chidrren under 5 years 704,819 adolescents 108909 preganant women 190,716 and women of reproductive gae group 109,385
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words) | Services were provided in the context of “doing no harm. As a targeted intervention, everyone targeted benefited without any inequalities identified. The counties supported in this project are among Liberia’s least performing counties The project specifically targetted and reached general and vulnerable populations including women, children, pregnant mothers and adolescents living in hard to reach communities in the three counties. The 35 facilities were specifically selected to ensure that the project interventions reached the direct and indirect beneficiaries and narrow on inequalities and reduce further vulnerability and leave no one behind. | 0.479 | 0
3.6 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | § Competing national priorities , EVD in neigboring country. Action: Facilitated joint planning and coordination between UN Agencies and national counterparts to harmonize and integrate activities. § Limited funds to support full-RMNCAH-N during and beyond COVID 19, including maternal newborn death surveillance and response. Action: Fostered strategic partnership, advocacy and resource mobilization from partners and donors to support essential health services delivery along the continuum of care. Use the MPTF to catalyze resource mobilization efforts. Engaged with other partners( GFF, GFATM, GAVI, other global COVID 19 funding streams e.g. HSS connector from Canada. § Inadequate electricity or power supply in some health facilities. Actions Alternative energy sources, for example, solar lamps and lighting were used in some health facilities. §Disruption in routine services during an outbreak is challenging as many service users were afraid to visit healt facilities. §Priority is shifted to the emergency as compared to routine services. |  | 0
3.7 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words) | Guidlines for annual operational planning were revised and used to support annual operational planning in all the 15 counties of Liberia. Guidlines for county review meeting for county health teams, district health teams and facilities were revised and adapted for use by MOH and partners during county quarterly reivew meetings. These templates guided and informed subsequent review meetings in all the 15 counties. Produced and utilized the WHO Safe Birth checklist to strengthen referral pathway. Integration of COVID 19 surveillance within the routine IDSR in Liberia.
3.8 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | To achieve the goal and objectives of the project, UNICEF, WHO, UNFPA and IOM had to plan, implemented and coordinated their efforts together in collaboration with MOH, other line Ministries and other partners. The project built on existing coordination platforms and structures within the Government and UNCT to ensure better planning and coordinated implementation, monitoring and reporting. These coordination structures included the Health Sector Coordination Committee, Health Coordination Committee, COVID 19 IMS, RMNCAH TWG, County Coordination Committees, Health Partners Group among others. In addition, a coordination structure/organogram was established under leadership of the RC to ensure effective coordination and collaboration among the UN agencies. WHO was assigned by RC to facilitate coordination of project activities among the 4 agencies as well as with Government and other partners. Key health sector partners were involved and engaged in the planning, implementation, coordination, monitoring and reporting of the program at national and sub national levels. These partners included but not limited to USAID, GFATM, EU, GAVI, US CDC, Last Mile Health, Partners in Health, CSOs, COVID 19 ACT-HSS funding from Canadian Government, WB/GFF funding for monitoring disruption in essential services delivery, access and utilization.
3.9 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words). | A rapid assessment was conducted to idenfy critical areas and gaps inform and guide the detailed implementation planning to support service delivery in the 35 selected facilities. County review meetings were also conducted to take stock of service delivery, emergency preparedness and response, impact of COVID 19 on service delivery and inform and guide county operational planning, coordination of efforts and monitoring and reporting. The review also looked at the national and specific county performance regarding key health servcie delivery indicators and lessons learnt and areas for improvement. The status of MPDSR and county coordination committees functions was also reviewed.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words). | There was no adjustment made.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | Core technical staff identified from the four agencies and MOH to facilitate project implementation. Life-saving maternal health medicines, drugs, equipment and RH commodities were distributed to health facilities in the three counties. To support and prevent stock-out during the peak of the rainy season, Gbarpolu and Grand Kru, the two hardest to reach counties; received six months buffer stock of RH commodities.Procured and delivered; 633 assorted IPC supplies, assorted laboratory services supplies to improve on routine healthcare service at 35 health facilities. Installed 35 Foot-pedal Hand Washing Stations and distributed visual aids/risk communication materials to 35 healthcare facilities.

## Project Indicators
Please include ALL indicators in the project document. Include the indicators and Baseline, Planned Target and Actuals for both OUTCOME and OUTPUT levels. "Actuals" refer to the total figures achieved for each indicator. Include separate actuals for 2021 and for 2022 (if applicable). Explain if targets were not achieved. Include means of verification. Use as many outputs cells as needed to present all project indicators.
| INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | DATA: ACTUALS 2022 (if applicable) | TOTAL actuals (agreggated 2021 and 2022 if applicable ) | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Capacity of health facilities in three counties strengthened to deliver a quality comprehensive package of RMNCAH&N se
Output 1.1 |  |  |  |  | 3851 births occurred in 35 health facilities; out of this, 99 of them were performed by unskilled providers whilst 3752 were attended to by SBA; this make 97.2%. | DHIS2/HMIS
Indicator 1.1.1: | Skilled Birth Attendant
Baseline: | 55%
Planned Target: | 60% | 97.5% | 96.9% | 97.2%
Indicator 1.1.2: | deliveries in health facilities |  |  |  |  | DHIS2/HMIS
Baseline: | 61%
Planned Target: | 74% | 97.6% | 97% | 97.3%
Indicator 1.1.3: | ceaserian section rate
Baseline: | 4%
Planned Target: | 5% | 6.7% | 7% | 6.7%
Indicator 1.1.4 | unmet need of Familly planning |  |  |  | We used Couple Years of Protection(CYP) instead of unmet need of family planning(the indcator in RBF) because there is no data on unmet need of family planning for 2021 and 2022 since it is collected every five years through houshold surveys. The CYP (estimates the protection from pregnancy provided by contraceptive methods during a one-year period) that is obtained from rountine(DHIS2/HMIS) data collection. Comparing the result achieved with the baseline shows a 65% increase ( from 8420 to 13934) | DHIS2/HMIS
Baseline: (CYP 8420) | 25.5% | 9976 | 3957 | 13934
Planned Target: (8883, a 5% increase from the CYP Baseline) | 20.5%
Indicator 1.1.5: | postpartum care coverage
Baseline: | 65% | 91% | 94% | 92%
Planned Target: | 68%
Indicator 1.1.6: | ANC 4+
Baseline: | 68% | 31% | 31% | 31% |  | RMNCAH Score card
Planned Target: | 78%
Indicator 1.1.7: | malaria IPTp3
Baseline: | 55%
Planned Target: | 65% | 42% | 51% | 45% |  | DHIS2/HMIS
Indicator 1.1.8: | DPT3/Penta 3 coverage
Baseline: | 32%
Planned Target: | 38% | 78.2% | 77.3% | 78% |  | DHIS2/HMIS
Indicator 1.1.9: | ARI/pnuemonia consultations <5 years
Baseline: | 78% | 68% | 65% | 68% | We used DHIS2 while baseline figure was from DHS which does not cover many private facilities. Addtionally, The decline may be attributed to the disruption in health service delivery, access to and utilization during the COVID 19 pandemic, availability of human resources and supply chain issues. | DHIS2/HMIS
Planned Target: | 85%
Indicator 1.1.10: | diarrhea consultations <5 years
Baseline: | 55%
Planned Target: | 65% | 36% | 35% | 36%
Indicator 1.1.11: | fever/malaria consultations <5 years
Baseline: | 41%
Planned Target: | 50% | 60% | 61% | 61%
Indicator 1.1.12: | number of adolescents reached with RMNCAH servcies through MPTF project
Baseline: | 0
Planned Target: | 8300
Indicator 1.1.13: | Number of facilities strengthened to deliver RMNCAH package
Baseline: | Baseline: 0
Planned Target: | Planned Target: 35 | 35 | 35 | 35 |  | Project report/HMIS
Indicator 1.1.14: | Number of targeted facilities strengthened to deliver compete set of EmONC signal functions
Baseline: | Baseline: 0
Planned Target: | Planned Target: 17 | 17 | 17 | 17 |  | Project report/HMIS
Output 1.2: | Supply chain management capacity of three CHT enhanced through the provision of lifesaving RMNCAH & N medicines, drugs commodities |  |  |  |  | DHIS2/HHFA- IDSR
Indicator 1.2.1: | Availability of tracer medicines
Baseline: | 42% | 70% | 70% | 70%
Planned Target: | 60%
Output 1.3: WASH and IPC standards reinforced in targetted health facilities/ health care workers to minimize health care workers infiections and risk of facilityand healthcare acquired infections | WASH and IPC standards reinforced in targetted health facilities/ health care workers to minimize health care workers infiections and risk of facilityand healthcare acquired infections
Indicator 1.3.1: | facilities meeting minimum WASH standards | 60% | 60% | 60%
Baseline: | 13%
Planned Target: | 35%
Output 1.4: Strengthened capacities of three county health teams for better oversight and coordination of RMNCAH interventions | Strengthened capacities of three county health teams for better oversight and coordination of RMNCAH interventions
Indicator 1.4.1: MPDR reporting rate | Matenal and Perinatal Death Surveillance (MPDR) reporting rate
Baseline: | 8.8% | 12% | 14% | 13%
Planned Target: | 20%
Indicator 1.4.2: | HMIS reporting rate
Baseline: | 85% | 96% | 97% | 97%
Planned Target: | 95%
Indicator 1.4.2: | CHTs with AoP, functional coordination and updated EPR plan
Baseline: | 0 | 1 | 3 | 3
Planned Target: | 3
Indicator 1.4.2: IDSR reporting | IDSR reporting
Baseline: | 100% | 100% | 100% | 100%
Planned Target: | 100%

## Communication
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well as picture material please make sure you include all credits and share them in high resolution.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board