## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | JOINT PROGRAM - "NUWA TAJIMAT" | Overall Duration (months) | 17
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-11-01
MPTF Office Project Reference Number: | 124540 | Original End Date (dd.mm.yyyy) | 2022-01-01
Country | Perú | In case of NCE Current End date(dd.mm.yyyy) | 2022-03-31
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | PAHO/WHO, UNFPA, WFP,UNAIDS | National counterparts (government, private, NGOs & others) and other International Organizations | Amazonas Health Directorate, Codorcanqui Health Network, National Center for Intercultural Health, Amazonas Regional Government, Condorcanqui local Goverment, Center for Disease Control and Prevention, Women's Emergency Center and the National Health Center for the Prevention and Control of Diseases.
Report Cleared By
o Name: | Igor Garafulic Olivares
o Title: | Resident Coordinator
o Email address: | igor.garafulic@un.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities andmj concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | The “Nuwa Tajimat” Joint Program (JP) was developed in the district of Nieva, which is one of the three districts of the province of Condorcanqui in the department of Amazonas, where the Awajún and Wampis indigenous peoples are located. It aims to address the impact of the COVID-19 pandemic on indigenous women's access to essential maternal health, sexual and reproductive health (SRH), response to gender-based violence (GBV) and nutrition services, which correspond to the four pillars of the JP. The activities of the JP were carried out in coordination with the Condorcanqui health network, Regional Directorate of Health Amazonas, local government and community leaders, in order to achieve intersectoral participation and achieve sustainability over time, adapting the activities to the needs of the population and respecting the worldview of the original peoples. Despite the great challenges faced by the JP such as the impact of the second wave of the pandemic (February-March 2021) that generated restrictions on mobilization; as well as difficult geographical access, connectivity and communication limitations; the project had important results and achievements detailed below: - With the technical and financial cooperation for the improvement and quality of health services, the health authorities approved the resolution of accreditation of two health establishments (HEs), with cultural adequacy and relevance at the first level of care which guarantees attention to the population respecting their culture. - The strengthening of community work through the Community Health Workers (CHWs) and the articulation with the Center for Prevention and Communal Surveillance (CPCS) allowed the arrival to families through home visits and educational sessions. - In order to contribute to the reduction of gaps in access to essential health services that save lives, the JP strengthened the care of pregnant women and women of childbearing age (WFA), with the intervention of a Mobile Brigade of Attention in SRH made up of two obstetricians, in communities of difficult geographical access (waterway and land). The brigade reached a total of 1753 orientations / counseling on SRH for informed decision of which 150 attentions were prenatal (85% were new pregnant women) which meant 40.3% of the total attention of the HEs prioritized for the intervention (includes screening of GBV to 44 pregnant women (15.9% of them were studying with GBV), 243 attentions in contraceptive methods representing 48.1% of the total attention of the prioritized health establishments, also contributed to the counseling and screening of STIs and AIDS in adults and young people. - Pregnant women's access to iron and folic acid supplementation was increased. Comparing with the coverage of 2020 (330 pregnant women) the JP contributed to the fact that 626 pregnant women were supplemented. In this sense, supplementation has doubled compared to 2020 and the goal established by the JP (413 pregnant women) was exceeded by 52%. - 214 women survivors of GBV have received care in socio-legal and health institutions in Condorcanqui, exceeding the programmed target of 33%. - The competencies of health personnel, CHWs in the four pillars of the JP were strengthened in 27 HEs contributing to access to essential services with an intercultural approach, as well as in the implementation of teams for the care of the pregnant woman in both the first and second levels of care. Of these, the implementation of a type I Blood Bank in the Hospital of Santa María de Nieva is important, key to reducing maternal mortality in the face of the main cause of it: hemorrhagic cause; benefiting the population of the entire province of Condorcanqui. The set of actions carried out by the JP has benefited a total of 21,342 people (population district of Nieva). 54% represent the female population of which 823 pregnant women have managed to receive 6 prenatal care that favored the prevention and detection of warning signs and avoid a maternal death. With these figures, the goal was exceeded by 25%.
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | The JP has as its main objective to address the impact of the COVID-19 pandemic on indigenous women's access to essential services and on maternal health, sexual and reproductive health (SRH), response to gender-based violence (GBV) and nutrition.
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | Outcome 1: Contribute to access to essential and vital health services with an emphasis on sexual and reproductive health in the context of COVID-19 and culturally relevant. The competencies of health personnel and CHWs have been strengthened in the 4 pillars of the JP to improve comprehensive care for pregnant women in health services. Likewise, comprehensive equipment has been implemented for the diagnosis of the pregnant woman in the first and second level of care. The interventions implemented in the JP have been taken up by the staff and strategy managers of the Condorcanqui Health Network as an institutional response that has favored sustainability beyond the focus of the JP. Through the intervention of the SRH brigade, timely and comprehensive care for pregnant women and WFA was strengthened, in an environment of trust and closeness through home visits and care in HEs including their communities. Outcome 2: "Indigenous women in the Amazon region exercise their sexual and reproductive rights, including the right not to be subjected to sexual and gender-based violence, through improved access to and timely response of culturally relevant health services to cases of sexual and gender-based violence in the context of COVID-19". The articulation between the institutions that make up the system of protection and care against GBV has been strengthened with the participation of: Women's Emergency Center (WEC), Community Center for Mental Health, Indigenous Peoples Strategy, technical secretary of the IPC. In addition, the participation of communal authorities in the process of articulation and the identification and registration of cases of GBV, including sexual violence, has been promoted. The capacity building of interdisciplinary teams of the HEs and WEC was strengthened to advance in the prevention and articulated and quality management of GBV cases in accordance with Law 30364. Law against violence against women and members of the family group, from a gender and intercultural approach.
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | Output 1.1 through dialogue and community participation, cultural adaptation was achieved, the strengthening of maternal health services and the generation of competencies in health personnel and CHWs, in response to cases of obstetric emergencies and care of the pregnant woman. Women and adolescents were also able to access essential SRH services (prenatal care, family planning, STIs and AIDS prevention and GBV screening) through the implementation of itinerant SRH brigades for care in hard-to-reach communities. Output 1.2 The strengthening of the capacities in maternal nutrition of 97 health professionals and technicians and 49 CHWs was achieved through training, monitoring, technical assistance, equipment of 48 HEs and production of communication material. Highlighting the articulated work of the health sector and community institutions Output 1.3 Strengthened the system of surveillance, monitoring and response of health personnel to maternal death with emphasis on the identification of COVID-19 cause Output 1.4 Community participation was strengthened by promoting practices related to health, maternal nutrition and COVID-19 control through culturally relevant material and training of communicators. Output 2.1 Achieved the Strengthening of the health and protection response (socio-legal) to prevent and treat cases of GBV in the context of COVID-19: through the development of a GBV response plan; protocols of attention and strengthening of competences of professionals, Output 2.2 Women's personal hygiene needs, including menstrual hygiene, were met and a culturally relevant women's empowerment communication strategy was implemented, which addressed the necessary transformation of gender norms that legitimize violence, and sought to promote their sexual and reproductive rights, including the right not to be subjected to violence.
3.2 | Results: Gender | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | GENDER MARKER 2 The Nuwa Tajimat Joint Programme (JP) has the main objective of addressing the impact of the COVID-19 pandemic on indigenous women's access to essential services and on maternal health, sexual and reproductive health (SRH), response to gender-based violence (GBV) and nutrition. In this sense, part of the objectives of the JP have been aimed at promoting the gender, human rights and interculturality approach. Likewise; gender is integrated into the analysis of cp as part of the context, causes, dynamics; ensuring that the project does not cause harm and does not reinforce inequality.
3.3 | Results: Direct Beneficiaries | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | Population of Nieva - (Focus of the Joint Program) TOTAL: 21,342 Age group: 0-4 = 7099 5-9 = 3152 10-14 = 18479 15-19 = 1358 20-59 = 7414 60 or more = 472 Gender: - female: 11,586 (54%) women of childbearing age: 6292 -male: 9,756 (46%) Source: INEI - REUNIS (2021) – Estimated
3.4 | Results: Indirect Beneficiaries | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | Population of the 3 districts of Condorcanqui ( Nieva, Río Santiago, Cenepa) TOTAL: 52,357 indigenous population 37,955 - 72% Gender - female: 26,886 (51.4%) -male: 25,471 (48.6%) Source: INEI - REUNIS (2021) - Estimated
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words) | Condorcanqui is a province characterized by its population in a situation of high vulnerability and where inequalities can be observed in access to health services; that is why in the development of the activities of the JP and as part of our recommendations; we highlight the ability to develop the activities starting from the analysis of the needs of the population, making them participants in these and being the protagonists. The JP, focusing on Amazonian women, seeks to promote their empowerment, the advancement of their autonomy, providing tools and information for the best exercise of their rights, eradicating all forms of revictimization of their figure.
3.6 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | The challenges and their solutions are described below: 1. Precarious communication infrastructure: for which a scheme of meetings was implemented once a week to coordinate, exchange experiences and update the activities to be carried out, as well as the planning of delivery of reports. 2. Difficulty in geographical accessibility: The "watershed implementation strategy" has been proposed for activities with the community, dividing the interventions into three geographically strategic points that are accessible, have stable communication and are recognized by the population. 4. Local Pandemic Prevention Measures: The JP has adapted to the sanitary restriction measures, rescheduling activities, reinforcing coordination with the Condorcanqui health network and maintaining the measures to prevent the spread of Covid-19 in the activities that were developed. 5. The high turnover of the HEs staff: Involving the Condorcanqui health network strategy managers allowed to maintain the processes of strengthening the capacities of the health personnel for the improvement of maternal health.
3.7 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words) | The JP is implemented in an indigenous region, so the articulated intercultural, community and intersectoral approach is key. In this regard we have identified the following lessons. 1. Include the compilation of "prior knowledge" through intercultural dialogues and situational diagnoses socio-cultural, is important to carry out the situational analysis of the territory. This process together with the local actors helps to determine the actions to be implemented. 2. Articulate activities with local state institutions, community leaders, key actors; as an intervention and sustainability strategy. 3. Importance of the use of the mother tongue (Awajún / Wampis) in relationships with community actors. 4. Validate the identified needs of the indigenous population before beginning the implementation of the project. 5. Accompaniment and monitoring of the training carried out in order to strengthen the skills learned and generate a change in attitudes. 6. The communication area must be developed as a transversal strategy; promoting the adherence of the population to preventive and health promotion activities. 7. Strengthen the management skills of health personnel in the 4 pillars of the JP 8. The presence of mobile brigades contributing to reduce the gap in access to health services in a humane and trustworthy environment 9. It is key to generate spaces for dialogue analysis and reflection with the actors involved in the 4 pillars of the JP. 10. Articulating the work and strengthening the capacities of the CHWs is important to generate a bond of trust with the community and strengthen health promotion and disease prevention
3.8 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | 1. Our main partner is the "Regional Directorate of Health Amazonas" and the "Condorcanqui Health Network", with whom a joint work plan has been developed, without duplicating activities and strengthening the existing activities to fulfill the tasks of the JP. Likewise, the JP managed to mobilize funds from the Condorcanqui Health Network - Nutrition and Maternal Health strategy; to train health personnel in the districts of “Río Santiago” and “Cenepa” in the nutrition component. 2. In relation to the work with community health agents, the work articulated with the Ministry of Public Health of the Provincial Municipality of Condorcanqui, through the work with the CPCS strengthen the work and guarantee its sustainability. 3. In relation to the attention of gender-based violence, the Provincial Instance of Consultation for the Prevention, Punishment and Eradication of Violence against Women and Members of the Family Group in charge of the protection/response to GBV, has forged alliances with a variety of actors at the local level including WEC, HEs and the Community Mental Health Centre "El buen vivir"; promoting a multisectoral and comprehensive approach to cases.
3.9 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words). | 1."Diagnosis of the nutritional situation of pregnant women and the identification of mechanisms of community participation" in the district of Nieva, which allowed to identify the main aspects to be strengthened both at the level of health personnel and community health agents, to improve nutrition in pregnancy 2. "Situational status of pre-exposure rabies vaccination (PrEP) in the Condorcanqui Network, Amazonas, in the scenario of the COVID-19 pandemic". With the objectives of updating the coverage of rabies PrEP vaccination and its stratification according to variables of interest and identifying relevant aspects related to rabies PrEP vaccination that affect or may affect to improve coverage. 3. "Situational status of vaccination against SARS-CoV-2 to people living with HIV in the Condorcanqui Network, Amazonas, in a pandemic scenario" with the aim of describing and identifying the coverage of the population living with HIV that has received two doses of the VACCINE against SARS-COV-2 in the Condorcanqui Health Network as well as describing the perception of health and vaccination of this vulnerable population. 4. "Training survey on individual and collective knowledge, attitudes and practices around maternal food and nutrition in the district of Nieva" whose objective was to have inputs to improve the actions of the project and for the implementation of the communication strategy for social and behavioral change, to improve maternal feeding and nutrition practices 5. "Investment Study for the achievement of the two transformative results related to Maternal Mortality and Family Planning in the province of Condorcanqui, Amazonas"; with the aim of reducing preventable maternal mortality and to increase the use of modern contraceptive methods in Condorcanqui.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words). | Not Applicable
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | MOBILIZATION OF FUNDS: The JP managed to mobilize an approximate S/ 10 130 PEN by the Condorcanqui Health Network - Nutrition and Maternal Health strategy; to train health personnel in the districts of Río Santiago and Cenepa on the theme: "Nutritional evaluation of pregnant women". This as a result of the importance generated by the intervention of the JP and the need to expand the benefit to the population of the aforementioned districts. The UNFPA agency mobilized its own emergency funds that allowed the donation of PPE (Mask KN95 - 5020 units, Mask type II - 89,450 units) to strengthen the biosecurity of sexual and reproductive health providers of the Condorcanqui Network and 60,000 three-fold masks for users of essential SRH services. With a total value of $31,998.38 USD DONATIONS: 1. For the strengthening in the care of the pregnant woman (a) First level of care in prioritized health facilities: • Nutrition Pillar: 13 tallimeters, 13 scales, 03 hemoglobinometers, 50 tables of recommendations for weight gain in pregnancy, 50 obstetric tapes, 50 pocket gestograms, 30 technical guides for anthropometric nutritional assessment of the pregnant woman. • Pilar Maternal Health: 66 anti-shock suits; 65 blood pressure monitors; 17 Dopplers. b) Second level of care at the Hospital Santa María de Nieva • To respond to the main cause of maternal death (hemorrhagic cause), a type I blood bank and photovoltaic equipment (solar panels, batteries) were implemented to give sustainability to the electrical fluid of the Implemented Blood Bank. 2. For the strengthening of the community and key actors • improve the conditions of hygiene, respect, dignity, and that access to information on self-care: 1000 Dignity Kits • Identification and strengthening the work of community agents: 210 community health agent kits 3. Communication material with cultural relevance • Pilar Maternal Health: 71 Banners on prevention measures against COVID-19 and 71 Banners on warning signs in pregnant women in the context of the COVID-19 pandemic; 250 guidance guides for community agents and 250 flipcharts for ACS home visits. • Nutrition pillar: 200 guides for intercultural counselling and communication for the improvement of nutrition practices aimed at health personnel; and 300 kits for DHW for nutritional advice consisting of a case with 9 sheets and 4 primers. • Pilar GBV: 61 banners, 300 plastic folders; 80 USB with the Violence Prevention course; all these materials contain prevention messages and GBV care.

## Project Indicators
Please include ALL indicators in the project document. Include the indicators and Baseline, Planned Target and Actuals for both OUTCOME and OUTPUT levels. "Actuals" refer to the total figures achieved for each indicator. Include separate actuals for 2021 and for 2022 (if applicable). Explain if targets were not achieved. Include means of verification. Use as many outputs cells as needed to present all project indicators.
| INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | % | DATA: ACTUALS 2022 (if applicable) | Total actuals 2021-2022 | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1
Indicator: Number of pregnant women who received 6 prenatal controls in Condorcanqui, Nieva | The importance of having the 6 prenatal controls is the identification of the risks in the pregnant woman, as well as the minimum controls in this period, informed by the health system. The goal was met by exceeding it by: 25% | 823 | 125% | Non applicable | 823 | Non applicable | Condorcanqui health network - Hospital Information System (HIS)
Baseline: 658
Planned Target: 790
Indicator: Number of health establishments with strengthened capacities in essential services and cultural relevance with an integrated network approach in Condorcanqui, Nieva | Health establishments prioritized for their strengthening in the 4 pillars of the JP | 27 | 100% | Non applicable | 27 | Non applicable | PAHO - UNFPA - WFP
Baseline: 0
Planned Target: 27
Output 1.1
Indicator 1.1.1: Number of obstetricians who were trained in "Obstetric Emergencies" belonging to health facilities in Condorcanqui, Nieva | The training in "Obstetric Emergencies" responds to the need to detect and respond to a situation where the pregnant woman is in danger and avoid a maternal death | 27 | 100% | Non applicable | 27 | Non applicable | PAHO - Condorcanqui health network
Baseline:23
Planned Target:27
Indicator 1.1.2: Blood bank implemented in Condorcanqui, Nieva | Implemented against the leading cause of maternal (hemorrhagic) death | 1 | 100% | Non applicable | 1 | Non applicable | PAHO - Condorcanqui health network, Regional Directorate of Health Amazonas
Baseline:0
Planned Target:1
Indicator 1.1.3: percentage of Community Health Workers strengthened in prevention and promotion measures in the context of COVID-19 in Condorcanqui, Nieva | Community Health Workers are the first contact of the health sector with the community, developing activities in an environment of trust. The goal was met by exceeding it by: 34% | 94 | 134% | Non applicable | 94 | Non applicable | PAHO - Condorcanqui health network
Baseline:0
Planned Target: 70%
Indicator 1.1.4: Number of health personnel who received training and were strengthened in Family Planning Modules in Condorcanqui district | Family planning training contributes to avoiding an unwanted pregnancy. The goal was met by exceeding it by: 9% | 32 | 109% | Non applicable | 32 | Non applicable | UNFPA - Condorcanqui health network
Baseline: 18
Planned Target: 32
Indicator 1.1.5: Percentage of contraceptive care, carried out by the mobile brigades in health establishments prioritized according to needs in Nieva | The Mobile Brigade of attention in SRH made up of two obstetricians, moved to the communities where access to care and geographical access (access by river) is limited. The brigade carried out a total of 243 care in contraceptive care representing 48.1% of the total attention of the prioritized health establishments. The goal was met with an additional contribution of 220.7% over the 15% that was set as a goal | 243 | 48% | Non applicable | 243 | Non applicable | UNFPA - Condorcanqui health network
Baseline: 0
Planned Target: 15%
Indicator 1.1.6: Percentage of adults and young people receiving counselling and screening for STIs and AIDS by mobile brigades in health establishments prioritized according to need in Nieva | The Mobile Brigade of attention in SRH made up of two obstetricians, moved to the communities where access to care and geographical access (access by river) is limited. The brigade carried out a total of 362 orientations/counseling. It represented 45.9% of the total care of the prioritized health facilities. The goal was met with an additional contribution of 206% over the 15% that was set as a goal | 362 | 46% | Non applicable | 362 | Non applicable | UNFPA - Condorcanqui health network
Baseline: 0
Planned Target: 15%
Indicator 1.1.7: Percentage of pregnant women who receive prenatal care by the mobile brigades in health establishments prioritized according to the need of Nieva | The Mobile Brigade of attention in SRH made up of two obstetricians, moved to the communities where access to care and geographical access (access by river) is limited. The brigade carried out a total of 150 services, representing 40.3% of the total number of services in the prioritized health facilities. The goal was met with an additional contribution of 168% over the 15% that was set as a goal | 150 | 40% | Non applicable | 150 | Non applicable | UNFPA - Condorcanqui health network
Baseline: 0
Planned Target: 15%
Output 1.2
Indicator 1.2.1: Number of pregnant women who received iron sulphate and folic acid supplementation in Condorcanqui, Nieva | The supplementation of iron, ferrous sulphlux and folic acid in prenatal consultations, contribute to the prevention of anemia in pregnancy. Exceeded the goal by 52% | 626 | 171% | Non applicable | 626 | Non applicable | WFP - Condorcanqui health network
Baseline:330
Planned Target: 413
Indicator 1.2.2: Number of health establishments prioritized that have their capacities strengthened in the nutrition component in Condorcanqui, Nieva | health establishments which have equipment for the diagnosis of anemia, as well as the personnel trained in this component | 8 | 100% | Non applicable | 8 | Non applicable | WFP - Condorcanqui health network
Baseline:0
Planned Target:8
Indicator 1.2.3: Number of Community Health Workers strengthened in the Nutrition component in health establishments prioritized in Condorcanqui, Nieva | The strengthening of the Community Health Workers responds to the prevention of anemia in pregnant women from community activities. The goal was exceeded by 75% | 49 | 164% | Non applicable | 49 | Non applicable | WFP - Condorcanqui health network
Baseline:0
Planned Target:28
Output 1.4
Indicator 1.4.1: Number of communication packages developed and disseminated with intercultural relevance translated into Awajún languages | Cultural relevance, in addition to translation into the Awjún language, includes material adapted to the territory and understanding of the population. | 4 | 80% | 1 | 4 | Non applicable | PAHO - UNFPA - WFP
Baseline: 0
Planned Target: 5
Outcome 2
Indicator: Number of women survivors of GBV receiving care in socio-legal and health institutions in Condorcanqui | It indicates the JP's strengthened response to GBV as part of our goals. Exceeded the goal by 33% | 214 | 107% | Non applicable | 214 | Non applicable | UNFPA - Women's Emergency Center
Baseline: 167
Planned Target: 200
Output 2.1
Indicator 2.1.1: Number of rape emergency kits delivered to Women of Childbearing Age at the Hospital of Santa María de Nieva Nieva | Kits provided to survivors of sexual assault to prevent communicable diseases and unwanted pregnancy. Exceeded the goal by 33% | 8 | 133% | Non applicable | 8 | Non applicable | UNFPA - Women's Emergency Center - Condorcanqui health network
Baseline:0
Planned Target:6
Indicator 2.1.2: GBV Response Plan for the Nieva District | Plan designed and adapted to the context of the territory of Condorcanqui to deal with GBV | 1 | 100% | Non applicable | 1 | Non applicable | UNFPA
Baseline:0
Planned Target:1

## Communication
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
2. Upload here: Communications and Visibility (OPTIONAL)
To share the video as well as picture material please make sure you include all credits and share them in high resolution.
WEB SITE: https://www.paho.org/es/peru-programa-conjunto-nuwa-tajimat
BROCHURE JP "NUWA TAJIMAT" https://www.paho.org/es/documentos/folleto-nuwa-tajimat-programa-cojunto-hacia-bienestar-mujer-amazonica