## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | Strengthening a gendered and generational socioeconomic response through evidence-based policy advocacy and analyses. | Overall Duration (months) | 17
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 2020-10-13
MPTF Office Project Reference Number: | 00124306 | Original End Date (dd.mm.yyyy) | 1 Apr 2022
Country | Uruguay | In case of NCE Current End date(dd.mm.yyyy) | 2022-06-30
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNDP, UNFPA, UNICEF & UNWOMEN. | National counterparts (government, private, NGOs & others) and other International Organizations | National Government: Ministry of Education and Culture, Ministry of Social Development, National Institute of Statistics, Planning and Budget Office. Local government: municipalities. International organizations: IOM & ECLAC. NGOs: El Abrojo, Cardijn, CIESU. Private sector: Opción Consultores. Academy: Catholic University of Uruguay, FCS-UMAD.
Report Cleared By
o Name: | Soledad Salvador
o Title: | Project Coordinator
o Email address: | soledad.salvador@unwomen.org
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | The project has two fundamental tasks: the redefinition of the basic floor of the social protection system, adapting its implementation to situations of social emergency, and the design and implementation of pilot programs that allow dealing with the great consequences of the health crisis, which are: the loss of jobs for women from vulnerable sectors and the discouragement of educational continuity in adolescents in secondary education. To meet the first objective, existing programs were leveraged: • Support for updating the eligibility to access the Uruguay Social Card Program (TUS) and development of an outsourcing model that allows speeding up the processes of accepting new households, favoring the State's timely response to new shocks or situations of over-demand. • Emergency support for early childhood care (Uruguay Grows With You programmatic area): the construction of a vulnerability index to sort families on the waiting list, the development of the Teleassistance service, the training of program operators on forced pregnancies and maternity, and development of a care protocol. In turn, information was collected with the Time Use Survey and the Survey of the migrant population in the framework of COVID-19; the information system was developed to improve data interoperability and georeferencing based on the Unified Address System, and support was given to the construction of the multidimensional poverty line (global and with a gender and generations approach). To advance the second objective, new pilot programs were designed and implemented: • Employability and Care Program (August 2021- March 2022) • Support for Migrant Women (November 2021 – March 2022). • Educational Revolt Program (September 2021 - December 2021) Likewise, within the framework of the reconfiguration of the social protection matrix, the focus was on the territorial level and innovative approaches were implemented to strengthen the articulation and national and local state capacities: - Based on the definition of “social protection policy baskets”, their impact was analyzed in various departments of the country. Within this framework, capacity and implementation gaps were identified in conjunction with local actors. The departments analyzed were Rivera, Cerro Largo and Tacuarembo. Likewise, territories were approached from a micro perspective in the departments of Canelones (municipality of La Floresta) and Montevideo (four neighborhoods). - A capacity development strategy was implemented at the local level through three "demos" linked to various dimensions of social protection, namely: • Care- Municipality B (Montevideo), participatory municipal care plan • Income generation- Melo (Cerro Largo) and Paso de los Toros (Tacuarembó), empowerment of women entrepreneurs. • Policies for childhood and adolescence- Rivera. Technical assistance to the INAU Honorary Consultative Council: participation in monthly meetings of the council to facilitate coordination between institutions, preparation of analysis of the situation of children and adolescents in Rivera and Livramento, implementation of focus groups with children and adolescents. Processes of experimentation and innovation of public policies were activated with a focus on care based on challenges identified by national actors (INAU and Secretariat of care/MIDES) As of August 2021, the communication actions of the project were promoted with the hiring of a consultant and the signing of an agreement with a communication agency. This made it possible to develop a quarterly Newsletter, prepare inputs for the presentation of the project in the activities (roll up, Power Point design) and collect testimonials and images for the production of three audiovisuals with the project's achievements. From January 2022, there was also the support of a communication intern from UN WOMEN.
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | The general objective of the project was to create the conditions so that the populations most vulnerable to the socioeconomic impact of the COVID-19 pandemic in Uruguay -in particular, women, boys and girls who are part of households with lower incomes and are located in border departments, in the interior of the country or on the outskirts of Montevideo– are covered by the non-contributory social protection and emergency care systems, minimizing the adverse impact of this and future shocks in the short and long term. On the one hand, to achieve this objective, actions were designed and implemented that will allow the redefinition of the non-contributory social protection system and the emergency care system in Uruguay so that services and benefits reach those who need them most. The development of integrated information systems (sensitive to gender, multidimensional poverty conditions and critical welfare deficits) and the strengthening of institutional capacities for multilevel coordination of social policies through joint work and the provision of technical assistance to different state entities, will improve the allocation of resources directly benefiting thousands of people in vulnerable conditions who required protection measures in the context of the pandemic. However, to the extent that establishing such systems implies strengthening the capacities of the state to use data and evidence to inform and implement its policies and programs, this has the potential to translate into more comprehensive and better targeted measures in other areas of public policy (micro and macroeconomic policy, for example) beyond the realm of social protection. On the other hand, programs were developed to promote the employability of women in situations of economic and social vulnerability, and to improve the educational trajectories of adolescents. At the beginning of the pandemic, women's employment was the one that suffered the greatest impact and then it was difficult to recover. For its part, the reduction of in-person activities in the study centers discouraged attendance and for this reason, actions were developed to accompany and promote educational reintegration. In this sense, the national government placed emphasis on the development of programs and actions that contribute to the economic empowerment of women, creating a Department of Economic Autonomy in the National Institute for Women; and developed a proposal for the María Espínola Centers that seeks to serve adolescents from vulnerable socioeconomic contexts in order to improve their educational performance.
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | Outcome 1: A new basic protection floor is in place for 2021 allowing to better target the most vulnerable Uruguayans, particularly women headed households and women working in the informal sector. To establish the basic social protection floor: • The methodological criteria to statistically identify the basic social protection floor were agreed upon with the National Directorate of Data Transfers and Analysis (DINTAD) of the Ministry of Social Development (MIDES). • The design of an intervention model for the care of families with children 0-3 years of age was agreed to be implemented during 2022. (UCC/MIDES) • The dimensions and indicators to be included in the construction of the Global Multidimensional Poverty Index (MPI) were agreed with the National Institute of Statistics (INE). The MPI for childhood and adolescence was updated, and the indicators and questions that should be surveyed for the construction of a MPI with a gender approach were defined. A first calculation of the gender MPI was made based on the dimensions prioritized by the academic and political leaders interviewed. • The baskets of social protection policies were analyzed to identify implementation gaps in the territory and promote institutional capacities for effective coordination. • The National Institute for Women (INMUJERES) was supported with technical assistance for the development of the Department of Economic Autonomy, for the mapping of existing socioeconomic indicators, and the preparation of a manual that strengthens the capacities of the State to generate policies that promote women's economic autonomy. Outcome 2: "Employability program for women in situations of economic and social vulnerability, and improvements in the educational trajectories of adolescents". Two pilot programs were developed to promote the employability of women in situations of socioeconomic vulnerability: • The Employability and Care Program, through which personalized social support, training in transversal and digital skills, specific technical training, and labor insertion and/or (re) educational insertion were provided to 52 vulnerable women with children, providing care services for children, and transporting women to participate in different activities. The social organization Cardijn Uruguay led the implementation, with the support of INMUJERES, Uruguay Crece Contigo of MIDES, UN Women, governments and local actors (municipalities, mayors and mayors) and representatives of the private sector. • The program “Support for women entrepreneurs with a focus on the migrant population through training, advice and monetary transfer” was implemented, executed by UN Women, the International Organization for Migration (IOM) and INMUJERES, through which training, support and the formalization of the enterprises of migrant women and of the localities of Chuy, Rivera and Montevideo was promoted. It covered 32 women (16 migrants and 16 nationals). In addition, to improve the educational trajectories of adolescents, the "ReVUELTA Educativa" program was implemented, which sought to guarantee the reintegration and educational continuity in the first cycle of secondary and technical-professional education (high schools and UTU) of young people in three educational centers in Montevideo and one in Rivera. The implementation of the program was in charge of the social organization El Abrojo, in association with the Catholic University of Uruguay (UCU), and the support of UNICEF. For its part, an intervention program was defined and evaluated in the María Espínola Centers (secondary education centers) and recommendations for its future implementation. The program will be reiterated with other support from UNICEF and ANEP in 2022.
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | Output 1.1: An Integrated data system is delivered to be used by the Uruguayan Government, to improve the capacity of social protection policies to target vulnerable population, particularly women working in the informal sector and women heads of household in charge of children. With the implementation of the project, the development of an integrated data system was achieved for the use of the Government of Uruguay to improve the capacity of social protection policies to effectively reach the population in a situation of vulnerability, in particular women who work in the informal sector and heads of households in charge of children, since it was completed: - The development of the unique Georeferencing system of the State databases. This interoperable system of information from the State's administrative records (education, health, social security, work and housing) will be of mandatory use by the different State institutions as of 2023. In addition, the Methods and Data Analysis Unit of The Faculty of Social Sciences designed and produced Dashboards with information on the programs managed by DINTAD, and thus have integrated analysis of the data in real time to be better prepared for future emergency situations. - The development of global and specific multidimensional poverty indicators for children and adolescents, and gender (jointly between UNDP, UNICEF and INE). These will be relevant inputs to feed the georeferenced data system. - The Third National Survey on Time Use and Unpaid Work, which will feed into the available information on gender inequalities and multidimensional poverty. - Information on recent migration to Uruguay, in particular on families with children, who have been one of the groups most vulnerable to the economic difficulties caused by COVID-19. Output 1.2: A redefinition of the non-contributory social protection systems and emergency support that responds to the new challenges brought by COVID-19 and prepares the country to face future outbreaks. With the implementation of the project, great progress was made in the process of redefining the non-contributory social protection and emergency support system, adapting it to the challenges generated by the pandemic and preparing it for future emergency situations. To overcome the difficulties that the measures to control the waves of COVID-19 contagion generated in order to continue granting social benefits to the most vulnerable population given the impediment of making face-to-face visits, progress was made in the design of a field survey model to validate the sworn statement instrument (which would allow beneficiaries to receive social benefits under oath) in the face of acute exogenous shocks (UNICEF-UNFPA/DINTAD). In addition, a risk measurement was developed to respond to families with young children at the national level (in conjunction with the UCC programme). Output 1.3: Effective coordination institutional capacities developed in target territories, with focus in subnational governments' capacities and multi-level coordination of social policies. In order to strengthen the capacity for inter-institutional coordination for the implementation of social policies at the local level in the prioritized territories, baskets of social protection policies were prepared in three departments in the interior of the country (Tacuarembó, Cerro Largo and Rivera), a locality (La Floresta in Canelones) and four neighborhoods of Montevideo. As a result, assets and gaps in the implementation of social protection policies at the territorial level were identified, and recommendations were prepared together with the national and departmental authorities. In turn, through the innovation and experimentation strategy (output 2.3), a methodology of "demonstrative cases" [Demos] was designed to collect learning, perceptions and collective constructions. This methodology allows not only to learn from the most complex and dynamic phenomena at the community level, but also to influence these dynamics, prioritizing the evolution of processes and relationships (networks) before particular and individualized results. The processes implemented in this strategy, which were identified – for the most part – through the diagnosis of social protection and resilience baskets in the territory, will contribute to closing implementation gaps. Output 2.1: Support for the ANEP María Espínola Centers to guarantee the permanence and educational continuity of adolescents from a critical socio-economic context and UCC initiatives to strengthen positive parenting practices. To support the development of ANEP's María Espínola Centers, the "ReVUELTA Educativa" program was implemented, whose objective is to guarantee the reintegration and educational continuity of adolescents in the first cycle of secondary and technical-professional education (high schools and UTU ). The program was implemented by the social organization El Abrojo, in association with the Catholic University of Uruguay (UCU), and was supported by UNICEF. The actions were aimed at the personalized accompaniment of the students that the center refers to the program and the work with their families to contribute to the integration and permanence in the centers. The program was implemented in four centers (one in Rivera and three in Montevideo), of the twelve that exist throughout the country. 230 students participated in the program: 64% from Montevideo centers (CEA 203 Manga 21%, Utu Maroñas 2 21% and Utu Lavalleja 22%) and 36% from Liceo Nº4 de Rivera. The difficulties they presented consisted of: a quarter of them were disconnected from the center, a third had intermittent attendance, half had reading and writing difficulties, and the rest had different variants of lack of motivation or interest. Among the first results identified at a quantitative level are that 60% of the students contacted reconnected with the study center and 70% improved their grades. To close the program, a filming session was organized to collect the experience through the vision of the students, families, authorities, educators and professionals who have been part of this process. Given the success of the program, ANEP and UNICEF have already agreed on a new edition in 2022. Support was given to UCC in the establishment of a telecare model to respond to families with children from 0 to 3 years of age at a national level. The operators will continue to provide assistance until September 2022, with their own funds from UNICEF and UNFPA. Also in conjunction with UCC, through a consultancy, a first content proposal was made (corresponding to pregnancy and the first year of life) for an App on positive parenting practices, nutrition and availability of care services at the local level. Output 2.2: Employability program for women in a situation of economic and social vulnerability together with the development of care strategies that allow women to participate in the program and sustain their labor insertion. The Employability and Care Program was implemented between August 2021 and March 2022, in two territories in the interior of the country: Paso de los Toros and Pueblo Centenario (in the north of the country), and Las Piedras and Colonia Nicolich (in the south, the department of Canelones). The formulation and execution of the program was the responsibility of the National Institute for Women (INMUJERES), the Program Area of Uruguay Crece Contigo of MIDES and UN Women. Its implementation was in charge of the CSO Cardijn Uruguay with the collaboration of governments and local actors (municipalities, mayors and mayors) and representatives of the private sector. As innovative aspects, the Program provided a solution for the care of children, and the transfer of women so that they can participate in the different activities. It also included: personalized psycho-social support, training in transversal and digital skills, specific technical training, and job placement and/or educational (re)placement. The specific technical training was aimed at dynamic sectors in the area and less feminized (Computer Science; Parks and Gardens; and Masonry and construction finalist). 53 women completed the program, of which: 14 resumed their studies, 23 did work practices and found work or have been nominated for job calls, and 13 formed a cooperative that provides masonry and gardening services in Paso de los Toros and Centenario. In different activities, the women themselves have recounted their experience and the contribution of the program to strengthening their self-esteem and their preparation for the world of work. In addition, the "Support for women entrepreneurs with a focus on the migrant population through training, advice and monetary transfer" program was implemented, which was carried out by UN Women with the International Organization for Migration (IOM) and the National Institute for Women (INMUJERES). During the pandemic, the flow of migrants in the dry border departments increased. The objective was to contribute to the generation of opportunities, capitalize on the benefits of migration in the country at the level of human and social capital, as well as favor socioeconomic inclusion processes and regularization of women's enterprises in Uruguay. This initiative lasted five months (November-March 2022) and covered 32 women (16 migrants and 16 from the host community). Lastly, marginal support was provided to promote the sustainability of women's employment in the Sarandí del Yí Nursery (of the UPM company). To this end, workshops were held with supervisors and workers between May and June 2022. The objective was for women to find a better place to insert themselves and stay, given the high vulnerability they face and the chances of desertion they suffer due to their care responsibilities. Output 2.3: Experimentation and innovation strategy for women's economic empowerment and a new architecture of solutions for care. An experimentation and innovation strategy was developed for the economic empowerment of women and a new architecture of solutions for care, to the extent that they were defined and agreed upon with the actors involved (Territorial Management Area and the Social Development Division of MIDES). The "demonstrative cases" [Demos] will be replicated/developed in different areas of the country to gather learning, perceptions and collective constructions. The demonstrative cases carried out are: • In Cerro Largo: the program of productive and commercial opportunities was developed for 20 women entrepreneurs from two localities (Arévalo, Noblía). Productive training program and capacity development through face-to-face and virtual meetings and personalized support with the aim that women entrepreneurs can professionalize their commercial strategy, enter a product sales network through a digital catalog and therefore achieve economic empowerment without the need for uprooting from their territory. • In Tacuarembó: accompaniment to a group of women beneficiaries of the project in the Municipal Nursery of Paso de los Toros. Work was done on the planning of inter-institutional work between the group of 13 women, the Municipality of Paso de los Toros and the Sembrando Project, to improve the management of the enterprise, and develop a planning of activities and roles for the whole year. • Rivera: Strengthening of the Rivera Honorary Consultative Council for Children and Adolescents. The process of preparing the departmental plan was supported with inputs of local information, analysis and use of evidence for decision-making and incorporation of the voice of children and adolescents arising from focus groups that investigated perceptions, opinions and stereotypes of gender as well as experiences in health and education services. Focus groups were implemented with children and adolescents in Rivera (groups from 9 to 11 years old and from 14 to 17 years old) • Montevideo: the care action plan of Municipality B and a visualization tool for citizens on care offers in the territory. Based on the results of these actions, experiences are extracted to feed the design of public policies at the local level. Two policy experiments were also carried out based on the needs raised by the National Secretariat for Care and the Secretariat for Early Childhood of INAU. They are: • Accessibility to Day Centers, there are difficulties for the transfer of older adults. • Strengthening of the communication strategy between the INAU and the CSOs that implement the CAIF Plan (child care centers for 1 to 3 year olds). The "Accessibility study for healthy child care: retraction and expansion scenarios due to health emergency in Montevideo" of the Catholic University of Uruguay (UCU) was completed. This study sought to provide evidence on the impact of the pandemic on the potential access of families with young children to the health system for basic check-ups.
3.2 | Results: Gender | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | The Project is Gender Marker 3, therefore, all the actions have been thought from its design with a gender approach. The Employability and Care program considered the situation of women most affected by the socioeconomic impact of the crisis generated by COVID-19. They are young women with small children from the interior of the country. At the same time, to facilitate attendance at training, care and transportation were resolved. The Cerro Largo and Tacuarembó “demo” supported ongoing processes to strengthen entrepreneurial capacities for economic autonomy. The "demo" of Municipality B generated a roadmap to advance in care responses and generated a tool to visualize the supply and demand of services with a focus on women with dependent children. The ReVuelta Educativa program considered the situation of adolescents who do not attend school due to home care responsibilities. The EUT survey seeks to make visible the change that the pandemic may have generated in the distribution of home care responsibilities. The elaboration of a Gender MPI will also help to understand the unequal impacts of the measures implemented during the pandemic on the poverty of men and women. The official MPI incorporates a gender approach.
3.3 | Results: Direct Beneficiaries | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | TOTAL 312 persons plus 4300 families. Disagregated by population group and age range (Female: 176 Male: 136 Children: 4300 (0-3 years old) Youth 250 Elder: 92 People living with a disability: no data (estimated low) Disaggregated by Location: Rural: XXX Urban: XXX Any other location: XXX
3.4 | Results: Indirect Beneficiaries | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | TOTAL: 1.2 mill Estimated: 1.2 mill and/or Verified: XXX
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words) | In the design of the program "Support for women entrepreneurs with a focus on the migrant population through training, advice and monetary transfer", women from the receiving community were incorporated as beneficiaries because the previous experience of the IOM showed that it was the best way to avoid causing harm to the migrant population. In the implementation of the ReVuelta Educativa program, the families of the students were involved so that the educational reinsertion is sustained over time. It was also planned to carry out the activities on the educational campus itself so as not to distort class attendance, and all the teaching and student support staff were involved so that they felt part of the process. Within the framework of the implementation of the Productive Skills Development program aimed at groups of women entrepreneurs from Cerro Largo, individual meetings were held with each of the participants to obtain a more precise diagnosis, incorporate dimensions not generally contemplated, define the steps to follow and strengthen bonds of trust. For its part, in the “Employability, care and labor insertion” program and in the intervention associated with the Paso de los Toros Municipal Nursery, support was provided for child care and the transfer of women to enable their participation in all activities.
3.6 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | The difficulties encountered in the development of the project were concentrated in the postponement of face-to-face activities due to the pandemic. This delayed the implementation of several activities. Among them, the survey of information provided through visits to the beneficiaries and applicants of the Uruguay Social Card (TUS). To solve it, the number of planned visits was reduced, a pilot survey was generated and the affidavit was implemented as an alternative to the face-to-face visit. The start of the implementation of the Educational ReVUELTA and Employability and Care Programs was also delayed. For the ReVuelta Educativa program, the greatest difficulty was that the implementation was carried out when the school year was already well advanced. This could have hindered the success of the call since educational reinsertion in the last months of the year could have been considered not as significant. However, the results achieved were very satisfactory, which shows that the intervention methodology proposed by the CSO was adequate. Its implementation also began with great receptivity in some centers and less expectation in others, but when it was achieved, they gained the trust of all the actors who were able to demand it. In some cases, permanent dialogue with these actors was the most effective measure to achieve the expected results. On the other hand, the Employability and Care program had its greatest challenge at the beginning of its implementation because it was not possible to consolidate a stable group of participants. This implied an adaptation of the schedule provided by the CSO and of the resources allocated to monitoring and individual accompaniment, as well as becoming actively involved in the search for new participants. It was planned to train 80 women, and to achieve this, some 100 women passed through the program, of which 52 completed the specific training stage. As a lesson, it remains to be reviewed in future editions of the program the strategies for dissemination and convocation of the participants, and greater support to sustain the participation of women who face various situations of vulnerability. In the Support Program for Migrant and Host Community Women Entrepreneurs developed by UNWomen and IOM together with INMujeres, it was identified that there was a disincentive for some participants (mainly Uruguayans) to formalize for fear of losing the non-contributory benefits they receive from the State. From MIDES it was reported that during 2022 they will suspend these controls and will evaluate at the end of the year what impact it had on the formalization of employment. Finally, all the women participating in the program completed the formalization process. Another great challenge was to carry out the survey of the field work of the Third National Survey of Time Use, coordinated jointly by INE and INMUJERES together with UNWOMEN and UNFPA, due to the fact that the contributions received in the first tender greatly exceeded the available budget, which forced the company contracted to implement the field to be solely in charge of the administrative management of the contracted human resources, leaving INMUJERES and INE in charge of the general coordination of planning, execution and analysis. On the other hand, the work with the local actors of Rivera, Tacuarembó, Cerro Largo, Canelones and Montevideo was slowed down by some difficulties of articulation between government bodies at the departmental and national levels, the change of authorities in MIDES, which is the counterpart of this component, and the impacts of the crisis generated by the pandemic on the functioning of all the organizations linked to social protection. This involved continuously adapting to these changes and being very understanding of the situation in order to fulfill the project's purposes. The risk associated with the budget constraint (risk 1) was real at the beginning but it was not a limitation in the implementation of the project. In the 2021 accountability, the resources for early childhood were expanded, which benefited the actions that were already being developed with MIDES and UCC program area. In relation to risk 2 "Time and delivery", the use of accelerated procedures and the implementation of partnership agreements with NGOs created synergies with government efforts to avoid delays in the implementation of the Employability and Care, and ReVuelta Educativa programs. In turn, risk 3 referred to “Social Norms” that implies considering whether in times of crisis the position of women as beneficiaries of transfer programs could exacerbate situations of violence. In the articulations generated between programs and in particular, in the implementation of the Employability and Care program, work has been carried out in a very cohesive way between the MIDES and INMUJERES programs (which provide violence care services), and the OSC that implement the employability program. Administrative fragmentation (Risk 4) has also manifested itself in the reduction of the areas of inter-institutional articulation, but it is sought that the project manages to overcome those barriers. The purpose of increasing the interoperability of information sources to define a new social protection floor represents a significant effort to understand the limitations that arises the fragmentation and try to overcome them. As for risk 5, referring to social distancing measures, it did not generate inconveniences for the exchange, but it did affect the moment of implementation of the programs (Employability and Care and ReVuelta Educativa), the actions in the territory and the field work of TUS. On the other hand, risk 6, which was related to the consequences of the economic crisis in the labor market and the destruction of jobs, the Employability and Care program provided for a final stage of accompaniment in labor insertion to support the sustainability of the job. In Canelones, where opportunities did not arise as quickly as in Paso de los Toros, the support team was reinforced in the search for internships and job opportunities in companies.
3.7 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words) | Overall, the formation of working groups by theme has been very important to advance in the implementation/follow-up of the components of the program. Constant dialogue with the counterparts and between agencies has been key to solve issues that and enhance activity results. Having a person responsible for the communication area of the project has been fundamental to improve external visibility and internal communication. These are some policy, programmatic or operational lessons or conclusions that similar programs can serve: • Model for carrying out accelerated fieldwork in the face of acute exogenous shocks. The affidavit as an instrument that helps reduce the error of exclusion during the pandemic are mechanisms that could be transferred to other areas of the State and replicated at the national and departmental levels. • The improvement in the inter-operability of the databases available in the Social Area Integrated Information System through the georeferencing of the information with a Single Address Register is a model to be followed by other countries. Resorting to administrative records to have updated information in real time (especially during an emergency) is increasingly important. This will also imply resolving legal and technological issues and establishing a work commission to respond to these issues. • Based on the experience supporting the Uruguay Crece Contigo Program, the possibility of thinking about an evaluation of the set of actions developed by 2022 and designing a care model with different intensity of intervention was raised. This involves actions that were developed within the framework of this project (such as Telecare and the risk index to categorize families). • The Employability and Care Program model was proposed by INMujeres as a pilot experience to replicate in other areas of the country. In turn, the challenges posed in relation to sustainability in the participation of women, the solution of care and transfer, as well as the Internet connection in case of resorting to virtual training instances, are lessons that can be transferred to other programs and other State agencies such as the National Institute for Employment and Vocational Training (INEFOP), which conducts courses to promote employability. • The Migrant Women Support Program will continue to be perfected and replicated in other areas of the country, such as the border with Argentina, which is also receiving a migrant population and where IOM is installing offices for personalized attention to that population. From the beginning, INMUJERES expressed interest in continuing to support these initiatives and working on their design and implementation. • The approach strategy of the Educational ReVUELTA Program is a fundamental input for future editions of the program since the creation of María Espínola centers will further the successful experiences. • The collection methodology of the Time Use Survey will also allow the extraction of lessons that generate learning for future editions and for its contribution to the regional debate in the framework of the ECLAC Conference on Statistics. • The implementation of demonstrative experiences in social protection policies - in conjunction with the Acceleration Laboratory - implies a novel experience in the region and the world will be transferable to other countries.
3.8 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | The work with the partners of the project has been developed through different working groups. At the beginning, four were formed and later they were expanded as the topics diversified. They are: 1) Group that handles data: it was formed prior to the approval of the project, but the project provided it with the resources to advance in the integration of the databases to strengthen the interoperability of the statistical system (the SIIAS – Integrated Information System of the Social Area) and support the georeferencing of the entire system. In the group participating by the government, the National Institute of Statistics (INE), the IDE (Spatial Data Infrastructure area) and the National Directorate for Data Transfer and Analysis (DINTAD) of MIDES, which is in charge of defining the beneficiaries for social benefits. By the United Nations agencies, leading participants from UNFPA and UN Women, and those responsible for the Uruguayan Agency for International Cooperation (AUCI) are always present. The project funds complement the resources that the institutions are already allocating to these ends. 2) Specific group for the development of the Time Use Survey in which the following participate: INE, INMUJERES, UNFPA, UN Women and ECLAC Chile. Contact was also established with the University of the Republic to discuss methodological issues of the survey and they requested to include some questions in the questionnaire for a research project that was presented to the National Agency for Research and Innovation (ANII). 3) MPI Groups: To advance in the formulation of the Multidimensional Poverty Indices, a group was formed made up of UNDP, UNICEF and the UNDP Regional Office for the Gender MPI, or the INE and the consultancy of OPHI (Oxford Poverty and Human Development Initiative) in the Global MPI. 4) Group of the Employability and Care program made up of INMUJERES, MIDES and UN Women was in charge of designing the program, calling organizations for its implementation and monitoring its execution. For its design, conversations were held with the National Director of Employment and with references from the National Institute of Employment and Vocational Training to collect their experience on the subject. An exchange was also carried out and a work table was established with the "Development in Transition" project that the National Employment Directorate (DINAE) is executing in other departments in the interior of the country with the Uruguayan Chamber of Information Technologies (CUTI) and the support of the Uruguayan Agency for International Cooperation (AUCI) and the European Union. During the execution of the program, ties have been established with the private sector, business chambers, municipal governments and mayors' offices. 5) Migrant population support group: Given the significant influx of migrants during the pandemic, and the difficulties that were identified for their labor insertion, it was agreed to jointly develop UNWOMEN with the International Organization for Migration (IOM) a program aimed at providing economic support, training and advice to women entrepreneurs. INMUJERES participated in the implementation of the initiative, contributing its perspective on the issues of economic autonomy. The monitoring group was made up of the three institutions. 6) Education Group: integrated by UNICEF and ANEP to design the call for the execution of the program in the María Espínola Centers, it incorporated the CSO that implements it during its execution. Given the success of the program and the expectations generated to continue with its implementation in 2022, it has already been decided to carry out an action with the support of OEI in the training of teachers of these centers to work on the learning difficulties of the students and replicate the program in 2022. 7) Territory Group: made up of UNDP, UNICEF, MIDES and local governments, it was formed for the implementation of local dialogues that allow defining an action agenda to close the implementation gaps in social protection policies. To make the results of these actions available to the general public, an agreement was made with the Ricaldoni Foundation and the UDELAR Faculty of Design to develop a visualization platform for the georeferencing system that emerges from the analysis of mobility and geographic gaps. The Catholic University of Uruguay also participates in this with the study on mobility. It is worth noting the unconditional support provided by the Uruguayan Agency for International Cooperation (AUCI) who participated in all the meetings of the Management Committee and in the working groups where their support and expertise on the issues were required. They have also favored exchanges with other cooperation projects, have supported the dissemination of activities, the coordination tasks of the project and have closely followed all the progress of its actions, helping to push or unblock the situations that required it.
3.9 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words). | - Closing report of the ReVUELTA Educativa program. '- Final report on the implementation of the Employability and Care program. '- Report on baskets of social protection policies. Canelones, Cerro Largo, Montevideo, Rivera and Tacuarembo. '- Accessibility gaps in women's autonomy policies in four territories in the interior of Uruguay. '- Potential accessibility to well child care in the city of Montevideo: analysis of retraction scenarios due to health emergency and strategic expansion of supply (PNUD URUGUAY – UCU) '- Multiple deprivations in childhood in Uruguay. Update to 2019. '- Witness report of the Emergency Basket Program. (UMAD-DINTAD) '- Strengthening institutional bridges: communication between INAU and CSOs '- The SNCyD Day Center service: The challenges regarding access '- Final report of activities "Productive Skills Development Program" '- Communication Report Marathon of innovation for children '- Inputs for the care plan of Municipality B.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words). | The First Management Committee approved the change in Outcome 2, Outputs 2.1 and 2.2, and indicator 2.1.2. The Outcome 2: “Expanded in-school system and care services are available for most vulnerable Uruguayans by 2021, especially in critical territories, minimizing epidemiological risks while reducing women's unpaid care workload”, was redefined as: "Employability program for women in situations of economic and social vulnerability, and improvements in the educational trajectories of adolescents ". The Output 2.1: “A national plan and protocol for the expansion of in school and care services is designed in dialogue with national stakeholders, using standards and international best practices” was redefined as: "Support for the ANEP Center Development Plan to guarantee the permanence and educational continuity of adolescents from a critical socio-economic context and UCC initiatives to strengthen positive parenting practices ". The Indicator 2.1.2: “Number of teachers with self-reported increased abilities to quality digital and remote education, by sex” is replaced by two others, which are: "Number of students who receive psychotechnical support until the end of the school year , out of the total number of students who start the courses in March "and" Number of students who finish the school year out of the total students who started the courses in March ". The targets for the new indicators are: "All students who require psychotechnical support receive it throughout the school year"; and "All students who started the school year finish it". The Output 2.2: “Large scale programs of care for children in most vulnerable areas will be piloted in partnerships with subnational governments and the private sector allowing working parents (particularly mothers) to return and remain in the labor force, combined with training and employment strategies targeted for vulnerable women ”was redefined as:" Employability program for women in a situation of economic and social vulnerability together with the development of care strategies that allow women to participate in the program and sustain their labor insertion ".
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | A part-time person responsible for the communication tasks of the project was hired. Carrying out the Time Use Survey implied that the State mobilized resources to support all the design, supervision and analysis work. The work carried out with DINTAD and UCC also involved a contribution of resources by the State to cover the set of activities carried out.

## Project Indicators
Please include ALL indicators in the project document. Include the indicators and Baseline, Planned Target and Actuals for both OUTCOME and OUTPUT levels. "Actuals" refer to the total figures achieved for each indicator. Include separate actuals for 2021 and for 2022 (if applicable). Explain if targets were not achieved. Include means of verification. Use as many outputs cells as needed to present all project indicators.
| INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | DATA: ACTUALS 2022 (if applicable) | TOTAL actuals (agreggated 2021 and 2022 if applicable ) | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]: A new basic protection floor is in place for 2021 allowing to better target the most vulnerable Uruguayans, particularly women head of households and women working in the informal sector. | [5 empty] | Reports prepared by the Unit of Methods and Access to Data (UMAD) of the Faculty of Social Sciences for DINTAD.
Indicator 1a: | Percentage (%) of beneficiaries of social protection schemes for vulnerable population, by type of programme. (Indicator contributing to SERP indicator 2.5)
Baseline: | By type of programme: Cash Conditional Transfers (CCT): 68,5% of poor households; Uruguay Social Card (TUS): 39,2% of poor households. Sex dissagregation not available yet. Percentage (%) of female-headed households of poor household=40% (Source: Social Sciences Faculty, based on National Continuous Household Survey 2019, INE.)
Planned Target: | CCT=at least 85% TUS=at least 50% Sex dissagregation will be advocated for. |  | Var CCT jun22/mar20 = 29% Var TUS jun22/mar20 = 26%
Indicator 1b: | Percentage (%) of poor female headed household benefitting from cash transfer programmes.
Baseline: | 66% (Source: own estimations based on National Continuous Household Survey, 2019, INE)
Planned Target: | Percentage (%) of women-headed households: at least 70% |  | %female household CCT = 96% %female household TUS = 90,3%
Output 1.1 An Integrated data system is delivered to be used by the Uruguayan Government, to improve the capacity of social protection policies to target vulnerable population, particularly women working in the informal sector and women heads of household in charge of children. | [5 empty] | The reports prepared by DINTAD based on the databases of the SIIAS (Integrated Information System of the Social Area) system.
Indicator 1.1.1: | An integrated non-contributory social protection system and emergency support mechanism is adopted by national institutions.
Baseline: | Boolean: Weak. Low interoperability incompleteness
Planned Target: | Boolean: Strong. High Interoperability, completeness |  | finished
Indicator 1.1.2: | Number of indicators sensible and gender transformative integrated as part of the new proposal of non-contributory social protection system and emergency support |  |  |  |  | The development of the Multidimensional Poverty Index with a gender approach and a manual on economic autonomy for State institutions.
Baseline: | 0
Planned Target: | At least 3 |  | a proposal for IPM Gender and the manual | a proposal for IPM Gender and the manual
Output 1.2 A redefinition of the non-contributory social protection systems and emergency support that responds to the new challenges brought by COVID-19 and prepares the country to face future outbreaks | [5 empty] | Information from the IDE (Spatial Data Infrastructure) on the institutions that have adopted the system.
Indicator 1.2.1: | Number of institutions that own and have capacities to operate an integrated data system to activate emergency support mechanisms and inform public policies to face future outbreaks.
Baseline: | 1
Planned Target: | At least 4 |  | its implementation will be mandatory in all state agencies from 2023
Output 1.3 Effective coordination institutional capacities developed in target territories, with focus in subnational governments capacities and multi-level coordination of social policies
Indicator 1.3.1: | Number of social development offices and development offices that engage in the regional network |  |  |  | Given the strategy adopted by OPP at the territorial level, it was assessed that the conditions were not in place to advance along this line during the project period. It is pending to retake this idea in the next meeting with the National Directorate of Social Development of MIDES. | Reports on progress in the implementation of the strategy that will include photos, videos, stories, etc..
Baseline: | 4
Planned Target: | 8 |  | no progress
Indicator 1.3.2: | National & subnational governments agree on an agenda to overcome implementations gaps in target territories |  |  |  |  | The agendas agreed with each local government.
Baseline: | No
Planned Target: | Yes |  | Yes
Outcome 2: Expanded in-school system and care services are available for most vulnerable Uruguayans by 2021, especially in critical territories, minimizing epidemiological risks while reducing women’s unpaid care workload. |  |  |  |  | The Outcome 2 statement was redefined as: "Employability program for women in situations of economic and social vulnerability, and improvements in the educational trajectories of adolescents".
Indicator 2a: | Percentage (%) of children from the first quintile of social vulnerability that participated in public education proposals. (Indicator contributing to SERP Indicator 2.2) |  |  |  | I was replaced for boolean indicators (No/Yes) in relation to the Empleability and Education programs
Baseline: | No
Planned Target: | Yes | Yes | Yes | Yes
Output 2.1: A national plan and protocol for the expansion of in school and care services is designed in dialogue with national stakeholders, using standards and international best practices. |  |  |  |  | The Output 2.1 statement was redefined as: "Support for the ANEP Center Development Plan to guarantee the permanence and educational continuity of adolescents from a critical socio-economic context and UCC initiatives to strengthen positive parenting practices".
Indicator 2.1.1: | A communication campaign, gender and age responsive, to promote the importance of educational continuity. |  |  |  | It was a back-to-school campaign called “Every Day Counts” and developed in conjunction with other agencies such as UNESCO and PAHO. | The video and cards of the campaign.
Baseline: | Boolean: No
Planned Target: | Boolean: Yes | Yes | Yes | Yes
Indicator 2.1.2: | Number of teachers with self-reported increased abilities to quality digital and remote education, by sex. |  |  |  | The targets for the new indicators are: "All students who require psychotechnical support receive it throughout the school year"; and "All students who started the school year finish it" | Closing report "ReVUELTA Educativa" (September-December 2021)
Baseline: | 0 |  |  |  |  | Informe de cierre "ReVUELTA Educativa" (Setiembre-Diciembre 2021)
Planned Target: | More than 50% | 230 young people (59% men and 41% women) were contacted, 138 (60%) reconnected with their study center and 92 (70%) improved their grades. | --- | 230 young people (59% men and 41% women) were contacted, 138 (60%) reconnected with their study center and 92 (70%) improved their grades.
Output 2.2: Large scale programmes of care for children in most vulnerable areas will be piloted in partnerships with subnational governments and the private sector allowing working parents (particularly mothers) to return and remain in the labor force, combined with training and employment strategies targeted for vulnerable women.
Indicator 2.2.1: | Number of new gender and age-responsive care initiatives developed in partnership with local stakeholders. |  |  |  | The Output 2.2 statement was redefined as: "Employability program for women in a situation of economic and social vulnerability together with the development of care strategies that allow women to participate in the program and sustain their labor insertion".
Baseline: | Given the change in output, this indicator had no effect.
Planned Target: | --- | --- | --- | ---
Indicator 2.2.2: | A new socioeducational and labour programme within the institutional offer is targeted exclusively for vulnerable women developed and piloted |  |  |  |  | The program itself and its evaluation reports.
Baseline: | No
Planned Target: | Yes | Yes | Yes | Yes
Indicator 2.2.3: | Percentage of time deliver in paid and unpaid work for women and men, based on National Time Use Survey. |  |  |  |  | The results report of the National Time Use Survey 2021.
Baseline: | Women: 35.5% paid work and 64.5% in unpaid work; Men: 68.1% paid work and 31.9% in unpaid work. (Source: Module Use of time and unpaid work of the Continuous Household Survey 2013, INE-INMUJERES-FCS)
Planned Target: | New National Time Use Survey: tbd |  | no data available yet
Output 2.3: Experimentation and innovation strategy for women economic empowerment and a new architecture of solutions for care
Indicator 2.3.1: | Number of gender and age responsive implemented and evaluated experiments in target territories. |  |  |  |  | The reports with the results of the experiments.
Baseline: | 0
Planned Target: | 3 |  | 5 | 5
Indicator 2.3.2: | Participative roadmap for a local innovation strategy elaborated and ready for implementation.
Baseline: | Boolean: No |  |  |  |  | Mapa de Cuidados del Municipio B
Planned Target: | Boolean: Yes |  | Yes | Yes
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication
1. Impact Stories from the Field |  | Links | credit of materials
Agreement with Pro Bono Advertising agency | An agreement was reached with an advertising agency Pro Bono, that has already been working with UN Women on gender equality issues, to support from August 2021 until June 2022 in the production of videos that collect the testimonies of the participants of the programs and actions that are being developed within the framework of the project. In addition, it will take care of a compilation to show the results of the project as a whole. | n/a | n/a
Employability, care and job placement program | Employability, care and labor market insertion program aimed at women in vulnerable situations and designed to lay the foundations for these women to advance towards economic autonomy. The program was coordinated by the National Women's Institute (INMUJERES), the Uruguay Grows with You Program Area of MIDES and UN Women Uruguay. The program was implemented by the social organization Cardijn Uruguay. The program was a pilot experience that generated a replicable and scalable model in different areas of the country. Innovative aspects of the program included childcare and transportation to enable them to participate in program activities. The pilot program reached women in three specific areas of Uruguay: Paso de los Toros, Pueblo Centenario, Las Piedras and Colonia Nicolich. The program included personalized social accompaniment throughout the process, training in transversal and digital skills, specific technical training and job placement and/or educational (re)insertion. The specific technical training was oriented to dynamic sectors in the area and less feminized (Information Technology; Parks and Gardens; and masonry and finalist of work). The testimonies shared correspond to Bettina Barboza and Zulma Pereyra, both participants in the Parks and Gardens course offered to women from Paso de los Toros and Pueblo Centenario. Thanks to the efforts made by the Cardijn Uruguay team, Bettina and Zulma have participated in job interviews and are the first to find employment in a company specialized in the maintenance of green spaces and gardening. Attached is a link to their testimonial videos and their experience. | https://drive.google.com/drive/folders/1iJm1PeygD5aKQqzWnhbXO1BDRpxo0viT?usp=sharing | MPTF Communication
| Link to the video summary of the entire program. It includes testimonials from women beneficiaries, counterparts and government authorities. | https://www.youtube.com/watch?v=7LW6rTZmNDk | Cardijn
| Visit of the Director of the National Women's Institute (INMUJERES): The director of the National Institute for Women-MIDES, Mónica Bottero, participated in a meeting in September with the women of Pueblo Centenario and Paso de los Toros, within the framework of the Employability and Care program. | Newspaper Infopractica | n/a
|  | APU website | n/a
|  | INMUJERES Website | INMUJERES
|  | Newspaper Semanario Centro | n/a
| Within the framework of the Employability and Care program, two activities were implemented: the first one in October 2021 was the official launching in the three territories where it is implemented (Paso de los Toros, Colonia Nicolich and Las Piedras). It was attended by the women who make up the training groups, representatives of the local and national government, UN Women and Soledad Salvador gave the opening speech. The second was implemented in November 2021, in the cities of Paso de los Toros and Colonia Nicolich, where sensitive and reflective activities were carried out in commemoration of #25N, International Day for the Elimination of Violence against Women, together with the group of women who are part of the program. | Infopráctica - portal web: LINK | n/a
|  | Semanario Centro Paso de los Toros - call to the event: LINK | n/a
|  | Semanario Centro Paso de los Toros - Cobertura del evento link | n/a
|  | Semanario “La Tribuna” de Paso de los Toros: - LINK | n/a
|  | Radio UNO: They covered the event at the event but we did not have the audio. | n/a
|  | Sitio web Municipio Canario: LINK | n/a
|  | Infopráctica – Convocatoria: LINK | n/a
|  | Infopráctica - Cobertura del evento LINK | n/a
|  | Municipio Paso de los Toros LINK | n/a
|  | Summary photographs of both activities and territories | MPTF Team
| Within the framework of the Employability, Care and Job Placement program, the company On Point Global held a workshop on How to prepare for a job interview. Participants from Colonia Nicolich and Las Piedras were invited to the workshop, which was held at the company's offices. It was a very enriching meeting, since in addition to providing recommendations for the application and presentation of job offers, there was a space for exchange where the women present were able to evacuate doubts but above all also to share their previous experiences. The workshop was given by personnel of the company. | https://drive.google.com/file/d/1Yb2fMRq5T5-aBXrsNcBKz5FAPoqyXS74/view?usp=sharing | OnPointGlobal
| An exchange day was organized by the International Labor Organization (ILO), the Ministry of Labor and Social Security (MTSS-DINAE), National Women's Institute (INMUJERES) and UN Women to reflect on strategies to promote the economic autonomy of young women with family responsibilities based on the report "Difficulties of access and support for young women in the world of work in Uruguay in a pandemic context" (prepared by Equipos Consultores for ILO) and the experience of the social organization Cardijn in implementing the Employability, Care and Labor Insertion program (designed and coordinated by INMUJERES, UCC and ONUMUJERES). | https://drive.google.com/file/d/1Y9UQdi_zcbzxH8EXmvht1ELVfPRJeY5A/view?usp=sharing | MPTF Team
| Seminario Internacional: Recuperación económica con perspectiva de género | https://www.youtube.com/watch?v=wszgXYMdz10
ReVUELTA Educativa Program | The objective of the "ReVUELTA Educativa" Program was to guarantee reinsertion and educational continuity in the first cycle of secondary and technical-professional education (high schools and UTU). The support, implemented by the social organization El Abrojo, was oriented to the personalized accompaniment of the young people and the work with their families to contribute to their integration and permanence in the study centers. The objective was to guarantee the reincorporation to school of young people and adolescents who have been disconnected from the educational system as a consequence of the health emergency. This program was carried out jointly with the National Public Education Administration (ANEP) and UNICEF. To close this program, a day of audiovisual filming was organized to capture the experience through the vision of students, families, authorities, educators and professionals who have been part of this process. The filming was carried out in December 2021 in one of the educational institutions. | https://drive.google.com/drive/folders/1SAMF2eLQH1LMQHDs7m80pSWDQ3me4iE0?usp=sharing | Photos of the filing: MPTF Communication & Alva Agency. Photos activities: El Abrojo Team
| Link to the video summary of the entire program. It includes testimonials from women beneficiaries, counterparts and authorities. | https://www.youtube.com/watch?v=xgrpuVYzAsc | MPTF Communication & Alva Agency.
Support for migrant and host community women entrepreneurs | In order to document the impact of the project on women, in February 2022, the MPTF communications team conducted a filming in Rocha, gathering testimonies from some of the beneficiaries and also from authorities. The film is currently being edited and will be shared once it is finished. The program is developed by the IOM team, the National Women's Institute and UN Women. | https://drive.google.com/file/d/1nvdYMFWasKLukro3Ql6EdPvVtOn_mGxc/view?usp=sharing | MPTF Team
| Link to the video summary of the entire program. It includes testimonials from women beneficiaries, counterparts and government authorities. | https://youtu.be/kW0uml0y2KM | MPTF Team
| In May 2022, the closing activity of the Strengthening of migrant women entrepreneurs and the host community program was held in the city of Rocha. The meeting was attended by women beneficiaries from the different regions where this program was implemented: Rocha, Rivera and Montevideo. | https://drive.google.com/file/d/1f2kAi9YNcYzXWFNzMTD1XlzD4Z1pWyq_/view?usp=sharing | MPTF Team
| In the month of March 2022, in the framework of International Women's Day, together with the International Organization for Migration and the National Institute for Women, UN Women carried out a campaign with the objective of disseminating and reinforcing the importance of women's participation in the labor market, a key aspect in the construction of a sustainable future. The following video shows the main video of the campaign, which reflects through the testimonies of women entrepreneurs in Uruguay how their process of empowerment and economic autonomy has been for them. This campaign was made possible thanks to the testimonies of the women of Rocha, who were beneficiaries of the program: Support for migrant and host community women entrepreneurs | https://www.facebook.com/oimuruguay/posts/7308130919226838 | n/a
|  | https://www.instagram.com/p/Ca5YxWyFYuO/ | n/a
|  | https://twitter.com/OimUruguay/status/1501658275997175809 | n/a
|  | Marcia: https://youtu.be/frkBADQL_dM | MPTF Team
|  | María de los Ángeles y Aylen: https://youtu.be/ZQEkn04fzWI | MPTF Team
|  | María Thomas: https://youtu.be/Lt9AxGX4Idk | MPTF Team
|  | Reina: https://youtu.be/Td4KsPJG1CQ | MPTF Team
Support to employment sustainability at UPM's Sarandí del Yí nursery | Agencies: UNWOMEN. Counterparts: INMUJERES. Implements: Cardijn. / In the territory: Territorial Referent of INMUJERES | https://drive.google.com/file/d/1azy05EOe-6UFdTPbStWPyfc2PMa5djZK/view?usp=sharing | Cardijn
Analysis of social protection policy baskets at the territorial level | Agencies: UNDP and UNICEF. Counterpart: MIDES and Municipalities. Implements: Center for Information and Studies of Uruguay (CIESU). The work was carried out in the departments of Rivera, Cerro Largo and Tacuarembó; and in La Floresta (department of Canelones) and in five neighborhoods of Montevideo (Aquiles Lanza, Cochabamba and Felipe Cardozo, Maracaná Norte and Maracaná Sur and Tasistro). An in-depth qualitative study was carried out in each of them. The results obtained were presented to MIDES authorities at a meeting held in March 2022. | https://drive.google.com/file/d/1x8K4q3-SNwuzhEuGLFTJ2pJNi7Uoiy64/view?usp=sharing | PNUD
Demonstrative cases (1) | Agencies: UNDP and UNICEF. Counterpart: INAU, MIDES and Municipalities. CASE 1: Cerro Largo "Development of productive and commercial skills" program. Target group: 20 women entrepreneurs. 2 localities of Cerro Largo (Arévalo, Noblía). 2 face-to-face meetings, 5 virtual workshops and personalized accompaniment. Objective: women entrepreneurs can professionalize their business strategy, enter a product sales network through a digital catalog and, therefore, achieve economic empowerment. Implemented by: SELLIN. | https://www.youtube.com/watch?v=qWDTnD-O414 | PNUD
Demonstrative cases (2) | CASE 2: PASO DE LOS TOROS MUNICIPAL NURSERY. Accompaniment of the group of women cooperative members who were beneficiaries of the Employability and Care program and who are working in a space provided by the Municipal Nursery of Paso de los Toros. Worked on the planning of inter-institutional work between the group of 13 women, the Municipality of Paso de los Toros and the Sembrando Project, to improve the management of the enterprise and develop the planning of activities and roles for the whole year. Development of 6 inter-institutional face-to-face workshops. Implemented by: Cardijn. | https://drive.google.com/file/d/1O3hDn6tdXMIX-PR1AmpEtk9KqT1AzDGn/view?usp=sharing | PNUD
Innovation marathon for children | Agencies: UNDP and UNICEF. Counterpart: INAU and Municipality of Montevideo. Implements: Julio Ricaldoni Foundation (FING) and Escuela Universitaria de Diseño. 1st prize: Solution for outdoor spaces by CAIF. | https://maraton.ricaldoni.org.uy/ | PNUD
|  | https://www.youtube.com/watch?v=GihvRUEk_Ns&t=1s | PNUD
|  | https://www.youtube.com/watch?v=rmAme9hYnVA | PNUD
2. Upload here: Communications and Visibility (OPTIONAL) |  | Links | credit of materials
Launching the project MPTF (March 2021) | 1. Newspaper: Semanario Búsqueda | Interview with the United Nations Resident Coordinator in Uruguay, Mireia Villar (25/3/2021) | n/a
| 2. Central Television News Program: Subrayado (Canal 10) | Interview with the Project Coordinator, Soledad Salvador (25/3/2021) | n/a
| 3. Radio programs: Más temprano que tarde (El Espectador, 810AM) | Interview with the Project Coordinator, Soledad Salvador (25/3/2021) | n/a
| 4. Social media: Dissemination on social networks (Twitter and Facebook) | Note on the Portal of the Uruguayan News Agency UY.Press (25/3/2021) | n/a
Publication "Analysis of the impact of the pandemic on the labor market, inequality and poverty according to gender" | To disseminate the report "Analysis of the impact of the pandemic on the labor market, inequality and poverty according to gender", in networks and media, the following plates were made. | LaDiaria Newsletter | n/a
|  | AUCI Website | n/a
|  | Plates | MPTF Team
Informative Digital Newsletter | In the month of October 2021, the first informative digital newsletter was prepared, announcing the progress of all the components of the MPTF Project. It was disseminated through counterparts, the media, journalists, interested parties and the agencies of the United Nations system in Uruguay. The second newsletter was issued in December 2021, updating the progress and results of the project. These communications have resulted in very positive feedback and partners interested in collaborating. For example, as a result of the information, a WEPs company has been contacted for synergies in support of the Employability and Care program. The 3rd newsletter was sent out in May 2022. | Newsletter_october2021 | MPTF Team
|  | Newsletter_December2021 | MPTF Team
|  | Link Newsletter May 2022 | MPTF Team
Survey on Time Use and Unpaid Work | In November, the third edition of the Survey on Time Use and Unpaid Work (Encuesta de Uso del Tiempo), organized by the National Institute of Statistics, the National Women's Institute, the Uruguayan Agency for International Cooperation, UNFPA and UN Women Uruguay, was announced through an event. It was disseminated through different media and Soledad Salvador, Coordinator of the MPTF, participated in an article in El Espectador radio station to complement the national dissemination of the topic. | Link interview radio Soledad Salvador | n/a
|  | INE WEBSITE | n/a
|  | AUCI website | n/a
|  | SocialMedia Post1 | n/a
|  | SocialMedia Post2 | n/a
|  | SocialMedia Post3 | n/a
|  | SocialMedia Post4 | n/a
|  | SocialMedia Post5 | n/a
|  | Radio El Espectador-Interview Soledad Salvador | n/a
Day of the Future | In September 2021, the Day of the Future was held, an initiative of La Diaria which, together with social organizations and different collectives, promotes various debates. In these meetings, civil society, academia and political actors of the country participate. Soledad Salvador, coordinator of the MPTF Project, was invited to reflect, along with other leaders, on the effects of the pandemic on women and dissidents and how this will impact the future. | Newspaper La Diaria difussion | n/a
|  | Newspaper La Diaria | n/a
|  | Newspaper La Diaria-Amplification | n/a
|  | Photos taken during the presentation | MPTF Team
Cities that Care | In November 2021, the seminar Ciudades que Cuidan: aportes a la sostenibilidad de la vida (Cities that Care: contributions to the sustainability of life) was held with the aim of incorporating the concept of care in daily practices to stimulate the development of concrete experiences in the territories and neighborhoods from collective self-management and public policies. Soledad Salvador participated in the round table entitled "The Common, the Public and Care". It was organized by the Municipality of Montevideo, the European Union, civil society and Municipality B. | SocialMediaPost1 | n/a
SocialMediaPost2
SocialMediaPost3
Seminar Recording
MOVETE | The fourth edition of MOVETE with #UTECGlobal was held in October 2021. This activity organized by the Global Linking Center (CVG) of the Universidad Tecnológica (UTEC, Uruguay) aims to exchange views on the future of higher education, the education of the future from the perspective of digital transformation, and opportunities for internationalization in the university environment. Soledad Salvador participated in the module on "Gender and equity in educational institutions". | AUCI website | n/a
AUCI Website2
SocialMediaPost
Seminar Recording
Human rights in times of pandemic | "Dialogues in the INDDHH: Human rights in times of pandemic". The impact that the COVID 19 crisis has had on women's rights and in particular on the right to live a life free of violence. Organized by the National Human Rights Institution and the Ombudsman's Office INDDHH. Soledad Salvador, MPTF Project Coordinator, has participated as speaker. August 2021 | Seminar Recording | n/a
SocialMediaPost
Government website
Challenges and strategies to address the gender perspective in the world of work | "Challenges and strategies to address the gender perspective in the world of work". Organized by Industria Integrada, a project created by the Cuesta Duarte Institute of the PIT-CNT - with the support of INEFOP to generate analysis capacities and proposals from the workers in the face of technological changes that take place in production processes, work organization and working conditions. Soledad Salvador, MPTF Project Coordinator, has participated as speaker. August 2021 | SocialMediaPost | n/a
Seminar Recording
TV program "Que nadie quede atrás" (No one left behind) | Participation of Soledad Salvador and representatives of other United Nations agencies, in the TV Series "No one left behind". The program is produced and broadcasted by the television channel "TV Ciudad" (of the government of the city of Montevideo) and United Nations Uruguay. In this second chapter, the topic of Gender Co-responsibility was addressed. September, 2021 | Link to the Tv program | Tv Ciudad y Naciones Unidas Uruguay
|  | SocialMediaPost | n/a
Conversation: Strengthening the National Integrated Care System in Uruguay | In May 2022, the Pro-Care Network, UNFPA, the Faculty of Social Sciences and the Cultural Center of Spain held a discussion on "Strengthening the National Integrated Care System in Uruguay: Towards a National Commitment". Different representatives of the government, the United Nations system and civil society participated in the event. The round table "The United Nations and its contribution to care policies in Uruguay" was attended by representatives of different agencies of the System: Magdalena Furtado from UN Women; Soledad Salvador, Coordinator of the MPTF Program; Fernando Filgueira from UNFPA; Michel Guinard from UNICEF; Gabriel Botino from UNDP; Gabriel Porcile from ECLAC and Hernán Montenegro from PAHO/WHO. | https://www.youtube.com/watch?v=rWM1pg69-LU | n/a
| In the framework of this topic, we share the article made in May by La Diaria, to the Coordinator of the MPTF Program, Soledad Salvador, entitled "The National Care System in Uruguay: an opportunity for the economic empowerment of women" Link to the article of La Diaria | https://ladiaria.com.uy/politica/articulo/2022/5/el-sistema-nacional-integrado-de-cuidados-en-uruguay-una-oportunidad-para-el-empoderamiento-economico-de-las-mujeres/ | La Diaria
A summary video was made describing the components implemented within the framework of the MPTF Project in Uruguay. | A video was made summarizing the activities implemented within the framework of the project. It was made with the support of the pro bono agency Alva. | https://www.youtube.com/watch?v=5bvxvFg4qNU | Alva & MPTF Team
3. Communication materials to inform public policies: |  | Links | credit of materials
Knowledge product -Impact of the pandemic on the labor market according to gender | Publication of study on the impact of the pandemic on the labor market according to gender (april, 2021) | Publication of a study on the impact of the pandemic on the labor market according to gender. (Abril, 2021) | information in the publication