## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to the secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality results reports please follow the next guidelines: a) The narratives should be a well written, succinct summary clarifying what was done during the reporting period and the results achieved. It should highlight the JP achievements. It should also specify scope and beneficiaries. b) Factual, evidence-based reporting against the outcome and output and corresponding indicators in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not should be provided. d) Factual, evidence-based reporting against the outcome results and its alignment with the overall SERP joint workplan, and linkage to reporting on global-level SERP indicators. e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not. g) Reflect on innovation. Avoid generic and standard descriptions. Rather, present well documented features of successful innovative solutions truly new for you and which could enable replication efforts.
3 | Please fill out all sections of the reporting template before submitting to the secretariat via email to: nina.andersen@undp.org and cc.: maria.herrera@undp.org
B
DEADLINE: MARCH 31 ST, 2022
1 | ALL projects receiving funds in late 2020 and in 2021 must complete an ANNUAL report as per the end of the calendar year with a reporting period : date of start until 31 December 2021.
2 | The joint programmes which completed their activities in 2021 should deliver a FINAL report by March 31 at the latest and will not be obligated to provide an annual report.
3 | The joint programmes completing activities in 2022 will be asked to submit a FINAL report (by 31 August 2022)
4 | ALL projects must report number of direct beneficiaries.
5 | ALL projects must provide an update on project indicators

## General Information
Programme Title & Project Number |  | Programme Duration
Programme Title: | Empowering Vulnerable and at-Risk Communities Adjust to the New Normal | Overall Duration (months) | 6
Programme Number (if applicable) | 123298 | Start Date (dd.mm.yyyy) | 2021-06-17
MPTF Office Project Reference Number: | 125952 | Original End Date (dd.mm.yyyy) | 2021-12-31
Country | Zambia | In case of NCE Current End date(dd.mm.yyyy)
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNDP | National counterparts (government, private, NGOs & others) and other International Organizations | ZFAWIB
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19 (up to 500 words). | The objective of the project was to support the Governments efforts in reducing the risk of the spread of COVID 19 by providing standardised and certified masks to 20, 000 vulnerable at-risk communities and to support the domestic market for face masks which meet the certified standard, by targeting Lusaka-based women tailors to establish the capacity to produce 50, 000 face masks. The project further aimed to provide an opportunity for the tailors to enhance their capacity to operate more effectively. To achieve this the project identified the Zambia Federation of Women in Business (ZFAWIB) to implement the project activities. ZFAWIB had an extensive beneficiary network in the country's capital of 500 women tailors and has set up a catalytic revolving fund for women tailors that are participating in the production of masks to enhance their business resilience in light of the disruptive impact COVID- 19 has had on their businesses. ZAFWIB working through their partners also aims to ensure that all the members / tailors open individual mobile money accounts using mobile network operators (MNOs) of their choice. The mobile money accounts will strictly be used as channels for receipt of funds from the buyers of face masks. This will in turn increase their access to financial services as well as reduce risks of cash handling during and after the pandemic.
2 | Purpose | Please describe the project general objective specifying its link to COVID-19 response. | Through the Zambia Federation of Women in Business(ZFAWIB) that has been selected as the project's responsible party under the ongoing Business Reselinece Facility, ZFAWIB aims to target 500 women tailors in Lusaka city to produce 50,000 face masks. The project aims to secure 50,000 of these masks to distribute to atleast 20,000 vulnerable at risk populations through on going projects, in an effort to contribute to the governemnts efforts of reducing the spread of COVID 19. The project also aimed at supporting women run business to revover from the impact COVID 19 had on their businesses and through the luanch of the revolving fund support their reselinece to future shocks.
3 | Results: Outcome Level | Please include narratives describing the main project achievements against the project's overall goal (up to 300 words) | The aim of the project was to support the efforts of the governmnet in mitigating the Socioeconomic Impact of COVID 19 and safeguard people and their livelihoods by increasing income for small scale business enterprises through the production of 50, 000 cloth masks of which total production was targeted specifically for women led MSMEs. The project identified ZFAWIB with a network of 500 tailors and 10 consultants to provide mentorship and qulaity control oversight to the 500 women tailors. Project activties began in September 2021 and in January 2022, 50,000 masks were delivered.
3.1 | Results: Output Level | Please include narratives describing the main annual/ final results of each output included in the project document (up to 200 words) | The project aimed to contribute to the reduction in spread of COVID-19 amongst vulnerable hard to reach households by distributing the 50,000 masks to 20,000 vulnerable at risk populations through on going projects.
3.2 | Results: Gender | Please include project Gender results and its linkage with COVID- 19 response. If applicable, refer to the project's gender equality marker and any impacts they may have had on programming quality and results (up to 150 words). | The project provided economic support to 500 women tailors in Lusaka to produce 50,000 masks. The women tailors had faced challenges due to the impact COVID 9 had on their busnesses. Part of the fund s from the project have been earmarked for the use of launching a revolving fund to ensure that the women who have tradiotnally faced difficulties in accessing credit have expanded opportunities in accessing credit to support their businesses. The project was categorsied as GEM3, this helped ensure that the selection process of the implementing partner and project beneficiaries were kept within the project targets. Further due to the nature of the project, synergies have been explored with the GBV phase II project to explore possibilities of supporting GBV survivors amongst the porject beneficiaries.
3.3 | Results: Direct Beneficiaries | Please include total number of DIRECT BENEFICIARIES disaggregated by gender, age , location (rural, urban, any other location). Please avoid duplicating beneficiaries ensuring the dissagregated data adds to the total presented. | TOTAL 500 women tailors. Female: 500 Disaggregated by Location: Urban: 500
3.4 | Results: Indirect Beneficiaries | Please include total number of INDIRECT BENEFICIARIES. Please clarify if these are estimated and/or verified. If possible, disaggregate beneficiries by gender. | Estimated: 2000; Verified: not verified
3.5 | Do not Harm | Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention. ( up to 100 words)
3.6 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken to achieve the expected results) Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms(use up to 150 words). | Sourcing 3 seperate groups posed a risk on coordinating activities and standardisation of face masks to be produced, to mitigate this risk one responsible party was chosen to coordinate the actitvities, this turned out to be beneficial as ZFAWIB had more female tailors than the proejct originally envisioned and had structured a revolving fund facility to empower it's members during and after the pandemic to have an accesible source of capital injection. the main difficulties encountered so far have been sorind onboaring ZFAWIB and allowing our partner to be accustomed to UNDP regulations and proceedures.
3.7 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) (up to 250 words)
3.8 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 250 words) | A new partnership has been developed with ZFAWIB. ZFAWIB intends to use the funds of thre project to not only target the production of 50,000 masks across 500 women tailors but also create a revolving fund for the tailors that have had limited access to capital for their businesses. Half of the funds raised from the sale of face masks will be equally distributed among the 500 tailors as part of their initial working capital. The remaining funds will be kept under one common account, opened within a recommended bank of the tailors’ choice. The account will be controlled by ZFAWIB. The available funds in the account, will be a working capital loan fund and can be accessed by any of the tailors, who participated on the pilot in future. The project will initially aims to commence with one intervention focusing on the growth and resilience of one MSME segment, which is the tailors. After monitoring the pilot for three months, and depending on the progress, the project will be extended to the other lines of MSMEs segments
3.9 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken (up to 200 words).
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place (Up to 100 words).
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners. | The project is currently exploring opportunities to leverage existing CO Governance and Gender projects trageting GBV survivors as it was found that nearly 82 women who particpated in the proejct were GBV survivors

## Project Indicators
Please include ALL indicators in the project document. Include the indicators and Baseline, Planned Target and Actuals for both OUTCOME and OUTPUT levels. "Actuals" refer to the total figures achieved for each indicator. Include separate actuals for 2021 and for 2022 (if applicable). Explain if targets were not achieved. Include means of verification. Use as many outputs cells as needed to present all project indicators.
| INDICATORS DESCRIPTION AND DATA | DATA: ACTUALS 2021 | DATA: ACTUALS 2022 (if applicable) | TOTAL actuals (agreggated 2021 and 2022 if applicable ) | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome: To increase income for small scale business enterprises through the production of 50, 000 cloth masks through the Zambia Bureau of Standards of which total production has been targeted specifically for women led MSMEs |  |  |  |  | Zambia Federation of Women in Business(ZFAWIB) was selected as the sole implementing partner due to their beneficiary coverage(500women tailors) and ongoing empowerment project with women that had their incomes disrupted by COVID 19. | ZFAWIB BRF Concept Note and UNDP RPA
Indicator:2 women and 1 youth led cooperative trained and mentored on the standardization of production of cloth masks by ZABS. | Number of groups engaged to produce masks | 1 | 0 | 1
Baseline:0
Planned Target:3
Output 1.1: To contribute to the reduction in spread of COVID-19 amongst vulnerable hard to reach households | [5 empty] | Delivery Note and Project report
Indicator 1.2 2 women-led and 1 youth-led cooperatives contracted to produce 50,000 of re-usable cloth masks according to defined ZABS standards. | Number of masks produced | 50000 | 0 | 50000
Baseline:0
Planned Target:50,000
Indicator 1.1.2:Distribution of the 50,000 cloth masks produced distributed among over 20,000 vulnerable women across 3 provinces | Number of masks deistributed | 0 | 0 | 0 | The masks are due for distribution once UN implementing agencies reconfirm required number | N/A
Baseline:0
Planned Target:20,000
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant.
Link to documentary still in draft:
https://undp.sharepoint.com/:v:/r/teams/ZMB/Operations%20Section/Communications/IEC%20Materials/Mask%20Production/Undp%20Documentary%20Final-1.m4v?csf=1&web=1&e=lBd8R1
2. Upload here: Communications and Visibility (OPTIONAL)
https://www.zm.undp.org/content/zambia/en/home/blog/scaling-our-interventions-to-mask-up-the-vulnerable-communities.html
Link to photos: https://undp.sharepoint.com/:f:/r/teams/ZMB/Operations%20Section/Communications/IEC%20Materials/Mask%20Production%20Photos?csf=1&web=1&e=cr4qlQ
Link to draft documentary(Still in Draft: https://undp.sharepoint.com/:v:/r/teams/ZMB/Operations%20Section/Communications/IEC%20Materials/Mask%20Production/Undp%20Documentary%20Final-1.m4v?csf=1&web=1&e=lBd8R1
Link to how to make a mask: https://undp.sharepoint.com/:f:/r/teams/ZMB/Operations%20Section/Communications/IEC%20Materials/Mask%20Production?csf=1&web=1&e=t17Mpx
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well as picture material please make sure you include all credits and share them in high resolution.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board