## Dépenses par Résultat
Projet PBF: (intitulé) - Rapport Financier - 30/04/2023
Nombre de resultat/ produit | Formulation du resultat/ produit/activite | Budget total planifié | Budget dépensé (30/04/2023) | Budget planifié | Budget dépensé (date) | Budget planifié | Budget dépensé (date) | Total Budget Planifié | Total Budget Dépensé (date) | Pourcentage du budget pour chaque produit ou activite reserve pour action directe sur égalité des sexes et autonomisation des femmes (GEWE) (cas echeant) | Budget GEWE exécuté (date) | Notes quelconque le cas echeant (.e.g sur types des entrants ou justification du budget)
|  | Agence 1 |  | Agence 2 |  | Agence 3
RESULTAT 1: | Women and marginalized groups are able to take part in, and influence the, peacebuilding process between Twa and Bantu people’s groups in Tanganyika, DRC.
Produit 1.1: | Young-adult and adult women and minority group members are empowered to steer peacebuilding work in their communities
Activite 1.1.1: | Envision key stakeholders / Leaders | 2700 | 2699.5
Activite 1.1.2: | Contextualise the PB tools | 1000 | 1000
Activite 1.1.3: | Train PB champions (gender and ethnic bias awareness raising, CCTD facilitation) | 34000 | 11060.65
Activite 1.1.4 | Hold community PB dialogue (CCTD series 1) | 9600 | 9565
Activite 1.1.5 | Hold community PB dialogue (CCTD series 2) | 9600 | 9526.45
Activite 1.1.6 | PB champion learning gathering/session on series 1 & 2 and training for CCTD series 3 and 4 salary and other administrative cost . | 74171.44 | 62379.32
Activite 1.1.7 | Hold community dialogues (CCTD series 3) | 9600 | 9575
Activite 1.1.8 | Hold community dialogues (CCTD series 4) & PCs draft form action plans (1 per HA) | 2500 | 2491
Activite 1.1.9 | Form community PB network | 2750 | 600
Activite 1.1.10 | PB champion learning gathering on series 3 and 4. | 3600 | 3538.41
Activite 1.1.11 | Monitor the effective implementation of action plans and adapt their content as required by the contexte | 2748 | 595
Activite 1.1.12 | PCs repeat CCTD cycles in the project’s target communities | 0 | 0
Activite 1.1.13 | Special Measures Support | 2000 | 1705
Activite 1.1.14 | Safeguarding | 1000 | 795
| Produit total | 155269.44 | 115530.33
Produit 1.2: | Women led CSO intervening in conflict transformation processes between Twas and Bantus receive support to improve its organisational capacity to effectively respond to conflict in their community
Activite 1.2.1 | Conduct organisational capacity building analysis of the WL CSO | 4286 | 2574
Activite 1.2.2 | Plan with WL CSOs a work-session to develop action-plans | 2500 | 599.5
Activite 1.2.3 | Provide seed to WL CSO | 2748 | 2588
Activite 1.2.4 | Monitor the effective implementation of action plans and adapt their content as required by the contexte | 7155 | 7144.71
Activite 1.2.5 | Train the new EWG members on their role and duties | 0 | 0
Activite 1.2.6 | Expand the network of EWG (early warning group) set up by the REFETANG in the project’s target areas. | 0 | 0
Activite 1.2.7 | Special Measures Support | 2000 | 1000
Activite 1.2.8 | Safeguarding | 1000 | 0
| Produit total | 19689 | 13906.21
Produit 1.3:
Activite 1.3.1
Activite 1.3.2
Activite 1.3.3
Activite 1.3.4
Activite 1.3.5
Activite 1.3.6
Activite 1.3.7
Produit total
Produit 1.4:
Activite 1.4.1
Activite 1.4.2
Activite 1.4.3
Activite 1.4.4
Activite 1.4.5
Activite 1.4.6
Activite 1.4.7
Produit total
RESULTAT 2: | Women and marginalized ethnic groups’ equal access to land are upheld in Tanganyika, DRC.
Produit 2.1 | Non-violent land disputes resolution mechanisms are settled and supported in 10 affected communities in Nyunzu HZ.
Activite 2.1.1 | Conduct Land tenure assessment study | 16000 | 12266.64
Activite 2.1.2 | Capacity building on land-governance sensitive to gender and ethnicity | 63051 | 21734.12
Activite 2.1.3 | Organize ethnically and gender diverse Multi stakeholders Consultation, Dialogue, Awareness and Information sessions (at the local and provincial level) | 30000 | 25882.94
Activite 2.1.4 | Set up of the RFC in 2 communities (institutional, spatial and legal framework) | 75000 | 18658.68
Activite 2.1.5 | Develop/refine and validate land reform tools (local land charter, provincial Edict, ADRs (Alternative Dispute Resolutions) and manual of procedures at the provincial and local levels that reflect principles of gender justice, inclusion and diversity. | 94600 | 52113.17
Activite 2.1.6 | Participatory mapping of Community land (at village level) inclusive of diversity (gender and ethnicity) | 30000 | 10309.81
Activite 2.1.7 | Participatory enumeration of land rights and recordation in the RFC | 30000 | 16231.93
Activite 2.1.8 | Issuing of land certificates | 23051.1 | 4543
Activite 2.1.9 | Special Measures Support | 2000 | 0
Activite 2.1.10 | Safeguarding | 1000 | 0
Activite 2.1.11
| Produit total | 364702.1 | 161740.29
Produit 2.2 | Existing PB steering committees focused on land-dispute that are supportive of women’s right to land tenure and are reinforced to resolve or effectively address land-disputes between Twa and Bantu peoples group
Activite 2.2.1 | Set up and operationalize the Local Land Committee (Steering Committee) | 40000 | 30236.19
Activite' 2.2.2 | Capacity development of the members of the Local Land Committee on Conflict mediation, Gender Evaluation Criteria, Continuum of Land rights, land governance and Transparency | 50000 | 47244.21
Activite 2.2.3 | Organize land claims documentation and mediation sessions through the LLC (local land committee) | 37500 | 29216.09
Activite 2.2.4 | Special Measures Support | 1500 | 1064
Activite 2.2.5 | Safeguarding | 500 | 0
Activite 2.2.6
Activite 2.2.7
| Produit total | 129500 | 107760.49
Produit 2.3
Activite 2.3.1
Activite 2.3.2
Activite 2.3.3
Activite 2.3.4
Activite 2.3.5
Activite 2.3.6
Activite 2.3.7
Produit total
Produit 2.4
Activite 2.4.1
Activite 2.4.2
Activite 2.4.3
Activite 2.4.4
Activite 2.4.5
Activite 2.4.6
Activite 2.4.7
Produit total
Cout de personnel du projet si pas inclus dans les activites si-dessus | Support staff from Tearfund involve in the project | 139450 | 104515.23
Couts operationnels si pas inclus dans les activites si-dessus | Office related support cost for Tearfund offices | 34500 | 11536.06
Budget de suivi | M&E Cost for the project | 78944 | 41179.61
Budget pour l'évaluation finale indépendante | Fees for the independent auditor | 9313.6822 | 0
| Coûts supplémentaires total | 262207.6822 | 157230.9
Totaux
|  | Organisation recipiendiaire 1 |  | Organisation recipiendiaire 2 |  | Organisation recipiendiaire 3 |  | Total reçu | Total dépensé
|  | Agence 1 |  | Agence 2 |  | Agence 3
| Sous-budget total du projet | 931368.2222 | 556168.22
| Coûts indirects (7%): | 65195.7756 | 38931.7754
| Total | 996563.9978 | 595099.9954
| Taux de depenses (31/12/2022) |  | 59.72%

## Dépenses par Catégorie Conjoint (hidden)
Budget PBF par catégorie de coûts
Titre du Projet | Artisannes de Paix: Setting inclusive Peacebuilding Networks in Tanganyika and addressing land issues in displaced Twa and Bantu communities
Numéro du Projet | 00131128
Période du rapport | March-2022 to December 2022
Note: Inclure les révisions budgétaires s'il y en a eu |  | n/a
| Budget Contractuel |  |  |  | Montants perçus et Dépenses par agence
CATEGORIES | Montant par agence récipiendaire |  |  | BUDGET TOTAL DU PROJET | Agence 1 |  | Agence 2 |  | Agence 3 |  | Dépenses globales (31/12/2022) | Taux d'exécution
| Tranche 1 (%) | Tranche 2 (%) | Tranche 3 (%) |  | Montant perçu | Dépenses | Montant perçu | Dépenses | Montant perçu | Dépenses
1. Personnel et autres frais de personnel | 70123.704 | 70123.704 | 60106.032 | 200353.44 | 80234.9307 | 186522.25 |  |  |  |  | 186522.25 | 232.5%
2. Fournitures, Produits de base, Matérieux | 38342.5 | 38342.5 | 32865 | 109550 | 52156.6204 | 66997.02 |  |  |  |  | 66997.02 | 128.5%
3. Equipments, Véhicules, and Meuble (y compris l'amortissement) | 1540 | 1540 | 1320 | 4400 | 1259.7888 | 878 |  |  |  |  | 878 | 69.69%
4. Services Contractuels | 176471.785 | 176471.785 | 151261.53 | 504205.1 | 114092.6072 | 204716.11 |  |  |  |  | 204716.11 | 179.4%
5.Voyages | 340.55 | 340.55 | 291.9 | 973 | 651.9578 | 640 |  |  |  |  | 640 | 98.17%
6. Transferts et Subventions aux contreparties | 18911.55 | 18911.55 | 16209.9 | 54033 | 54032.6289 | 54159.36 |  |  |  |  | 54159.36 | 100.2%
7. Frais Généraux de fonctionnement et autres coûts directs | 20248.7888 | 20248.7888 | 17356.1047 | 57853.6822 | 23550.344 | 42255.48 |  |  |  |  | 42255.48 | 179.4%
Sous-Total Coûts du Projet | 325978.8778 | 325978.8778 | 279410.4667 | 931368.2222 | 325978.8778 | 556168.22 |  |  |  |  | 556168.22 | 170.6%
8. Coût de support indirect (7%) | 22818.5214 | 22818.5214 | 19558.7327 | 65195.7756 | 22818.5214 | 38931.7754 |  |  |  |  | 38931.7754 | 170.6%
TOTAL | 348797.3992 | 348797.3992 | 298969.1993 | 996563.9978 | 348797.3992 | 595099.9954 |  |  |  |  | 595099.9954 | 170.6%
>75%

## Dépenses par Catégorie
Budget PBF par catégorie de coûts
Titre du Projet | Artisannes de Paix: Setting inclusive Peacebuilding Networks in Tanganyika and addressing land issues in displaced Twa and Bantu communities
Numéro du Projet | 00131128
Période du rapport | March-2022 to April 2023
Note: Inclure les révisions budgétaires s'il y en a eu | n/a
| Budget Contractuel |  |  |  | Montants perçus et Dépenses par l'agence
CATEGORIES | Montant par agence récipiendaire |  |  | BUDGET TOTAL DU PROJET | Agence |  | Dépenses globales (30/04/2023) | Taux d'exécution
| Tranche 1 (%) | Tranche 2 (%) | Tranche 3 (%) |  | Montant perçu | Dépenses
1. Personnel et autres frais de personnel | 70123.704 | 70123.704 | 60106.032 | 200353.44 | 80234.9307 | 186522.25 | 186522.25 | 93.1%
2. Fournitures, Produits de base, Matérieux | 38342.5 | 38342.5 | 32865 | 109550 | 52156.6204 | 66997.02 | 66997.02 | 61.16%
3. Equipments, Véhicules, and Meuble (y compris l'amortissement) | 1540 | 1540 | 1320 | 4400 | 1259.7888 | 878 | 878 | 19.95%
4. Services Contractuels | 176471.785 | 176471.785 | 151261.53 | 504205.1 | 114092.6072 | 204716.11 | 204716.11 | 40.6%
5.Voyages | 340.55 | 340.55 | 291.9 | 973 | 651.9578 | 640 | 640 | 65.78%
6. Transferts et Subventions aux contreparties | 18911.55 | 18911.55 | 16209.9 | 54033 | 54032.6289 | 54159.36 | 54159.36 | 100.2%
7. Frais Généraux de fonctionnement et autres coûts directs | 20248.7888 | 20248.7888 | 17356.1047 | 57853.6822 | 23550.344 | 42255.48 | 42255.48 | 73.04%
Sous-Total Coûts du Projet | 325978.8778 | 325978.8778 | 279410.4667 | 931368.2222 | 325978.8778 | 556168.22 | 556168.22 | 59.72%
8. Coût de support indirect (7%) | 22818.5214 | 22818.5214 | 19558.7327 | 65195.7756 | 22818.5214 | 38931.7754 | 38931.7754 | 59.72%
TOTAL | 348797.3992 | 348797.3992 | 298969.1993 | 996563.9978 | 348797.3992 | 595099.9954 | 595099.9954 | 59.72%
Signed by :
Hebdavi Kyeya
Country Director
Tearfund

## UPB Budget Table Report
Annex D - PBF Project Budget
CSO Version
Table 1 - PBF project budget by outcome, output and activity
| Outcome/ Output number | Description (Text) | Recipient Organization | Recipient Organization 2 Budget | Recipient Organization 3 Budget | Total | % of budget per activity allocated to Gender Equality and Women's Empowerment (GEWE) (if any): | Current level of expenditure/ commitment (to be completed at time of project progress reporting) | GEWE justification (e.g. training includes session on gender equality, specific efforts made to ensure equal representation of women and men etc.) | Any other remarks (e.g. on types of inputs provided or budget justification, esp. for TA or travel costs) | Balance | %
PSF CODE | OUTCOME 1: | Women and marginalized groups are able to take part in, and influence the, peacebuilding process between Twa and Bantu people’s groups in Tanganyika, DRC.
| Output 1.1: | Young-adult and adult women and minority group members are empowered to steer peacebuilding work in their communities
1.1.0 | Activity 1.1.0: | Conduct baseline survey | 0 |  |  |  | 100% | 0 | The baseline will assess attitudes, beliefs and practices relating to PB from a gender and ethnic-focus. The findings will serve to identify the enablers and barriers to conflict transformation and the inclusion of women in the project target zones. | The costing for this activity is found in M&E section ligne 184. All M&E costings under M&E in ligne 184 are based on the costing for similar activities conducted by our organisation. | 0 | 0%
1.1.1 | Activity 1.1.1: | Envision key stakeholders / Leaders | 2700 |  |  | 2700 | 50% | 2699.5 | 50% of the envisioned leaders are women; topics addressed during the training include: gender equality and inclusion of women in the PB process |  | 0.5 | 99.98%
1.1.2 | Activity 1.1.2: | Contextualise the PB tools | 1000 |  |  | 1000 | 100% | 1000 | All existing CCTD tools will be contextualized to strengthen the focus on gender and ethnicity from the findings of the baseline. | This pricing is based on similar expenditures and invoices shared by our logistics department | 0 | 100%
1.1.3 | Activity 1.1.3: | Train PB champions (gender and ethnic bias awareness raising, CCTD facilitation) | 34000 |  |  | 34000 | 100% | 11060.65 | 100% of PB Champions will go through a training that focuses on gender equality in PB and inclusion (gender, ethnic...). 50% of participants are young-adult and adult women, minority groups included, will be trained to facilitate CCTDs. This implies improving women ability to assert themselves in a public setting, gain confidence in their abilities, and engage effectively in the PB process in their community | The training will be held in 2 series (Module 1,2 and module 3,4). These cost include the organization of the the training, Accomodation and trips for the consultant and Tearfund team from Goma to Tanganyika. | 22939.35 | 32.53%
1.1.4 | Activity 1.1.4 | Hold community PB dialogue (CCTD series 1) | 9600 |  |  | 9600 | 100% | 9565 | Safe spaces, civic-spaces are created to free women to speak out their minds and share on issues pertaining to their community. 100% of the project's facilitators (PCs) are decision makers. |  | 35 | 99.64%
1.1.5 | Activity 1.1.5 | Hold community PB dialogue (CCTD series 2) | 9600 |  |  | 9600 | 100% | 9526.45 | Same as above. |  | 73.55 | 99.23%
1.1.6 | Activity 1.1.6 | PB champion learning gathering/session on series 1 & 2 and training for CCTD series 3 and 4 salary and other administrative cost . | 74171.44 |  |  | 74171.44 | 100% | 62379.32 | 50% of participants are women; women are included in the adaptation (learning process) of the CCTD approach. There contributions help shape the project implementation and PB outcomes in their community |  | 11792.12 | 84.1%
1.1.7 | Activity 1.1.7 | Hold community dialogues (CCTD series 3) | 9600 |  |  | 9600 | 100% | 9575 | Same as above. |  | 25 | 99.74%
1.1.8 | Activity 1.1.8 | Hold community dialogues (CCTD series 4) & PCs draft form action plans (1 per HA) | 2500 |  |  | 2500 | 100% | 2491 | Same as above. |  | 9 | 99.64%
1.1.9 | Activity 1.1.9 | Form community PB network | 2750 |  |  | 2750 | 100% | 600 | 50% of PB network members are women (young adults or adult). Women will not only have a representative role, they also have a decision making position to lead PB processes in their community. |  | 2150 | 21.82%
1.1.10 | Activity 1.1.10 | PB champion learning gathering on series 3 and 4. | 3600 |  |  | 3600 | 100% | 3538.41 | 50% of participants are women; women are included in the adaptation (learning process) of the CCTD approach. There contributions help shape the project implementation and PB outcomes in their community |  | 61.59 | 98.29%
1.1.11 | Activity 1.1.11 | Monitor the effective implementation of action plans and adapt their content as required by the contexte | 2748 |  |  | 2748 | 100% | 595 | Data collected is disaggregated by gender and age; this activity seeks to ensure that the implementation of activities is done in a gender sensitive manner. |  | 2153 | 21.65%
1.1.12 | Activity 1.1.12 | PCs repeat CCTD cycles in the project’s target communities | 0 |  |  | 0 | 100% | 0 | Women take the lead in reiterating CCTD in their communities, leading on the process: which may involve training others in their community to be PCs. | Once the community has adopted the approach CCTDs are implemented without additional cost; hence of an expenditure on this ligne. | 0 | 0%
1.1.13 | Activity 1.1.13 | Special Measures Support | 2000 |  |  | 2000 | 100% | 1705 | This additional support is particularly focused towards special measures that will ensure that women and young people will have the motivation to participate and to be able to contribute substantially to the conversations/ consultations. Please refer to gender marker score section fin the narrative for full details. |  | 295 | 85.25%
1.1.14 | Activity 1.1.14 | Safeguarding | 1000 |  |  | 1000 | 100% | 795 | A portion of the budget will also be allocated for safeguarding, particularly for activities such as trainings and retooling sessions, communications and visibility planning and promotion of the reporting mechanisms, among others. |  | 205 | 79.5%
|  | Output Total | 155269.44 | 0 | 0 | 155269.44 | 151920.44 | 115530.33 | 0 | 0 | 34874.52 | 74.41% | 112476.58
| Output 1.2: | Women led CSO intervening in conflict transformation processes between Twas and Bantus receive support to improve its organisational capacity to effectively respond to conflict in their community
1.2.1 | Activity 1.2.1 | Conduct organisational capacity building analysis of the WL CSO | 4286 |  |  | 4286 | 100% | 2574 | The capacity building analysis will aim to strengthen the work of the WL CSO REFETANG. The amount will fully be used to strengthen this women's network which strives to advocate for women of all ethnic background in all 6 Territories of Tanganyika. |  | 1712 | 60.06%
1.2.2 | Activity 1.2.2 | Plan with WL CSOs a work-session to develop action-plans | 2500 |  |  | 2500 | 100% | 599.5 | This workshop will lead to making effective the needs jointly identified with REFETANG to improve its organizational (members' skill set, technical expertise...) to be more impactful |  | 1900.5 | 23.98%
1.2.3 | Activity 1.2.3 | Provide seed to WL CSO | 2748 |  |  | 2748 | 100% | 2588 | Joint monitoring activities will be conducted with REFETANG to assess progress made on the deliverables of its action plans. These monitoring sessions will lead to joint problem-solving and adaptations to the organisation's action plan which are lead by REFETANG members. This amount will also serve to support the new EWGs, with access to basic phones and airtime to raise alerts in a timely manner. |  | 160 | 94.18%
1.2.4 | Activity 1.2.4 | Monitor the effective implementation of action plans and adapt their content as required by the contexte | 7155 |  |  | 7155 | 100% | 7144.71 | 100% of the seed fund will be allocated to the network. Initial consultation with the REFTANGs point to a IGA which will benefit the community (with a focus on young women and women) while enabling the organization to be financially independent. Income generation, and the support which the project will provide through an IGA officer will contribute to a sustainable use of funding and the capacitation of women from the network to be trained to manage their activity. |  | 10.29 | 99.86%
1.2.5 | Activity 1.2.5 | Train the new EWG members on their role and duties | 0 |  |  | 0 | 100% | 0 | This activity is one of the core activities of the REFETANG: women (80% of the EWGs) are among the first change agents in their community to raise an alert ahead of a protection violation. EWGs are multi-generational and multi-ethnique; members will be adequately trained to fill their roles by the project. Thematic areas will be jointly identified between Tearfund and the REFETANG. Initial conversation with the REFETANG was the basis of the training, which involves 75 persons (15 people per HA; there are 5 HA where EWGs will be implanted). |  | 0 | 0%
1.2.6 | Activity 1.2.6 | Expand the network of EWG (early warning group) set up by the REFETANG in the project’s target areas. | 0 |  |  | 0 | 100% | 0 | This activity is not costed, as it can be done without an actual expense from the project. This will be done in the 2nd phase and 3rd phase (the durability phase) of the project. This activity is initiated and led by EWG members. |  | 0 | 0%
1.2.7 | Activity 1.2.7 | Special Measures Support | 2000 |  |  | 2000 | 100% | 1000 | This additional support is particularly focused towards special measures that will ensure that women and young people will have the motivation to participate and to be able to contribute substantially to the conversations/ consultations. Please refer to gender marker score section fin the narrative for full details. |  | 1000 | 50%
1.2.8 | Activity 1.2.8 | Safeguarding | 1000 |  |  | 1000 | 100% | 0 | A portion of the budget will also be allocated for safeguarding, particularly for activities such as trainings and retooling sessions, communications and visibility planning and promotion of the reporting mechanisms, among others. |  | 1000 | 0%
|  | Output Total | 19689 | 0 | 0 | 19689 | 19689 | 13906.21 | 0 | 0 | 5782.79 | 70.63% | 13906.21
t 1.3: | Output 1.3:
1.3.1 | Activity 1.3.1 |  | 0 |  |  | 0
1.3.2 | Activity 1.3.2 |  | 0 |  |  | 0
1.3.3 | Activity 1.3.3 |  | 0 |  |  | 0
1.3.4 | Activity 1.3.4 |  | 0 |  |  | 0
1.3.5 | Activity 1.3.5 |  | 0 |  |  | 0
1.3.6 | Activity 1.3.6 |  | 0 |  |  | 0
1.3.7 | Activity 1.3.7 |  | 0 |  |  | 0
1.3.8 | Activity 1.3.8 |  | 0 |  |  | 0
|  | Output Total | 0 | 0 | 0 | 0 | 0 | 0
t 1.4: | Output 1.4:
1.4.1 | Activity 1.4.1 |  | 0 |  |  | 0
1.4.2 | Activity 1.4.2 |  | 0 |  |  | 0
1.4.3 | Activity 1.4.3 |  | 0 |  |  | 0
1.4.4 | Activity 1.4.4 |  | 0 |  |  | 0
1.4.5 | Activity 1.4.5 |  | 0 |  |  | 0
1.4.6 | Activity 1.4.6 |  | 0 |  |  | 0
1.4.7 | Activity 1.4.7 |  | 0 |  |  | 0
1.4.8 | Activity 1.4.8 |  | 0 |  |  | 0
|  | Output Total | 0 | 0 | 0 | 0 | 0 | 0
| OUTCOME 2: | Women and marginalized ethnic groups’ equal access to land are upheld in Tanganyika, DRC.
| Outcome 2.1 | Non-violent land disputes resolution mechanisms are settled and supported in 10 affected communities in Nyunzu HZ.
2.1.1 | Activity 2.1.1 | Conduct Land tenure assessment study | 16000 |  |  | 16000 | 90% | 12266.64 | 90% of women will take part in this activity. 90% of participants will be women to ensure issues of discrimination and needs are identified and addressed in the roll out of activities. |  | 3733.36 | 76.67%
2.1.2 | Activity 2.1.2 | Capacity building on land-governance sensitive to gender and ethnicity | 63051 |  |  | 63051 | 80% | 21734.12 | 80% community members who will be trained are women. This activity will increase women's awareness of their rights (rights to own land, legal process in place to reinstitute land to women, and ethnic minorities, who have been expropriated.It is important to have men attend the training as well as they are the ones currently the main decision makers in land ownership and reform issues. |  | 41316.88 | 34.47%
2.1.3 | Activity 2.1.3 | Organize ethnically and gender diverse Multi stakeholders Consultation, Dialogue, Awareness and Information sessions (at the local and provincial level) | 30000 |  |  | 30000 | 100% | 25882.94 | Stakeholders at the local, territorial and provincial level will be sensitized on land-issues and the rights of women, as well as minority groups, to own land. Women and minorities will be facilitated to bring their grievances before authorities. This activity will serve as a means to advocate for women's right to land. |  | 4117.06 | 86.28%
2.1.4 | Activity 2.1.4 | Set up of the RFC in 2 communities (institutional, spatial and legal framework) | 75000 |  |  | 75000 | 100% | 18658.68 | In each communities; this legal framework will enable women to gain access to land and get redress when their rights are violated. |  | 56341.32 | 24.88%
2.1.5 | Activity 2.1.5 | Develop/refine and validate land reform tools (local land charter, provincial Edict, ADRs (Alternative Dispute Resolutions) and manual of procedures at the provincial and local levels that reflect principles of gender justice, inclusion and diversity. | 94600 |  |  | 94600 | 100% | 52113.17 | In each communities, 50% of the project participants will be women. |  | 42486.83 | 55.09%
2.1.6 | Activity 2.1.6 | Participatory mapping of Community land (at village level) inclusive of diversity (gender and ethnicity) | 30000 |  |  | 30000 | 100% | 10309.81 | 100% of participants will be women. Their active participation will be crucial to ensure that women's needs are met throughout the roll-out of the PARF approach. |  | 19690.19 | 34.37%
2.1.7 | Activity 2.1.7 | Participatory enumeration of land rights and recordation in the RFC | 30000 |  |  | 30000 | 90% | 16231.93 | 90% of women are targeted to engage proactively women who are culturally disallowed to own land. This activity has the ability to create space for a legal framework supporting women's access to land. Women's participation will be facilitated by a consultative process with women in target communities to ensure activities are implemented to adapt to their schedule and other particular needs. | The costing for this activity is based on the costing incurred by IRI-UCBC to conduct participatory activities and recordation of the RFC. | 13768.07 | 54.11%
2.1.8 | Activity 2.1.8 | Issuing of land certificates | 23051.1 |  |  | 23051.1 | 90% | 4543 | This activity will consolidate women's right to land-ownership. In order to encourage and facilitate women's access to land, 90% of certificates issues will be for women claiming land-ownership. | As for above, the costing for this activity is standard and based on IRI's standard expenditures to conduct this activity. | 18508.1 | 19.71%
2.1.9 | Activity 2.1.9 | Special Measures Support | 2000 |  |  | 2000 | 100% | 0 | This additional support is particularly focused towards special measures that will ensure that women and young people will have the motivation to participate and to be able to contribute substantially to the conversations/ consultations. Please refer to gender marker score section fin the narrative for full details. |  | 2000 | 0%
2.1.10 | Activity 2.1.10 | Safeguarding | 1000 |  |  | 1000 | 100% | 0 | A portion of the budget will also be allocated for safeguarding, particularly for activities such as trainings and retooling sessions, communications and visibility planning and promotion of the reporting mechanisms, among others. |  | 1000 | 0%
|  | Output Total | 364702.1 | 0 | 0 | 364702.1 | 345186.79 | 161740.29 | 202961.81 | 202965.6656 | 202965.6656 | 44.35% | 154090.309
| Output 2.2 | Existing PB steering committees focused on land-dispute that are supportive of women’s right to land tenure and are reinforced to resolve or effectively address land-disputes between Twa and Bantu peoples group
2.2.1 | Activity 2.2.1 | Set up and operationalize the Local Land Committee (Steering Committee) | 40000 |  |  | 40000 | 90% | 30236.19 | 90% of decision making roles on LLC committees will be held by women who represent 50% of the LLCs. | All costings for RFC activities are based on the delivery of similar work conducted by IRI . | 9763.81 | 75.59%
2.2.2 | Activity 2.2.2 | Capacity development of the members of the Local Land Committee on Conflict mediation, Gender Evaluation Criteria, Continuum of Land rights, land governance and Transparency | 50000 |  |  | 50000 | 90% | 47244.21 | This activity will involve 90% of women. Capacity building on land-right, gender and land-governance will benefit the immediate beneficiaries of the project. The medium, to long-term effect of this initiative might well go beyond the life-cycle of the project by leading to structural reform in the community. |  | 2755.79 | 94.49%
2.2.3 | Activity 2.2.3 | Organize land claims documentation and mediation sessions through the LLC (local land committee) | 37500 |  |  | 37500 | 100% | 29216.09 | Women are the majority on the LLC (local land committees--i.e. 90% of its members cf. result framework indicator 2.2.2.1. Majority female representation on LLCs will contribute to encouraging other women to bring land-disputes to be mediated and encourage women to speak out when their rights are being violated. What's more ALL LLC members (men and women) are sensitized on and trained to fairly mediate cases of land involving women. |  | 8283.91 | 77.91%
2.2.4 | Activity 2.2.4 | Special Measures Support | 1500 |  |  | 1500 | 100% | 1064 | This additional support is particularly focused towards special measures that will ensure that women and young people will have the motivation to participate and to be able to contribute substantially to the conversations/ consultations. Please refer to gender marker score section fin the narrative for full details. |  | 436 | 70.93%
2.2.5 | Activity 2.2.5 | Safeguarding | 500 |  |  | 500 | 100% | 0 | A portion of the budget will also be allocated for safeguarding, particularly for activities such as trainings and retooling sessions, communications and visibility planning and promotion of the reporting mechanisms, among others. |  | 500 | 0%
2.2.6 | Activity 2.2.6 | 0 | 0 |  |  | 0 |  | 0 |  |  | 0 | 0%
2.2.7 | Activity 2.2.7 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0%
2.2.8 | Activity 2.2.8 |  | 0 |  |  | 0 |  | 0 |  |  | 0 | 0%
|  | Output Total | 129500 | 0 | 0 | 129500 | 120500 | 107760.49 | 0 | 0 | 21739.51 | 83.21% | 100013.45
ut 2.3 | Output 2.3
2.3.1 | Activity 2.3.1 |  | 0 |  |  | 0
2.3.2 | Activity 2.3.2 |  | 0 |  |  | 0
2.3.3 | Activity 2.3.3 |  | 0 |  |  | 0
2.3.4 | Activity 2.3.4 |  | 0 |  |  | 0
2.3.5 | Activity 2.3.5 |  | 0 |  |  | 0
2.3.6 | Activity 2.3.6 |  | 0 |  |  | 0
2.3.7 | Activity 2.3.7 |  | 0 |  |  | 0
2.3.8 | Activity 2.3.8 |  | 0 |  |  | 0
|  | Output Total | 0 | 0 | 0 | 0 | 0 | 0
ut 2.4 | Output 2.4
2.4.1 | Activity 2.4.1 |  | 0 |  |  | 0
2.4.2 | Activity 2.4.2 |  | 0 |  |  | 0
2.4.3 | Activity 2.4.3 |  | 0 |  |  | 0
2.4.4 | Activity 2.4.4 |  | 0 |  |  | 0
2.4.5 | Activity 2.4.5 |  | 0 |  |  | 0
2.4.6 | Activity 2.4.6 |  | 0 |  |  | 0
2.4.7 | Activity 2.4.7 |  | 0 |  |  | 0
2.4.8 | Activity 2.4.8 |  | 0 |  |  | 0
|  | Output Total | 0 | 0 | 0 | 0 | 0 | 0
ME 3: | OUTCOME 3:
ut 3.1 | Output 3.1
3.1.1 | Activity 3.1.1 |  | 0 |  |  | 0
3.1.2 | Activity 3.1.2 |  | 0 |  |  | 0
3.1.3 | Activity 3.1.3 |  | 0 |  |  | 0
3.1.4 | Activity 3.1.4 |  | 0 |  |  | 0
3.1.5 | Activity 3.1.5 |  | 0 |  |  | 0
3.1.6 | Activity 3.1.6 |  | 0 |  |  | 0
3.1.7 | Activity 3.1.7 |  | 0 |  |  | 0
3.1.8 | Activity 3.1.8 |  | 0 |  |  | 0
|  | Output Total | 0 | 0 | 0 | 0 | 0 | 0
t 3.2: | Output 3.2:
3.2.1 | Activity 3.2.1 |  | 0 |  |  | 0
3.2.2 | Activity 3.2.2 |  | 0 |  |  | 0
3.2.3 | Activity 3.2.3 |  | 0 |  |  | 0
3.2.4 | Activity 3.2.4 |  | 0 |  |  | 0
3.2.5 | Activity 3.2.5 |  | 0 |  |  | 0
3.2.6 | Activity 3.2.6 |  | 0 |  |  | 0
3.2.7 | Activity 3.2.7 |  | 0 |  |  | 0
3.2.8 | Activity 3.2.8 |  | 0 |  |  | 0
|  | Output Total | 0 | 0 | 0 | 0 | 0 | 0
ut 3.3 | Output 3.3
3.3.1 | Activity 3.3.1 |  | 0 |  |  | 0
3.3.2 | Activity 3.3.2 |  | 0 |  |  | 0
3.3.3 | Activity 3.3.3 |  | 0 |  |  | 0
3.3.4 | Activity 3.3.4 |  | 0 |  |  | 0
3.3.5 | Activity 3.3.5 |  | 0 |  |  | 0
3.3.6 | Activity 3.3.6 |  | 0 |  |  | 0
3.3.7 | Activity 3.3.7 |  | 0 |  |  | 0
3.3.8 | Activity 3.3.8 |  | 0 |  |  | 0
|  | Output Total | 0 | 0 | 0 | 0 | 0 | 0
ut 3.4 | Output 3.4
3.4.1 | Activity 3.4.1 |  | 0 |  |  | 0
3.4.2 | Activity 3.4.2 |  | 0 |  |  | 0
3.4.3 | Activity 3.4.3 |  | 0 |  |  | 0
3.4.4 | Activity 3.4.4 |  | 0 |  |  | 0
3.4.5 | Activity 3.4.5 |  | 0 |  |  | 0
3.4.6 | Activity 3.4.6 |  | 0 |  |  | 0
3.4.7 | Activity 3.4.7 |  | 0 |  |  | 0
3.4.8 | Activity 3.4.8 |  | 0 |  |  | 0
|  | Output Total | 0 | 0 | 0 | 0 | 0 | 0
ME 4: | OUTCOME 4:
ut 4.1 | Output 4.1
4.1.1 | Activity 4.1.1 |  | 0 |  |  | 0
4.1.2 | Activity 4.1.2 |  | 0 |  |  | 0
4.1.3 | Activity 4.1.3 |  | 0 |  |  | 0
4.1.4 | Activity 4.1.4 |  | 0 |  |  | 0
4.1.5 | Activity 4.1.5 |  | 0 |  |  | 0
4.1.6 | Activity 4.1.6 |  | 0 |  |  | 0
4.1.7 | Activity 4.1.7 |  | 0 |  |  | 0
4.1.8 | Activity 4.1.8 |  | 0 |  |  | 0
|  | Output Total | 0 | 0 | 0 | 0 | 0 | 0
ut 4.2 | Output 4.2
4.2.1 | Activity 4.2.1 |  | 0 |  |  | 0
4.2.2 | Activity 4.2.2 |  | 0 |  |  | 0
4.2.3 | Activity 4.2.3 |  | 0 |  |  | 0
4.2.4 | Activity 4.2.4 |  | 0 |  |  | 0
4.2.5 | Activity 4.2.5 |  | 0 |  |  | 0
4.2.6 | Activity 4.2.6 |  | 0 |  |  | 0
4.2.7 | Activity 4.2.7 |  | 0 |  |  | 0
4.2.8 | Activity 4.2.8 |  | 0 |  |  | 0
|  | Output Total | 0 | 0 | 0 | 0 | 0 | 0
ut 4.3 | Output 4.3
4.3.1 | Activity 4.3.1 |  | 0 |  |  | 0
4.3.2 | Activity 4.3.2 |  | 0 |  |  | 0
4.3.3 | Activity 4.3.3 |  | 0 |  |  | 0
4.3.4 | Activity 4.3.4 |  | 0 |  |  | 0
4.3.5 | Activity 4.3.5 |  | 0 |  |  | 0
4.3.6 | Activity 4.3.6 |  | 0 |  |  | 0
4.3.7 | Activity 4.3.7 |  | 0 |  |  | 0
4.3.8 | Activity 4.3.8 |  | 0 |  |  | 0
|  | Output Total | 0 | 0 | 0 | 0 | 0 | 0
ut 4.4 | Output 4.4
4.4.1 | Activity 4.4.1 |  | 0 |  |  | 0
4.4.2 | Activity 4.4.2 |  | 0 |  |  | 0
4.4.3 | Activity 4.4.3 |  | 0 |  |  | 0
4.4.4 | Activity 4.4.4 |  | 0 |  |  | 0
4.4.5 | Activity 4.4.5 |  | 0 |  |  | 0
4.4.6 | Activity 4.4.6 |  | 0 |  |  | 0
4.4.7 | Activity 4.4.7 |  | 0 |  |  | 0
4.4.8 | Activity 4.4.8 |  | 0 |  |  | 0
|  | Output Total | 0 | 0 | 0 | 0 | 0 | 0
3.1 | Additional personnel costs | Support staff from Tearfund involve in the project | 139450 |  |  | 139450 | 16% | 104515.23 | Two out of the seven staff salaries will be covered by the project and their FTE costs represents 16% of the total expenditure under this section. Salaries will serve to the economic empowerment of women who are paid at the same rate as their male counterparts. |  | 34934.77 | 74.95%
3.2 | Additional operational costs | Office related support cost for Tearfund offices | 34500 |  |  | 34500 | 15% | 11536.06 | Expenses under this section will contribute equally to the women and men staff in Tearfund's offices.Women represent roughly 15% of Tearfund's staff. |  | 22963.94 | 33.44%
3.3 | Monitoring budget | M&E Cost for the project | 78944 |  |  | 78944 | 100% | 41179.61 | The baseline and endline and will assess attitudes, beliefs and practices relating to PB from a gender and ethnic-focus. The findings will serve to identify the enablers and barriers to conflict transformation and the inclusion of women in the project target zones. Monitoring of all activities will be conducted in consultation with women, and marginalized groups, in target communities to ensure that the project is adapted to meet their needs throughout the life-cycle of the project. |  | 37764.39 | 52.16%
3.4 | Budget for independent final evaluation | N/A | 0 |  |  | 0 |  | 0 | This activity is not budgeted as the project's total budget is less than 1.5M. USD. |  | 0 | 0%
3.5 | Budget for independent audit | Fees for the independent auditor | 9313.6822 |  |  | 9313.6822 | 100% | 0 | This activity will contribute to the learning on gender as it relates to CCTD and land-reform. The outcomes of the audit will consolidate. This expenditure is directly linked to the project. |  | 9313.6822 | 0%
|  | Total Additional Costs | 262207.6822 | 0 | 0 | 262207.6822 | 115744.6822 | 157230.9 | 0 | 0 | 104976.7822 | 59.96% | 59632.4558
Totals
|  |  | Recipient Organization | Recipient Organization 2 | Recipient Organization 3 | Total |  | Current level of expenditure/ commitment (to be completed at time of project progress reporting) |  |  | Balance | %
|  |  |  | #REF! | #REF!
|  | Sub-Total Project Budget | 931368.2222 | 0 | 0 | 931368.2222 | 174958.44 | 556168.22 | 494202.1 | 1225328.76 | 370339.2678 | 59.72%
|  | Indirect support costs (7%): | 65195.7756 | 0 | 0 | 65195.7756 |  | 38931.7754 | 34594.147 | 85773.0132 | 25923.7487 | 59.72%
|  | Total | 996563.9978 | 0 | 0 | 996563.9978 |  | 595099.9954 | 528796.247 | 1311101.7732 | 396263.0166 | 59.72%
Performance-Based Tranche Breakdown
|  |  | Recipient Organization | Recipient Organization 2 | Recipient Organization 3 | Total | Tranche %
|  |  |  | #REF! | #REF!
|  | First Tranche: | 348797.3992 | 0 | 0 |  | 35%
|  | Second Tranche: | 348797.3992 | 0 | 0 |  | 35%
|  | Third Tranche | 298969.1993 |  |  |  | 30%
|  | Total: | 996563.9978 | 0 | 0
|  | $ Towards GEWE (includes indirect costs) | 805753.7761 |  |  |  | Total Expenditure | 556168.22 |  |  |  |  | 470927.3351
|  | % Towards GEWE | 80.85% |  |  |  | Delivery Rate: | 0.59715
|  | $ Towards M&E (includes indirect costs) | 94435.72
|  | % Towards M&E | 9.476%
Note: PBF does not accept projects with less than 5% towards M&E and less than 15% towards GEWE. These figures will show as red if this minimum threshold is not met.

## MPTF-O Expense Report Format
TEARFUND PROGRESS FINANCE REPORT
MPTFO Project | Agency Project | UNDG Expense Category | Description | USD Amount
131128 | Tearfund DRC | 1 | 1. Staff and other personnel | 186522.25
131128 | Tearfund DRC | 2 | 2. Supplies, Commodities, Materials | 66997.02
131128 | Tearfund DRC | 3 | 3. Equipment, Vehicles, and Furniture (including Depreciation) | 878
131128 | Tearfund DRC | 4 | 4. Contractual services | 204716.11
131128 | Tearfund DRC | 5 | 5. Travel | 640
131128 | Tearfund DRC | 6 | 6. Transfers and Grants to Counterparts | 54159.36
131128 | Tearfund DRC | 7 | 7. General Operating and other Costs | 42255.48
131128 | Tearfund DRC | 8 | 7% Indirect Costs | 38931.7754
595099.9954